Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for 
 Scheduling the Book Writing Process Exercise

Introduction to Personal Process

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Introduction to Personal Process

Scheduling the Book Writing Process

Overview

| #### Exercise #### Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objective | 2 |
|  | Exercise Instructions | 2 |
|  | Book Writing Process Script and Project Planning Summary | 3 |
|  | Task and Schedule Template | 5 |
|  | Earned Value Plan Plot template | 7 |

| #### Exercise #### Objective | The objective of this exercise is for you to learn how to create an earned value plan. |
| --- | --- |

| #### Exercise #### Instructions | Using the planned data on the project planning summary form, create an earned value plan for this work. - On the task template, list the activities in the order that they should be completed. - Fill in the estimated hours for each activity in the Plan Hours column of the task template. Calculate the cumulative task hours for each task and the total task hours for the entire process. Enter these on the task template. - On the schedule template, specify 20 hours as the direct hours per week that you plan to devote to these tasks, beginning March 1. (Note that during the week of April 12, you are on vacation and will spend 0 hours on the tasks.) Compute the cumulative scheduled hours for each week. Be sure to schedule enough hours to cover the total task hours. - On the task template, start with the first activity and determine the workweek during which each task will be completed. Do this by finding the first week on the schedule template in which the cumulative scheduled hours exceed the cumulative plan hours for the task. Enter the week of task completion date in the Plan Date column of the task template. - Calculate the planned value and cumulative planned value for the tasks and enter these on the task template. On the task template, find the largest cumulative planned value for each date and enter this value in the Cumulative Planned Value column on the schedule template for the corresponding date. - From the schedule template, plot the cumulative planned value on the horizontal axis and the weeks on the vertical axis. - When you are finished, examine your task plan to see if there are large tasks that could be broken down into lower level tasks. |
| --- | --- |

Book Writing Process Script

| Purpose |  | To guide you in writing books |
| --- | --- | --- |
| Entry Criteria |  | - Idea and/or need for book - Book writing process project plan summary form - Task and schedule planning templates - Time and defect logs - Defect type standard - Stop watch (optional) |
| Step | Activities | Description |
| 1 | Planning | - Design the book. Include the purpose and audience, topical outline, flow, identified sections, chapters, and appendices. - Estimate the size of each book section and the total book, and enter these data on the project plan summary form. - Estimate the time required for each section and the entire book, and enter these data on the project plan summary form. Use historical data rates in minutes per page to guide this estimation. - Use To Date percentages and distribute the time across the phases. - Produce the task and schedule planning templates. - Complete the time and defect logs for this phase. |
| 2 | Annotate Outline | - Conduct needed research. - Produce detailed chapter outlines and summaries. - Review and update the annotated outline. - Complete the time and defect logs for this phase. |
| 3 | Draft Manuscript | - Write draft sections of the book. - Edit the draft sections. - Rewrite draft sections as needed. - Complete the time and defect logs for this phase. |
| 4 | Peer Review | - Hand out draft manuscript for peer review. - Gather comments from peer review. - Incorporate comments into sections. - Complete the time and defect logs for this phase. |
| 5 | Publisher Review | - Submit to publisher and gather comments on the manuscript. - Rewrite and edit each section, based on publisher comments. - Submit final manuscript to the publisher. - Complete the time and defect logs for this phase. |
| 6 | Complete Book | - Make final updates to the book sections. - Produce miscellaneous content (e.g., index, front matter, etc.). - Complete the time and defect logs for this phase. |
| 7 | Postmortem | - Record actual development data (size, time, and defects). - Calculate new To Date data. |
| Exit Criteria |  | - Published book - Completed defect and time logs - Completed task and schedule plans - Completed project plan summary form with estimated and actual data |