Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

| Instructional Product Development Script |  |
| --- | --- |
| Purpose | To guide teams in designing effective instructional materials |
| Entry Criteria | - There is a clear need for the product. - There is no other instruction available off the shelf and there are documented reasons why the product should be developed in-house. - The people and money needed for product development are approved and allocated. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Product Planning | - The development team meets to plan the product. - Determine product type, delivery mechanism, learning assessments, and other parameters of the instructional product. - Build audience definition and overall educational objectives. - Identify the major topics to be covered in the course. - Identify materials and human resources needed for course development. - Identify development and delivery constraints. - Determine the preliminary development plan, including overall task list, development schedule, and interim milestones. - Assign roles and allot the development work among team members. - Balance the workload among team members. - Identify risks to the development plan and plan mitigation strategies. - Document the plan and obtain approval from management. |
| 2 | High-level Design | - Develop a high-level design (Product Matrix Template). For each component of the product, determine and document the - component name - list of topics included in the component - educational objectives for the specific component (derive from overall objectives) - delivery details for each component - learning assessments for each component - duration of the component (how much time is allotted for instruction) - Hold an inspection or peer review of the HLD and revise as needed. - Document all data collected (time, size, defects). |
| 3 | Detailed-level Design | - For each component, develop a detailed design. - topic outline for lectures or web presentation - supporting details for each topic and/or illustrations, examples, etc. - description of exercises, assignments, tests, etc. - Perform an individual review of the design documents and revise as needed. - Hold a team walkthrough for all components and revise documents as needed. - Document all data collected (time, size, defects). |
| 4 | Product Development | - Develop the component materials. - Produce lecture slides, exercise materials, web pages, etc. - Perform an individual review of all products produced. - Correct errors and revise materials and needed. - Conduct a peer review of the materials and revise as needed. - Document all data collected (time, size, defects). |
| 5 | Dry Run | Hold a dry run of the materials with a group of reviewers who fit the characteristics of the target audience. - Deliver all lectures and exercises, or provide student access to materials and test functioning of all links, pages, etc. - Hold a debrief session at the end of the dry run and elicit comments, suggestions, problems, etc. - Revise materials as needed. - Document all data collected (time, size, defects). |
| 6 | Pilot Test | Deliver the course to an audience for the first time. - Conduct the instruction and learning assessments. - Elicit feedback from the participants regarding effectiveness of instruction and student satisfaction. - Revise instruction as needed. - Document all data collected (time, size, defects). |
| 7 | Revise Product and Publish | - Produce a final version of all course materials, incorporating changes as needed based on feedback from the pilot test. |
| PM | Project Postmortem | Hold team postmortem meeting. - Gather project and product data and produce a final report. - Put the final report in the project data repository. - Assess the instructional development process and prepare PIPs. |

| Exit Criteria | - The product is completed. - All documentation for the product has been generated. - Data has been gathered, analyzed, and stored in the instructional team repository. |
| --- | --- |