## Slide 3: What Is the Team Software Process?
The Team Software Process (TSP) is an integrated set of practices for developing software.
The TSP is a process-based solution to common software engineering and management challenges:
  cost and schedule predictability
  productivity and product quality
  process improvement

## Slide 4: A Peek into a TSP Weekly Meeting
We are about to watch a TSP team conduct part of their weekly meeting.
  The team is composed of four team members, a team leader and a TSP coach.
  The team developed their plan and started work seven weeks ago.
  The team is meeting weekly to discuss the status against their plan and to manage the quality of their product.
After we watch the video, we will have a class discussion about how the teams in your organization plan and manage their work.

## Slide 5: In Your Organization?
What is your organization’s current practice?
  How is it similar to what we just observed?
  How is it different?
In your organization
  Who makes the plans?
  How are they developed?
  Who makes the commitments to management?
How well do these practices satisfy the principles of building motivated self-managed work teams?

## Slide 6: The TSP Weekly Meeting - Reprise
The team we “glimpsed” in the video
  creates detailed plans that all team members are committed to
  gathers complete, consistent, and accurate data
  tracks the status of its plan on a weekly basis and takes responsibility for schedule problems
  regularly conducts load balancing to ensure an optimized schedule with respect to time-to-delivery
  reviews the quality of its product weekly and is accountable for building a superior product

## Slide 7: Topics
The TSP
  establishes self-managed teams
  is guided by a defined process framework
  provides a team-based project planning process guided by a coach
  includes metrics for tracking project status and product quality
  provides immediate, measurable benefits

## Slide 8: TSP Teams Are Self-Managed
Traditional team
The leader plans, directs,
and tracks the team’s
work.
Self-managed team
The team members participate
in planning, managing, and
tracking their own work.

## Slide 9: TSP Team Member Roles
All team members have traditional roles; for example developer, tester, or inspector.
They also share self-management responsibilities through eight defined management roles.
  Customer Interface
  Design
  Implementation
  Planning
  Process
  Quality
  Support
  Test
Team Leader

## Slide 10: The Team Leader’s Role
The team leader does not typically take one of the aforementioned eight team roles.
The team leader’s role on a TSP team is to
  guide the team in doing its work
  support the self-managed team concept
  take the time to reach full consensus on all important issues
  ensure that the team establishes high standards for the work
  promote and facilitate team problem solving
  provide management support to the team and interface with management for the team
  protect the team so that team members can focus on the project
Handout: TSP Team Leader Roles and Responsibilities

## Slide 11: The Team Lead as Developer
It is generally best for the team leader to devote their energy and time to leading the team.
In some cases, it may be appropriate for a team leader to engage in development work. For example,
  with small teams
  in situations where the team leader possesses unique skills
But team leaders who are also developers can become enmeshed in work details and be less effective leaders.

## Slide 12: Topics
The TSP
  establishes self-managed teams
  is guided by a defined process framework
  provides a team-based project planning process guided by a coach
  includes metrics for tracking project status and product quality
  provides immediate, measurable benefits

## Slide 13: The TSP Defined Process Framework
TSP is based on a defined process framework.
The TSP process framework was designed to be integrated with existing processes, methods, and tools.
Processes within the framework can be tailored by the team under the guidance of a TSP coach.
The TSP process
  guides the work (but doesn’t constrain it)
  ensures consistency of results
  promotes effective communication
  stimulates individual and team improvement

## Slide 14: The TSP Process Scripts
All activities to plan, track, develop, and maintain a software product are guided by process scripts.
Scripts provide expert-level guidance on how to use the processes within the framework.

## Slide 15: Topics
The TSP
  establishes self-managed teams
  is guided by a defined process framework
  provides a team-based project planning process guided by a coach
  includes metrics for tracking project status and product quality
  provides immediate, measurable benefits

## Slide 16: Planning and Team Building
The TSP launch process addresses planning and team building.
A typical launch takes two-four days. Small teams need less time.
  The launch is considered part of the project work.
  All team members participate.
  The launch is guided by an SEI-certified TSP coach.
Management provides the goals and constraints for the project.
The team then develops its plan for meeting management’s objectives.
If necessary, the team negotiates with management to arrive at a mutually agreeable outcome.

## Slide 17: TSP Development Strategy
A team can begin using TSP on a newly started project or on a project that is already underway (any cycle or phase of a cycle).
The TSP planning cycle begins with a launch or a re-launch and ends with a postmortem.
The development strategy is guided by business and technical needs.
  iteratively in small cycles
  in a spiral with increasing cycle content
  sequentially as in a waterfall

## Slide 18: Planning in TSP – Bird’s Eye View
The Project
Release 1
Release 2
Release n
Cycle 1
Cycle 2
Cycle 3
Cycle 4
Cycle 5
Cycle 6
Cycle 7
Cycle n
Launch
R
P
R
P
R
P
R
P
R
P
R
P
R
P
P*
The initial launch plan covers today through the last release of the project.
A cycle is a planning period.
The current cycle is planned in granular detail by the team as they are about to execute that particular cycle.
Future cycles are planned during the launch, but not with the detail that the current cycle is planned with.
Each new cycle begins with a relaunch.
Release and cycle durations are project-dependent.
Each cycle begins with a launch or relaunch and ends with a postmortem.

## Slide 19: Multiple Levels of Planning
Launch or Relaunch
Postmortem
Cycle (a.k.a., iteration or sprint)
Weekly objectives
Two-three tasks per team member

## Slide 20: The TSP Launch Process
A qualified coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
1
Establish product and business goals
1
Assign roles and define team goals
2
Produce development strategy & process
3
Build overall and near-term plans
4
Develop the quality plan
5
Build individual & consolidated plans
6
Conduct risk assessment
7
Prepare management briefing & launch report
8
Hold management review
9
Launch postmortem

## Slide 21: Class Discussion - Coaches
What is the role of a coach on a team?

## Slide 22: The TSP Coach
The TSP coach is a TSP expert who works collaboratively with the team leader to ensure project success. The coach
  guides the TSP team through the TSP launch process
  coaches the TSP team members as they work on the project
  is not a team member or the team leader
The TSP coach is an expert in the TSP process.
  TSP information products provide expert-level guidance with the assumption that a coach will be assisting the team.
  Every team and project is different and how the TSP is specifically implemented depends on the particular project context. The coach assists the team in tailoring the TSP appropriately.

## Slide 23: The TSP Coach
The coach is an objective and impartial observer who can provide guidance to the team in resolving issues and reaching consensus.
The coach facilitates the launch process so that the team leader can fully participate in all launch activities.

## Slide 24: Topics
The TSP
  establishes self-managed teams
  is guided by a defined process framework
  provides a team-based project planning process guided by a coach
  includes metrics for tracking project status and product quality
  provides immediate, measurable benefits

## Slide 25: Tracking and Status Reporting
A self-managed team makes their own plan and is held accountable for managing their plan.
For a TSP project, four base measures are collected to support tracking against the plan. They are
  schedule (that is, completion status of tasks)
  size
  time
  defects

## Slide 26: Schedule
Schedule is the most commonly used project measure.
Schedule precision depends on task granularity.
TSP task granularity is in hours (not days, weeks, or months).

## Slide 27: Time
Time is a measure of the effort required to complete a task.
The TSP time measure is task hours.
Task hours are the time spent on a project task, minus any interruption time.
TSP team members record their time as they work, not at the end of the day, week, or month.

## Slide 28: Size
The time required to complete a task is usually correlated with the size of the work product.
TSP size measures are selected based on their correlation with time.
TSP uses size data to
  normalize other measures
  estimate time
  track progress

## Slide 29: Defects
Quality without numbers is just talk.
In the TSP, the key quality measure is a count of the number of defects in the product.
Defect content must be managed before other attributes of product quality can be addressed.
In TSP, a defect is defined as any error in the interim or final work product that requires rework to ensure compliance with the requirements and design of the product.
In the TSP, defects are logged as they are found and fixed.
Defect tracking takes place throughout the development life cycle.

## Slide 30: What the Base Measures Provide
Base Measures provide the necessary information to answer important questions about the project.
  When do we expect to finish?
  How confident are we in that expectation?
  Why are we behind/ahead of schedule?
  How do we spend our time?
  What do we expect the quality of the final product to be?
  How confident are we in that expectation?
  When are defects being injected and removed?
  How effective are our reviews and inspections?

## Slide 31: Topics
The TSP
  establishes self-managed teams
  is guided by a defined process framework
  provides a team-based project planning process guided by a coach
  includes metrics for tracking project status and product quality
  provides immediate, measurable benefits

## Slide 32: TSP Benefit: Reduction in System Test Time
Typical software project teams spend 40-50% of their effort in system test, finding and fixing defects.
By sending cleaner code to system test, the total time spent in system test can be reduced to 9-15%.
Reducing system test time increases the time that teams can spend in developing product during a typical year-long release cycle … by almost 50%.

## Slide 33: Results: Schedule and Effort Deviations
Before TSP
Percent Average Schedule Deviation
-20
0
20
60
100
140
40
80
120
-40
160
After TSP
Before TSP
Percent Average Effort Deviation
-60
-40
-20
20
60
100
0
40
80
-80
120
After TSP
Schedule Deviation
Effort Deviation
25th to 75th percentile
Outlier
Max/min data point
N = 15
N = 15
N = 16
N = 16
[Source: McAndrews, D. 2000]

## Slide 34: Results: Defects Delivered
CMMI Maturity Level
[Source: Jones, C. 2011]
Note: Function points were translated to KLOC using backfire method (1FP = 100 LOC) .

## Slide 35: TSP Compared to Other Methodologies
[Source: Jones, C. 2012]
* RUP is Rational Unified Process.
Note: Function points were translated to KLOC using backfire method (1FP = 100 LOC) .

## Slide 36: Improved Quality of Work Life
“We feel under control now. Don’t ever want to go back to the way we did things before …”
“It’s not chaotic anymore. Not thrashing. We’re getting more work done in less time than ever before.”
“Ability for the engineers and teams to use data to improve their own software development performance.”
“Team members feel empowered by having ownership of the team plan.”
“TSP has enabled common understanding and shared vision.”
“Teams are able to see the bigger picture within a project.”
Comments are from presentations delivered at the 2012 TSP Symposium http://www.sei.cmu.edu/tspsymposium/2012/proceedings.cfm

## Slide 37: To Obtain the TSP Results
To realize the benefits of TSP, the team leader and team members must develop a shared understanding that
  commitments are not made without a plan
  the people who do the work must be involved in planning the work
  all team members share in the ownership and responsibility for their commitments
  all products must be carefully reviewed
  each team member is responsible for the quality of their work products and their schedule
  all members of the team must be trained so that they can perform their TSP responsibilities

## Slide 38: The Importance of Developer Training
In order to be successful with TSP, each member of the team is trained so that they acquire skills to
  make realistic plans
  negotiate commitments
  track their work
  produce high quality products
It is important that you support and encourage your team to successfully complete PSP/TSP training.
  Software developers: PSP Fundamentals and Advanced PSP
  Other team members: TSP Team Member Training

## Slide 39: Messages to Remember
TSP promotes project ownership by the team.
TSP provides the tools to enable the team to be successful.
Empirical results demonstrate the effectiveness of TSP
  high-maturity outcomes
  predictable cost and schedule
  near defect-free quality
  satisfied developers, managers, and customers
  accelerated process maturity

## Slide 40: References
McAndrews, D. The Team Software Process: An Overview and Preliminary Results of Using Disciplined Practices (CMU/SEI-2000-TR-015, ADA387260). Pittsburgh, PA: Software Engineering Institute, Carnegie Mellon University, 2000. http://www.sei.cmu.edu/publications/documents/00.reports/00tr015.html.
Jones, C. Software Quality in 2010: A Survey of the State of the Art. http://www.sqgne.org/presentations/2010-11/Jones-Nov-2010.pdf (2011).
Jones, C. Software Quality in 2011: A Survey of the State of the Art. http://sqgne.org/presentations/2011-12/Jones-Sep-2011.pdf (2012).