## Slide 1
Leading a Development Team
Team Launch

## Slide 3: Overview
A peek into a TSP launch (video)
TSP launch overview
Roles and responsibilities
  Team leader
  Coach

## Slide 4: A Peek into a TSP Launch
We are about to watch a TSP team at the conclusion of a launch as the team leader presents alternative plans to management.
  The team determined that they could not meet all of management’s functionality and schedule goals.
  The team developed a set of alternative plans and is presenting them to management. Management must select a plan that best meets the business’s needs.
After we watch the video, we will have a class discussion about how the teams in your organization negotiate commitments with management.

## Slide 5: Review: Self-Managed Teams
TSP team leaders create a cohesive and cooperative environment by building and maintaining self-managed teams.
Self-managed teams have the following characteristics:
  sense of membership and belonging
  commitment to a common team goal
  ownership of the process and plan
  the skill to plan and the discipline to follow its plan
  dedication to superior work
  commitment to doing the job
The best approach for motivating the team is to promote voluntary, public, credible, and owned commitments.

## Slide 6: Overview
A peek into a TSP launch (video)
TSP launch overview
Roles and responsibilities
  Team leader
  Coach

## Slide 7: The TSP Launch
The TSP launch is the mechanism for establishing the conditions for a self-managed team.
  The launch workshop accelerates team-building.
  The team establishes a common understanding of the work and the approach it will use.
  The team makes a plan to which it can commit and obtains management support for that plan.

## Slide 8: The Team Leader and the TSP Coach
During the TSP launch, the TSP team leader and TSP coach work collaboratively to bring about the desired outcomes.
They share responsibility for providing the guidance that enables a team to jell while producing a high-quality plan at the same time.
The TSP team leader’s primary focus is to ensure that the team is building a rational plan in response to management goals.
The coach’s primary focus is to ensure that the team is following a rational process to build the plan, based on a quality-development process that uses historical data (when it is available).

## Slide 9: Launch Preparation
The team leader works with the TSP coach to prepare for the launch.
The TSP coach will provide the detailed guidance to ensure the following is accomplished:
  A TSP coaching plan is established.
  All team members are trained in PSP or they receive TSP Team Member training prior to the launch.
  Management prepares a clear and compelling presentation that establishes goals for the team. The presentation is delivered during meeting 1 of the launch.
  Management is clear about the priorities between schedule, resources, and content.

## Slide 10: The TSP Launch Process
A qualified coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
1
Establish product and business goals
1
Assign roles and define team goals
2
Produce development strategy & process
3
Build overall and near-term plans
4
Develop the quality plan
5
Build individual & consolidated plans
6
Conduct risk assessment
7
Prepare management briefing & launch report
8
Hold management review
9
Launch postmortem

## Slide 11: Meeting 1: Establish Product and Business Goals
The first step during the launch is for the team to understand what it is being asked to do.
During meeting 1, management and marketing meet with the team to share their views about
  what they want the team to develop
    essential features
    nice-to-have features
  when the product is needed
  what resources the team has
  what flexibility the team has
  why this job is important
  how management will measure success

## Slide 12: Meeting 2: Establish Team Goals
After the initial meeting, management leaves the launch and the team beings to develop their plan.
During launch meeting 2, the team sets its goals and organizes itself.
The team leader leads a review of management’s goals to ensure that the team understands them well enough to make a plan.
The team adds three to five team-specific goals.

## Slide 13: Meeting 2: Organize the Team
The management responsibility is shared on a self-managed team.
Traditional project management responsibilities are distributed among eight team roles.
  customer interface manager
  design manager
  implementation manager
  test manager
    planning manager
    quality manager
    process manager
    support manager

## Slide 14: Meeting 2: Organize the Team, cont.
Each team member assumes the responsibility for at least one team management role.
Defined roles
  ensure that key areas are covered
  give each team member a responsibility in running the team
  build a sense of membership and ownership among the team members
  free the team leader to focus on the role of coaching and leading the team
TSP roles work best when the team leader relies on each of the role managers for the project’s success.
The team leader should present his or her expectations for each role.

## Slide 15: Meeting 3: Define the Work and the Approach
In meeting 3, the team accomplishes three important prerequisites to building the team plan.
  identifies all of the work the team needs to do
  identifies the build strategy the team will use to develop the software
  identifies or defines the processes the team will follow to do the work
Conceptual design
Development strategy
List of products
Project process
Project strategy

## Slide 16: Meeting 4: Build the Overall Plan
In launch meeting 4, the team creates the overall plan by establishing
  the estimated sizes of the products to be produced (how big is the job)
  the tasks needed to complete the work (with effort estimates)
    next-phase tasks, detailed to the work-step level
    later phases planned at a high level
  the estimated team hours available each week for the work
  an initial schedule for the project
Estimate size
Define tasks
Estimate resources
Estimate available time
Overall plan
TSP Planning Guidelines

## Slide 17: Meeting 4: If the Plans Do Not Match the Goals
The team leader should lead the team in developing alternative plans.
For example, the team could look at how many additional resources it would take to complete the project by the requested date.
If the overall plan does not meet management expectations, the issue is discussed with management to determine resolution.

## Slide 18: Meeting 5: Build a Quality Plan
In launch meeting 5, the team builds a quality plan that estimates the
  number of defects that will be injected in each phase
  number of defects that will be removed in each phase
  quality of the final product (defect density)
  quality of the development process (process quality index)
The team ensures that the plan meets the quality goals.
Review quality goals
Estimate defects injected
Estimate defects removed
Quality plan

## Slide 19: Meeting 6: Build Individual Work Plans
In launch meeting 6, the team leader is looking to each team member to build a personal plan he or she can commit to.
In building their plans, the team members
  allocate tasks to individuals
  refine size and effort estimates using their own data and processes
  break tasks to the granularity of around 10 hours or less per task
  estimate their own available task hours for each week
  create an earned-value plan
  balance workloads across all team members
Allocate tasks
Create individual plans
Balance the workload
Balanced plan

## Slide 20: Meeting 6: Build a Consolidated Team Plan
Individual team member’s plans for the next project phase are consolidated into a single team plan that contains a
  task list of all individual tasks with
    estimated hours
    planned dates
    planned values
  schedule with
    planned team hours per week
    planned team earned value per week
The team uses this plan to guide and track its work during the next project phase.

## Slide 21: Meeting 7: Identify Risks and Mitigation Strategies
In launch meeting 7, the team identifies and assesses project risks.
The risks are documented in the team’s plan.
Risks are assigned to team members to track throughout the project.
The team identifies mitigation and recovery strategies for high-priority risks.

## Slide 22: TSP Launch Products
What?
How?
When?
Who?
How well?
What if?
Team goals
Conceptual design
Planned products
Size estimates
Team strategy
Team-defined process
Task plan
Schedule plan
Earned-value plan
Team roles
Task plans
Earned-value plan
Quality plan
Risk evaluation
Alternate plans
Business needs
Management goals
Product requirements

## Slide 23: Meeting 8 - Prepare Management Briefing
In launch meeting 8, the team leader leads the team in building a presentation of the plan for management.
The building of the presentation is part of the jelling and commitment process for team members.
The team leader will present the plan to management in meeting 9 and call on appropriate role managers for questions that pertain to their roles.
In meeting 8, it is important to anticipate the questions management will ask and be prepared with answers.

## Slide 24: Meeting 9 - Management Review of the Plan(s)
In launch meeting 9, the team leader presents the team plan (and alternatives, if any) to management.
Management determines whether
  the plan is based on sound estimates, historical data, and a quality process
  the team believes in its plan
  the plan or an alternative meets the business need
Management
  approves the plan or an alternative
  might ask the team to look at a different alternative

## Slide 25: Overview
A peek into a TSP launch (video)
TSP launch overview
Roles and responsibilities
  Team leader
  Coach

## Slide 26: Team Leader’s Launch-Related Responsibilities
Ensure that the team is prepared.
Practice rational management.
  Use data to make decisions.
  Don’t make or argue commitments without plans.
Be a positive role model with a positive attitude.
When leading team discussions
  don’t dominate
  make sure everyone participates
  look for signs of resistance and bring issues to the surface
Don’t do the work for the team, but don’t let the team make bad decisions either.
Keep the focus on quality.

## Slide 27: The Coach’s Role During the Launch
TSP process expert for details of the
  launch process
  schedule and quality planning
  the TSP support tool
Meeting facilitator (objective and independent) who
  helps bring the group to consensus
  keeps the team focused on important issues
  ensures full participation of all team members

## Slide 28: Coach Responsibilities
The goals of the launch process are
  to build a team that is ready to jell
  for the team to build a plan it is committed to
  for management to be convinced that the plan is sound
The principal responsibilities of the TSP coach during the launch are to ensure that
  the process is followed
  everyone is involved and contributes to the launch outcomes
  communication is effective and congruent

## Slide 29: Class Discussion - Team Leader Responsibilities
Share ideas about
  team leader behaviors
  behavior changes that you will need to make to address the team leader role
  behavior changes that may be difficult and how you might overcome the difficulties
Take 15 minutes to
  review team leader roles and responsibilities*
  think about the behavior changes that are implied in the document and identify those that would likely be most difficult for you
  come up with ideas of how you’ll overcome those difficulties
  We will then have a 15-minute class discussion.
Purpose
Instructions
* This document is located at the end of the previous course module.

## Slide 30: Messages to Remember
The launch is the TSP mechanism that establishes the conditions for a jelled and self-managed team.
A launch is successful when the outcome is a team that is committed to its plan.
A launch is the first opportunity for the team and team leader to act as a self-managed team.
The coach is there for a reason; use the coach.

## Slide 31: Guided Tour Through a TSP Plan
Purpose: To familiarize you with the parts of a TSP plan.
  Overall project plan
  Individual near-term plans
  Consolidated near-term team plan
TSP Plan