## Slide 1
Leading a Development Team
Managing the Plan

## Slide 3: Topics
Introduction
Schedule status indicators
Maintaining team commitment

## Slide 4: Where Are We?
Throughout the project, a primary question facing the team leader and the team is:
Will the team be able to meet its committed date?
To answer this question, consider the following:
  Does the team’s current plan meet the committed completion date?
  What is the status of the team’s tasks against the current plan?
  If the current plan does not meet the committed completion date, what is the projected completion date?

## Slide 5: Tracking Status
How precisely should we track our work?
If you cannot recognize a one-day slip, you can only take action when the delay is obvious.
But, by then, it is usually too late to recover.
With the TSP, one-day schedule slips can be detected.
“…schedule slips, one day at a time.”
- Fred Brooks in The Mythical Man Month

## Slide 6: Planning is Dynamic
The project is dynamic. Therefore, the plan must be dynamic.
As the team identifies additional work that was not initially envisioned during the launch, these tasks are added to the plan.
Therefore, the team needs to constantly monitor the plan to understand the status of the project with respect to the committed completion date.
There are a number of measures used in TSP that support the team so that they have up-to-date knowledge of schedule status.
TSP software tools support the team in developing, monitoring, and managing your TSP plan. Examples include
  TSP Excel Tool
  Process Dashboard
  Other proprietary applications

## Slide 7: The TSP Project Plan Summary
Different TSP support tools may have a dissimilar “look-and-feel,” but they all collect and report the same type of information.
After the project commences, the TSP support tool reports team performance comparing performance estimates to actuals.
Key performance indicators are reported in the tool’s project plan summary so that you (or any team member) can understand the team’s status at any time during the project.

## Slide 8: Topics
Introduction
Schedule status indicators
Maintaining team commitment

## Slide 9: Schedule Status Indicators
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
In this section, we will explore a number of project status indicators to help you understand the status of your project.

## Slide 10: What is the Earned Value Method?
You need a way to track and report progress. The challenge is that
  most projects have many tasks of differing types and sizes
  tasks are completed in a different order than originally planned
The Earned Value (EV) method provides a convenient way to address this tracking and reporting problem.
  The EV method establishes a value for every task, regardless of its type.
  Whenever you complete a task, regardless of its type, you earn this EV amount.
  To judge progress against the plan, compare the EV each week with the planned earned value (PV) for that week.

## Slide 11: TSP Earned Value Method
Planned Value (PV)
PV for a task is an estimate of the work required to complete the task. It is expressed as the percent of the overall work required in a project plan.
Earned Value (EV)
A task’s PV is earned when a task is completed. It must be entirely completed to earn the value.
Regardless of the actual effort required to complete the task, the earned value that is achieved is the value that was planned (i.e., the PV).
A project’s cumulative EV is the total of the PV for all project tasks that have been completed to date.

## Slide 12: Simple Example: Earned Value
30%
20%
30%
20%
10.5
30%
3
5
8
10
Cum. est. ef.
A
B
C
D
Task
3
2
3
2
Est. effort
PV
EV
Act. effort
1.3
20%
3.2
Cum. PV
30%
50%
80%
100%
Cum. EV
30%
50%
10.5
Cum. act. ef.
11.8
15.0
30%
80%
5.6
20.6
20%
100%

## Slide 13: Using EV Method to Determine Schedule Status
To determine a project’s current schedule status, compare the current cumulative EV to the planned cumulative PV.
  If EV > PV, the project is ahead of schedule
  If EV < PV, the project is behind schedule
To calculate an estimate of how far ahead or behind schedule the project is
PV - EV
Avg. EV (to-date)

## Slide 14: Example: Approximating the Schedule Status
Given:
Therefore:
The project is currently behind by
PV - EV
Avg. EV (to-date)
=
54.3 – 31.2
31.2 / 6
=
4.4 weeks
 | Planned Value (PV) | Earned Value (EV)
Week 6 | 5.6 | 5.6
To Date | 54.3 | 31.2

## Slide 15: Estimating the Project Completion Date
To estimate the project completion date
  Determine the EV required to complete the project.
  Calculate the rate at which the team is accumulating EV.
  Determine how long it will take the team to earn the remaining EV.

## Slide 16: Example: Estimating Project Completion Date
Given:
 | Planned Value (PV) | Earned Value (EV)
Week 6 | 5.6 | 5.6
To Date | 54.3 | 31.2
Therefore:
Amount of EV yet to earn on project:
100 – 31.2 = 68.8 EV
Remaining estimated time in project:
68.8 / 5.2 = 13.2 weeks
Estimated week for completion:
6 + 13.2 = 19.2 weeks
The EV rate thus far is:
31.2 / 6 = 5.2 EV per week

## Slide 17: Assumptions of the EV Method
The EV method assumes that
  the plan is reasonably accurate
  the rate of task completion in the future will be roughly the same as what it was in the past
  actual project resources will be available as planned
    if staffing level increases, the EV projections will be pessimistic
    if staffing level decreases, the EV projections will be optimistic

## Slide 18: Earned Value Example
What is the schedule status?
Cumulative PV
Percent Planned or Earned Value
Cumulative EV

## Slide 19: Why Is the Team Behind?
In the last example the team might be behind for one or more of the following reasons:
  Team members aren’t working the number of task hours that were estimated in the plan.
  Effort for some or all tasks has been underestimated.
  Change requests come in that must be processed.
  Task(s) were mistakenly omitted during the launch that needed to be executed, but they weren’t added to the plan.
  An external dependency does not come in on time.

## Slide 20: Accurate Data is Key
The key to keeping commitments is to promptly detect schedule slips as soon as they occur.
With the TSP, one-day schedule slips can be recognized.
  Team members make personal plans with their work broken into tasks that require less than 10 hours of effort.
  Plan status is based on data that is collected in real time by team members
    task time (while executing a task)
    task complete time
  Data is accurate when team members conduct their work with process discipline.

## Slide 21: Test Your Understanding
Current status can be assessed by comparing the actual earned value to date with the planned earned value to date.
Using these values, answer the following questions:
Is the team ahead or behind schedule?
How far ahead or behind?
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Earned value this cycle to date | 43.6 | 34.5 | 1.3 | 9.1

## Slide 22: Example: Determining Current Status
In this example,
the team has completed 34.5% of the work after nine weeks, so the average EV burn rate is
the project is behind by 9.1 EV
Therefore, the project is behind by
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Earned value this cycle to date | 43.6 | 34.5 | 1.3 | 9.1

## Slide 23: Investigating the Source of Schedule Deviation
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
Three TSP measures can help you understand what might be causing schedule deviation.

## Slide 24: Checking Effort Growth
The Baseline task hours represent the total number of estimated task hours when the plan was baselined, usually at the launch.
The current plan hours represent the total number of estimated task hours in the current plan.
The Percent Change is the percent increase or decrease in task hours since the plan was baselined. in the example above, task hours have increased by:
 | Task Hours
Baseline | 660.8
Current | 745.5
Percent Change | 12.8%

## Slide 25: Investigating the Source of Schedule Deviation
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
Three TSP measures can help you understand what might be causing the deviation.

## Slide 26: Task Hours
Task time represents direct time actually spent on tasks that are in the plan.
Analyzing the actual vs. plan schedule hours can sometimes help explain schedule deviations.
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2
In this example, by week 9, the team has applied 229.9 less hours to the work than they had planned.

## Slide 27: To-Date Hours for Tasks Completed
Comparing the actual value to the planned value provides an indicator of task effort estimation accuracy.
The ratio, plan/actual is an indicator of schedule growth due to over-estimation or underestimation of task effort. A ratio close to 1 indicates that overall, the task effort estimates are balanced between overestimates and underestimates.
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2

## Slide 28: To-Date Hours for Tasks Uncompleted
To-Date Hours for tasks uncompleted denotes total task time that has accumulated for uncompleted tasks. This represents work-in-progress.
To-date hours for tasks uncompleted is an indictor of unrealized earned value.
An excessive value for this measure may indicate possible problems with how the tasks have been set up.
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2
Notes: This is the difference between the actual task hours and task hours for completed tasks.
It is an indicator of
  potential earned value
  possible problems

## Slide 29: Unrealized Earned Value
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Earned value this cycle to date | 43.6 | 34.5 | 1.3 | 9.1
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2
Unrealized EV =
(To-date hours for tasks uncompleted) * (EV per task hour)
Potential EV =
267.8 * (34.5 / 1279.3)
Potential EV =
267.8 * 0.03 = 7.2 EV (tied up in uncompleted tasks)
Unrealized EV can sometimes provide an explanation for some of the difference between planned value (PV) and earned value (EV).

## Slide 30: Possible Problems With Task Set-Up
A large number of task hours for unfinished tasks could also indicate a problem with the schedule or with the implementation.
This value of to-date hours for tasks uncompleted should be less than 20 hours per team member. If not, then it is possible that
  some tasks are too large; tasks should be set up so that they are less than approximately 10 hours in duration
  task(s) are not being completed because of one or more dependencies on other tasks

## Slide 31: Project End Date
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
Are adjustments needed to optimize project completion?

## Slide 32: Project End Dates
Baseline: project completion date for the baselined plan
Current Plan: project completion date for the current plan
Predicted: project completion date given the current load balancing among team member
 | Project End Dates
Baseline | 3/19/2012
Current Plan | 3/26/2012
Predicted | 7/30/2012

## Slide 33: Predicted End Date
Predicted project end date is the date the project will end based on the latest calendar date that a team member completes their work.
 | Project End Dates
Baseline | 3/19/2012
Current Plan | 3/26/2012
Predicted | 7/30/2012
Each of the TSP support tools provides features that facilitate workload balancing among team members.
If the workload of the team is not balanced, the team’s predicted end date will be suboptimal.

## Slide 34: A Quick Way to Estimate Predicted End Date
An approximate (and optimistic) estimate of a balanced plan predicted end date can be achieved by dividing the number of hours of work remaining by the average team hours worked per week.
To obtain a more accurate earned-value-based predicted end date from the TSP tool, have the team members work together to balance the workload.
Have the planning manager and coach review the individual plans for any anomalies with respect to the predicted end date.

## Slide 35: Section Summary
In this section, we explored a number of project status indicators that can help you understand the status of your project.
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date

## Slide 36: Managing the Plan Exercise
A 20-minute group exercise.
Each group should be prepared to make a five-minute presentation of your conclusions.
Exercise guide

## Slide 37: Topics
Introduction
Schedule status indicators
Maintaining team commitment

## Slide 38: Owning the Plan Commitments
The team members created the plan during the launch and made a public, voluntary, and credible commitment.
They left the launch owning the plan and the commitment.
What are the actions that a team leader could unwittingly take that could make the tea members lose their sense of ownership and commitment to the plan?

## Slide 39: Promoting Team Ownership of the Plan
The actions that a team leader takes speaker louder than words.
Actions the team leader can take to enable shared ownership of and commitment to the team plan include
  setting the expectation that the planning manager knows more, cares more, and does more about the plan than the team leader does
  asking for schedule status at the team meeting weekly
  ensuring that coaching is provided to all team members
  asking the team to come up with solutions when problems occur
  supporting the team in the decisions they make

## Slide 40: Weekly Meeting
The team leader guides the team through the weekly status meeting to ensure the following topics are reviewed on a regular basis.
  Status against team goals
  Activities of the role managers
  Status against personal plans to understand if load balancing is required and if there are any significant team risks
The TSP provides a weekly meeting script to guide the team through the steps of sharing key project information.

## Slide 41: Working With the Planning Manager
Communicate clearly with the planning manager regarding your expectations of the role.
Ensure that the planning manager obtains appropriate coaching and training to address the responsibilities of the role.
Encourage the planning manager to
  review team member’s personal plans to detect load-balancing problems
  work with the quality manager to ensure that personal reviews and inspections are meeting expectations
  work with the process manager to ensure that the plan is either following the process or that PIPs are generated
The planning manager should always be able to answer the key question, “Is the team behind schedule, by how much, and why?”

## Slide 42: Working with the Customer-Interface Manager
Communicate clearly with the customer-interface manager (CIM) regarding your expectations of the role.
Ensure that the CIM obtains appropriate coaching and training to address the responsibilities of the role.
The key responsibility of the role is management of the requirements process so that
  the impact of all new requirements or requirements changes are evaluated
  schedule and budget changes are negotiated and accepted by the customer and management
  unplanned work is first negotiated and agreed to (by management) before it is added to the plan or implemented

## Slide 43: Working with the TSP Coach
Work with the coach to develop a coaching plan. Obtain the coach’s and the team’s agreement with the plan.
The coach
  should check team and team-member plans weekly for data integrity, quality, and process problems.
  can provide an objective perspective
  is critical in helping the team manage problems early enough so that remedial actions can be taken to address project schedule risk

## Slide 44: Messages to Remember
The team leader ensures that the
  team is using data to manage the team plan
  team members manage their personal plans
  team understands the status of the project
  team proactively manages the project risks and issues that threaten the team’s commitments
  coach develops, maintains, and implements a sound plan for supporting the team