## Slide 1
Leading a Development Team
Reporting to Management

## Slide 3: Topics
The Management Role
Status reporting guidelines
Frequency of status reporting
Packaging the report for management
Content of the report
Are you the manager of a TSP team?
What to expect from a TSP pilot
Data-driven decision-making
How management can help the team

## Slide 4: Management Role
Establish business and product objectives, success criteria
Negotiate and approve plans
Monitor progress
Motivate proper use of data by management team
Reward quality and success

## Slide 5: Status Reporting Frequency
Weekly for the team lead’s direct management
Monthly for upper level management
General Guidelines for TSP Teams
However, reporting frequency is organization-dependent.
Work with management before a launch or as part of Meeting 1 of the launch to determine the appropriate reporting frequency.

## Slide 6: When Reporting to Management
TSP teams collect and manage a lot of detailed data.
When reporting to management, be careful not to overwhelm with too much detail.
Use data, but succinctly describe project status.
Be prepared to backup any assertions with the detail, but keep it in your hip pocket.

## Slide 7: Repackage the Data to Promote Clarity

## Slide 8: Topics
The Management Role
Status reporting guidelines
Frequency of status reporting
Packaging the report for management
Content of the report
Are you the manager of a TSP team?
What to expect from a TSP pilot
Data-driven decision-making
How management can help the team

## Slide 9: What Information Does Management Need?
Report summary
Current status
Completion projections
Recovery plan (if needed)
Quality Indicators
Next Steps

## Slide 10: Begin by Summarizing the Key Launch Results
If the project is on track, then say so.
If the project is behind schedule, then say so, but
  emphasize that a recovery plan has been developed and will be presented
  If you need help from management to recover, then indicate whether the help required is significant or minimal.

## Slide 11: Use Data to Describe Status

## Slide 12: General Guidelines
Compare current status against the baseline.
Describe any problems the team is encountering.
  If workload growth has been a problem, say why and give the principal sources.
  If task-hour performance is a problem, explain why.
Describe what has changed since the last status report.
  If previously planned actions were not taken, explain why not.
  If actions were taken but did not work, explain why not.

## Slide 13: Projecting When the Project Will Complete
State the team’s current projection for completing the project.
  Any projection is based on assumption(s).
  Accompany your projection with clearly stated assumptions.
  Use data to justify your assumptions.
  When part of a recovery plan, deliver the projection in the context of the plan.

## Slide 14: Examples: Assumptions When Projecting Project Completion
Some typical projection assumptions:
  The future task-hour rate will approximate the average of the last four weeks.
  The weekly EV rate will continue as it has for the project to date.
  We will reduce workload growth to 5% by taking the following actions: …
  We expect that the 3% plan underestimate to date will continue for the remainder of the project.

## Slide 15: Consider Developing Multiple Projections
Make several schedule projections.
  Base one on the assumption that current trends will continue.
  Base another on the assumption that your team’s recovery plan is effectively implemented.
Also consider other scenarios that seem likely to occur:
  one or more major risks materialize
  workload changes
  resource changes

## Slide 16: Developing a Schedule Projection - 1
Baseline cumulative plan value is the plan the team developed during the launch.
Based on
total estimated effort to complete project
task hours the team has available each week
Baseline Cumulative Plan Value
Percent Effort
Percent Planned or Earned Value

## Slide 17: Developing a Schedule Projection - 2
Cumulative plan value is the team’s current plan.
Team is expected to update on weekly basis.
In this example, the amount of estimated work has increased.
Percent Planned or Earned Value
Week
Baseline Cumulative Plan Value
Cumulative Plan Value

## Slide 18: Developing a Schedule Projection - 3
Cumulative earned value is the percentage of the total work completed thus far.
In this example, the team is falling behind and is at risk with respect to honoring the original commitment to management.
The key questions are
Why is the team behind?
How far behind is the team?
Baseline Cumulative Plan Value
Cumulative Earned Value
Cumulative Plan Value
Percent Planned or Earned Value

## Slide 19: Developing a Schedule Projection - 4
Cumulative predicted earned value is an estimate of the rate at which work will be completed based on the data thus far.
Percent Planned or Earned Value
Percent Planned or Earned Value
Baseline Cumulative Plan Value
Cumulative Earned Value
Cumulative Plan Value
Cumulative Predicted Earned Value

## Slide 20: The Recovery Plan
If the project is behind schedule, the team must have a recovery plan to present.
  Present alternative projections accompanied by your assumption(s) for each projection.
  If the team is unsure about a recovery plan, then clearly state the issues involved and request management guidance.

## Slide 21: Example: Recovery Plan
This team developed a recovery plan based on increasing task hours by having dedicated “non-interrupt” hours each day.
Percent Planned or Earned Value
Baseline Cumulative Plan Value
Cumulative Earned Value
Cumulative Plan Value
Cumulative Predicted Earned Value
Recovery Plan

## Slide 22: Report Indicators of Quality
As product components are completed, report their quality indicator statistics.
Component A
Component A

## Slide 23: Concluding the Report
If the project is on track, then everyone is happy.
If the project is behind, then you have presented a recovery plan.
  Summarize your presentation by precisely defining what you plan to do and when you plan to do it.
  If you need help from management, be clear about what you need and when you need it.
  State what management can expect to see at the next meeting, based on the recovery plan that was agreed to.
TSP Project Status Report - Specification STATUS

## Slide 24: Topics
The Management Role
Status reporting guidelines
Frequency of status reporting
Packaging the report for management
Content of the report
Are you the manager of a TSP team?
What to expect from a TSP pilot
Data-driven decision-making
How management can help the team

## Slide 25: As a Manager, What Are Your Initial Expectations?
If you are a manager of a new TSP project, it is important to realize that
  the initial project is most probably estimating their work in the absence of historical data
  adjustments will need to be made to estimating parameters after sufficient data is collected and analyzed by the team
  there is an initial learning curve with TSP; the team may require time to change old habits
Once a team has generated accurate performance data, it is reasonable to begin setting improvement goals.

## Slide 26: Cultivating a Data-Driven Organization
When organizations have accurate data on prior projects, comparisons with TSP projects can be helpful and constructive.
When organizations do not have prior data, comparisons are generally based on idealized memories.
As management, you can dramatically assist the transition to TSP by using data to guide judgments and the decision-making process.

## Slide 27: Management Reaction to Data
With the introduction of the TSP, managers are presented with authentic data that have been captured in real-time. For most software managers, this is a completely new experience.
The way that management reacts to the data has a major impact on knowledge workers.
  Using the data to evaluate performance makes that data threatening to people.
  If people feel threatened, they will either stop gathering detailed data or they will “adjust” the data.
Using data to assess personal performance would destroy the effectiveness of TSP.

## Slide 28: Responding To Data: An Example
A TSP team reports to management that they are behind schedule due to overestimation of team member task hours.
While the estimated task hours for the last two weeks was 20 hours per week, the team was only able to achieve an average of 15 hours per individual.
If you are the manager of the team, what would be your response?

## Slide 29: Consequences of Your Response to Data
Many new TSP teams find that they can only achieve 12 task hours (or less) per team member per week.
If the team is pressured to increase their hours, team members will simply start adjusting their data to show more hours.
What impact would such a response have on the project completion date?

## Slide 30: A Better Response
Management can help the team by approaching problems like this with a supportive attitude.
An appropriate response to the problem of low task hours would be to suggest that the TSP coach lead a session with the team members
  to understand the impact of low task hours on their committed plan
  to have team members challenge themselves to understand the causes of low task hours
  to develop a list of things that team members or management could do to raise their task hours

## Slide 31: Other Ways That Management Could Help
Other ways that management can help the team increase task time:
  protecting team members from special requests
  providing full-time dedicated resources
  authorizing needed training
  providing an adequate and cohesive workspace for the team
  providing adequate resources for TSP team coaching

## Slide 32: Another Example Scenario
Some organizations have existing standards for reporting schedule status (e.g., the use of a specific project management tool).
The TSP tool may not support the standard unless additional effort is applied to transforming the output to the standardized format.
In this case, a TSP team leader may face a significant challenge if there are two separate schedules to maintain and keep in synch.
If you are the manager, how could you help?

## Slide 33: Supporting the Team
For TSP pilot projects, there is already a learning curve involved with transitioning to a new way of performing the work.
The weekly status report should not require the additional overhead of having the team manage and synch two different reporting formats.
Management can help the team by
  waiving the requirement to report status in the standard format
  considering the new report standard at the completion of the pilot

## Slide 34: Ingredients for Successful TSP Teams

## Slide 35: Messages to Remember
TSP Team:
Prepare your status reports thoughtfully.
Use data! But, repackage the data to promote clarity of your key messages.
When behind on schedule, be prepared to say why … and have a compelling recovery plan at the ready.
Management:
Foster data-driven decision making in your organization.
Never use data to assess the performance of individuals.
Support and trust the team. Help them to succeed.

## Slide 36: Exercise: Reporting to Management
A 30-minute group exercise.
Be prepared to report your conclusions.
Exercise guide