## Slide 1
Leading a Development Team
Getting Better At It

## Slide 3: Topics
Checkpoint review
Cycle and project postmortem
Process improvement proposals (PIPS)

## Slide 4: The Checkpoint Review
A checkpoint review is a one- or two-day event where the team’s coach
  analyzes the team’s data
  interviews team members
to determine the fidelity of TSP practices by the team.
The checkpoint review is conducted early on—during the third or fourth week of the project cycle.
The primary purpose of the review is to diagnose and correct any problems that the team may be having with TSP implementation.
The outcome of a checkpoint review is a report that
  identifies strengths and weaknesses of the TSP implementation
  recommends corrective actions

## Slide 5: Why A Checkpoint Review?
For many individuals, implementing TSP, especially for the first time, is a very different way of conducting work.
It is not uncommon that a team will have some difficulties with the process, the TSP support tool, or the role responsibilities of team members.
The checkpoint review is an early-on remedial intervention that can help a team make adjustments so that they are practicing the TSP as intended.
The checkpoint review is always conducted for a new team. After the initial planning cycle, the checkpoint review becomes optional and is conducted on an as-needed basis.
The intention of the checkpoint review is to help and support the team.

## Slide 6: Conducting the Checkpoint
The coach analyzes individual and team data.
Coach meets with the team to discuss their issues, concerns, and suggestions for improvement.
Coach meets one-on-one with each team member.
Coach analyzes the interview data and prepares preliminary findings.
Coach meets with team to discuss preliminary findings and the coach’s recommendations.
Coach and team leader review final findings and recommendations with the team.
Coach and team leader review final findings with management.

## Slide 7: Action Plan
The team develops an action plan to address any findings that result from the checkpoint review.
The checkpoint review is an
excellent opportunity to make course corrections early on during a project.

## Slide 8: Topics
Checkpoint review
Cycle and project postmortem
Process improvement proposals (PIPS)

## Slide 9: Postmortems
A postmortem is a planned activity that focuses on learning from past experiences.
Postmortems are also known as lessons-learned meetings and retrospectives.
In the TSP, postmortems are encouraged
  at the personal level, after completing work on a project part
  at the team level, after completing a launch or re-launch
  at the team level, after completing a project cycle
The expected outcomes of a postmortem include:
  Historical data and analysis results
  Process improvement proposals (PIPs)

## Slide 10: Our Context
In this module, we consider project cycle postmortems.

## Slide 11: Cycle Postmortems and Project Postmortem
The Project
Release 1
Release 2
Release n
Cycle 1
Cycle 2
Cycle 3
Cycle 4
Cycle 5
Cycle 6
Cycle 7
Cycle n
Launch
R
P
R
P
R
P
R
P
R
P
R
P
R
P
P*

## Slide 12: How to?
The TSP script, PM, provides guidance for conducting a postmortem.
There are two parts to a postmortem.
  Preparation
  Meeting
During the preparation phase, the planning manager consolidates the project data, and analyzes it to present three project perspectives:
  Planning
  Quality
  Process
During the meeting phase, the team meets to
  review the analysis results
  collect and discuss subjective feedback
  draw conclusions
  develop an action plan to address postmortem findings

## Slide 13: Planning Analysis: Questions to Ask
Question | Measures that address question
How accurate was the completion date estimate? | Plan weeks Actual weeks
How accurate was the effort estimate? | Total plan task hours Total actual task hours
Percentage of requirements addressed? | % requirements addressed
What was the rate of effort growth during the project? | Effort growth / time
What was the rate of project size growth project? | Size growth / time
How did planned weekly task hours compare to actual weekly task hours? | Planned weekly task hours Actual weekly task hours
How did the rate of weekly task completion compare to the planned weekly rate of task completion? | Weekly planned value Weekly earned value
Were the size estimates accurate? | Planned task hrs. for completed tasks Actual task hrs. for completed tasks
Were the size estimates accurate? | Planned size Actual size

## Slide 14: Planning Analysis: Questions to Ask
Question | Measures that address question
How good was our quality? | Planned defect density in pilot test Actual defect density in pilot test
What types of defects did we inject? What types of defects occurred most frequently? What defects required the longest fix times? | Pareto analysis of defects by type Pareto analysis of defect types by find/fix time
Where were defects injected? | # defects injected per process phase
Where were defects removed? | # defects removed per process phase
What was the defect injection rate? | Defects injected per hour
What was the defect removal rate? | Defects removed per hour
Were reviews and inspections effective? | Yield per review phase Yield per inspection phase
What were the review rates? | Product size reviewed per hour
What was the quality of each work product? | Defect density after unit test

## Slide 15
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Estimate quality
Produce schedule
Develop product
Productivity database
Process phases
Quality database
Resources available
Size, resource, & schedule data
Process analysis
Tracking reports
Work delivery
Customer need
Customer
Management
Legend
Items
Tasks
Size database
Define requirements
Updated
TSP Planning Framework

## Slide 16: Topics
Checkpoint review
Cycle and project postmortem
Process improvement proposals (PIPS)

## Slide 17: Process Improvement Proposals
Process improvement is a cornerstone of the TSP.
A key outcome of any postmortem is the generation of process improvement proposals (PIPs).
  Are there process steps that can be improved?
  If a process step wasn’t followed, reconsider the need for the process step in the future.
  If an activity was repeated multiple times but was not defined, then the team should consider defining a process for it. (This will then permit you to measure, plan, and track your work.)

## Slide 18: Where Does It Stop?
It doesn’t. That’s why it’s called continuous process improvement.
Teams must continue to strive to be better.
Competition and the desire for increased quality, profit, and customer satisfaction are what motivate teams to search continually for process improvements.
The problems of software process change are often complicated by the fact that no one is responsible to make it happen.
If software process improvement isn't anybody's job, it is not surprising that it doesn't get done!
If it is important enough to do, however, someone must be assigned the responsibility and given the necessary resources. Until this is done, software process development will remain a nice thing to do someday, but never today.
- Watts Humphreys