Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Answers for

# PROBE Part II Exercise

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Size Estimating Template

| Student | JD Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Instructor | Humphrey | Program # | 9A |

| BASE PROGRAM LOC |  |  |  |  |  |  |  |  |  | ESTIMATE |  |  |  |  | ACTUAL |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASE SIZE (B) => => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 224 |  |  |  |  |
| LOC DELETED (D) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
| LOC MODIFIED (M) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |
| OBJECT LOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BASE ADDITIONS |  | TYPE1 |  |  | METHODS |  |  | REL. SIZE |  |  | LOC |  |  | LOC |  |  |
| Misc additions |  |  |  |  |  |  |  |  |  |  |  | 9 |  |  |  |  |
| TOTAL BASE ADDITIONS (BA) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 9 |  |  |  |  |
| NEW OBJECTS |  | TYPE |  |  | METHODS |  |  | REL. SIZE |  |  | LOC (New Reused*) |  |  |  |  |  |
| Input_data |  |  | I/O |  |  | 1 |  |  | M |  |  | 16 |  |  |  |  |
| Linked_List |  |  | Data |  |  | 5 |  |  | M |  |  | 44 |  |  |  |  |
| Calc_mean |  |  | Calc |  |  | 1 |  |  | M |  |  | 11 |  |  |  |  |
| Calc_SD |  |  | Calc |  |  | 1 |  |  | L |  |  | 25 |  |  |  |  |
| Print_result |  |  | I/O |  |  | 1 |  |  | M |  |  | 16 |  |  |  |  |
| TOTAL NEW OBJECTS (NO) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 112 |  |  |  |  |
| REUSED OBJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| REUSED TOTAL (R) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | SIZE |  |  | TIME |  |
| Estimated Object LOC (E): E = BA+NO+M |  |  |  |  |  |  |  |  |  |  |  | 141 |  |  |  |  |
| Regression Parameters: Size and Time |  |  |  |  |  |  |  |  |  |  |  | 29.34 |  |  | 71.91 |  |
| Regression Parameters: Size and Time |  |  |  |  |  |  |  |  |  |  |  | .83 |  |  | 1.71 |  |
| Estimated New and Changed LOC (N): N = + *E |  |  |  |  |  |  |  |  |  |  |  | 146.37 |  |  |  |  |
| Estimated Total LOC: T = N + B - D - M + R |  |  |  |  |  |  |  |  |  |  |  | 350.37 |  |  |  |  |
| Estimated Total New Reuse (sum of * LOC): |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
| Estimated Total Development Time: Time = + *E |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 313.01 |  |
| Prediction Range: Range |  |  |  |  |  |  |  |  |  |  |  | 37 |  |  | 32 |  |
| Upper Prediction Interval: UPI = N + Range |  |  |  |  |  |  |  |  |  |  |  | 183.37 |  |  | 345.01 |  |
| Lower Prediction Interval: LPI = N - Range |  |  |  |  |  |  |  |  |  |  |  | 109.37 |  |  | 281.01 |  |
| Prediction Interval Percent: |  |  |  |  |  |  |  |  |  |  |  | 70% |  |  | 70% |  |

PSP2.1 Project Plan Summary

| Engineer | JD Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Project |  | Program | 9A |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour |  |  |  |  |  |  |  |  |  |  |  |  |
| Planned Time |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | (Planned / Actual) |  |  |  |
| % Reuse |  |  |  |  |  |  |  |  |  |  |  |  |
| % New Reuse |  |  |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC |  |  |  |  |  |  |  |  |  |  |  |  |
| Yield % |  |  |  |  |  |  |  |  |  |  |  |  |
| % Appraisal COQ |  |  |  |  |  |  |  |  |  |  |  |  |
| % Failure COQ |  |  |  |  |  |  |  |  |  |  |  |  |
| COQ A/F Ratio |  |  |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC): | Plan |  |  |  | Actual |  |  |  | To Date |  |  |  |
| Base(B) | 224 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Modified (M) | 20 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Added (A) | 126 |  |  |  |  |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |  |
| Reused (R) | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Total New & Changed (N) | 146 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |  |
| Total LOC (T) | 350 |  |  |  |  |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |  |
| Total New Reuse | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Object LOC (E) | 141 |  |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) | 183 |  |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) | 109 |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |  |
| Planning | 49 |  |  |  |  |  |  |  |  |  |  |  |
| Design | 87 |  |  |  |  |  |  |  |  |  |  |  |
| Design review | 16 |  |  |  |  |  |  |  |  |  |  |  |
| Code | 64 |  |  |  |  |  |  |  |  |  |  |  |
| Code review | 20 |  |  |  |  |  |  |  |  |  |  |  |
| Compile | 15 |  |  |  |  |  |  |  |  |  |  |  |
| Test | 33 |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem | 29 |  |  |  |  |  |  |  |  |  |  |  |
| Total | 313 |  |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) | 345 |  |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 281 |  |  |  |  |  |  |  |  |  |  |  |

1 L-Logic, I-I/O, C-Calculation, T-Text, D-Data, S-Set-up