Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for

# PROBE Part II Exercise

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

PROBE Part II Exercise

Overview

| #### Exercise #### Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Instructions | 2 |
|  | JD’s PROBE Data | 3 |
|  | Size Estimating Template and Instructions | 5 |
|  | Project Plan Summary form and Instructions | 7 |

| #### Exercise #### Objectives | After completing this exercise, participants will - understand the last three steps of the PROBE method - estimate program size - estimate resources - calculate prediction intervals - have completed JD’s size estimating template have completed the plan column program size and time in phase sections of JD’s project plan summary |
| --- | --- |

| #### Exercise #### Instructions | You have been provided with JD’s data for the last three steps of the PROBE method. - JD’s size regression data - JD’s effort regression data - JD’s time in phase To Date % from his last project - JD’s prediction interval ranges - JD’s partially completed size estimating template Using this data, complete all of the bottom calculation portion of JD’s size estimating template. When you have completed JD’s size estimating template, use the data from the size estimating template and JD’s other data to fill in the plan column program size and time in phase sections of JD’s project plan summary. |
| --- | --- |

### JD’s Data for the Last Three Steps of PROBE

| #### JD’s Size #### Regression |  | Regression Parameters for Size Estimates 0 = 29.34 1 = .83 R2 = .8 | . |
| --- | --- | --- | --- |

| #### JD’s Effort Regression |  | Regression Parameters for Effort Estimates 0 = 71.91 1 = 1.71 R2 = .7 |  |
| --- | --- | --- | --- |

Continued on next page

### JD’s Data for the Last Three Steps of PROBE, continued

| #### JD’s Time in Phase To Date % | From his last PSP project, the following table contains JD’s time in phase. To Date % |
| --- | --- |

| Phase | % Time |
| --- | --- |
| Planning | 16% |
| Design | 28% |
| Design Review | 5% |
| Code | 20% |
| Code Review | 6% |
| Compile | 5% |
| Test | 11% |
| Postmortem | 9% |

| #### JD’s Prediction Interval Ranges |  |
| --- | --- |

| Item | PI Range | PI Percentage |
| --- | --- | --- |
| Size | 37 | 70% |
| Time | 32 | 70% |

Size Estimating Template

| Student | JD Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Instructor | Humphrey | Program # | 9A |

| BASE PROGRAM LOC |  |  |  |  |  |  |  |  |  | ESTIMATE |  |  |  |  | ACTUAL |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASE SIZE (B) => => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 224 |  |  |  |  |
| LOC DELETED (D) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
| LOC MODIFIED (M) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 20 |  |  |  |  |
| OBJECT LOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BASE ADDITIONS |  | TYPE1 |  |  | METHODS |  |  | REL. SIZE |  |  | LOC |  |  | LOC |  |  |
| Main additions |  |  |  |  |  |  |  |  |  |  |  | 9 |  |  |  |  |
| TOTAL BASE ADDITIONS (BA) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 9 |  |  |  |  |
| NEW OBJECTS |  | TYPE |  |  | METHODS |  |  | REL. SIZE |  |  | LOC (New Reused*) |  |  |  |  |  |
| Input_data |  |  | I/O |  |  | 1 |  |  | M |  |  | 16 |  |  |  |  |
| Linked_List |  |  | Data |  |  | 5 |  |  | M |  |  | 44 |  |  |  |  |
| Calc_mean |  |  | Calc |  |  | 1 |  |  | M |  |  | 11 |  |  |  |  |
| Calc_SD |  |  | Calc |  |  | 1 |  |  | L |  |  | 25 |  |  |  |  |
| Print_result |  |  | I/O |  |  | 1 |  |  | M |  |  | 16 |  |  |  |  |
| TOTAL NEW OBJECTS (NO) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 112 |  |  |  |  |
| REUSED OBJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| REUSED TOTAL (R) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | SIZE |  |  | TIME |  |
| Estimated Object LOC (E): E = BA+NO+M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regression Parameters: Size and Time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regression Parameters: Size and Time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated New and Changed LOC (N): N = + (*E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Total LOC: T = N + B - D - M + R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Total New Reuse (sum of * LOC): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Total Development Time: Time = + (*E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prediction Range: Range |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval: UPI = N + Range |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval: LPI = N - Range |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prediction Interval Percent: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Size Estimating Template Instructions (Continued)

| Calculations | - Estimated Object LOC: sum the base additions (BA), new object (NO), and modified (M) LOC and enter as estimated object LOC (E). - Regression Parameters: follow the procedure in the PROBE Estimating Script (Table C36, page 679) to calculate the size and time regression parameters. - Estimated New and Changed LOC (N): using the size regression parameters and the estimated object LOC (E), calculate the estimated new and changed LOC (N) as: N=β0+β1∗E - Estimated Total LOC: calculate the estimated total LOC as T=N+B-D-M+R. - Estimated Total New Reuse: sum and enter the New Reuse * items. - Estimate Total Development Time: using the time regression parameters and estimated object LOC (E), calculate the estimated development time as: Time=β0+β1∗E - Calculate and enter the projection Range for both the size and time estimates. - Calculate the upper (UPI) and lower (LPI) prediction intervals for both the size and time estimates: - UPI=N+Range, - LPI=N-Range If the LPI is negative, use zero. - Prediction Interval Percent: - List the probability percent used to calculate the prediction intervals (70% or 90%) |
| --- | --- |

PSP2.1 Project Plan Summary

| Engineer | JD Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Project |  | Program | 9A |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour |  |  |  |  |  |  |  |  |  |  |  |  |
| Planned Time |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | (Planned / Actual) |  |  |  |
| % Reuse |  |  |  |  |  |  |  |  |  |  |  |  |
| % New Reuse |  |  |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC |  |  |  |  |  |  |  |  |  |  |  |  |
| Yield % |  |  |  |  |  |  |  |  |  |  |  |  |
| % Appraisal COQ |  |  |  |  |  |  |  |  |  |  |  |  |
| % Failure COQ |  |  |  |  |  |  |  |  |  |  |  |  |
| COQ A/F Ratio |  |  |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC): | Plan |  |  |  | Actual |  |  |  | To Date |  |  |  |
| Base(B) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |  |
| Deleted (D) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Modified (M) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Added (A) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |  |
| Reused (R) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Total New & Changed (N) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |  |
| Total LOC (T) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |  |
| Total New Reuse |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Object LOC (E) |  |  |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) |  |  |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) |  |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |  |
| Planning |  |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |  |
| Design review |  |  |  |  |  |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |  |
| Code review |  |  |  |  |  |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |  |  |  |  |  |
| Test |  |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) |  |  |  |  |  |  |  |  |  |  |  |  |

PSP2.1 Project Plan Summary Instructions

| Purpose | To hold the estimated and actual project data in a convenient and readily retrievable form |
| --- | --- |
| Header | Enter the specified data. |
| Program Size (LOC) | Prior to Development: • From the Size Estimating Template enter the estimated Base (B), Deleted (D), Modified (M), Reused (R), New and Changed LOC (N), New Reused, and Object LOC (E), • Calculate the Added LOC (A) as A=N-M. • Calculate the Total LOC (T) as T=N+B-M-D+R. After Development: • If the base LOC (B) has changed, enter the new value. • Measure the total program size and enter it as the Total LOC (T) - Actual . • Review your source code and, with the help of program 3A, determine the Actual LOC that were deleted (D), modified (M), or reused (R), and the number of Object LOC(E) • Calculate the LOC of added code as A = T - B+ D - R. • Calculate the total new and changed LOC as N = A + M. |
| Time in Phase | • Under Plan, enter your original estimate of the total development time and the time required by phase. • Under Actual, enter the actual time in minutes spent in each development phase. • Under To Date, enter the sum of the actual time and the To Date time from your most recently developed program. • Under To Date %, enter the percentage of To Date time in each phase. |

1 L-Logic, I-I/O, C-Calculation, T-Text, D-Data, S-Set-up