Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Earned Value Plan Exercise

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

Earned Value Plan Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Instructions | 2 |
|  | JD’s Availability Data | 2 |
|  | JD’s Project Plan Summary | 3 |
|  | Task Planning Template and Instructions | 5 |
|  | Schedule Planning Template and Instructions | 7 |

| #### Exercise Objectives | After completing this exercise, participants will - understand how to produce an earned value plan - have completed an earned value plan for JD |
| --- | --- |

| #### Exercise #### Instructions | You have been provided with - JD’s availability to work on program 9A - JD’s completed plan for program 9A - a blank task template - a blank schedule template Using these and the PSP phases as task, create - JD’s task plan - JD’s schedule plan After you have completed the task and schedule templates, we will have a class discussion. |
| --- | --- |

| #### JD’s Availability | JD predicts that he will only have 1 hour per day to work on this project. |
| --- | --- |

Continued on next page

PSP2.1 Project Plan Summary

| Engineer | J. D. Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Project | PSP | Program | 9A |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour | 28 |  |  |  |  |  |  |  |  |  |  |  |
| Planned Time | 313 |  |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | (Planned / Actual) |  |  |  |
| % Reuse | 0% |  |  |  |  |  |  |  |  |  |  |  |
| % New Reuse | 0% |  |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC | 13.7 |  |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC | 102.7 |  |  |  |  |  |  |  |  |  |  |  |
| Yield % | 57.1% |  |  |  |  |  |  |  |  |  |  |  |
| % Appraisal COQ | 11.5% |  |  |  |  |  |  |  |  |  |  |  |
| % Failure COQ | 15.3% |  |  |  |  |  |  |  |  |  |  |  |
| COQ A/F Ratio | .75 |  |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC): | Plan |  |  |  | Actual |  |  |  | To Date |  |  |  |
| Base(B) | 224 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Modified (M) | 20 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Added (A) | 126 |  |  |  |  |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |  |
| Reused (R) | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |  |
| Total New & Changed (N) | 146 |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |  |
| Total LOC (T) | 350 |  |  |  |  |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |  |
| Total New Reuse | 0 |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Object LOC (E) | 141 |  |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) | 183 |  |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) | 109 |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |  |
| Planning | 49 |  |  |  |  |  |  |  |  |  |  |  |
| Design | 87 |  |  |  |  |  |  |  |  |  |  |  |
| Design review | 16 |  |  |  |  |  |  |  |  |  |  |  |
| Code | 64 |  |  |  |  |  |  |  |  |  |  |  |
| Code review | 20 |  |  |  |  |  |  |  |  |  |  |  |
| Compile | 15 |  |  |  |  |  |  |  |  |  |  |  |
| Test | 33 |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem | 29 |  |  |  |  |  |  |  |  |  |  |  |
| Total | 313 |  |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) | 345 |  |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 281 |  |  |  |  |  |  |  |  |  |  |  |

PSP2.1 Project Plan Summary (continued)

| Student | J. D. Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Project | PSP | Program | 9A |

| Defects Injected | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning | 1 |  |  |  |  |  |  |  |  |  |  |
| Design | 5 |  |  |  |  |  |  |  |  |  |  |
| Design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Code | 8 |  |  |  |  |  |  |  |  |  |  |
| Code review | 0 |  |  |  |  |  |  |  |  |  |  |
| Compile | 0 |  |  |  |  |  |  |  |  |  |  |
| Test | 1 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 15 |  |  |  |  |  |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| Design | 2 |  |  |  |  |  |  |  |  |  |  |
| Design review | 3 |  |  |  |  |  |  |  |  |  |  |
| Code | 0 |  |  |  |  |  |  |  |  |  |  |
| Code review | 3 |  |  |  |  |  |  |  |  |  |  |
| Compile | 5 |  |  |  |  |  |  |  |  |  |  |
| Test | 2 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 15 |  |  |  |  |  |  |  |  |  |  |
| After Development |  |  |  |  |  |  |  |  |  |  |  |
| Defect Removal Efficiency | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Defects/Hour - Design review | 11.25 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Code review | 9 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Compile | 20 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Test | 3.6 |  |  |  |  |  |  |  |  |  |  |
| DRL(DLDR/UT) | 3.1 |  |  |  |  |  |  |  |  |  |  |
| DRL(Code Review/UT) | 2.5 |  |  |  |  |  |  |  |  |  |  |
| DRL(Compile/UT) | 5.6 |  |  |  |  |  |  |  |  |  |  |

Task Planning Template

| Student |  | Date |  |
| --- | --- | --- | --- |
| Instructor |  | Program # |  |

| Task |  | Plan |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value |
| Totals |  |  |  |  |  |  |  |  |  |

Task Planning Template Instructions

| Purpose | • To estimate the development time for each project task • To compute the planned value for each project task • To estimate the planned completion date for each task • To provide a basis for tracking schedule progress even when the tasks are not completed in the planned order |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Include every significant task. • Use task names and numbers that support the activity and are consistent with the project work breakdown structure. |
| Header | Enter the following: • Your name • Today's date • The instructor's name • The program number |
| Task | • Enter a task number and name. List the tasks in the order in which you expect to complete them. • Select tasks that have explicit completion criteria, for example planning completed, program compiled and all defects corrected, testing completed and all defects corrected, and so on. |
| Plan - Hours | • Enter the planned hours for each task. |
| Plan - Planned Value | • Total the planned hours for all the tasks. • For each task, calculate the percent its planned hours are of total hours. • Enter this percentage as the planned value for that task. • The total planned value should equal 100. |
| Plan - Cumulative Hours | • Enter the cumulative sum of the plan hours down through each task. |
| Plan - Cumulative Value | • Sum the planned values down through each task. • Before proceeding, complete the Schedule Planning Template down through Plan-Cumulative Hours . • Then complete the Schedule Planning and Task Planning templates together. |
| Plan Date - Monday | • For each cumulative hours entry, find the plan cumulative hours entry on the Schedule Planning Template that equals or just exceeds it • Enter the date from that row (of the Schedule Planning Template) as the plan date on the Task Planning Template. • If several weeks on the Schedule Template have the same cumulative value, enter the earliest date. • Unless you made daily plans, pick the plan date as the Monday of the week during which completion for that task is planned. |
| Actual Date | • As each task is completed, enter the completion date. |
| Earned Value | • For each completed task, enter the planned value. |
| Cumulative Earned Value | • As each task is completed, total all the earned value entries and enter that total beside the latest task that was completed. |

Schedule Planning Template

| Student |  | Date |  |
| --- | --- | --- | --- |
| Instructor |  | Program # |  |

|  |  | Plan |  |  | Actual |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | Date | Direct | Cumulative | Cumulative | Direct | Cumulative | Cumulative | Adjusted |
| No. | Monday | Hours | Hours | Planned Value | Hours | Hours | Earned Value | Earned Value |

Schedule Planning Template Instructions

| Purpose | - To record the estimated and actual hours expended by calendar period - To relate the task planned value to the calendar schedule - To calculate adjusted planned and earned values when tasks change |
| --- | --- |
| General | - Expand this template or use multiple pages as needed - Complete in conjunction with the task planning template |
| Header | Enter the following: - Your name - Today's date - The instructor's name - The program number |
| Week Number | - From the project start, enter a week number, typically starting with 1 - For very small projects, it may be more convenient to use days instead of weeks. |
| Date (Monday) | - Enter the calendar date for each week. - Pick a standard day in the week, for example, Monday. |
| Plan-Direct Hours | - Enter the planned number of direct project hours you expect to spend each week. - Consider non-work time such as vacations, holidays, and so on. - Consider other committed activities such as classes, meetings, and other projects. |
| Plan-Cumulative Hours | - Enter the cumulative planned hours through each week |
| Plan-Cumulative Planned Value | For each week: - Take the plan cumulative hours from the Schedule Planning Template. - On the Task Planning Template, find the task with nearest equal or lower plan cumulative hours and note its plan cumulative value. - Enter this cumulative value in the Schedule Planning Template for that week. - If the cumulative value for the prior week still applies, enter it again. |
| Actual | - During development, enter the actual direct hours, cumulative hours, and cumulative earned value for each week. - Determine status against plan by comparing the cumulative planned value and the actual cumulative earned value. |
| Adjusted Earned Value | Proportionately adjust the earned value up or down as tasks are added or deleted. The adjusted earned value compensates for these changes without requiring a complete new plan. |