Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Coaching PSP-trained Developers Exercise
Part 1

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

Coaching PSP-trained Developers Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Instructions | 2 |
|  | Background Information | 3 |
|  | Otto’s Project Plan Summary | 4 |
|  | Otto’s Cycle Summary (Plan) | 6 |
|  | Otto’s Size Estimating Template | 7 |

| Exercise Objectives | After completing this exercise, participants will - have a better understanding of the issues involved in using PSP at work - understand how to evaluate a PSP plan, how to check progress against a plan, and how to evaluate a completed PSP project |
| --- | --- |

| #### Exercise #### Instructions | Read the background information, then - review Otto’s PSP project plan summary, cycle summary, and size estimating template for adding compact disk capability to the existing radio - identify any problems with the plan and recommend changes - prepare and present a short presentation (10 minutes) on your findings |
| --- | --- |

Background

| #### Background | Otto Audio has recently received the business to supply a major automotive manufacturer with a new model of car radio. This new model will offer the driver the ability to play a cassette tape, compact disk, or AM/FM tuner - all integrated into the single radio mounted in the instrument panel. Otto Audio has developed previous radios with a cassette and tuner. The new model will employ a large percentage of the previous model’s design. In particular, the embedded software for the new model will be built upon the existing software for the cassette/tuner model. You, the manager responsible for developing the software for this new radio, assigned Otto, a PSP-trained software developer, the task of adding the compact disc functionality to the existing software. To perform this task, Otto was given a specification for controlling the new compact disc mechanism and an operational competitive radio model (a Sunny), which his design should emulate behaviorally. Otto proceeded to review the existing software and develop a plan to build and integrate the compact disc software. Otto has now completed his PSP project plan summary, cycle summary (plan), and size estimating template and has brought them to you for review. |
| --- | --- |

PSP3 Project Plan Summary

| Engineer | Otto | Date | 10/31 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | initial plan |
| Component | Compact Disc | Language | C |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour | 22.79 |  |  |  |  |  |  |  |  |  |  |
| Planned Time | 1554 |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | (Planned/Actual) |  |  |
| % Reused | .5 |  |  |  |  |  |  |  |  |  |  |
| % New Reused | 24.5 |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC | 33.9 |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC | 107 |  |  |  |  |  |  |  |  |  |  |
| Yield | 15.9% |  |  |  |  |  |  |  |  |  |  |
| % Appraisal COQ | 4.0 |  |  |  |  |  |  |  |  |  |  |
| % Failure COQ | 24 |  |  |  |  |  |  |  |  |  |  |
| COQ A/F Ratio | .17 |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC) | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Base(B) | 7000 |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Modified (M) | 25 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Added (A) | 565 |  |  |  |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |
| Reused (R) | 40 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Total New & Changed (N) | 590 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |
| Total LOC (T) | 7605 |  |  |  |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |
| Total New Reused | 145 |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) | 932 |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) | 248 |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 155 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 124 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 31 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 140 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 31 |  |  |  |  |  |  |  |  |  |  |
| Code | 591 |  |  |  |  |  |  |  |  |  |  |
| Code review | 31 |  |  |  |  |  |  |  |  |  |  |
| Compile | 62 |  |  |  |  |  |  |  |  |  |  |
| Test | 311 |  |  |  |  |  |  |  |  |  |  |
| Postmortem | 78 |  |  |  |  |  |  |  |  |  |  |
| Total | 1554 |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) | 2455 |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 653 |  |  |  |  |  |  |  |  |  |  |

PSP3 Project Plan Summary (continued)

| Engineer | Otto | Date | 10/31 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | initial plan |
| Component | Compact Disc | Language | C |

| Defects Injected | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 6 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 8 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Code | 49 |  |  |  |  |  |  |  |  |  |  |
| Code review | 0 |  |  |  |  |  |  |  |  |  |  |
| Compile | 0 |  |  |  |  |  |  |  |  |  |  |
| Test | 0 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 63 |  |  |  |  |  |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 2 |  |  |  |  |  |  |  |  |  |  |
| Code | 0 |  |  |  |  |  |  |  |  |  |  |
| Code review | 8 |  |  |  |  |  |  |  |  |  |  |
| Compile | 33 |  |  |  |  |  |  |  |  |  |  |
| Test | 20 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 63 |  |  |  |  |  |  |  |  |  |  |
| After Development |  |  |  |  |  |  |  |  |  |  |  |
| Defect Removal Efficiency | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Defects/Hour - Design review | 3.9 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Code review | 15.5 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Compile | 31.9 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Test | 3.9 |  |  |  |  |  |  |  |  |  |  |
| DRL(DLDR/UT) | 1.0 |  |  |  |  |  |  |  |  |  |  |
| DRL(CodeReview/UT) | 4.0 |  |  |  |  |  |  |  |  |  |  |
| DRL(Compile/UT) | 8.2 |  |  |  |  |  |  |  |  |  |  |

Cycle Summary

| Engineer | Otto |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  | 10/31 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project | 2001 XQ35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Initial Plan |  |  |  |  |  |
| Component | Compact Disc |  |  |  |  |  |  |  |  |  |  | Language |  |  |  |  | C |  |  |  |  |  |
| Cycle |  |  | 1 |  |  |  |  | 2 |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |
|  |  |  | Plan |  |  | Actual |  | Plan |  |  | Actual |  |  |  | Plan |  |  |  |  | Actual |  |  |
| Program Size (LOC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Base(B) |  | 7000 |  |  |  |  |  |  | 7335 |  |  |  |  |  |  | 7000 |  |  |  |  |  |  |
| Deleted (D) |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Modified (M) |  | 0 |  |  |  |  |  |  | 25 |  |  |  |  |  |  | 25 |  |  |  |  |  |  |
| Added (A) |  | 295 |  |  |  |  |  |  | 270 |  |  |  |  |  |  | 565 |  |  |  |  |  |  |
| Reused (R) |  | 40 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 40 |  |  |  |  |  |  |
| Total New & Changed (N) |  | 295 |  |  |  |  |  |  | 295 |  |  |  |  |  |  | 590 |  |  |  |  |  |  |
| Total LOC (T) |  | 7335 |  |  |  |  |  |  | 7605 |  |  |  |  |  |  | 7605 |  |  |  |  |  |  |
| Total New Reused |  | 145 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 145 |  |  |  |  |  |  |
| Time in Phase (min.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 124 |  |  |  |  |  |  |  |  |  |  |  |  |  | 124 |  |  |  |  |  |  |
| HLD Review |  | 31 |  |  |  |  |  |  |  |  |  |  |  |  |  | 31 |  |  |  |  |  |  |
| Design |  | 70 |  |  |  |  |  |  | 70 |  |  |  |  |  |  | 140 |  |  |  |  |  |  |
| Design Review |  | 15 |  |  |  |  |  |  | 16 |  |  |  |  |  |  | 31 |  |  |  |  |  |  |
| Code |  | 295 |  |  |  |  |  |  | 296 |  |  |  |  |  |  | 591 |  |  |  |  |  |  |
| Code Review |  | 15 |  |  |  |  |  |  | 16 |  |  |  |  |  |  | 31 |  |  |  |  |  |  |
| Compile |  | 31 |  |  |  |  |  |  | 31 |  |  |  |  |  |  | 62 |  |  |  |  |  |  |
| Test |  | 103 |  |  |  |  |  |  | 208 |  |  |  |  |  |  | 311 |  |  |  |  |  |  |
| Total |  | 684 |  |  |  |  |  |  | 637 |  |  |  |  |  |  | 1321 |  |  |  |  |  |  |
| Defects Injected |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |
| HLD Review |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Design Review |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code |  | 24 |  |  |  |  |  |  | 25 |  |  |  |  |  |  | 49 |  |  |  |  |  |  |
| Code Review |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Compile |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Test |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Total |  | 34 |  |  |  |  |  |  | 29 |  |  |  |  |  |  | 63 |  |  |  |  |  |  |
| Defects Removed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| HLD Review |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design Review |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 2 |  |  |  |  |  |  |
| Code |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code Review |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Compile |  | 16 |  |  |  |  |  |  | 17 |  |  |  |  |  |  | 33 |  |  |  |  |  |  |
| Test |  | 7 |  |  |  |  |  |  | 13 |  |  |  |  |  |  | 20 |  |  |  |  |  |  |
| Total |  | 28 |  |  |  |  |  |  | 35 |  |  |  |  |  |  | 63 |  |  |  |  |  |  |

Size Estimating Template

| Engineer | Otto | Date | 10/31 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 | Language | C |

| BASE PROGRAM LOC |  |  |  |  |  |  |  |  |  | ESTIMATE |  |  |  |  | ACTUAL |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASE SIZE (B) => => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 7000 |  |  |  |  |
| LOC DELETED (D) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
| LOC MODIFIED (M) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 25 |  |  |  |  |
| OBJECT LOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BASE ADDITIONS |  | TYPE1 |  |  | METHODS |  |  | REL. SIZE |  |  | LOC |  |  | LOC |  |  |
| CD Buttons |  |  | My L |  |  |  |  |  | large |  |  | 60 |  |  |  |  |
| CD Displays |  |  |  |  |  |  |  |  | v large |  |  | 142 |  |  |  |  |
| TOTAL BASE ADDITIONS (BA) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 202 |  |  |  |  |
| NEW OBJECTS |  | TYPE |  |  | METHODS |  |  | REL. SIZE |  |  | LOC (New Reused*) |  |  |  |  |  |
| CD Control |  |  | My I/O |  |  |  |  |  | large |  |  | 85* |  |  |  |  |
| CD Initialize |  |  | My L |  |  |  |  |  | medium |  |  | 25* |  |  |  |  |
| CD Monitor |  |  | My L |  |  |  |  |  | medium |  |  | 35* |  |  |  |  |
| TOTAL NEW OBJECTS (NO) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 145 |  |  |  |  |
| REUSED OBJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Synch Serial Com |  |  |  |  |  |  |  |  |  |  |  | 40 |  |  |  |  |
| REUSED TOTAL (R) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 40 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | SIZE |  |  | TIME |  |
| Estimated Object LOC (E): E = BA+NO+M |  |  |  |  |  |  |  |  |  |  |  | 372 |  |  |  |  |
| Regression Parameters: 0 Size and Time |  |  |  |  |  |  |  |  |  |  |  | 462 |  |  | 889 |  |
| Regression Parameters: 1 Size and Time |  |  |  |  |  |  |  |  |  |  |  | .344 |  |  | 1.788 |  |
| Estimated New and Changed LOC (N): N = 0 + 1*E |  |  |  |  |  |  |  |  |  |  |  | 590 |  |  |  |  |
| Estimated Total LOC: T = N + B - D - M + R |  |  |  |  |  |  |  |  |  |  |  | 7605 |  |  |  |  |
| Estimated Total New Reuse (sum of * LOC): |  |  |  |  |  |  |  |  |  |  |  | 145 |  |  |  |  |
| Estimated Total Development Time: Time = 0 + 1*E |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1554 |  |
| Prediction Range: Range |  |  |  |  |  |  |  |  |  |  |  | 342 |  |  | 901 |  |
| Upper Prediction Interval: UPI = N + Range |  |  |  |  |  |  |  |  |  |  |  | 932 |  |  | 2455 |  |
| Lower Prediction Interval: LPI = N - Range |  |  |  |  |  |  |  |  |  |  |  | 248 |  |  | 653 |  |
| Prediction Interval Percent: |  |  |  |  |  |  |  |  |  |  |  | 70 |  |  | 70 |  |

Total Base is the starting Base for Cycle 1

Total LOC is the final size for Cycle 2

1 L-Logic, I-I/O, C-Calculation, T-Text, D-Data, S-Set-up