Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Coaching PSP-trained Developers Exercise
Part 2

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

Coaching PSP-trained Developers Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | Background Information | 3 |
|  | Otto’s In-progress Project Plan Summary | 4 |
|  | Otto’s In-progress Cycle Summary | 6 |
|  | Otto’s In-progress Task and Schedule Templates | 7 |
|  | Otto’s In-progress Earned Value Chart | 9 |
|  | Otto’s Design Review Checklist | 10 |
|  | Otto’s Code Review Checklist | 11 |

| #### Exercise Objectives | After completing this exercise, participants will - have a better understanding of the issues involved in using PSP at work - understand how to evaluate a PSP plan, how to check progress against a plan, and how to evaluate a completed PSP project |
| --- | --- |

| #### Exercise #### Instructions | - Review the background information and Otto’s in-progress PSP data. - Based on his data, identify what “coaching” you would provide to Otto. - Prepare and present a short presentation (10 minutes) on your findings. |
| --- | --- |

Background

| #### Background | After you helped Otto to revise his PSP plan, he developed a project schedule using the task and schedule planning templates and began work on the project. He has progressed through the code review phase of the first cycle and has asked you to review his progress to date. |
| --- | --- |

PSP3 Project Plan Summary

| Engineer | Otto | Date | 11/13 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | in-progress |
| Component | Compact Disc | Language | C |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour | 22.80 |  |  |  |  |  |  |  |  |  |  |
| Planned Time | 1445 |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | (Planned/Actual) |  |  |
| % Reused | .5 |  |  |  |  |  |  |  |  |  |  |
| % New Reused | 28.2 |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC | 15.8 |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC | 106 |  |  |  |  |  |  |  |  |  |  |
| Yield | 61% |  |  |  |  |  |  |  |  |  |  |
| % Appraisal COQ | 28 |  |  |  |  |  |  |  |  |  |  |
| % Failure COQ | 14 |  |  |  |  |  |  |  |  |  |  |
| COQ A/F Ratio | 2.0 |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC) | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Base(B) | 7000 |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Modified (M) | 25 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Added (A) | 524 |  |  |  |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |
| Reused (R) | 40 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Total New & Changed (N) | 549 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |
| Total LOC (T) | 7564 |  |  |  |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |
| Total New Reused | 155 |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) | 869 |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) | 229 |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 144 |  | 120 |  |  |  |  |  |  |  |  |
| High-level design | 116 |  | 65 |  |  |  |  |  |  |  |  |
| High-level design review | 58 |  | 20 |  |  |  |  |  |  |  |  |
| Detailed design | 173 |  | 40* |  |  |  |  |  |  |  |  |
| Detailed design review | 116 |  | 10* |  |  |  |  |  |  |  |  |
| Code | 332 |  | 483* |  |  |  |  |  |  |  |  |
| Code review | 231 |  | 45* |  |  |  |  |  |  |  |  |
| Compile | 58 |  |  |  |  |  |  |  |  |  |  |
| Test | 145 |  |  |  |  |  |  |  |  |  |  |
| Postmortem | 72 |  |  |  |  |  |  |  |  |  |  |
| Total | 1445 |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) | 1900 |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 990 |  |  |  |  |  |  |  |  |  |  |

PSP3 Project Plan Summary (continued)

| Engineer | Otto | Date | 11/13 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | in-progress |
| Component | Compact Disc | Language | C |

| Defects Injected | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 6 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 8 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Code | 44 |  |  |  |  |  |  |  |  |  |  |
| Code review | 0 |  |  |  |  |  |  |  |  |  |  |
| Compile | 0 |  |  |  |  |  |  |  |  |  |  |
| Test | 0 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 58 |  |  |  |  |  |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 4 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 8 |  |  |  |  |  |  |  |  |  |  |
| Code | 0 |  |  |  |  |  |  |  |  |  |  |
| Code review | 23 |  |  |  |  |  |  |  |  |  |  |
| Compile | 14 |  |  |  |  |  |  |  |  |  |  |
| Test | 9 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 58 |  |  |  |  |  |  |  |  |  |  |
| After Development |  |  |  |  |  |  |  |  |  |  |  |
| Defect Removal Efficiency | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Defects/Hour - Design review | 4.2 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Code review | 6.0 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Compile | 14.5 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Test | 3.6 |  |  |  |  |  |  |  |  |  |  |
| DRL(DLDR/UT) | 1.2 |  |  |  |  |  |  |  |  |  |  |
| DRL(CodeReview/UT) | 1.7 |  |  |  |  |  |  |  |  |  |  |
| DRL(Compile/UT) | 4.0 |  |  |  |  |  |  |  |  |  |  |

Cycle Summary

| Engineer | Otto |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  | 11/13 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project | 2001 XQ35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | in-progress |  |  |  |  |  |
| Component | Compact Disc |  |  |  |  |  |  |  |  |  |  | Language |  |  |  |  | C |  |  |  |  |  |
| Cycle |  |  | 1 |  |  |  |  | 2 |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |
|  |  |  | Plan |  |  | Actual |  | Plan |  |  | Actual |  |  |  | Plan |  |  |  |  | Actual |  |  |
| Program Size (LOC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Base(B) |  | 7000 |  |  | 7000 |  |  |  | 7290 |  |  |  |  |  |  | 7000 |  |  |  |  |  |  |
| Deleted (D) |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Modified (M) |  | 0 |  |  | 0 |  |  |  | 25 |  |  |  |  |  |  | 25 |  |  |  |  |  |  |
| Added (A) |  | 250 |  |  | 285 |  |  |  | 274 |  |  |  |  |  |  | 524 |  |  |  |  |  |  |
| Reused (R) |  | 40 |  |  | 40 |  |  |  | 0 |  |  |  |  |  |  | 40 |  |  |  |  |  |  |
| Total New & Changed (N) |  | 250 |  |  | 285 |  |  |  | 299 |  |  |  |  |  |  | 549 |  |  |  |  |  |  |
| Total LOC (T) |  | 7290 |  |  | 7325 |  |  |  | 7564 |  |  |  |  |  |  | 7564 |  |  |  |  |  |  |
| Total New Reused |  | 155 |  |  | 190 |  |  |  | 0 |  |  |  |  |  |  | 155 |  |  |  |  |  |  |
| Time in Phase (min.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 116 |  |  | 65 |  |  |  |  |  |  |  |  |  |  | 116 |  |  |  |  |  |  |
| HLD Review |  | 58 |  |  | 20 |  |  |  |  |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Design |  | 79 |  |  | 40 |  |  |  | 94 |  |  |  |  |  |  | 173 |  |  |  |  |  |  |
| Design Review |  | 53 |  |  | 10 |  |  |  | 63 |  |  |  |  |  |  | 116 |  |  |  |  |  |  |
| Code |  | 151 |  |  | 483 |  |  |  | 181 |  |  |  |  |  |  | 332 |  |  |  |  |  |  |
| Code Review |  | 104 |  |  | 45 |  |  |  | 127 |  |  |  |  |  |  | 231 |  |  |  |  |  |  |
| Compile |  | 26 |  |  |  |  |  |  | 32 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Test |  | 48 |  |  |  |  |  |  | 97 |  |  |  |  |  |  | 145 |  |  |  |  |  |  |
| Total |  | 635 |  |  |  |  |  |  | 594 |  |  |  |  |  |  | 1229 |  |  |  |  |  |  |
| Defects Injected |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 6 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |
| HLD Review |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design |  | 4 |  |  | 0 |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Design Review |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code |  | 20 |  |  | 5 |  |  |  | 24 |  |  |  |  |  |  | 44 |  |  |  |  |  |  |
| Code Review |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Compile |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Test |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Total |  | 30 |  |  |  |  |  |  | 28 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Defects Removed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| HLD Review |  | 4 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |
| Design |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design Review |  | 4 |  |  | 0 |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Code |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code Review |  | 10 |  |  | 5 |  |  |  | 13 |  |  |  |  |  |  | 23 |  |  |  |  |  |  |
| Compile |  | 6 |  |  |  |  |  |  | 8 |  |  |  |  |  |  | 14 |  |  |  |  |  |  |
| Test |  | 3 |  |  |  |  |  |  | 6 |  |  |  |  |  |  | 9 |  |  |  |  |  |  |
| Total |  | 27 |  |  |  |  |  |  | 31 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |

Table C47 Task Planning Template

| Engineer | Otto | Date | 11/13 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | in-progress |

| Task |  | Plan |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date | Date | Earned Value | Cumulative Earned Value |
| 1 | Plan | 2.40 | 10 | 2.40 | 10 | 11/5 | 11/4 | 10 | 10 |
| 2 | HLD | 1.93 | 8 | 4.33 | 18 | 6 | 5 | 8 | 18 |
| 3 | HLD Review | 0.97 | 4 | 5.30 | 22 | 6 | 5 | 4 | 22 |
| 4 | C1: Design | 1.32 | 5.5 | 6.62 | 27.5 | 7 | 6 | 5.5 | 27.5 |
| 5 | Design Review | 0.88 | 3.7 | 7.50 | 31.1 | 7 | 6 | 3.7 | 31.2 |
| 6 | Code | 2.52 | 10.4 | 10.02 | 41.6 | 11 | 12 | 10.4 | 41.6 |
| 7 | Code Review | 1.75 | 7.3 | 11.77 | 48.9 | 11 | 13 | 7.3 | 48.9 |
| 8 | Compile | 0.43 | 1.8 | 12.20 | 50.7 | 12 |  |  |  |
| 9 | Test | 0.80 | 3.3 | 13.00 | 54.0 | 12 |  |  |  |
| 10 | C2: Design | 1.57 | 6.5 | 14.57 | 60.5 | 13 |  |  |  |
| 11 | Design Review | 1.05 | 4.4 | 15.62 | 64.8 | 13 |  |  |  |
| 12 | Code | 3.02 | 12.5 | 18.63 | 77.4 | 15 |  |  |  |
| 13 | Code Review | 2.10 | 8.7 | 20.73 | 86.1 | 18 |  |  |  |
| 14 | Compile | 0.53 | 2.2 | 21.27 | 88.3 | 18 |  |  |  |
| 15 | Test | 1.62 | 6.7 | 22.88 | 95.0 | 19 |  |  |  |
| 16 | Postmortem | 1.20 | 5 | 24.08 | 100 | 20 |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |
| Totals |  |  |  |  |  |  |  |  |  |

Table C49  Schedule Planning Template

| Engineer | Otto | Date | 11/13 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | in-progress |

|  |  |  | Plan |  |  |  | Actual |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | Date |  | Direct | Cumulative | Cumulative | Direct |  | Cumulative | Cumulative | Adjusted |  |
| No. |  |  | Hours | Hours | Planned Value | Hours |  | Hours | Earned Value | Earned Value |  |
| 1 | 11/4 |  | 2 | 2 | 0 | 2 |  | 2 | 10 |  |  |
| 2 | 5 |  | 2 | 4 | 10 | 1.41 |  | 3.41 | 22 |  |  |
| 3 | 6 |  | 2 | 6 | 22 | 1.33 |  | 4.74 | 31.2 |  |  |
| 4 | 7 |  | 2 | 8 | 31.1 | 2 |  | 6.74 | 31.2 |  |  |
| 5 | 8 |  | 2 | 10 | 31.1 | 2 |  | 8.74 | 31.2 |  |  |
| 6 | 11/11 |  | 2 | 12 | 48.8 | 2 |  | 10.74 | 31.2 |  |  |
| 7 | 12 |  | 2 | 14 | 54.0 | 1.57 |  | 12.31 | 41.6 |  |  |
| 8 | 13 |  | 2 | 16 | 64.8 | .75 |  | 13.06 | 48.9 |  |  |
| 9 | 14 |  | 2 | 18 | 64.8 |  |  |  |  |  |  |
| 10 | 15 |  | 2 | 20 | 77.4 |  |  |  |  |  |  |
| 11 | 11/18 |  | 2 | 22 | 88.3 |  |  |  |  |  |  |
| 12 | 19 |  | 2 | 24 | 95.0 |  |  |  |  |  |  |
| 13 | 20 |  | 2 | 26 | 100 |  |  |  |  |  |  |
| 14 | 21 |  | 2 | 28 |  |  |  |  |  |  |  |
| 15 | 22 |  | 2 | 30 |  |  |  |  |  |  |  |
| 16 | 11/25 |  | 2 | 32 |  |  |  |  |  |  |  |
| 17 | 26 |  | 2 | 34 |  |  |  |  |  |  |  |
| 18 | 27 |  | 2 | 36 |  |  |  |  |  |  |  |
| 19 | 28 |  | 2 | 38 |  |  |  |  |  |  |  |
| 20 | 29 |  | 2 | 40 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |  |  |  |  |

Otto’s Design Review Checklist

PROGRAM NAME AND #:2001 XQ35 CD				Interim (Cycle 1)

| Purpose | To guide you in conducting an effective design review | 1 |  |  |  |
| --- | --- | --- | --- | --- | --- |
| General | - As you complete each review step, check that item in the box to the right. - Complete the checklist for one program unit before you start to review the next. | x |  |  |  |
| Complete | Ensure that the requirements, specifications, and high-level design are completely covered by the design. | x |  |  |  |
| Logic | Verify that program sequencing is proper. | x |  |  |  |
| Special Cases | Check all boundary conditions. | x |  |  |  |
| Functional use | Verify that all functions, procedures, or objects are fully understood and properly used. | x |  |  |  |
| Standards | Review the design for conformance to all applicable design standards. | x |  |  |  |

Otto’s Code Review Checklist

PROGRAM  NAME AND #:     2001 XQ35 CD			Interim (Cycle 1)

| Purpose | To guide you in conducting an effective code review | 1 |  |  |  |
| --- | --- | --- | --- | --- | --- |
| General | - As you complete each review step, check that item in the box to the right. - Complete the checklist for one program unit before you start to review the next. | x |  |  |  |
| Complete | Verify that the code covers all of the design. | x |  |  |  |
| Includes | Verify that includes are complete. | x |  |  |  |
| Initialization | Check variable and parameter initialization. | x |  |  |  |
| Line by Line Check | Check every LOC for - instruction syntax - proper punctuation | x |  |  |  |
| Names | Check for proper name spelling and use. | x |  |  |  |
| Strings | Check that all strings are - identified by pointers - terminated in NULL | x |  |  |  |
| Output Format | Check for proper output format. | x |  |  |  |
| Logic Operators | Verify the proper use of all logic operators. | x |  |  |  |
| Standards | Ensure that the code conforms to the coding standards. | x |  |  |  |
| File Open and Close | Verify that all files are properly used. | x |  |  |  |

Total Base is the starting Base for Cycle 1

Total LOC is the final size for Cycle 2