Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Coaching PSP-trained Developers Exercise
Part 2a

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

Coaching PSP-trained Developers Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | Background Information | 3 |
|  | Otto’s Completed Cycle Summary (Actual) | 4 |
|  | Otto’s Completed Task and Schedule Templates | 5 |
|  | Otto’s Completed Earned Value Chart | 7 |

| #### Exercise Objectives | After completing this exercise, participants will - have a better understanding of the issues involved in using PSP at work - understand how to evaluate a PSP plan, how to check progress against a plan, and how to evaluate a completed PSP project |
| --- | --- |

| #### Exercise #### Instructions | - Review the background information and Otto’s in-progress PSP data. - When would you predict that Otto will complete this project? |
| --- | --- |

Background

| #### Background | Otto has completed cycle 1 of his PSP project and has provided you with this in-progress data. |
| --- | --- |

Cycle Summary

| Engineer | Otto |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  | 11/19 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project | 2001 XQ35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | end of c1 |  |  |  |  |  |
| Component | Compact Disc |  |  |  |  |  |  |  |  |  |  | Language |  |  |  |  | C |  |  |  |  |  |
| Cycle |  |  | 1 |  |  |  |  | 2 |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |
|  |  |  | Plan |  |  | Actual |  | Plan |  |  | Actual |  |  |  | Plan |  |  |  |  | Actual |  |  |
| Program Size (LOC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Base(B) |  | 7000 |  |  | 7000 |  |  |  | 7290 |  |  |  |  |  |  | 7000 |  |  |  |  |  |  |
| Deleted (D) |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Modified (M) |  | 0 |  |  | 0 |  |  |  | 25 |  |  |  |  |  |  | 25 |  |  |  |  |  |  |
| Added (A) |  | 250 |  |  | 285 |  |  |  | 274 |  |  |  |  |  |  | 524 |  |  |  |  |  |  |
| Reused (R) |  | 40 |  |  | 40 |  |  |  | 0 |  |  |  |  |  |  | 40 |  |  |  |  |  |  |
| Total New & Changed (N) |  | 250 |  |  | 285 |  |  |  | 299 |  |  |  |  |  |  | 549 |  |  |  |  |  |  |
| Total LOC (T) |  | 7290 |  |  | 7325 |  |  |  | 7564 |  |  |  |  |  |  | 7564 |  |  |  |  |  |  |
| Total New Reused |  | 155 |  |  | 190 |  |  |  | 0 |  |  |  |  |  |  | 155 |  |  |  |  |  |  |
| Time in Phase (min.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 116 |  |  | 65 |  |  |  |  |  |  |  |  |  |  | 116 |  |  |  |  |  |  |
| HLD Review |  | 58 |  |  | 20 |  |  |  |  |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Design |  | 79 |  |  | 40 |  |  |  | 94 |  |  |  |  |  |  | 173 |  |  |  |  |  |  |
| Design Review |  | 53 |  |  | 10 |  |  |  | 63 |  |  |  |  |  |  | 116 |  |  |  |  |  |  |
| Code |  | 151 |  |  | 483 |  |  |  | 181 |  |  |  |  |  |  | 332 |  |  |  |  |  |  |
| Code Review |  | 104 |  |  | 45 |  |  |  | 127 |  |  |  |  |  |  | 231 |  |  |  |  |  |  |
| Compile |  | 26 |  |  | 105 |  |  |  | 32 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Test |  | 48 |  |  | 312 |  |  |  | 97 |  |  |  |  |  |  | 145 |  |  |  |  |  |  |
| Total |  | 635 |  |  | 1080 |  |  |  | 594 |  |  |  |  |  |  | 1229 |  |  |  |  |  |  |
| Defects Injected |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 6 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |
| HLD Review |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design |  | 4 |  |  | 5 |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Design Review |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code |  | 20 |  |  | 27 |  |  |  | 24 |  |  |  |  |  |  | 44 |  |  |  |  |  |  |
| Code Review |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Compile |  | 0 |  |  | 2 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Test |  | 0 |  |  | 3 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Total |  | 30 |  |  | 37 |  |  |  | 28 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Defects Removed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| HLD Review |  | 4 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |
| Design |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design Review |  | 4 |  |  | 0 |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Code |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code Review |  | 10 |  |  | 5 |  |  |  | 13 |  |  |  |  |  |  | 23 |  |  |  |  |  |  |
| Compile |  | 6 |  |  | 19 |  |  |  | 8 |  |  |  |  |  |  | 14 |  |  |  |  |  |  |
| Test |  | 3 |  |  | 13 |  |  |  | 6 |  |  |  |  |  |  | 9 |  |  |  |  |  |  |
| Total |  | 27 |  |  | 37 |  |  |  | 31 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |

Table C47 Task Planning Template

| Engineer | Otto | Date | 11/19 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | end of c1 |

| Task |  | Plan |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date | Date | Earned Value | Cumulative Earned Value |
| 1 | Plan | 2.40 | 10 | 2.40 | 10 | 11/5 | 11/4 | 10 | 10 |
| 2 | HLD | 1.93 | 8 | 4.33 | 18 | 6 | 5 | 8 | 18 |
| 3 | HLD Review | 0.97 | 4 | 5.30 | 22 | 6 | 5 | 4 | 22 |
| 4 | C1: Design | 1.32 | 5.5 | 6.62 | 27.5 | 7 | 6 | 5.5 | 27.5 |
| 5 | Design Review | 0.88 | 3.7 | 7.50 | 31.1 | 7 | 6 | 3.7 | 31.2 |
| 6 | Code | 2.52 | 10.4 | 10.02 | 41.6 | 11 | 12 | 10.4 | 41.6 |
| 7 | Code Review | 1.75 | 7.3 | 11.77 | 48.9 | 11 | 13 | 7.3 | 48.9 |
| 8 | Compile | 0.43 | 1.8 | 12.20 | 50.7 | 12 | 14 | 1.8 | 50.7 |
| 9 | Test | 0.80 | 3.3 | 13.00 | 54.0 | 12 | 19 | 3.3 | 54 |
| 10 | C2: Design | 1.57 | 6.5 | 14.57 | 60.5 | 13 |  |  |  |
| 11 | Design Review | 1.05 | 4.4 | 15.62 | 64.8 | 13 |  |  |  |
| 12 | Code | 3.02 | 12.5 | 18.63 | 77.4 | 15 |  |  |  |
| 13 | Code Review | 2.10 | 8.7 | 20.73 | 86.1 | 18 |  |  |  |
| 14 | Compile | 0.53 | 2.2 | 21.27 | 88.3 | 18 |  |  |  |
| 15 | Test | 1.62 | 6.7 | 22.88 | 95.0 | 19 |  |  |  |
| 16 | Postmortem | 1.20 | 5 | 24.08 | 100 | 20 |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |
| Totals |  |  |  |  |  |  |  |  |  |

Table C49  Schedule Planning Template

| Engineer | Otto | Date | 11/19 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | end of c1 |

|  |  |  | Plan |  |  |  | Actual |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | Date |  | Direct | Cumulative | Cumulative | Direct |  | Cumulative | Cumulative | Adjusted |  |
| No. |  |  | Hours | Hours | Planned Value | Hours |  | Hours | Earned Value | Earned Value |  |
| 1 | 11/4 |  | 2 | 2 | 0 | 2 |  | 2 | 10 |  |  |
| 2 | 5 |  | 2 | 4 | 10 | 1.41 |  | 3.41 | 22 |  |  |
| 3 | 6 |  | 2 | 6 | 22 | 1.33 |  | 4.74 | 31.2 |  |  |
| 4 | 7 |  | 2 | 8 | 31.1 | 2 |  | 6.74 | 31.2 |  |  |
| 5 | 8 |  | 2 | 10 | 31.1 | 2 |  | 8.74 | 31.2 |  |  |
| 6 | 11/11 |  | 2 | 12 | 48.8 | 2 |  | 10.74 | 31.2 |  |  |
| 7 | 12 |  | 2 | 14 | 54.0 | 1.57 |  | 12.31 | 41.6 |  |  |
| 8 | 13 |  | 2 | 16 | 64.8 | .75 |  | 13.06 | 48.9 |  |  |
| 9 | 14 |  | 2 | 18 | 64.8 | 2.25 |  | 15.31 | 50.7 |  |  |
| 10 | 15 |  | 2 | 20 | 77.4 | 2.33 |  | 17.64 | 50.7 |  |  |
| 11 | 11/18 |  | 2 | 22 | 88.3 | 1.13 |  | 18.77 | 50.7 |  |  |
| 12 | 19 |  | 2 | 24 | 95.0 | 2 |  | 20.77 | 54 |  |  |
| 13 | 20 |  | 2 | 26 | 100 |  |  |  |  |  |  |
| 14 | 21 |  | 2 | 28 |  |  |  |  |  |  |  |
| 15 | 22 |  | 2 | 30 |  |  |  |  |  |  |  |
| 16 | 11/25 |  | 2 | 32 |  |  |  |  |  |  |  |
| 17 | 26 |  | 2 | 34 |  |  |  |  |  |  |  |
| 18 | 27 |  | 2 | 36 |  |  |  |  |  |  |  |
| 19 | 28 |  | 2 | 38 |  |  |  |  |  |  |  |
| 20 | 29 |  | 2 | 40 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |  |  |  |  |

Total Base is the starting Base for Cycle 1

Total LOC is the final size for Cycle 2