## Slide 1
Managing TSP Teams
Exercise 4: Back-up Data

## Slide 3: Quality Assurance Concerns
Based on data from prior projects, Quality Assurance believes that insufficient time is planned for testing.

## Slide 4
Lisa’s team has earned 53 EV points in 22 weeks.
This is a rate of 2.409 EV per week.

## Slide 5
Jeff’s team has earned 51.8 EV in 20 weeks.
This is a rate of 2.59 EV per week.

## Slide 6: EV Schedule Estimate

## Slide 13: Test Defect Estimate

## Slide 14: Estimating Test Defects - Lisa
For Lisa’s team
  SUMQ data indicate the team is gathering defect data.
  However, Lisa’s team is not meeting its quality goals.
  The unit test defects are 2.24 times the number planned.
  The estimate is that integration and system test defects will also be 2.24 times the number planned.

## Slide 15: Estimating Test Defects - Jeff
Jeff’s team has not been recording all of its defect data so we must do the following.
For defects injected, multiply phase time by injection rate.
Find defects removed by using the yield for each phase.
Ignore defects injected before implementation.
Since developers who use the PSP and gather defects data inject fewer defects, multiply these estimates by the following factors.
for additional design defects injected – 1.09
for additional coding defects injected – 1.53

## Slide 16: Defects Injected – Jeff’s Team
*
When developers do not record defect data, they inject more defects than when they do.

## Slide 17: Defects Removed – Jeff’s Team

## Slide 18: Test Time per Defect
Based on data from George’s team, the time required to remove defects in integration and system test is as follows.
Integration test time: 14.27 hours per defect removed
System test time: 25 hours per defect removed

## Slide 19: Weekly Task Time
The weekly task time for the teams is as follows.
In 20 weeks, Jeff’s team has worked 1,698.3 task hours. That is 84.92 task hours per week.
Lisa’s team has worked 1,679.9 task hours in 22 weeks for an average of 76.36 task hours per week.

## Slide 20: Test Time Estimate – Lisa
The estimated test time for Lisa’s team is as follows.
Integration test: 30.7 defects at 14.27 hours each is 438.1
task hours.
System test: 15.0 defects at 25 hours each is 375 task
hours.
Total estimated test time is 813.1 hours.

## Slide 21: Test Time Estimate – Jeff
For Jeff’s team, the estimated test time is as follows.
  Integration test: 123.7 defects at 14.27 hours = 1,765.4 task hours.
  System test: 52.2 defects at 25 hours each = 1305 task hours.
  Total estimated test time is 3,070.4 task hours.

## Slide 22: Test Schedule Estimate - Lisa
Lisa’s team planned on 362.9 hours of testing, so the 813.1 test time estimate adds 450.2 task hours.
At 76.36 task hours per week, this adds 5.9 weeks to the EV estimate of 19.5 weeks, ending in 25. 4 weeks.

## Slide 23: Test Schedule Estimate - Jeff
Jeff’s team planned on 288 hours of testing, so the 3,070.4 hour estimate adds 2,782.4 hours to that plan.
At 84.92 task hours per week, this will add 32.8 weeks to the EV estimate of 18.6 weeks, giving 51.4 more weeks.