## Slide 1
Managing TSP Teams
Module 6: Building Quality Products

## Slide 3: TSP Quality Management
What is quality?
The software quality problem
The defect-removal problem
Managing quality
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 4: What is Quality?
Basic definition: Meeting the user’s needs
There are three categories of product quality.
  functionality
  properties (e.g., safety, security, privacy, usability)
  defects
A software product can’t be safe or secure until it is nearly defect-free.
The current software process is preoccupied with removing defects.
Little or no time is left for the other aspects of quality.
Notes: Describe common definition of quality used in quality and TQM circles: meeting user’s needs. Discuss how user’s see quality of products from at least from 3 perspectives:
  Functionality – does what it is supposed to do
  Properties – any number of characteristics that are important
  Defects – mistakes that need to be corrected
Describe why defects aren’t important to the customer as long as they can use the system - but that defects are significant to he development organization because defects consume resources to the point where there is no time to work on important customer needs.

## Slide 5: The Software Quality Problem
Software quality problems are largely caused by defects.
  Defects are injected by the product’s developers.
  Even experienced and capable developers inject many defects.
Current practices rely on testing to remove these defects.
Testing is necessary but, for finding and fixing defects, it is
  time-consuming
  expensive
  ineffective
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 6: The Defect Problem
Programs are complex products.
  Small programs have thousands of instructions.
  Large programs have millions of instructions.
  These instructions are individually produced.
  Each instruction must be precisely correct.
Any simple mistake can cause the program not to work.
When people do complex tasks, they inevitably make mistakes.
On average, experienced programmers inject a defect about every 10 instructions.
Notes: Describe why defects are so numerous in software products by emphasizing the complexity of a software program. Give examples.
Bottom line: Everyone makes mistakes and in software programs the mistakes can be numerous!

## Slide 7: Testing
A single test
  exercises the product under one set of conditions
  produces correct or incorrect results
If there is a problem, developers must find the defect, fix it, and then test the fix.
For products with many possible operating conditions, many tests are required.
Projects that rely on testing for quality spend a lot of time and money on testing.
Notes: Start building the argument against reliance on testing to remove defects. Try to keep this discussion interactive. Nearly all participants will have some experience with testing cycles that go on forever.

## Slide 8: Testing Takes a Long Time
0
20
40
60
80
100
120
140
160
180
200
1
10
19
28
37
46
55
64
73
82
91
100
109
118
Weeks
Cumulative Defects
All
Non-Crit
Critical
Magellan Spacecraft – 22,000 LOC
Notes: Notice after several years of testing there are still defects! We need a source for this slide and maybe some additional thoughts on what to say here.

## Slide 9: Traditional Defect Removal Costs
Consider a 100,000 LOC system.
  no reviews or inspections
  20+ defects/KLOC typical at test entry
  2,000 defects to find and fix
Testing takes about half of the project’s cost and schedule.
  1.5 days per defect
  3,000 programmer days
  about 12 programmer years
By using the TSP, a development team could cut testing time to a few weeks.
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 10: Testing Effectiveness
Large complex programs cannot be exhaustively tested.
  It is impossible to test every operating condition.
  Testing must focus on only the most frequent conditions.
  Extensive user testing finds even more defects.
Testing finds a percentage of the defects in a product, usually less than 50%.
To get a quality product out of test, you must put a quality product into test.
Notes: Watts comment: validate a program’s functionality and properties

## Slide 11: Testing is Ineffective
Overload
Hardware
failure
Operator
error
Data error
Resource
contention
Configuration
Safe and secure
region = tested
(shaded)
Unsafe and insecure
region = untested
(unshaded)
Notes: Disciplined processes use reviews and inspections to clear the entire “mine field.”
Use examples of why the boundary conditions are the most important.
Air traffic control landing all planes on 9/11/01
Nuclear Regulatory Commission – everything goes wrong at the same time
Extreme cases are the one you run into and need the system to work.

## Slide 12: The TSP is Faster and Better
With TSP
  most defects are removed by reviews and inspections
  few defects are left for testing
  testing takes relatively little time
By using TSP, organizations can
  cut testing times by 80% or more
  shorten schedules
  reduce costs
  produce better products
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 13: Reviews and Inspections Save Time
Source: Xerox
1
10
100
1000
10000
Time in Minutes
Design
Review
Design
Inspect.
Code
Review
Code
Inspect
Unit
Test
System
Test
Defect-removal Phase
5
22
2
25
32
1405
Notes: MPH comment: completely changed format of this graph so that the filled white box behind the graph is gone; title has been moved to correct placement and changed to be consistent with slide master format.

## Slide 14: Measuring Software Quality
To produce quality systems, the quality of all its parts must be measured and managed.
These measures must be made at every step in the process.
With TSP and PSP, developers use quality measures to manage the quality of their work. The developers
  inject fewer defects
  remove most defects soon after injecting them
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 15: TSP Quality Measures
There are many potential software quality measures.
With the TSP, every product element and every process step can be measured.
Notes: In the Nov 2001 dryrun, it was suggested that more measures be added – I decided for now not to add any additional measures.
The point here is very simple and is maybe best illustrated with Watts’ story from the end of chapter 5.
Watts was given the job of fixing the software quality problem at IBM. The hardware folks already were doing and had showed significant gains in quality. The software folks resisted identifying any measure of quality, claiming you could measure software quality. Over the protests of the software developers, Watts defined a quality measure and how it would be used. Every software product was required to have a quality plan before it could be announced. Once a product was shipped, defect data from field engineering was gather and the quality measure calculated and posted with the plan data to the executive quality reporting system. Over the next several years, the measured quality of IBM’s new software products improved by an average of 35% a year, or nearly 10 times in 5 years. The impact was visible outside IBM, Amdahl, an IBM competitor noticed that the quality of IBM software improved significantly.

## Slide 16: Component Quality Profile
Standard design time
Standard code
review time
Compile
quality
Unit test
quality
Standard design
review time
Notes: MPH comment: removed box and white background; changed title format to match the master slide’s format; changed font on graph labels to bold.

## Slide 17: PQI vs. Post-development Defects
0
5
10
15
20
25
0
0.1
0.2
0.4
0.5
0.6
PQI Values
Post-Development
Defects/KLOC
0.3
Notes: MPH comment: changed to remove white box and black line from background; title reformatted; moved diagram to be placed better on page.

## Slide 18: Quality Management
With the TSP, the developers
  record all of their defects
  use process data to analyze product quality
  strive to fix all defects before test
In managing quality, TSP teams use the
  process quality profile
  process quality index (PQI)
The following charts illustrate TSP quality management.

## Slide 19: Selected TSP Quality Profiles
PQI = 0.97
PQI = 0.88
PQI = 0.71
PQI = 0.59
PQI = 0.15
PQI = 0.04

## Slide 20: Selected TSP Quality Profiles
PQI = 0.97
PQI = 0.88
PQI = 0.71
PQI = 0.59
PQI = 0.15
PQI = 0.04
Test defects = 0
Test defects = 0
Test defects = 0
Test defects = 0
Test defects = 1
Test defects = 3

## Slide 21: A Traditional Quality Profile
With current typical software practice, PQI is at or near 0.
With TSP, PQI is measured and can be managed with control charts.
No defects have been found when PQI is above 0.4.
Typical Non-TSP Quality Profile
0
0.2
0.4
0.6
0.8
1
Design/Code Time
Code Review Time
  Compile Defects/KLOC
Unit Test Defects/KLOC
Design Review Time
PQI = 0.00
Notes: MPH comment: Changed the graph to correct typo in the header.

## Slide 22: Managing Quality
By using PQI, teams can manage product quality.
  set PQI parameter control limits
  use control charts to identify special causes
  fix defective
programs
before test
Notes: The important point here is that the teams sets a measurable product quality goal and then builds a plan that shows how they will achieve that goal.
Having a plan to achieve their quality goal, the team can them manage quality during the development.

## Slide 23: Quality Implications
With proper training, guidance, and motivation, most programmers can produce near-defect-free programs.
With essentially defect-free products
  testing times are sharply reduced
  delivered products work
  maintenance costs are reduced
The key is the developers’ ability to produce defect-free products.
  measure quality
  manage quality
  personal quality commitment

## Slide 24: Quality Goals and Plans
With data, TSP teams can
  set measurable quality goals
  make quality plans to meet these goals
  estimate the defects injected and removed in each phase
  track the work to see if they are meeting their quality plans
Notes: The important point here is that the teams sets a measurable product quality goal and then builds a plan that shows how they will achieve that goal.
Having a plan to achieve their quality goal, the team can them manage quality during the development.

## Slide 25: Example: Planning for Quality -1
A TSP team plans to develop 20 KLOC.
The goal is a design review yield of at least 70%.
  The plan shows 442 hours in detailed design.
  Data show that developers inject 1.3 defects per hour in detailed design.
  Data show that they remove 3 defects per hour in detailed design reviews.
What is the minimum design review time required to remove these defects?
Notes: The projected number of defects to be injected is 442*1.3 = 575 defects.
A 70% yield would be finding 403 defects.
At an average rate of 3 defects/hour removed, they would need to plan 134 hours.
Note, this example is really simplified.
First, it does not consider defects already in the product before detailed design, however, these are probably much smaller in comparison to the number injected in detailed level design. So ignoring them does not affect the result significantly.
Secondly, this doesn’t consider the other rule-of-thumb that design review should be 50% of the design time.

## Slide 26: Example: Planning for Quality -2
Defects injected
  442 hours of design
  1.3 defects injected per hour
  1.3*442 = 574.6 defects injected
Defect removal
  574.6 defects total
  3 defects removed per hour
  574.6/3 = 191.5 hours of design review time
The team should plan on 191.5 hours of review time.
To achieve a 70% yield, they must spend at least
0.7*191.5 = 134.1 hours in design reviews.
Notes: The projected number of defects to be injected is 442*1.3 = 575 defects.
A 70% yield would be finding 403 defects.
At an average rate of 3 defects/hour removed, they would need to plan 134 hours.
Note, this example is really simplified.
First, it does not consider defects already in the product before detailed design, however, these are probably much smaller in comparison to the number injected in detailed level design. So ignoring them does not affect the result significantly.
Secondly, this doesn’t consider the other rule-of-thumb that design review should be 50% of the design time.

## Slide 27: Maintain Process Discipline
To produce quality systems, every part must be of high quality.
This is possible only if every developer consistently follows a quality process.
To consistently follow a quality process, developers must
  be properly trained (with the PSP)
  work on a disciplined team (with the TSP)
  have coaching support and guidance
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 28: Management Support
People do not naturally do disciplined work.
To ensure disciplined work, management must
  train and support the developers
  ensure that the developers’ work is guided and monitored
  provide coaching assistance
Management must also
  build and maintain effective teams
  ensure that all team members are trained and willing to follow the process
  recognize and reward quality work
Notes: We’ll cover some basic terminology and concepts and then get into TSP quality management.

## Slide 29: Messages to Remember
High-quality processes produce high-quality products.
Quality work is not done by accident; it requires discipline, commitment, management, and measurement.
Quality work saves time and money.
The cornerstone of a high-quality software process is early defect removal.
TSP shows teams how to efficiently remove defects at the earliest possible point in the process.