Table C22  PSP0.1 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP0.1 Project Plan Summary form • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | Make your best estimate of the total new and changed LOC required to develop this program. |
| 3 | Resource Estimate | • Make your best estimate of the time required to develop this program. • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
|  | Exit Criteria | • Documented requirements statement • Project Plan Summary form with estimated program size and development time data • Completed Time Log |