Table C36  PROBE Estimating Script

|  | Purpose | To guide the PROBE estimation process |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Size Estimating Template and instructions • LOC per method data for object types • Time Recording Log • Historical size and time data |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Estimate Objects | Follow the Size Estimating Template instructions to estimate the new object LOC and new reused LOC. |
| 3 | Other Program LOC | Follow the Size Estimating Template instructions to estimate base, deleted, modified, added, and reused LOC. |
| 4 | The Size Estimating Procedure | A  If you have sufficient estimated object LOC and actual new and changed LOC (three or more points that correlate), use procedure 4A. B  If you do not have sufficient estimated object LOC data but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 4B. C  If you have insufficient data or they do not correlate, use procedure 4C. D  If you have no historical data, use procedure 4D. |
| 4A | The Size Estimating Procedure 4A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | The Size Estimating Procedure 4B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not reasonably near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | The Size Estimating Procedure 4C | If you have any data on estimated object LOC and actual new and changed LOC, set = 0 and = (total new and changed LOC to date/total estimated object LOC to date). |
| 4D | The Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate the new and changed LOC from the estimated object LOC. |

(Continued)

Table C36  PROBE Estimating Script (Continued)

| 5 | The Time Estimating Procedure | A  If you have sufficient estimated object LOC and actual development time data (three or more points that correlate), use procedure 5A. B  If you do not have sufficient estimated object LOC data, but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 5B. C1  If you have some estimated object LOC data and they are insufficient or do not correlate, use procedure 5C1. C2  If you have some estimated new and changed LOC data and they are insufficient or do not correlate, use procedure 5C2. C3  If you only have actual data on new and changed LOC, use procedure 5C3. D  If you have no historical data, use procedure 5D. |
| --- | --- | --- |
| 5A | The Time Estimating Procedure 5A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C1. |
| 5B | The Time Estimating Procedure 5B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C2. |
| 5C1 | The Time Estimating Procedure 5C1 | If you have any data on estimated object LOC and actual development time, set = 0 and = (total development time to date/total estimated object LOC to date). |
| 5C2 | The Time Estimating Procedure 5C2 | If you have data on estimated new and changed LOC and actual development time, set = 0 and = (development time to date/estimated new and changed LOC to date). |
| 5C3 | The Time Estimating Procedure 5C3 | If you only have actual time and size data, set = 0 and = (development time to date/new and changed LOC to date). |
| 5D | The Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated object LOC. |
| 6 | Time and Size Prediction Intervals | - If you used the regression method, calculate the prediction interval as described in Table A29 (page 550). - If you did not use the regression method, estimate the maximum and minimum development times from your maximum and minimum productivity for prior programs. |