Table C48  Task Planning Template Instructions

| Purpose | • To estimate the development time for each project task • To compute the planned value for each project task • To estimate the planned completion date for each task • To provide a basis for tracking schedule progress even when the tasks are not completed in the planned order |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Include every significant task. • Use task names and numbers that support the activity and are consistent with the project work breakdown structure. |
| Header | Enter the following: • Your name • Today’s date • The project number • The instructor’s name |
| Task | • Enter a task number and name. List the tasks in the order in which you expect to complete them. • Select tasks that have explicit completion criteria, for example, planning completed, program compiled and all defects corrected, testing completed and all defects corrected, and so on. |
| Plan  Hours | Enter the planned hours for each task. |
| Plan  Planned Value | • Total the planned hours for all the tasks. • For each task, calculate the percent its planned hours are of total hours. • Enter this percentage as the planned value for that task. • The total planned value should equal 100. |
| Plan  Cumulative Hours | Enter the cumulative sum of the plan hours down through each task. |
| Plan  Cumulative Value | • Sum the planned values down through each task. • Before proceeding, complete the Schedule Planning Template down through PlanCumulative Hours. • Then complete the Schedule Planning and Task Planning templates together. |
| Plan Date  Monday | • For each cumulative hours entry, find the plan cumulative hours entry on the Schedule Planning Template that equals or just exceeds it. • Enter the date from that row (of the Schedule Planning Template) as the plan date on the Task Planning Template. • If several weeks on the Schedule Planning Template have the same cumulative value, enter the earliest date. • Unless you made daily plans, pick the plan date as the Monday of the week during which completion for that task is planned. |
| Actual Date | As each task is completed, enter the completion date. |
| Earned Value | For each completed task, enter the planned value. |
| Cumulative Earned Value | As each task is completed, total all the earned value entries and enter that total beside the latest task that was completed. |