Table C50  Schedule Planning Template Instructions

| Purpose | • To record the estimated and actual hours expended by calendar period • To relate the task planned value to the calendar schedule • To calculate adjusted planned and earned values when tasks change |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Complete it in conjunction with the Task Planning Template. |
| Header | Enter the following: • Your name • Today’s date • The project number • The instructor’s name |
| Week Number | • From the project start, enter a week number, typically starting with 1. • For very small projects, it may be more convenient to use days instead of weeks. |
| Date (Monday) | • Enter the calendar date for each week. • Pick a standard day in the week, for example, Monday. |
| PlanDirect Hours | • Enter the planned number of direct project hours you expect to spend each week. • Consider non-work time such as vacations, holidays, and so on. • Consider other committed activities such as classes, meetings, and other projects. |
| Plan Cumulative Hours | Enter the cumulative planned hours through each week. |
| Plan Cumulative Planned Value | For each week, do the following: • Take the plan cumulative hours from the Schedule Planning Template. • On the Task Planning Template, find the task with nearest equal or lower plan cumulative hours and note its plan cumulative value. • Enter this cumulative value in the Schedule Planning Template for that week. • If the cumulative value for the prior week still applies, enter it again. |
| Actual | • During development, enter the actual direct hours, cumulative hours, and cumulative earned value for each week. • Determine status against plan by comparing the cumulative planned value and the actual cumulative earned value. |
| Adjusted Earned Value | Proportionately adjust the earned value up or down as tasks are added or deleted. The adjusted earned value compensates for these changes without requiring a complete new plan. |