Table C53  PSP2 Development Script

| Phase Number | Purpose | To guide the development of small programs |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Project Plan Summary form with estimated program size and development time • For projects of several days’ duration, completed Task Planning and Schedule Planning Templates • Time and Defect Recording Logs • Defect Type Standard and Coding Standard |
| 1 | Design | • Review the requirements and produce a design to meet them. • Record time in Time Recording Log. |
| 2 | Design Review | • Follow the Design Review Checklist and review the design. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 3 | Code | • Implement the design following the Coding Standard. • Record in the Defect Recording Log any requirements or design defects found. • Record time in Time Recording Log. |
| 4 | Code Review | • Follow the Code Review Checklist and review the code. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 5 | Compile | • Compile the program until error-free. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 6 | Test | • Test until all tests run without error. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. • Complete a Test Report Template on the tests conducted and the results obtained. |
|  | Exit Criteria | • A thoroughly tested program that conforms to the Coding Standard • Completed Design Review and Code Review Checklists • Completed Test Report Template • Completed Defect and Time Recording Logs |