Table C60  PSP2.1 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP2.1 Project Plan Summary form • Size Estimating, Task Planning, and Schedule Planning Templates • Historical estimated and actual size and time data • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure that the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | • Produce a program conceptual design. • Use the PROBE method to estimate the new and changed LOC required to develop this program. • Estimate the base, added, deleted, modified, and reused LOC. • Complete the Size Estimating Template and Project Plan Summary form. • Calculate the 70 percent size prediction interval (you may use a spread sheet). |
| 3 | Resource Estimate | • Use the PROBE method to estimate the time required to develop the new program. • Calculate the 70 percent prediction interval (you may use a spreadsheet). • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
| 4 | Task and Schedule Planning | For projects requiring several days or more of work, complete the Task Planning and Schedule Planning Templates. |
| 5 | Defect Estimate | • Based on your To Date data on defects per new and changed LOC, estimate the total defects to be found in this program. • Based on your To Date % data, estimate the numbers of defects to be injected and removed by phase. |
|  | Exit Criteria | • Documented requirements statement • The program conceptual design • Completed Size Estimating Template • For projects of several days duration, completed Task and Schedule Planning Templates • Project Plan Summary form with estimated program size, development time, and 70 percent prediction intervals • Completed Time Recording Log |