## Slide 1: Personal Software ProcessSM for Engineers: Part I Planning Overview and Size Measurement
Notes: <number>

## Slide 3: Lecture Topics
Planning overview
Software size
  why measure size
  size measurement criteria
  the SEI size measurement framework
Counting program size
  counters
  coding standards
Notes: <number>

## Slide 4: Why Make Plans?
Plans
  allow you to make commitments that you can meet
  provide a basis for agreeing on the job
  guide your work
  help to track your progress
  ensure project completion
Notes: <number>

## Slide 5: The Project Planning Framework
Product
delivery
Tracking
reports
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Size
database
Productivity
database
Notes: <number>

## Slide 6: Why Measure Size?
Size measures
  help you to make better plans
  assist you in tracking development
  normalize other measures
    development resources
    defect rates
Notes: <number>

## Slide 7: Size Measurement Criteria
Size measurements must be
  related to development effort
  precise
  machine countable
  suitable for early planning
Notes: <number>

## Slide 8: Size Versus Development Effort
The principal requirement: If the size measure is not directly related to development cost, it is not worth using.
There are many possible measures.
  lines of code (LOC)
  function points
  pages, screens, scripts, reports
The size measure should be sensitive to language, design, and development practice.
Notes: <number>

## Slide 9: C++ LOC Versus Development Time
Notes: <number>

## Slide 10: Pascal LOC Versus Time
Notes: <number>

## Slide 11: Text Pages Versus Time
Text Pages
Notes: <number>

## Slide 12: Script LOC Versus Time
Notes: <number>

## Slide 13: Report LOC Versus Time
Notes: <number>

## Slide 14: Screen LOC Versus Time
Notes: <number>

## Slide 15: Relationship to Development
LOC is a reasonably good measure for development of source programs such as Pascal and C++.
Pages are an acceptable measure for document development.
LOC is not an adequate measure for screens, reports, or scripts.
Some other possible measures are function points, screens, and modules.
Notes: <number>

## Slide 16: Precision and Accuracy
Imprecise and inaccurate
Precise and inaccurate
Imprecise and accurate
Precise and accurate
x
x
x
x
x
x
x
xx
x x
x
x
x
x
x
x
x
x
x
x
x x
x x
x x
x
Notes: <number>

## Slide 17: Measurement Precision
When two people measure the same thing, will they get the same result?
To do so requires a precise measurement definition.
The measure must also be properly applied.
  Pascal LOC do not equate to assembler LOC.
  New LOC do not equate to modified LOC.
  Logical LOC do not equate to physical LOC.
  C++ LOC may not relate to C++ LOC.
Notes: <number>

## Slide 18: Machine Countable
Size measurement is time-consuming and inaccurate.
Automated counters can work only on definable program characteristics.
Counters can be complex.
  size definition selected
  counting method
Notes: <number>

## Slide 19: Suitable for Early Planning -1
The issue is, what can you visualize early?
  For a house, square feet predict cost.
  Few people can visualize a house in terms of square feet of living space.
  Numbers of rooms are more intuitive.
Intuitive size measures are needed for good plans.
Notes: <number>

## Slide 20: Suitable for Early Planning -2
Unfortunately, the popular intuitive measure is not measurable, and the popular measurable measure is not intuitive.
Function points
  intuitive
  not directly measurable
LOC
  not intuitive
  directly measurable
Notes: <number>

## Slide 21: Selecting a Size Measure -1
Start with product development data.
  resources required
  product characteristics
  any special development conditions
Rank products by resources required.
See what characteristics distinguish those products that took the greatest effort from those that took the least.
Notes: <number>

## Slide 22: Selecting a Size Measure -2
See if these differences are measurable.
  Correlate this measure for the product set.
  If there is no correlation, try again.
There may be no single best measure.
  A combination of measures could be needed.
  Methods for handling multiple measures are discussed later.
Notes: <number>

## Slide 23: Selecting a Size Measure -3
If you are better at estimating resources than program size, size estimation will not improve your planning.
If you estimate resources directly, you must
  keep accurate records
  build a large database
  use an estimating guru
Notes: <number>

## Slide 24: The SEI Measurement Framework
The SEI measure uses logical (versus physical) lines of code.
Statement specifications
  executable
  nonexecutable
  counted statement types
Application
  language and code type
  origin and usage
Notes: <number>

## Slide 25: Counting Program Size -1
Logical lines
  invariant to editing changes
  correlate with development effort
  uniquely definable
  complex to count
Physical lines
  easy to count
  not invariant
  not uniquely definable
Notes: <number>

## Slide 26: Counting Program Size -2
The PSP uses a coding standard and a physical LOC counter.
  defined coding standard
  physical line for each logical line
This standard must be faithfully followed.
Then, physical line counting equals logical line counting.
Notes: <number>

## Slide 27: A Counting Example
procedure ISet.Set(var N: int; var inc: boolean);
begin
inc := false;
SearchPtr := SetStart;
while (SearchPtr<>nil) and (inc == false) do
if SearchPtr^.ThisN == N
then
inc := true
else
SearchPtr:=SearchPtr^.NextN;
end;
Notes: <number>

## Slide 28: The PSP Counting Standard
Count all statements. This includes
  begin, end, if, then, else,
  {, }, ;, .,
  declarations, directives, headers, etc.
Do not count blanks, comment lines, automatically generated code, or reused code.
Count new and changed code for measuring and estimating development productivity.
Notes: <number>

## Slide 29: Line of Code Accounting
For small programs, size tracking can be done manually, but it requires care.
For larger programs, size tracking requires an accounting system.
LOC accounting provides an orderly and precise way to track LOC changes through multiple program versions.
Notes: <number>

## Slide 30: Example of LOC Accounting -1
Version 0
350 LOC
Enhance to version 1
+ 125 new and
changed LOC
Expected size
350+125=475 LOC
What happened?
Measured size
450 LOC
Notes: <number>

## Slide 31: Example of LOC Accounting -2
 | Added | Subtracted | Base
Base V0 |  |  | 0
Deleted |  | 0 | 
Modified | 0 | 0 | 
Added | 350 |  | 
Total V0 LOC | 350 | -0 | 350
Deleted |  | 0 | 
Modified | 25 | 25 | 
Added | 100 |  | 
Final Product | 125 | -25 | 450
Total New and Changed LOC |  |  | 475
Notes: <number>

## Slide 32: Messages to Remember
To effectively plan and manage your work, you must measure product size.
The PSP uses LOC as the size measure.
For other measures, size must correlate with development time.
Every size measure should be precisely defined and automatically countable.
Notes: <number>