## Slide 1: Personal Software ProcessSM for Engineers: Part I Size Estimating
Notes: <number>

## Slide 3: Lecture Topics
Why estimate size?
Estimating background
Size estimating principles
Size estimating proxies
Notes: <number>

## Slide 4: Why Estimate Size?
Size estimates allow you to make better plans.
  more accurately size the job
  divide the job into separable elements
Size estimates assist you in tracking progress. You can
  judge when the job scope changes
  better measure the work
Value in this course
  learn estimating methods
  build estimating skills
Notes: <number>

## Slide 5: Estimating Background
Estimating models in other fields
  have a large historical base
  are widely used
  generate detailed planning data
  require a size estimate as input
Software size estimating experience
  100% + errors are normal.
  Few developers make estimates.
  Fewer still use orderly methods.
Notes: <number>

## Slide 6: Size Estimating Principles -1
Estimating is an uncertain process.
  No one knows how big the product will be.
  The earlier the estimate, the less is known.
  Estimates can be biased by business and other pressures.
Estimating is an intuitive learning process.
  Ability improves with experience and data.
  Some people will be better at estimating than others.
Notes: <number>

## Slide 7: Size Estimating Principles -2
Estimating is a skill.
  Improvement will be gradual.
  You may never get very good.
The objective is to become consistent.
  You will understand the variability of your estimates.
  You seek an even balance between under- and overestimates.
Notes: <number>

## Slide 8
Size Estimating Error Range
-100
0
100
200
300
400
500
1
2
3
4
5
6
7
8
9
10
Program Number
% Error
Max
Class
Min
Notes: <number>

## Slide 9: Size Estimating Principles -3
Principal advantages of using a defined estimating method
  You have known practices that you can work to improve.
  It provides a framework for gathering estimating data.
  By using consistent methods and historical data, your estimates will get more consistent.
Notes: <number>

## Slide 10: The Project Planning Framework
Product
delivery
Tracking
reports
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Size
database
Productivity
database
Notes: <number>

## Slide 11: Popular Estimating Approaches
Fuzzy logic
Function points
Standard components
Delphi
Notes: <number>

## Slide 12: Fuzzy Logic Size Estimating -1
Gather size data on previously developed programs.
Subdivide these data into size categories and subcategories.
Notes: <number>

## Slide 13: Fuzzy Logic Size Estimating -2
When estimating a new program, compare the planned program with prior programs and select the most appropriate size category.
For a medium-small, estimated LOC = 23,988
Notes: <number>

## Slide 14: Fuzzy Logic Advantages
Fuzzy logic estimating
  is based on relevant historical data
  is easy to use
  requires no special tools or training
  provides reasonably good estimates in cases where new work is like prior experience
Notes: <number>

## Slide 15: Fuzzy Logic Disadvantages
It requires a lot of data.
The estimators must be familiar with the historically-developed programs.
It provides only a crude sizing.
It is not useful for new program types.
It is not useful for programs that are much larger or smaller than the historical data.
Notes: <number>

## Slide 16: Function Point Estimating
A function point is an arbitrary unit.
  based on application functions (inputs, outputs, files, inquiries, interfaces)
  scaled by simple, average, complex
For job complexity, adjust a further +/- 35%.
Notes: <number>

## Slide 17: Function Point Estimating Procedure
Determine numbers of each function type in the application.
Judge the scale and complexity of each function. Calculate function point total.
Use historical data on development cost per function point to make the estimate.
Multiply function points times rate to get the estimate.
Notes: <number>

## Slide 18: Function Point Advantages
They are usable in the earliest requirements phases.
They are independent of programming language, product design, or development style.
There exists a large body of historical data.
It is a well-documented method.
There is an active users’ group.
Notes: <number>

## Slide 19: Function Point Disadvantages
You cannot directly count an existing product’s function point content.
Without historical data, it is difficult to improve estimating skill.
Function points do not reflect language, design, or style differences.
Function points are designed for estimating commercial data processing applications.
Notes: <number>

## Slide 20: Standard Component Sizing -1
Establish the principal product size levels.
  components, modules, screens, etc.
  determine typical sizes of each
For a new product
  Determine the component level at which estimation is practical.
  Estimate how many of those components are likely to be in the product.
  Determine the maximum and minimum numbers possible.
Notes: <number>

## Slide 21: Standard Component Sizing -2
Calculate the size as the number of components of each type times typical sizes of each type. Add all of the type sizes to figure a total size.
Calculate for the maximum, minimum, and likely numbers of components.
Calculate size as {maximum+4*(likely)+minimum}/6
Notes: <number>

## Slide 22: Standard Component Sizing - Advantages and Disadvantages
Advantages
  based on relevant historical data
  easy to use
  requires no special tools or training
  provides a rough estimate range
Disadvantages
  must use large components early in a project
  limited data on large components
Notes: <number>

## Slide 23: Delphi Size Estimating
Uses several estimators
  Each makes an independent estimate.
  Each submits their estimate to a coordinator.
Coordinator
  calculates average estimate
  enters on form: average, other estimates (anonymous), and previous estimate
When reestimates stabilize
  average is the estimate
  range is range of original estimates
Notes: <number>

## Slide 24: Delphi Size Estimating - Advantages and Disadvantages
Advantages
  can produce very accurate results
  utilizes organization’s skills
  can work for any size product
Disadvantages
  relies on a few experts
  is time consuming
  is subject to common biases
Notes: <number>

## Slide 25: Size Estimating Proxies -1
The basic issue
  Good size measures are detailed.
  Estimators rarely can think in detail early in a project.
Alternatives
  Wait to estimate until you have the detail.
  Make your best guess.
  Identify a suitable proxy.
Notes: <number>

## Slide 26: Size Estimating Proxies -2
A good proxy should correlate closely to development costs.
A good proxy should be easy to visualize early in development.
It should also be a physical entity that can be counted.
Notes: <number>

## Slide 27: Estimating Building Costs
Problem
  The builder needs to know the floor area (in sq. ft.) to estimate the cost of construction.
  The client normally cannot provide their requirements in sq. ft., but knows the type and number of rooms desired.
Solution
  Use rooms as a proxy for size and translate from these into sq. ft. using historical (typical) data.
Notes: <number>
To explain how proxies work for estimating, let's look at an example from outside the software field.

## Slide 28: Example: Client Requirements
Bedrooms: 1 large, 2 medium and 1 small
Bathrooms: 1 large and 2 medium
Kitchen: 1 large
Living room: 1 large
Dining room: 1 medium
Family room: 1 large
Utility: 1 medium
Notes: <number>
A client might have the following requirements for their new house.

## Slide 29: Historical Building Data
 | small | medium | large
Bedrooms | 90 | 140 | 200
Bathrooms | 25 | 60 | 120
Kitchens | 100 | 130 | 160
Living rooms | 150 | 250 | 400
Dining rooms | 100 | 140 | 200
Family rooms | 150 | 240 | 340
Utility | 25 | 50 | 80
Notes: <number>
The builder can use historical data to build this table showing typical room sizes.

## Slide 30: Proxy Calculation
Bedroom | 1 large | = | 1 x | 200 | = | 200
Bedroom | 2 medium | = | 2 x | 140 | = | 280
Bedroom | 1 small | = | 1 x | 90 | = | 90
Bathroom | 1 large | = | 1 x | 120 | = | 120
Bathroom | 2 medium | = | 2 x | 60 | = | 120
Kitchen | 1 large | = | 1 x | 130 | = | 130
Living room | 1 large | = | 1 x | 400 | = | 400
Dining room | 1 medium | = | 1 x | 140 | = | 140
Family room | 1 large | = | 1 x | 340 | = | 340
Utility | 1 medium | = | 1 x | 50 | = | 50
 |  | Total (sq. ft.) |  |  | = | 1870
Notes: <number>
We can combine the two sets of information to calculate the estimated area of the client's new house.
Could animate this to fill in the table in stages. Start with the first 2 columns, then add the rest of each row (row 1, row 2, then the rest, with total row as final step)

## Slide 31: Example Proxies
Objects
Product elements
  components
  screens, reports, scripts, files
  book chapters
Notes: <number>
For software development, we need to identify suitable proxies.

## Slide 32: Objects as Proxies -1
Correlation with development hours
  Numbers of objects correlate reasonably well.
  Object LOC correlate very closely.
  Object LOC can be estimated using the standard component estimating method.
  The LOC estimate can be calculated from the historical relationship between object LOC and program LOC.
Notes: <number>

## Slide 33: Objects as Proxies -2
When objects are selected as application entities, they can be visualized early in development.
Functions and procedures can often be estimated in the same way.
Objects, functions, procedures, and their LOC can be automatically counted.
Notes: <number>

## Slide 34: Object LOC Correlation With Development Hours
Notes: <number>

## Slide 35: Example Proxies - Other
Possible candidates
  screens, reports, scripts, files
  book chapters
If the number of items correlates with development, you estimate the number of items.
With a suitable proxy size measure, you can often estimate proxy size.
Notes: <number>

## Slide 36: Chapter Pages Versus Time
Notes: <number>

## Slide 37: Next Lecture: The PROBE Method
The PROBE estimating method
Statistical estimating considerations
A size estimating example
Estimating considerations
Notes: <number>

## Slide 38: Messages to Remember
Accurate size estimates will help you to make better development plans.
Size estimating skill improves with practice.
A defined and measured process provides a repeatable basis for improvement.
There are several ways to make size estimates.
Notes: <number>