## Slide 1: Personal Software ProcessSM for Engineers: Part I The PROBE Estimating Method
Notes: <number>

## Slide 3: Lecture Topics
Size estimating review
The PROBE estimating method
Preparing to use PROBE
  categorizing object data
  the regression method
  the prediction interval
Notes: <number>

## Slide 4: PROBE Method Update
Revisions to the original PROBE method are incorporated into the August 1997 reprint of the textbook. The revised forms include
  C36, page 679, PROBE estimating script
  C39, page 683, size estimating template
  C40, page 684, size estimating template instructions
  Table 5.8, page 120, size estimating example
  all project plan summaries from PSP1 to PSP3
If you have an earlier version of the textbook, remember to update it.
Notes: <number>

## Slide 5: Size Estimating Review
Repeat for
all parts
Repeat until the
product parts are
the right size
Product requirement
Size estimate
Produce conceptual
design
Subdivide the product
into parts
Do the parts resemble
parts in the database?
Select the database parts
most like new ones
Estimate the new
part’s relative size
Sum the estimated sizes
of the new parts
Estimate total
product size
Obtain historical
size data
Notes: <number>

## Slide 6: The PSP Planning Framework
PROBE Method
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource
schedule
data
Process
analysis
Resources
available
Productivity
database
Size
database
Customer
need
Product
delivery
Tracking
reports
Customer
Management
Items
Tasks
Notes: <number>

## Slide 7: The PROBE Estimating Method
Conceptual
design
Start
Identify and size objects
Number of
methods
Object
type
Relative
size
Reuse
categories
Estimate other LOC
Estimate
program size
Calculate
prediction interval
Size estimate
Estimate
resources
Calculate
prediction interval
Resource estimate
Notes: <number>

## Slide 8: Conceptual Design
A conceptual design is needed to
  relate the requirements to the product
  define the product elements that will produce the desired functions
  estimate the size of what will be built
For understood designs, conceptual designs can be done quickly.
If you do not understand the design, you do not know enough to make an estimate.
Notes: <number>

## Slide 9: Identify the Objects -1
Where possible, select application entities.
Judge how many methods each object is likely to contain.
Determine the type of the object, e.g., data, calculation, file, control, etc.
Judge the relative size of each object: very small (VS), small (S), medium (M), large (L), or very large (VL).
Notes: <number>

## Slide 10: Identify the Objects -2
From historical object data, determine the size in LOC/method of each object.
Multiply by the number of methods to get the estimated object LOC.
Judge which objects will be added to the reuse library and note as “New Reused.”
Notes: <number>

## Slide 11: Identify the Objects -3
When objects do not fit an existing type, they are frequently composites.
  Ensure that they are sufficiently refined.
  Refine those that are not elemental objects.
Watch for new object types.
Notes: <number>

## Slide 12: Identifying Objects - Example 1
In Table 5.8, three new objects are identified with their numbers of methods, relative size, and LOC.
New Objects Type Methods Size LOC
  Matrix Data 13 M 115
  Linear System Calc. 8 L 197
  Linked List Data 3 L 49
How were these values determined?
Notes: <number>

## Slide 13: Identifying Objects - Example 2
Two reused objects are also shown in table 5.8, page 120.
New objects to be put in the reuse library are identified by an asterisk, such as linked list.
The unmodified reused objects are
Linked list 73
Data entry 96
Linked list is an existing 73 LOC object with three added methods of 49 LOC.
Notes: <number>

## Slide 14: Estimate Program Size -1
Total program size consists of
  newly-developed code (adjusted with the regression parameters)
  reused code from the library
  base code from prior versions, less deletions
Newly developed code consists of
  base additions (BA): additions to the base
  new objects (NO): newly developed objects
  modified code (M): base LOC that are changed
Newly developed code is referred to as estimated object LOC (E).
Notes: <number>

## Slide 15: Estimate Program Size -2
Calculate the estimated new and changed LOC (N) from the estimated object LOC (E).
E = BA+NO+M
Use linear regression to calculate
  new and changed LOC
  development time
Notes: <number>

## Slide 16: Estimate Program Size -3
Calculate regression parameters 0 and 1 from data on each previously developed program.
For the x values, use estimated object LOC (E).
For the y values, use the
  actual new and changed LOC in each finished program for size estimates
  actual total development time for each finished program for time estimates
Notes: <number>

## Slide 17: Estimate Program Size -4
Code used from the reuse library should be counted and included in the total LOC size estimate.
Base code consists of LOC from a previously developed program version or modified code from the program library.
While base code is a form of reuse, only unmodified code from the reuse library is counted as reused LOC in the PSP.
Notes: <number>

## Slide 18: Completing the Estimate -1
The completed estimate consists of the
  estimated new and changed LOC calculated with the size regression parameters
  70% upper prediction interval (UPI) and lower prediction interval (LPI) for the new and changed LOC
  total LOC, considering new, base, reused, deleted, and modified code
  projected new reuse LOC to be added to the reuse library
Notes: <number>

## Slide 19: Completing the Estimate -2
The completed estimate also includes the
  estimated development time calculated with the time regression parameters
  70% upper prediction interval (UPI) and lower prediction interval (LPI) for the development time
Notes: <number>

## Slide 20: Completed Example -1
Base program (B) 695 LOC
Deleted (D) 0 LOC
Modified (M) 5 LOC
Base additions (BA) 0 LOC
New objects: NO = 115+197+49 = 361 LOC
Reused programs 169 LOC
Notes: <number>

## Slide 21: Completed Example -2
Use the size regression parameters to calculate new and changed LOC (N).
0Size = 62 and 1Size = 1.3
Estimated object: E = BA + NO + M = 366 LOC
New and changed: N = 62 + 1.3 * 366 = 538 LOC
Total: T = 538 + 695 - 5 + 169 = 1397 LOC
Estimated total new reuse = 49 LOC
Notes: <number>

## Slide 22: Completed Example -3
Use the time regression parameters to calculate development time.
0Time = 108 and 1Time = 2.95
Development time = 108 + 2.95 * 366 = 1186 min.
Notes: <number>

## Slide 23: Calculate the Prediction Interval
Calculate the prediction range for size and time.
Calculate the upper and lower prediction interval (UPI/LPI) for size.
  UPI = N + Range = 538 + 235 = 773 LOC
  LPI = N - Range (or 0) = 538 - 235 = 303 LOC
Calculate the range for time.
  UPI = Time + Range = 1186 +431 = 1617 min.
  LPI = Time - Range (or 0) = 1186 - 431 = 775 min.
Notes: <number>

## Slide 24: After Development
After development, measure and record actual size of
  base, deleted, and modified LOC
  base additions
  new objects
  reused objects
If an object was
  planned but not developed, then its actual size is 0 LOC
  developed but not planned, then its planned size is 0 LOC
Notes: <number>

## Slide 25: Preparing to Use PROBE
To use PROBE for size and time estimates, you will need the following items.
  historical data on objects, divided into types
  estimating factors for the relative sizes of each object type
  regression parameters for predicting size and time based on historical data
  historical data on estimated and actual program size and development time for calculating regression parameters and prediction intervals
Notes: <number>

## Slide 26: Historical Data on Objects
Object size is highly variable.
  depends on language
  influenced by design style
  normalizing by number of methods can help
Pick basic types.
  logic, control
  I/O, files, display
  data, text, calculation
  set-up, error handling
Notes: <number>

## Slide 27: Estimating Factors for New Objects
You seek size ranges for each type that will help you judge the sizes of new objects.
To calculate these size ranges
  take the mean
  take the standard deviation
  very small (VS) = mean - 2 * standard deviations
  small (S) = mean - standard deviation
  medium (M) = mean
  large (L) = mean + standard deviation
  very large (VL) = mean + 2 * standard deviations
  Read section 5.5 (pages 125-134) in the textbook for details.
Notes: <number>

## Slide 28: Normal Distribution with Size Ranges
Notes: <number>

## Slide 29: Log-Normal Distribution
These size ranges assume that the object data are normally distributed.
If the data are log-normally distributed, take the log of the data before making the size range calculations.
Then, after computing the size ranges, take the antilog to get the factors in LOC.
Notes: <number>

## Slide 30: A Log-Normal Distribution
Notes: <number>

## Slide 31: Estimating Factors -1
You have the following data on an object type.
  one object, three methods, 39 total LOC
  one object, five methods, 127 total LOC
  one object, two methods, 64 total LOC
  one object, three methods, 28 total LOC
  one object, one method, 23 LOC
  one object, two methods, 44 total LOC
The LOC per method is 13, 25.4, 32, 9.333, 23, 22
Notes: <number>

## Slide 32: Estimating Factors -2
The logs of these data are
2.565, 3.235, 3.466, 2.234, 3.135, 3.091
The average is 2.954.
The standard deviation is 0.421.
The log values of the size ranges are
  very large (VL) = 2.95 + 2*0.421 = 3.79
  large (L) = 2.95 + 0.421 = 3.37
  medium (M) = 2.95
  small (S) = 2.95 - 0.421= 2.53
  very small (VS) = 2.95 - 2*0.421 = 2.11
Notes: <number>

## Slide 33: Estimating Factors -3
From these log size ranges, the LOC ranges are obtained by taking the antilog.
  very large (VL) = exp(3.79) = 44.3
  large (L) = exp(3.37) = 29.1
  medium (M) = exp(2.95) = 19.1
  small (S) = exp(2.53) = 12.6
  very small (VS) = exp(2.11) = 8.3
Repeat these calculations for every object type.
Notes: <number>

## Slide 34: C++ Object Size Ranges
Type
VS
VL
M
S
L
Calculation
Data
I/O
Logic
Set-up
Text
2.34 5.13 11.25 24.66 54.04
2.60 4.79 8.84 16.31 30.09
9.01 12.06 16.15 21.62 28.93
7.55 10.98 15.98 23.25 33.83
3.88 5.04 6.56 8.53 11.09
3.75 8.00 17.07 36.41 77.66
LOC per method
Notes: <number>

## Slide 35: Statistically-Based Estimates
PROBE uses historical data, linear regression, and the prediction interval to produce an estimate of known accuracy.
Regression provides the best fit, or minimum variance, of a line to these data.
The variance of the data is used to determine the prediction interval.
Notes: <number>

## Slide 36: Estimating Basis
With PROBE, estimates are based on one of four methods.
To use either regression method, you need
  a reasonable amount of historical data
  data that correlate
  reasonable parameters
Method
A regression with estimated object LOC
B regression with estimated new and changed LOC
C the averaging method
D engineering judgement
Notes: <number>

## Slide 37
Notes: <number>

## Slide 38
Notes: <number>

## Slide 39: The Regression Parameters
The regression parameters are calculated using the following formula.
where x and y are the appropriate historical data, and n is the number of data points
Notes: <number>

## Slide 40: Method A: Regression with Estimated Object LOC
Method A uses the relationship between estimated object LOC and
  actual new and changed LOC
  actual development time
The criteria for using this method are
  three or more data points that are correlated (R2 > 0.5)
  reasonable regression parameters (see table C36, page 679)
  completion of all programs through 6A
Notes: <number>

## Slide 41: Method B: Regression with Estimated New and Changed LOC
Method B uses the relationship between estimated new and changed LOC and
  actual new and changed LOC
  actual development time
The criteria for using this method are
  three or more data points that are correlated (R2 >0.5)
  reasonable regression parameters (see table C36, page 679)
  completion of all programs through 4A
Notes: <number>

## Slide 42: Method C: Averaging Method
Method C uses a ratio to adjust size or time based on historical averages.
The averaging method is easy to use and requires only one data point.
Averages assume that there is no fixed overhead.
The average method is described in table C36 (page 679), PROBE estimating script.
Notes: <number>

## Slide 43: Method D: Engineering Judgement
Method D is used in the absence of historical data.
  uses judgement to estimate new and changed LOC from estimated object LOC
  uses judgement to estimate the required development time
Method D is used when methods A, B, and C cannot be used.
Notes: <number>

## Slide 44: The Prediction Interval
The prediction interval provides a likely range around the estimate.
  A 90% prediction interval gives the range within which 90% of the estimates will likely fall.
  It is not a forecast, only an expectation.
  It applies only if the estimate behaves like the historical data.
It is calculated from the same data used to calculate the regression parameters.
Notes: <number>

## Slide 45
Notes: <number>

## Slide 46: Messages to Remember
The PROBE method is a structured way to make software size estimates.
It uses your personal size data.
It provides a statistically sound range within which the actual program size is most likely to fall.
Notes: <number>