Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Student Workbook for
 PSP2 Exercise

Personal Software Process for Engineers: Part II

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

- Personal Software Process for Engineers: Part II

- PSP2 Exercise

- Overview

| #### Exercise #### Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | PSP2 Process Scripts | 3 |
|  | BK’s Defect Data | 6 |
|  | BK’s Project Plan Summary | 7 |
|  | Project Plan Summary Instructions | 10 |

| #### Prerequisites #### and References | Prerequisite reading - Chapter 8 References - Appendix C5 |
| --- | --- |

| #### Exercise #### Objectives | After completing this exercise, you will - understand how defects injected and removed are projected in the planning phase - understand how to use the PSP2 Plan Summary |
| --- | --- |

| #### Exercise #### Instructions | Read through the PSP2 process scripts. Read BK’s scenario for program 7A. Use BK’s historical defect data and R4 goal to complete the unshaded portions of CK project plan summary in the “Plan” column. |
| --- | --- |

Table C51  PSP2 Process Script

| Phase Number | Purpose | To guide you in developing module-level programs |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP2 Project Plan Summary form • Size Estimating Template • Historical estimated and actual size and time data • Time and Defect Recording Logs • Defect Type Standard • Stop watch (optional) |
| 1 | Planning | • Produce or obtain a requirements statement. • Use the PROBE method to estimate the total new and changed LOC required and the prediction interval. • Complete the Size Estimating Template. • Use the PROBE method to estimate the development time required and the prediction interval. • Complete a Task Planning Template. • Complete a Schedule Planning Template. • Enter the plan data in the Project Plan Summary form. • Complete the Time Recording Log. |
| 2 | Development | • Design the program. • Review the design and fix and log all defects found. • Implement the design. • Review the code and fix and log all defects found. • Compile the program and fix and log all defects found. • Test the program and fix and log all defects found. • Complete the Time Recording Log. |
| 3 | Postmortem | Complete the Project Plan Summary form with actual time, defect, and size data. |
|  | Exit Criteria | • A thoroughly tested program • Completed Project Plan Summary form with estimated and actual data • Completed estimating and planning templates • Completed Design Review Checklist and Code Review Checklist • Completed Test Report Template • Completed PIP forms • Completed Defect and Time Recording Logs |

Table C52  PSP2 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP2 Project Plan Summary form • Size Estimating, Task Planning, and Schedule Planning Templates • Historical estimated and actual size and time data • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | • Produce a program conceptual design. • Use the PROBE method to estimate the new and changed LOC required to develop this program. • Estimate the base, added, deleted, modified, and reused LOC. • Complete the Size Estimating Template and Project Plan Summary form. • Calculate the 70 percent size prediction interval (you may use a spread sheet). |
| 3 | Resource Estimate | • Use the PROBE method to estimate the time required to develop the new program. • Calculate the 70 percent time prediction interval (you may use a spreadsheet). • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
| 4 | Task and Schedule Planning | For projects requiring several days or more of work, complete the Task Planning and Schedule Planning Templates. |
| 5 | Defect Estimate | • Based on your To Date data on defects per new and changed LOC, estimate the total defects to be found in this program. • Based on your To Date % data, estimate the numbers of defects to be injected and removed by phase. |
|  | Exit Criteria | • Documented requirements statement • The program conceptual design • Completed Size Estimating Template • For projects of several days duration, completed Task and Schedule Planning Templates • Project Plan Summary form with estimated program size, development time, and 70 percent prediction intervals • Completed Time Recording Log |

- This page intentionally left blank.

- BK’s Defect Data

| #### BK's Scenario for Program 7A | BK is in the planning phase for assignment 7A. He has reviewed the requirements for this assignment, completed the size estimate, used the PROBE worksheet, and now has the attached project plan summary filled in as indicated. To date, BK has experienced a total defect density of 102 defects/KLOC. As a result of the analysis BK did in his mid-term report, his goal is to achieve 50% review yield in each of the design and code reviews. Using this information, BK must now complete the remaining entries for the “Plan” column of the project plan summary. |
| --- | --- |

| #### BK's % Defects Injected by Phase | To date, the percentage defects injected by phase are as follows. |
| --- | --- |

| Phase | To Date % |
| --- | --- |
| Planning | 0% |
| Design | 27% |
| Code | 73% |
| Compile | 0% |
| Test | 0% |
| Total | 100% |

| #### BK's % Defects Removed by Phase | To date, the percentage defects removed by phase are as follows. |
| --- | --- |

| Phase | To Date % |
| --- | --- |
| Planning | 0% |
| Design | 0% |
| Code | 0% |
| Compile | 68% |
| Test | 32% |
| Total | 100% |

| #### Using BK’s Historical Data | To complete the project plan - Compute the Total Defects and the Defects Injected profile, using BK’s historical data. - Determine the Defect Removal profile, using BK’s historical data and yield goals. - Compute the Defect Removal Efficiency metrics. - Compute the summary metrics. |
| --- | --- |

Table C55  PSP2 Project Plan Summary

| Student | BK | Date |  |
| --- | --- | --- | --- |
| Program | Correlation and Significance | Program # | 7A |
| Instructor | Humphrey | Language | Pascal |

| Summary | Plan |  |  |  |  |  |  | Actual |  |  |  |  |  |  | To Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Planned Time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (Planned/Actual) |  |  |
| % Reuse |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % New Reused |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Yield % |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC) | Plan |  |  |  |  |  |  | Actual |  |  |  |  |  |  | To Date |  |  |
| Base(B) | 224 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  |  |  |  | (Measured) |  |  |  |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  |  |  |  | (Counted) |  |  |  |  |  |  |  |  |  |
| Modified (M) | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  |  |  |  | (Counted) |  |  |  |  |  |  |  |  |  |
| Added (A) | 126 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (N  M) |  |  |  |  |  |  | (T  B + D  R) |  |  |  |  |  |  |  |  |  |
| Reused (R) | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  |  |  |  | (Counted) |  |  |  |  |  |  |  |  |  |
| Total New & Changed (N) | 146 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  |  |  |  | (A + M) |  |  |  |  |  |  |  |  |  |
| Total LOC (T) | 350 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (N + B  M  D + R) |  |  |  |  |  |  | (Measured) |  |  |  |  |  |  |  |  |  |
| Total New Reused | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated Object LOC (E) | 102 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) | 183 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Internal (70%) | 109 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  |  |  |  | To Date |  |  |  |  |  | To Date % |  |
| Planning | 49 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design | 87 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design Review | 44 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Code | 64 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Code Review | 44 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compile | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test | 33 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total | 365 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) | 397 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 333 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

(continued)

Table C55  PSP2 Project Plan Summary (continued)

| Student | BK | Date |  |
| --- | --- | --- | --- |
| Program | Correlation and Significance | Program # | 7A |
| Instructor | Humphrey | Language | Pascal |

| Defects Injected | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |
| Design Review |  |  |  |  |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |
| Code Review |  |  |  |  |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |  |  |  |  |
| Test |  |  |  |  |  |  |  |  |  |  |  |
| Total Development |  |  |  |  |  |  |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |
| Design Review |  |  |  |  |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |
| Code Review |  |  |  |  |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |  |  |  |  |
| Test |  |  |  |  |  |  |  |  |  |  |  |
| Total Development |  |  |  |  |  |  |  |  |  |  |  |
| After Development |  |  |  |  |  |  |  |  |  |  |  |
| Defect Removal Efficiency | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Defects/Hour  Design Review |  |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour Code Review |  |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour  Compile |  |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour  Test |  |  |  |  |  |  |  |  |  |  |  |
| DRL(DLDR/UT) |  |  |  |  |  |  |  |  |  |  |  |
| DRL(CodeReview/UT) |  |  |  |  |  |  |  |  |  |  |  |
| DRL(Compile/UT) |  |  |  |  |  |  |  |  |  |  |  |

Table C56  PSP2 Project Plan Summary Instructions

| Purpose | To hold the estimated and actual project data in a convenient and readily retrievable form |
| --- | --- |
| Header | Enter the specified data. |
| Summary | • Enter the new and changed LOC per hour planned and actual for this program and for all programs developed to date. • Enter the planned and actual times for this program and the sums of the planned and actual times for all the exercises to date. • CPI = (To Date Planned Time)/(To Date Actual Time). • Enter the planned, actual, and To Date Reuse data. • Enter the planned, actual, and To Date defect data. • Enter the planned and actual yield. |
| Program Size (LOC) | Prior to Development: • If you are modifying or enhancing an existing program, count that program’s LOC and enter it under BasePlan. • From the Size Estimating Template, enter estimated object LOC (E) under Plan. • Enter the estimated new and changed LOC (N) from the Size Estimating Template. • Estimate the numbers of added (A) and modified (M) LOC so that N = A + M. • Estimate the numbers of deleted (D) and reused (R) LOC and combine with the measured base (B) LOC so that T = N + B  M  D + R. After Development: • If the base LOC (B) has changed, enter the new value. • Measure the total program size and enter it under Total LOC (T) Actual. • Review your source code and, with the help of program 3A, determine the actual LOC that were deleted (D), modified (M), or reused (R). • Calculate the LOC of added code as A = T  B+ D  R. • Calculate the total new and changed LOC as N = A + M. |
| Time in Phase | • Under Plan, enter estimated total time from the Size Estimating Template and time by phase. • Under Actual, enter the actual time for each phase. • Under To Date, enter the sum of the actual time and the To Date time from your most recently developed program. • Under To Date %, enter the percentage of To Date time in each phase. |

(Continued)

Table C56  PSP2 Project Plan Summary Instructions (Continued)

| Defects Injected | • Under Actual, enter the number of defects injected in each phase. • Under To Date, enter the sum of the actual numbers of defects injected in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects injected by phase. |
| --- | --- |
| Defects Removed | • Under Actual, enter the numbers of defects removed in each phase. • Under To Date, enter the sum of the actual number of defects removed in each phase and the To Date value from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects removed by phase. • After development, record any defects later found during program use, reuse, or modification. |
| Defect Removal Efficiency | • Under Plan, enter the planned efficiencies for this project. • Under Actual, enter the actual efficiencies achieved. • Under To Date, enter the actual efficiencies for all the projects to date. |