Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Student Workbook for
Assignment Workshop 10A

Personal Software Process for Engineers: Part II

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.
Distribution limited by the Software Engineering Institute to attendees.

Personal Software Process for Engineers: Part II

Assignment Workshop 10A

Overview

| #### Workshop Overview | The workshop will cover the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Workshop Objectives | 3 |
|  | Program Requirements for Assignment 10A | 3 |
|  | Multiple Regression | 5 |
|  | The Gauss Method | 8 |
|  | Assignment Instructions | 11 |
|  | Guidelines and Evaluation Criteria | 19 |
|  | PSP2.1 Assignment Package | A1 |

| Prerequisites and References | Prerequisite reading • Chapter 11 References • Section A9 • Section A10 • Section A11 • Section C7 • Section D3 |
| --- | --- |

### Program Requirements for Assignment 10A

| Workshop Objectives | After this workshop, you will • understand program 10A requirements • have completed program 10A planning - conceptual design - size estimate - resource estimate - defect estimate |
| --- | --- |

| Program 10A Requirements | Using PSP2.1, develop program 10A to calculate the three-variable multiple-regression estimating parameters (0, 1, 2, 3). Make an estimate from user-supplied inputs, and determine the 70% and 90% prediction intervals for the estimate. Use a linked list to store the data and the Simpson’s integration routine from 5A to calculate the t distribution. Test the program using the data in table D16, page 763, as the historical data. For the user inputs, use 185 LOC of new code, 150 LOC of reused code, and 45 LOC of modified code. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Prog. # | New LOC | Reused LOC | Modified LOC | Hours |  |
|  |  |  | w | x | y | z |  |
|  |  | 1 | 345 | 65 | 23 | 31.4 |  |
|  |  | 2 | 168 | 18 | 18 | 14.6 |  |
|  |  | 3 | 94 | 0 | 0 | 6.4 |  |
|  |  | 4 | 187 | 185 | 98 | 28.3 |  |
|  |  | 5 | 621 | 87 | 10 | 42.1 |  |
|  |  | 6 | 255 | 0 | 0 | 15.3 |  |
|  |  | Sum | 1670 | 355 | 149 | 138.1 |  |
|  |  | Average | 278.33 | 59.17 | 24.83 | 23.02 |  |
|  |  | Estimate | 185 | 150 | 45 | ?? |  |

Continued on next page

Program Requirements for Assignment 10A, Continued

| Program 10A Requirements, Continued | Also test the program using the data in table A32, page 556, as the historical data. For the user inputs, use 650 LOC of new code, 3000 LOC of reused code, and 155 LOC of modified code. |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Prog# |  | New LOC |  | Reused LOC |  | Modified LOC | Development Hours |  |  |  |
|  |  |  |  | w |  | x |  | y | z |  |  |  |
|  |  | 1 |  | 1,142 |  | 1,060 |  | 325 | 201 |  |  |  |
|  |  | 2 |  | 863 |  | 995 |  | 98 | 98 |  |  |  |
|  |  | 3 |  | 1,065 |  | 3,205 |  | 23 | 162 |  |  |  |
|  |  | 4 |  | 554 |  | 120 |  | 0 | 54 |  |  |  |
|  |  | 5 |  | 983 |  | 2,896 |  | 120 | 138 |  |  |  |
|  |  | 6 |  | 256 |  | 485 |  | 88 | 61 |  |  |  |
|  |  | Sum |  | 4,863 |  | 8,761 |  | 654 | 714 |  |  |  |
|  |  | Estimate |  | 650 |  | 3,000 |  | 155 | ??? |  |  |  |
|  | Submit a test report with your results in the format in table D17, page 764. |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Test |  | Parameter |  | Expected Value |  |  | Actual Value |  |  |
|  |  |  | Table D16 |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | 0 |  | 0.56645 |  |  |  |  |  |
|  |  |  |  |  | 1 |  | 0.06533 |  |  |  |  |  |
|  |  |  |  |  | 2 |  | 0.008719 |  |  |  |  |  |
|  |  |  |  |  | 3 |  | 0.15105 |  |  |  |  |  |
|  |  |  |  |  | Projected Hours |  | 20.76 |  |  |  |  |  |
|  |  |  |  |  | UPI (70%) |  | 26.89 |  |  |  |  |  |
|  |  |  |  |  | LPI (70%) |  | 14.63 |  |  |  |  |  |
|  |  |  |  |  | UPI (90%) |  | 33.67 |  |  |  |  |  |
|  |  |  |  |  | LPI (90%) |  | 7.84 |  |  |  |  |  |
|  |  |  | Appendix A |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | 0 |  | 6.7013 |  |  |  |  |  |
|  |  |  |  |  | 1 |  | 0.0784 |  |  |  |  |  |
|  |  |  |  |  | 2 |  | 0.0150 |  |  |  |  |  |
|  |  |  |  |  | 3 |  | 0.2461 |  |  |  |  |  |
|  |  |  |  |  | Projected Hours |  | 140.9 |  |  |  |  |  |
|  |  |  |  |  | UPI (70%) |  | 179.7 |  |  |  |  |  |
|  |  |  |  |  | LPI (70%) |  | 102.1 |  |  |  |  |  |
|  |  |  |  |  | UPI (90%) |  | 222.74 |  |  |  |  |  |
|  |  |  |  |  | LPI (90%) |  | 59.06 |  |  |  |  |  |

Multiple Regression

| Introduction to Multiple Regression | Suppose that you had the following data on six projects. - development hours required - new, reused, and modified LOC Suppose that you wished to estimate the hours for a new project that you judged would have 650 LOC of new code, 3,000 LOC reused code, and 155 LOC of modified code. How would you estimate the development hours and the prediction interval? |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Prog# | New LOC | Reused LOC | Modified LOC | Development Hours |  |
|  |  |  | w | x | y | z |  |
|  |  | 1 | 1,142 | 1,060 | 325 | 201 |  |
|  |  | 2 | 863 | 995 | 98 | 98 |  |
|  |  | 3 | 1,065 | 3,205 | 23 | 162 |  |
|  |  | 4 | 554 | 120 | 0 | 54 |  |
|  |  | 5 | 983 | 2,896 | 120 | 138 |  |
|  |  | 6 | 256 | 485 | 88 | 61 |  |
|  |  | Sum | 4,863 | 8,761 | 654 | 714 |  |
|  |  | Estimate | 650 | 3,000 | 155 | ??? |  |

| #### Calculating Multiple Regression Parameters | Multiple regression provides a way to estimate the effects of multiple variables when you do not have separate data for each. The 13 steps are described as follows. - Use the following multiple regression formula to calculate the project value. zk=β0+wkβ1+xkβ2+ykβ3 - Find the Beta parameters by solving the following simultaneous linear equations. β0n+β1i=1nwi+β2i=1nxi+β3i=1nyi=i=1nziβ0i=1nwi+β1i=1nwi2+β2i=1nwixi+β3i=1nwiyi=i=1nwizi β0i=1nxi+β1i=1nwixi+β2i=1nxi2+β3i=1nxiyi=i=1nxizi β0i=1nyi+β1i=1nwiyi+β2i=1nxiyi+β3i=1nyi2=i=1nyizi |
| --- | --- |

Continued on next page

Multiple Regression, Continued

| #### Calculating Multiple Regression Parameters, Continued | - When you calculate the values of the terms, you get the following simultaneous linear equations. 6β0+4,863β1+8,761β2+654β3=7144,863β0+4,521,899β1+8,519,938β2+620,707β3=667,8328,761β0+8,519,938β1+21,022,091β2+905,925β3=1,265,493654β0+620,707β1+905,925β2+137,902β3=100,583 - Diagonalize, using Gauss’ method. This successively eliminates one parameter at a time from the equations by successive multiplication and subtraction to give the following. 6β0+4,863β1+8,761β2+654β3=7140β0+580,437.5β1+1,419,148β2+90,640β3=89,1350β0+0β1+4,759,809β2−270,635β3=5,002.3320β0+0β1+0β2+37,073.93β3=9,122.275 - Solve for the Beta terms. β0=6.7013β1=0.0784β2=0.0150β3=0.2461 - Determine the prediction interval by solving for the range with the following equation. Range=tα2,n−4s1+1n+wk−wavg2wi−wavg2+xk−xavg2xi−xavg2+yk−yavg2yi−yavg2 - Calculate the variance as follows. s2=1n−4zi−β0−β1wi−β2xi−β3yi2 |
| --- | --- |

Continued on next page

Multiple Regression, Continued

| #### Calculating Multiple Regression Parameters, continued | - The variance evaluates to the following. - The terms under the square root are as follows. Newk−Newavg2=wk−wavg2=650−810.52=25,760.25Reusek−Reuseavg2=xk−xavg2=3,000−1,460.172=2,371,076.43Modifyk−Modifyavg2=yk−yavg2=155−1092=2,116 - The value of the t distribution for a 70% prediction interval is found under the 85% column and two degrees of freedom in table A2, page 489. It is 1.386. - The square root is evaluated. Range=1.386∗22.6511+16+25,760.25580,437.5+2,371,076.438,229,571+2,11666,616=38.846 - The final estimate is as follows. z = 6.71+0.0784*650+0.0150*3,000+0.2461*155 = 140.902 hours - The prediction interval of 38.846 hours means that the estimate is between 102.1 and 179.7 hours. |
| --- | --- |

The Gauss Method

| #### The Gauss method | A frequently-occurring problem in scientific engineering, and business applications is to solve a system of N equations with N unknowns. Gaussian elimination is a commonly-used algorithm for solving these equations. The Gauss method converts this 2X+3Y=83X+6Y=15 to this X+2Y=5Y=2 This technique is called triangularization. What is the value of X? |
| --- | --- |

| #### Gauss Method Example | Solve this system. The pivot [Row 1, Col 1] 2X+3Y=83X+6Y=15 - The equation with the largest absolute coefficient in the pivot column [any row, col 1] is exchanged with the equation in the pivot row. 3X+6Y=152X+3Y=8 - Reduce the coefficient for the pivot term to 1 by multiplying through by the reciprocal of the coefficient. 13∗3X+13∗6Y=13∗152X+3Y=8 We now have x+2Y=52X+3Y=8 |
| --- | --- |

Continued on next page

The Gauss Method, Continued

| #### The Gauss method, continued | - Eliminate the pivot column terms in all rows below the pivot row - Multiply the pivot row by the negated coefficient of the row below the pivot term to be eliminated, -2 in this example. X+2Y=52X+3Y=8 −2 *X+2Y=5 = −2X+−4Y=−10 Note: don’t change the pivot row; put this result in a temp store. - Add the 3a result to the row being eliminated. - Repeat 3a and 3b for each row below the pivot term. X+2Y=52X+3Y=8 + −2X+−4Y=−10 = X+2Y=5−Y=−2 - Complete the triangularization by repeating steps 1 to 3 as needed, then solve for the remaining terms using back-substitution. x+2y=5Y=2 X+4=5Y=2 X=?Y=2 |
| --- | --- |

Continued on next page

The Gauss Method, Continued

| #### The Gauss Algorithm | On a computer, the equations are represented by a matrix of the coefficients. X; Y. 2; 3; 8. 3; 6; 15. The algorithm is the same. Given X; Y. 2; 3; 8. 3; 6; 15. X; Y. 3; 6; 15. 2; 3; 8. X; Y. 1; 2; 5. 2; 3; 8. X; Y. 1; 2; 5. 0; -1; -2. X; Y. 1; 2; 5. 0; 1; 2. X; Y. 1; 2; 5; X=1. 0; 1; 2; Y=2. |
| --- | --- |

| #### A Gauss Algorithm | 1. I = 1 2. LET P=AK , I = max{¦AJ,I¦ : I = J <= N} (Find the pivot value which is the largest number in the column below the I,I position.) 3. IF P = 0 THEN EXIT (If the remainder of this column is zero, a unique solution does not exist.) 4. IF K > I THEN FOR J = I TO N + 1 SWAP A(I,J) AND A(K,J) (Get the pivot value into the I,I position.) 5. FOR J = I + 1 TO N + 1 LET AI,J = AI,J / AI,I (Get a one in the I,I position.) SET AI,I = 1. 6. FOR L = I + 1 to N multiply row I by -AL,I and add to row L (Zero out the column below the I,I position.) 7. I = I + 1. IF I < N THEN GO TO 2. 8. EXIT to back-substitution |
| --- | --- |

### Assignment Instructions

| #### Assignment Instructions | Before starting assignment 10A, review the top-level PSP2.1 process script below to ensure that you understand the “big picture” before you begin. Also, ensure that you have all of the inputs required before you begin the planning phase. |
| --- | --- |

Table C59  PSP2.1 Process Script

| Phase Number | Purpose | To guide you in developing module-level programs |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP2.1 Project Plan Summary form • Size Estimating Template • Historical estimated and actual size and time data • Time and Defect Recording Logs • Defect Type Standard • Stop watch (optional) |
| 1 | Planning | • Produce or obtain a requirements statement. • Use the PROBE method to estimate the total new and changed LOC required and the prediction interval. • Complete the Size Estimating Template. • Use the PROBE method to estimate the required development time and the prediction interval. • Complete a Task Planning Template. • Complete a Schedule Planning Template. • Enter the plan data in the Project Plan Summary form. • Complete the Time Recording Log. |
| 2 | Development | • Design the program using design templates where appropriate. • Review the design and fix and log all defects found. • Implement the design. • Review the code and fix and log all defects found. • Compile the program and fix and log all defects found. • Test the program and fix and log all defects found. • Complete the Time Recording Log. |
| 3 | Postmortem | Complete the Project Plan Summary form with actual time, defect, and size data. |
|  | Exit Criteria | • A thoroughly tested program • Completed Project Plan Summary form with estimated and actual data • Completed estimating and planning templates • Completed design templates • Completed Design Review Checklist and Code Review Checklist • Completed Test Report Template • Completed PIP forms • Completed Defect and Time Recording Logs |

Continued on next page

Assignment Instructions, Continued

| #### Planning Phase | Plan assignment 10A following the PSP2.1 planning phase script. |
| --- | --- |

Table C60  PSP2.1 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP2.1 Project Plan Summary form • Size Estimating, Task Planning, and Schedule Planning Templates • Historical estimated and actual size and time data • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure that the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | • Produce a program conceptual design. • Use the PROBE method to estimate the new and changed LOC required to develop this program. • Estimate the base, added, deleted, modified, and reused LOC. • Complete the Size Estimating Template and Project Plan Summary form. • Calculate the 70 percent size prediction interval (you may use a spread sheet). |
| 3 | Resource Estimate | • Use the PROBE method to estimate the time required to develop the new program. • Calculate the 70 percent prediction interval (you may use a spreadsheet). • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
| 4 | Task and Schedule Planning | For projects requiring several days or more of work, complete the Task Planning and Schedule Planning Templates. |
| 5 | Defect Estimate | • Based on your To Date data on defects per new and changed LOC, estimate the total defects to be found in this program. • Based on your To Date % data, estimate the numbers of defects to be injected and removed by phase. |
|  | Exit Criteria | • Documented requirements statement • The program conceptual design • Completed Size Estimating Template • For projects of several days duration, completed Task and Schedule Planning Templates • Project Plan Summary form with estimated program size, development time, and 70 percent prediction intervals • Completed Time Recording Log |

|  | Verify that you have met all of the exit criteria for the planning phase, then have an instructor review your plan. After your plan has been reviewed, proceed to the development phase. |
| --- | --- |

Continued on next page

### Assignment Instructions, Continued

|  | Use the PROBE method for size and resource estimating. |
| --- | --- |

Table C36  PROBE Estimating Script

|  | Purpose | To guide the PROBE estimation process |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Size Estimating Template and instructions • LOC per method data for object types • Time Recording Log • Historical size and time data |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Estimate Objects | Follow the Size Estimating Template instructions to estimate the new object LOC and new reused LOC. |
| 3 | Other Program LOC | Follow the Size Estimating Template instructions to estimate base, deleted, modified, added, and reused LOC. |
| 4 | The Size Estimating Procedure | A  If you have sufficient estimated object LOC and actual new and changed LOC (three or more points that correlate), use procedure 4A. B  If you do not have sufficient estimated object LOC data but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 4B. C  If you have insufficient data or they do not correlate, use procedure 4C. D  If you have no historical data, use procedure 4D. |
| 4A | The Size Estimating Procedure 4A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | The Size Estimating Procedure 4B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not reasonably near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | The Size Estimating Procedure 4C | If you have any data on estimated object LOC and actual new and changed LOC, set = 0 and = (total new and changed LOC to date/total estimated object LOC to date). |
| 4D | The Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate the new and changed LOC from the estimated object LOC. |

Continued on next page

### Assignment Instructions, Continued

Table C36  PROBE Estimating Script (Continued)

| 5 | The Time Estimating Procedure | A  If you have sufficient estimated object LOC and actual development time data (three or more points that correlate), use procedure 5A. B  If you do not have sufficient estimated object LOC data, but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 5B. C1  If you have some estimated object LOC data and they are insufficient or do not correlate, use procedure 5C1. C2  If you have some estimated new and changed LOC data and they are insufficient or do not correlate, use procedure 5C2. C3  If you only have actual data on new and changed LOC, use procedure 5C3. D  If you have no historical data, use procedure 5D. |
| --- | --- | --- |
| 5A | The Time Estimating Procedure 5A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C1. |
| 5B | The Time Estimating Procedure 5B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C2. |
| 5C1 | The Time Estimating Procedure 5C1 | If you have any data on estimated object LOC and actual development time, set = 0 and = (total development time to date/total estimated object LOC to date). |
| 5C2 | The Time Estimating Procedure 5C2 | If you have data on estimated new and changed LOC and actual development time, set = 0 and = (development time to date/estimated new and changed LOC to date). |
| 5C3 | The Time Estimating Procedure 5C3 | If you only have actual time and size data, set = 0 and = (development time to date/new and changed LOC to date). |
| 5D | The Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated object LOC. |
| 6 | Time and Size Prediction Intervals | - If you used the regression method, calculate the prediction interval as described in Table A29 (page 550). - If you did not use the regression method, estimate the maximum and minimum development times from your maximum and minimum productivity for prior programs. |

Continued on next page

Assignment Instructions, Continued

| #### Development Phase | Develop the program following the PSP2.1 development phase script. |
| --- | --- |

Table C61  PSP2.1 Development Script

| Phase Number | Purpose | To guide the development of small programs |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Project Plan Summary form with estimated program size and development time • For projects of several days’ duration, completed Task Planning and Schedule Planning Templates • Time and Defect Recording Logs • Defect Type Standard and Coding Standard |
| 1 | Design | • Review the requirements and produce an external specification to meet them. • Complete Function Specification and Operational Scenario Templates to record this specification. • Produce a design to meet this specification. • Record the design in Functional Specification, Operational Specification, State Specification, and Logic Specification Templates, as required. • Record in the Defect Recording Log any requirements defects found. • Record time in Time Recording Log. |
| 2 | Design Review | • Follow the Design Review Checklist and review the design. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 3 | Code | • Follow the Coding Standard and implement the design. • Record in the Defect Recording Log any requirements or design defects found. • Record time in Time Recording Log. |
| 4 | Code Review | • Follow the Code Review Checklist and review the code. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 5 | Compile | • Compile the program until error-free. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |

Continued on next page

Assignment Instructions, Continued

Table C61  PSP2.1 Development Script (Continued)

| 6 | Test | • Test until all tests run without error. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. • Complete a Test Report Template on the tests conducted and the results obtained. |
| --- | --- | --- |
|  | Exit Criteria | • A thoroughly tested program that conforms to the Coding Standard • Completed Design Templates • Completed Design Review and Code Review Checklists • Completed Test Report Template • Completed Defect and Time Recording Logs |

|  | Verify that you have met all of the exit criteria for the development phase, then proceed to the postmortem phase. |
| --- | --- |

Continued on next page

Assignment Instructions, Continued

| #### Postmortem #### Phase | Conduct the postmortem following the PSP2.1 postmortem script. |
| --- | --- |

Table C62  PSP2.1 Postmortem Script

| Phase Number | Purpose | To guide the PSP postmortem process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description and requirements statement • Project Plan Summary form with program size, development time, and defect data • For projects of several days’ duration, completed Task Planning and Schedule Planning Templates • Completed Test Report Template • Completed Design Templates • Completed Design Review and Code Review Checklists • Completed Time Recording Log • Completed Defect Recording Log • A tested and running program that conforms to the Coding Standard |
| 1 | Defects Injected | • Determine from the Defect Recording Log the number of defects injected in each PSP2.1 phase. • Enter this number under Defects InjectedActual on the Project Plan Summary form. |
| 2 | Defects Removed | • Determine from the Defect Recording Log the number of defects removed in each PSP2.1 phase. • Enter this number under Defects RemovedActual on the Project Plan Summary form. • Calculate the actual overall process yield and enter it in the Project Plan Summary form. |
| 3 | Size | • Count the LOC in the completed program. • Determine the base, reused, deleted, modified, added, total, total new and change, and new reused LOC. • Enter these data in the Project Plan Summary form. |
| 4 | Time | • Review the completed Time Recording Log. • Enter the total time spent in each PSP2.1 phase in the Actual column of the Project Plan Summary form. |
|  | Exit Criteria | • A fully tested program that conforms to the Coding Standard • Completed Design Templates • Completed Design Review and Code Review Checklists • Completed Test Report Template • Completed Project Plan Summary form • Completed PIP forms describing process problems, improvement suggestions, and lessons learned • Completed Defect and Time Recording Logs |

|  | Verify that you have met all of the exit criteria for the PSP2.1 postmortem phase, then submit your assignment. |
| --- | --- |

Continued on next page

Assignment Instructions, Continued

| #### Submitting Your Assignment | When you’ve completed the postmortem phase, submit your assignment package, source code, and test results to the instructor. The order for the assignment package is • PSP2.1 project plan summary • test report • design review checklist • code review checklist • PIP form • size estimating template • PROBE worksheet • operational scenario template • functional specification template • state specification template • logic specification template • time recording log • defect recording log • source program listing |
| --- | --- |

### Guidelines and Evaluation Criteria for Assignment 10A

| #### Evaluation Criteria | Your process report must be • complete • legible • in the specified order | Your process data must be • accurate • precise • self-consistent |
| --- | --- | --- |

| #### Suggestions | Keep your programs simple. You will learn as much from small programs as from large ones. Keep your reports and standards simple and short. Do not hesitate to copy or build on the PSP materials. Do it right the first time. If you are not sure, find out. Software is not a solo business, so you do not have to work alone. You must, however, produce your own estimates, designs, and code. You may have others review your work, and you may change it as a result. You should note any help in your process report. Include the review time that you and your associates spend, and log the defects found. |
| --- | --- |