Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Table C31  PSP1 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP1 Project Plan Summary form • Size Estimating Template • Historical estimated and actual size data • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | • Produce a program conceptual design. • Use the PROBE method to estimate the new and changed LOC required to develop this program. • Estimate the base, added, deleted, modified, and reused LOC. • Complete the Size Estimating Template and Project Plan Summary form. |
| 3 | Resource Estimate | • Based on the time required per LOC on previous programs, make your best estimate of the time required to develop this program. • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
|  | Exit Criteria | • Documented requirements statement • The program conceptual design • Completed Size Estimating Template • Completed Project Plan Summary form with estimated program size and development time data • Completed Time Recording Log |