Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Table C54  PSP2 Postmortem Script

| Phase Number | Purpose | To guide the PSP postmortem process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description and requirements statement • Project Plan Summary form with program size, development time, and defect data • For projects of several days’ duration, completed Task Planning and Schedule Planning Templates • Completed Test Report Template • Completed Design Review and Code Review Checklists • Completed Time Recording Log • Completed Defect Recording Log • A tested and running program that conforms to the Coding Standard |
| 1 | Defects Injected | • Determine from the Defect Recording Log the number of defects injected in each PSP2 phase. • Enter this number under Defects InjectedActual on the Project Plan Summary form. |
| 2 | Defects Removed | • Determine from the Defect Recording Log the number of defects removed in each PSP2 phase. • Enter this number under Defects RemovedActual on the Project Plan Summary form. • Calculate the actual overall process yield and enter it in the Project Plan Summary form. |
| 3 | Size | • Count the LOC in the completed program. • Determine the base, reused, deleted, modified, added, total, total new and change, and new reuse LOC. • Enter these data on the Project Plan Summary form. |
| 4 | Time | • Review the completed Time Recording Log. • Enter the total time spent in each PSP2 phase in the Actual column of the Project Plan Summary form. |
|  | Exit Criteria | • A fully tested program that conforms to the Coding Standard • Completed Design Review and Code Review Checklists • Completed Test Report Template • Completed Project Plan Summary form • Completed PIP forms describing process problems, improvement suggestions, and lessons learned • Completed Defect and Time Recording Logs |