Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Assignment Kit for
Program 4

Personal Software Process (PSP) for Engineers: Part I

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution limited by the Software Engineering Institute to attendees.

Personal Software Process for Engineers: Part I

Assignment Kit for Program 4

Overview

| #### Overview | This assignment kit covers the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Prerequisites | 2 |
|  | Program 4 requirements | 3 |
|  | Using relative size tables in the PSP | 5 |
|  | Calculating a relative size table using standard deviation | 5 |
|  | Example of calculating a relative size table | 7 |
|  | Assignment instructions | 10 |
|  | Guidelines and evaluation criteria | 17 |

| Prerequisites | Reading • Chapter 7 |
| --- | --- |

### Program 4 requirements

| Program 4 requirements | Using PSP1.1, write a program to calculate relative size ranges for very small, small, medium, large, and very large ranges using standard deviation. Thoroughly test the program. Test the program using the data provided in tables 1 and 2. Expected values are included in table 3. |
| --- | --- |

| Class Name | Class LOC | Number of Methods |
| --- | --- | --- |
| each_char | 18 | 3 |
| string_read | 18 | 3 |
| single_character | 25 | 3 |
| each_line | 31 | 3 |
| single_char | 37 | 3 |
| string_builder | 82 | 5 |
| string_manager | 82 | 4 |
| list_clump | 87 | 4 |
| list_clip | 89 | 4 |
| string_decrementer | 230 | 10 |
| Char | 85 | 3 |
| Character | 87 | 3 |
| Converter | 558 | 10 |

Table 1. LOC/Method Data

| Chapter | Pages |
| --- | --- |
| Preface | 7 |
| Chapter 1 | 12 |
| Chapter 2 | 10 |
| Chapter 3 | 12 |
| Chapter 4 | 10 |
| Chapter 5 | 12 |
| Chapter 6 | 12 |
| Chapter 7 | 12 |
| Chapter 8 | 12 |
| Chapter 9 | 8 |
| Appendix A | 8 |
| Appendix B | 8 |
| Appendix C | 20 |
| Appendix D | 14 |
| Appendix E | 18 |
| Appendix F | 12 |

Table 2. Pgs/Chapter

Continued on next page

### Program 4 requirements, Continued

#### Program 4 requirements, continued

|  | VS | S | M | L | VL |
| --- | --- | --- | --- | --- | --- |
| LOC/Method | 4.3953 | 8.5081 | 16.4696 | 31.8811 | 61.7137 |
| Pgs/Chapter | 6.3375 | 8.4393 | 11.2381 | 14.9650 | 19.9280 |

Table 3. Expected Values

Relative Size Table

| #### Using relative size tables in the PSP | In the PSP, relative size tables are used to give you a framework for judging the size of new parts in your planned products. For example, if you know the sizes of all previously developed parts of a certain type, you can then better judge the likely size of a new part of that type. The standard deviation procedure described in the following section allows you to balance your esimates so they more or less conform to the normal distribution. The medium range (M) is the area from -0.5 standard deviations to +0.5 standard deviations from the mean, as shown in Figure 1. Assuming that the data approximates a normal distribution, the likely number of parts that are within plus or minus 0.5 standard deviation of the average value is 38.3 percent. Following similar logic, the range percentages area are as follows: - 6.68 % should be very small - 24.17% should be small - 38.2% should be medium - 24.17% should be large - 6.68% should be very large Figure 1. Ranges of standard deviations |
| --- | --- |

| Calculating a relative size table using standard deviation | The PROBE estimating method divides historical size data into categories that represent your kind of work. One way of doing this is based on standard deviation. First, divide your historical data into functional categories that each have at least 6 to 8 members (calculation, text, and data, for example). For each category you can then calculate the relative size ranges for VS, S, M, L, and VL following the below procedure. - Divide the part sizes by the number of items in each part to determine size per item, if applicable. For instance, you may not have enough data on classes to develop a relative size table, but you do have sufficient data on methods. Instead of using total LOC per class, you can use LOC/method. |
| --- | --- |

Continued on next page

Relative Size Table, Continued

| Calculating a relative size table using standard deviation, continued | - Next, you’ll need to log-normally transform the data. This is necessary because you cannot have negative sizes and the smaller values tend to bunch up. Log-normally transforming the data allows you plot the data around a mean of zero. For each size value,xi, take the natural logarithm, ln, to give ln (xi). - Calculate the average of these n logarithmic values:avg=i=1nln(xi)n. - Calculate the variance of these values: var=σ2=i=1nln(xi)−avg2(n−1). - Calculate the standard deviation: σ=var. - Calculate the logarithmic ranges: ln(VS) = avg−2σ ln(S) = avg−σ ln(M) = avg ln(L) = avg+σ ln(VL) = avg+2σ - Last, convert the natural log values back to their original form by calculating the anti-logarithm (calculate e to the power of the log value) to get the midpoints of the size ranges VS = eln(VS) S = eln(S) M = eln(M) L = eln(L) VL = eln(VL) |
| --- | --- |

Example of calculating a relative size table

| Example of calculating a relative size table | In this example, we’ll calculate the relative size ranges for very small, small, medium, large, and very large ranges using standard deviation for the data in the table below. |
| --- | --- |

| Class Name | Class LOC | Number of Methods | LOC/method |
| --- | --- | --- | --- |
| each_char | 18 | 3 | 6.0000 |
| string_read | 18 | 3 | 6.0000 |
| single_character | 25 | 3 | 8.3333 |
| each_line | 31 | 3 | 10.3333 |
| single_char | 37 | 3 | 12.3333 |
| string_builder | 82 | 5 | 16.4000 |
| string_manager | 82 | 4 | 20.5000 |
| list_clump | 87 | 4 | 21.7500 |
| list_clip | 89 | 4 | 22.2500 |
| string_decrementer | 230 | 10 | 23.0000 |
| Char | 85 | 3 | 28.3333 |
| Character | 87 | 3 | 29.0000 |
| Converter | 558 | 10 | 55.8000 |

|  | - Divide the part sizes by the number of items in each part to determine size per item, if applicable. In this instance, the LOC/method is calculated for each class. - For each size value, xi, calculate the natural logarithm, ln, to give ln(xi). |
| --- | --- |

| Class Name | LOC/method | ln(xi) |
| --- | --- | --- |
| each_char | 6.0000 | 1.7918 |
| string_read | 6.0000 | 1.7918 |
| single_character | 8.3333 | 2.1203 |
| each_line | 10.3333 | 2.3354 |
| single_char | 12.3333 | 2.5123 |
| string_builder | 16.4000 | 2.7973 |
| string_manager | 20.5000 | 3.0204 |
| list_clump | 21.7500 | 3.0796 |
| list_clip | 22.2500 | 3.1023 |
| string_decrementer | 23.0000 | 3.1355 |
| Char | 28.3333 | 3.3440 |
| Character | 29.0000 | 3.3673 |
| Converter | 55.8000 | 4.0218 |
| Total |  | 36.4197 |

Continued on next page

Example of calculating a relative size table, Continued

| Example of calculating a relative size table, continued | - Calculate the average of these n logarithmic values: avg=i=1nln(xi)n=36.419713=2.8015. - Calculate the variance of these values: var=σ2=i=1nln(xi)−avg2(n−1)=5.235012=0.4363 |
| --- | --- |

| Class Name | LOC/method | ln(xi) | (ln(xi)-avg)2 |
| --- | --- | --- | --- |
| each_char | 6.0000 | 1.7918 | 1.0196 |
| string_read | 6.0000 | 1.7918 | 1.0196 |
| single_character | 8.3333 | 2.1203 | 0.4641 |
| each_line | 10.3333 | 2.3354 | 0.2173 |
| single_char | 12.3333 | 2.5123 | 0.0836 |
| string_builder | 16.4000 | 2.7973 | 0.0000 |
| string_manager | 20.5000 | 3.0204 | 0.0479 |
| list_clump | 21.7500 | 3.0796 | 0.0773 |
| list_clip | 22.2500 | 3.1023 | 0.0905 |
| string_decrementer | 23.0000 | 3.1355 | 0.1115 |
| Char | 28.3333 | 3.3440 | 0.2943 |
| Character | 29.0000 | 3.3673 | 0.3201 |
| Converter | 55.8000 | 4.0218 | 1.4890 |
| Total |  | 36.4197 | 5.2350 |

|  | - Calculate the standard deviation: σ=var=0.4363=0.6605 - Calculate the logarithmic ranges: ln(VS) = avg−2σ=2.8015−1.3210=1.4805 ln(S) = avg−σ=2.8015−0.6605=2.1410 ln(M) = avg=2.8015 ln(L) = avg+σ=2.8015−0.6605=3.4620 ln(VL) = avg+2σ=2.8015−1.3210=4.1225 |
| --- | --- |

Continued on next page

Example of calculating a relative size table, Continued

| Example of calculating a relative size table, continued | - Convert the natural log values back to their original form by calculating the anti-logarithm by calculating e to the power of the log value to determine the midpoints of the size ranges: VS = eln(VS)=e1.4805=4.3953 S = eln(S)=e2.1410=8.5081 M = eln(M)=e2.8015=16.4696 L = eln(L)=e3.4620=31.8811 VL = eln(VL)=e4.1225=61.7137 |
| --- | --- |

### Assignment instructions

| #### Assignment instructions | Before starting program 4, review the top-level PSP1.1 process script below to ensure that you understand the “big picture” before you begin. Also, ensure that you have all of the required inputs before you begin the planning phase. |
| --- | --- |

PSP1.1 Process Script

| Purpose | - To guide the development of module-level programs |
| --- | --- |
| Entry Criteria | - Problem description - PSP1.1 Project Plan Summary form - Size Estimating template - Historical size and time data (estimated and actual) - Time and Defect Recording logs - Defect Type, Coding, and Size Counting standards - Stopwatch (optional) |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Planning | - Produce or obtain a requirements statement. - Use the PROBE method to estimate the added and modified size of this program. - Complete the Size Estimating template. - Use the PROBE method to estimate the required development time. - Complete a Task Planning template. - Complete a Schedule Planning template. - Enter the plan data in the Project Plan Summary form. - Complete the Time Recording log. |
| 2 | Development | - Design the program. - Implement the design. - Compile the program, and fix and log all defects found. - Test the program, and fix and log all defects found. - Complete the Time Recording log. |
| 3 | Postmortem | - Complete the Project Plan Summary form with actual time, defect, and size data. |

| Exit Criteria | - A thoroughly tested program - Completed Project Plan Summary form with estimated and actual data - Completed Size Estimating and Task and Schedule Planning templates - Completed Test Report template - Completed PIP forms - Completed Time and Defect Recording logs |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Planning phase | Plan program 4 following the PSP1.1 planning phase and the PROBE estimating scripts. |
| --- | --- |

PSP1.1 Planning Script

| Purpose | - To guide the PSP planning process |
| --- | --- |
| Entry Criteria | - Problem description - PSP1.1 Project Plan Summary form - Size Estimating, Task Planning, and Schedule Planning templates - Historical size and time data (estimated and actual) - Time Recording log |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Program Requirements | - Produce or obtain a requirements statement for the program. - Ensure that the requirements statement is clear and unambiguous. - Resolve any questions. |
| 2 | Size Estimate | - Produce a program conceptual design. - Use the PROBE method to estimate the added and modified size of this program. - Complete the Size Estimating template and Project Plan Summary form. |
| 3 | Resource Estimate | - Use the PROBE method to estimate the time required to develop this program. - Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. (Note: This step is completed by the SEI student workbook.) |
| 4 | Task and Schedule Planning | For projects lasting several days or more, complete the Task Planning and Schedule Planning templates. |

| Exit Criteria | - Documented requirements statement - Program conceptual design - Completed Size Estimating template - For projects lasting several days or more, completed Task and Schedule Planning templates - Completed Project Plan Summary form with estimated program size and development time data - Completed Time Recording log |
| --- | --- |

|  | Verify that you have met all of the exit criteria for the planning phase, then have an instructor review your plan. After your plan has been reviewed, proceed to the development phase. |
| --- | --- |

Continued on next page

### Assignment instructions, Continued

|  | Use the PROBE method to create size and resource estimates. |
| --- | --- |

PROBE Estimating Script

| Purpose | - To guide the size and time estimating process using the PROBE method |
| --- | --- |
| Entry Criteria | - Requirements statement - Size Estimating template and instructions - Size per item data for part types - Time Recording log - Historical size and time data |
| General | - This script assumes that you are using added and modified size data as the size-accounting types for making size and time estimates. - If you choose some other size-accounting types, replace every “added and modified” in this script with the size-accounting types of your choice. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Parts Additions | Follow the Size Estimating Template instructions to estimate the parts additions and the new reusable parts sizes. |
| 3 | Base Parts and Reused Parts | - For the base program, estimate the size of the base, deleted, modified, and added code. - Measure and/or estimate the size of the parts to be reused. |
| 4 | Size Estimating Procedure | - If you have sufficient estimated proxy size and actual added and modified size data (three or more points that correlate), use procedure 4A. - If you do not have sufficient estimated data but have sufficient plan added and modified and actual added and modified size data (three or more points that correlate), use procedure 4B. - If you have insufficient data or they do not correlate, use procedure 4C. - If you have no historical data, use procedure 4D. |
| 4A | Size Estimating Procedure 4A | - Using the linear-regression method, calculate theβ0and β1 parameters from the estimated proxy size and actual added and modified size data. - If the absolute value ofβ0is not near 0 (less than about 25% of the expected size of the new program), orβ1is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | Size Estimating Procedure 4B | - Using the linear-regression method, calculate theβ0andβ1parameters from the plan added and modified size and actual added and modified size data. - If the absolute value of β0is not near 0 (less than about 25% of the expected size of the new program), orβ1is not near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | Size Estimating Procedure 4C | If you have any data on plan added and modified size and actual added and modified size, setβ0= 0 and β1 = (actual total added and modified size to date/plan total added and modified size to date). |
| 4D | Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate added and modified size. |

(continued)

Continued on next page

### Assignment instructions, Continued

PROBE Estimating Script (Continued)

| Step | Activities | Description |
| --- | --- | --- |
| 5 | Time Estimating Procedure | - If you have sufficient estimated proxy size and actual development time data (three or more points that correlate), use procedure 5A. - If you do not have sufficient estimated size data but have sufficient plan added and modified size and actual development time data (three or more points that correlate), use procedure 5B. - If you have insufficient data or they do not correlate, use procedure 5C. - If you have no historical data, use procedure 5D. |
| 5A | Time Estimating Procedure 5A | - Using the linear-regression method, calculate theβ0andβ1 parameters from the estimated proxy size and actual total development time data. - Ifβ0is not near 0 (substantially smaller than the expected development time for the new program), orβ1is not within 50% of 1/(historical productivity), use procedure 5B. |
| 5B | Time Estimating Procedure 5B | - Using the linear-regression method, calculate theβ0andβ1 regression parameters from the plan added and modified size and actual total development time data. - Ifβ0is not near 0 (substantially smaller than the expected development time for the new program), orβ1is not within 50% of 1/(historical productivity), use procedure 5C. |
| 5C | Time Estimating Procedure 5C | - If you have data on estimated – added and modified size and actual development time, setβ0= 0 and β1 = (actual total development time to date/estimated – total added and modified size to date). - If you have data on plan – added and modified size and actual development time, setβ0= 0 and β1 = (actual total development time to date/plan total added and modified size to date). - If you only have actual time and size data, setβ0= 0 and β1 = (actual total development time to date/actual total added and modified size to date). |
| 5D | Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated added and modified size. |
| 6 | Time and Size Prediction Intervals | - If you used regression method A or B, calculate the 70% prediction intervals for the time and size estimates. - If you did not use the regression method or do not know how to calculate the prediction interval, calculate the minimum and maximum development time estimate limits from your historical maximum and minimum productivity for the programs written to date. |

| Exit Criteria | - Completed estimated and actual entries for all pertinent size categories - Completed PROBE Calculation Worksheet with size and time entries - Plan and actual values entered on the Project Plan Summary |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Development phase | Develop the program following the PSP1.1 development phase script. |
| --- | --- |

PSP1.1 Development Script

| Purpose | - To guide the development of small programs |
| --- | --- |
| Entry Criteria | - Requirements statement - Project Plan Summary form with estimated program size and development time - For projects lasting several days or more, completed Task Planning and Schedule Planning templates - Time and Defect Recording logs - Defect Type standard and Coding standard |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Design | - Review the requirements and produce a design to meet them. - Record in the Defect Recording log any requirements defects found. - Record time in the Time Recording log. |
| 2 | Code | - Implement the design following the Coding standard. - Record in the Defect Recording log any requirements or design defects found. - Record time in the Time Recording log. |
| 3 | Compile | - Compile the program until there are no compile errors. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. |
| 4 | Test | - Test until all tests run without error. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. - Complete a Test Report template on the tests conducted and the results obtained. |

| Exit Criteria | - A thoroughly tested program that conforms to the Coding standard - Completed Test Report template - Completed Time and Defect Recording logs |
| --- | --- |

|  | Verify that you have met all of the exit criteria for the development phase, then proceed to the postmortem phase. |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Postmortem #### phase | Conduct the postmortem following the PSP1.1 postmortem script. |
| --- | --- |

PSP1.1 Postmortem Script

| Purpose | - To guide the PSP postmortem process |
| --- | --- |
| Entry Criteria | - Problem description and requirements statement - Project Plan Summary form with program size and development time data - For projects lasting several days or more, completed Task Planning and Schedule Planning templates - Completed Test Report template - Completed Time and Defect Recording logs - A tested and running program that conforms to the coding and size counting standards |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Defect Recording | - Review the Project Plan Summary to verify that all of the defects found in each phase were recorded. - Using your best recollection, record any omitted defects. |
| 2 | Defect Data Consistency | - Check that the data on every defect in the Defect Recording log are accurate and complete. - Verify that the numbers of defects injected and removed per phase are reasonable and correct. - Using your best recollection, correct any missing or incorrect defect data. |
| 3 | Size | - Count the size of the completed program. - Determine the size of the base, deleted, modified, base additions, reused, new reusable code, and added parts. - Enter these data in the Size Estimating template. - Determine the total program size - Enter this data in the Project Plan Summary form. |
| 4 | Time | - Review the completed Time Recording log for errors or omissions. - Using your best recollection, correct any missing or incomplete time data. |

| Exit Criteria | - A thoroughly tested program that conforms to the coding and size counting standards - Completed Test Report template - Completed Project Plan Summary form - Completed PIP forms describing process problems, improvement suggestions, and lessons learned - Completed Time and Defect Recording logs |
| --- | --- |

|  | Verify that you have met all of the exit criteria for the PSP1.1 postmortem phase, then submit your assignment. |
| --- | --- |

Continued on next page

Assignment instructions, Continued

| #### Submitting your assignment | When you’ve completed the postmortem phase, submit your assignment package, source code, and test results to the instructor. The order for the assignment package is • PSP1.1 Project Plan Summary form • Test Report template • PIP form • Size Estimating template • PROBE Calculation worksheet • Time Recording log • Defect Recording log • source program listing • test results |
| --- | --- |

### Guidelines and evaluation criteria for program 4

| #### Evaluation criteria | Your process report must be • complete • legible • in the specified order | Your process data must be • accurate • precise • self-consistent |
| --- | --- | --- |

| #### Suggestions | Remember, you should complete this assignment today. Keep your programs simple. You will learn as much from developing small programs as from large ones. If you are not sure about something, ask your instructor for clarification. Software is not a solo business, so you do not have to work alone. - You must, however, produce your own estimates, designs, code, and completed forms and reports. - You may have others review your work, and you may change it as a result. - You should note any help you receive from others in your process report. Log the review time that you and your associates spend, and log the defects found or any changes made. |
| --- | --- |