## Slide 1: Tutorial: Using PSP1.1
Personal Software ProcessSM for Engineers: Part I

## Slide 3
Copyright 2016 Carnegie Mellon University [Distribution Statement A] This material has been approved for public release and unlimited distribution. Please see Copyright notice for non-US Government use and distribution. This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center. NO WARRANTY. THIS CARNEGIE MELLON UNIVERSITY AND SOFTWARE ENGINEERING INSTITUTE MATERIAL IS FURNISHED ON AN “AS-IS” BASIS. CARNEGIE MELLON UNIVERSITY MAKES NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, AS TO ANY MATTER INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, EXCLUSIVITY, OR RESULTS OBTAINED FROM USE OF THE MATERIAL. CARNEGIE MELLON UNIVERSITY DOES NOT MAKE ANY WARRANTY OF ANY KIND WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT. This material is distributed by the Software Engineering Institute (SEI) only to course attendees for their own individual study. Except for the U.S. government purposes described below, this material SHALL NOT be reproduced or used in any other manner without requesting formal permission from the Software Engineering Institute at permission@sei.cmu.edu. The U.S. Government's rights to use, modify, reproduce, release, perform, display, or disclose this material are restricted by the Rights in Technical Data-Noncommercial Items clauses (DFAR 252-227.7013 and DFAR 252-227.7013 Alternate I) contained in the above identified contract. Any reproduction of this material or portions thereof marked with this legend must also reproduce the disclaimers contained on this slide. Although the rights granted by contract do not require course attendance to use this material for U.S. Government purposes, the SEI recommends attendance to ensure proper understanding. Carnegie Mellon® is registered in the U.S. Patent and Trademark Office by Carnegie Mellon University. Personal Software ProcessSM, PSPSM, Team Software ProcessSM and TSPSM are service marks of Carnegie Mellon University. DM-0004310

## Slide 4: Tutorial Objectives
After this tutorial, you will
  understand the new elements of PSP1.1
  know how to use the PSP1.1 scripts and forms
  be prepared to use PSP1.1 for program 4

## Slide 5: PSP1.1 Objectives
The objectives of PSP1.1 are to introduce and practice methods for
  making resource and schedule plans
  tracking your performance against these plans
  judging likely project completion dates

## Slide 6: New Process Elements
There are two new process elements.
  task planning template
  schedule planning template
These are typically used for projects that take several days or weeks.
They are not required for the PSP exercises.
The project plan summary has been expanded to include basic process statistics.

## Slide 7: PSP1.1 Project Plan Summary
The summary section has been expanded to include
  Planned time
  Actual time
  CPI
  %Reused
  %New Reusable
These values are calculated automatically.

## Slide 8: Measurement Definitions -1
Planned Time
  Plan: planned development time for this project
  To-Date: sum of planned development time for all completed projects + this project
Actual Time
  Actual: actual development time for this project
  To-Date: sum of actual development time for all completed projects + this project
Cost Performance Index (CPI)
  To-Date planned time / To-Date actual time

## Slide 9: Measurement Definitions -2
%Reused: percentage of reused size for this project
  Reused / Total * 100
%New Reusable: percentage of new reusable code developed for this project
  New Reusable / Added and Modified * 100

## Slide 10: Task and Schedule Plans
Task and schedule plans are used to estimate when work will be completed.
Tasks are entered on the task plan.
  each task in order
  planned hours
  actual hours
  date task completed
Schedule hours are entered on the schedule plan.
  planned hours for each schedule week
  actual hours for each schedule week

## Slide 11: Task Plan -1
The phases of each project are automatically added to the task plan when the project is created.
Only the actual date completed needs to be entered, the other data are automatically calculated.

## Slide 12: Task Plan -2
Use the task order menu to
  Update the task and schedule plan
  Change task order for the selected task or tasks

## Slide 13: Schedule Plan
The planned hours for each schedule week must be entered.
Other data are calculated automatically.

## Slide 14: Messages to Remember
Task and schedule planning templates are not required for small programs, but are helpful for longer tasks.
PSP1.1 gives you insight into your historical performance (CPI).