# Instructor’s Guide

PSP: A Self-Improvement Process for Software Engineers

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to PSP Instructors.

Table of Contents

1.	Introduction	6

1.1	PSP Course Goals	6

1.2	The PSP Course Strategy	7

1.3	Experience with the PSP	7

1.4	PSP Principles	8

1.5	The PSP Teaching Strategy	8

1.6	Learning Statistical Methods	11

1.7	Using Other Programs	11

1.8	The PSP Quality Focus	11

1.9	PSP Course Support Tools	12

1.10	Exercise Kits	12

1.11	Assignment Kits	12

1.12	PSP Process Materials	13

2.	General Teaching Suggestions	14

2.1	Industrial PSP Course Scheduling Suggestions	15

2.2	Academic PSP Course Scheduling Suggestions	16

2.3	General Assignment Guidelines	16

2.4	General Grading Guidelines	16

3.	Interpreting Class Data	18

3.1	Class Data Feedback	18

3.2	Class Feedback Charts	18

4.	Teaching PSP0 Topics	25

4.1	PSP0 Objectives	25

4.2	PSP0 Lecture: Course Overview Part I	26

4.3	PSP0 Lecture: Introduction to the PSP and TSP	27

4.4	PSP0 Process Tutorial	28

4.5	PSP0 Programming Exercise Assignment	28

4.6	Grading PSP0 Assignments	28

4.7	PSP0 Tips and Hints	30

4.	Teaching PSP0.1 Topics	35

5.1	PSP0.1 Objectives	32

5.2	PSP0.1 Lecture: Process Measurement	32

5.3	PSP0.1 Process Tutorial	34

5.4	The Size-Measurement Report Assignment	34

5.5	The Coding Standard Report Assignment	35

5.6	PSP0.1 Programming Exercise Assignments	35

5.7	Grading the Size-Measurement Report Assignment	35

5.8	Grading the Coding Standard Report Assignment	35

5.9	Grading PSP0.1 Programming Assignments	35

5.10	PSP0.1 Tips and Hints	36

6.	Teaching PSP1 Topics	38

6.1	PSP1 Objectives	38

6.2	PSP1 Lecture: Estimating with PROBE I	38

6.3	PSP1 Process Tutorial	40

6.4	PSP1 Programming Exercise Assignments	40

6.5	Grading PSP1 Programming Assignments	41

6.6	PSP1 Tips and Hints	42

7.	Teaching PSP1.1 Topics	43

7.1	PSP1.1 Objectives	43

7.2	PSP1.1 Lecture: Estimating with PROBE II	43

7.3	PSP1.1 Lecture: Using PSP Data	45

7.4	PSP1.1 Process Tutorial	47

7.5	PSP1.1 Programming Exercise Assignments	47

7.6	The Interim Report Assignment	47

7.7	The Design and Code Review Checklist Assignment	48

7.8	Grading PSP1.1 Programming Assignments	48

7.9	Grading the Interim Report Assignment	49

7.10	Grading the Design and Code Review Checklists	49

7.11	PSP1.1 Tips and Hints	49

8.	Teaching PSP2 Topics	50

8.1	PSP2 Objectives	50

8.2	PSP2 Lecture: Course Overview Part II	50

8.3	PSP2 Lecture: Software Quality	51

8.4	PSP2 Process Tutorials	54

8.5	PSP2 Programming Exercise Assignments	54

8.6	Grading PSP2 Programming Assignments	55

8.7	PSP2 Tips and Hints	56

9.	Teaching PSP2.1 Topics	57

9.1	PSP2.1 Objectives	57

9.2	PSP2.1 Lecture: Software Design I	57

9.3	PSP2.1 Lecture: Software Design II	60

9.4	PSP2.1 Lecture: Design Verification	61

9.5	PSP2.1 Lecture: Using the PSP	63

9.6	PSP2.1 Process Tutorial	64

9.7	PSP2.1 Programming Exercise Assignments	65

9.8	The Final Report Assignment	66

9.9	Grading PSP2.1 Programming Assignments	66

9.10	Grading the Final Report Assignment	67

9.11	PSP2.1 Tips and Hints	67

References	70

1.	Introduction

This guide provides teaching suggestions and links to support materials for courses taught using the textbook, PSP: A Self-Improvement Process for Software Engineers.  The suggestions in this guide are based on the experiences of instructors at the Carnegie Mellon® Software Engineering Institute (SEI) and those of many other experienced instructors who have taught the SEI’s Personal Software ProcessSM (PSPSM) methodology to thousands of students and professional software developers.

This Instructor’s Guide contains nine chapters. This introductory chapter provides an overview of the PSP course strategy and principles, a list of available support materials, guidance on where to obtain these materials, and suggestions on how to use them.  Chapter 2 provides general teaching suggestions and Chapter 3 describes the PSP class data.  Chapters 4 through 9 provide teaching suggestions for each PSP process level.

# 1.1	PSP Course Goals

While many advances have been made in the computer science and software engineering fields, general software practice still produces insecure, unsafe, or unusable programs that are delivered late and over budget.  The goal of the PSP is to address these problems by improving the personal practices of software engineers.  Today, in spite of the best efforts of the computer science and software engineering communities, software developers do not regularly use the best available known methods.  Many follow a largely intuitive craft-like practice by picking up new methods from their peers and by using techniques that have long been discredited.

The overall goals of the PSP course are to do the following.

- convince software developers and their management to apply the proven scientific practices of measurement and controlled experimentation

- show aspiring software engineers how to define their personal processes, to plan and measure their personal work, and to manage the quality of their personal products

- establish a software-engineering culture where measurement and analysis are used in scientifically sound ways to make project decisions and to guide process improvement

- motivate software engineers to build on the experiences of their predecessors and to properly use the most effective practices and methods produced by the software engineering community

The PSP process goals described in this guide for each process level build on and augment these overall goals.

# 1.2	The PSP Course Strategy

The PSP course objective is to introduce both students and experienced software developers to disciplined engineering methods.  The course shows PSP students how to manage and plan their work and how to measure and manage the quality of the products they produce.  The ultimate objective of the PSP course is to demonstrate to these students with data on their own work that the PSP’s practices will help them to improve their personal performance as working engineers.  However, for the course to be successful, the students should agree with and share the course objective of improving the predictability, quality, and productivity of their personal work.

While the PSP course is not difficult for anyone who can write small programs, those who do not have at least basic programming skills should be discouraged from taking the class.  The course assumes that each attendee has the following skills and available support facilities:

- The students must know and be reasonably fluent in at least one programming language.

- They should use the language with which they are most fluent for doing the course exercises.

- The students must have an installed software development environment that they know how to use.

- Each student must have one of the available PSP support tools.

- The student must be competent in basic mathematics through algebra.

- It is also helpful, but not required, that the students be familiar with basic statistics and simple formal notations.

# 1.3	Experience with the PSP

Through working with many organizations and development teams, the SEI has found that consistent and proper use of disciplined software engineering practices substantially improves development predictability and productivity and results in greatly improved product quality. Furthermore, PSP-trained developers find that following the PSP methods on Team Software ProcessSM (TSPSM) teams is a truly enjoyable and rewarding way to work.  In fact, after working on a TSP team, many developers refuse to work any other way.

Since proper use of the PSP takes considerable personal discipline, both training and practice are generally required before developers use these methods well enough to fully appreciate their benefits.  Even after completing PSP training, continued use of the methods requires a supportive development environment, a peer group that follows the same practices, management support, and skilled and capable coaching.  While the PSP methods can be very effective, even when used by individual developers, it takes considerable practice and experience before these methods feel natural and normal.  However, after developers routinely use them, they provide a scientifically sound foundation for continued personal growth and improvement.

# 1.4	PSP Principles

To address learning and skill-building problems, the PSP course is based on the following fundamental principles:

- Use of a defined and structured process improves working efficiency.

- Properly designed personal processes conveniently fit the individual skills and preferences of each developer.

- For professionals to be comfortable with a defined process, they must be involved in and agree with its definition.

- As a professional’s personal skills and abilities evolve, so should his or her personal processes.

- Continuous process improvement is enhanced by rapid and explicit feedback.

The logic for the PSP process was derived from these fundamental principles and is as follows:

- Software professionals will better understand what they do if they define, measure, and track their work.

- They will then have a defined process structure and measurable criteria for evaluating and learning from their own and others’ experiences.

- With this knowledge, they can select those methods and practices that best suit their particular tasks and abilities.

- By using a customized set of orderly, consistently practiced, and high-quality personal practices, developers will be more effective members of their development teams and projects.

The principal reason that the PSP course takes the time that it does is to give students the evidence to motivate them to use these methods in their work.  After they have properly used these practices during PSP training, they will have data that show how these practices improve both their personal performance and the quality of their products.  Your job as an instructor is to ensure that they obtain the data to convince them of these benefits.  While working in a TSP team can then help to build this appreciation, a proper foundation in PSP training is the essential first step.

# 1.5	The PSP Teaching Strategy

The key elements of the PSP course are

- a self-teaching system

- handling skeptics

- the evolutionary PSP process

- the classroom lectures

- the classroom exercises

- the classroom tutorials and quizzes

- the PSP programming exercises

- the report exercises

- gathering defect data

The following sections describe these elements and explain how they work and how they are related.

## 1.5.1	A Self-Teaching System

Most developers need to learn the PSP by following a course, but they don’t learn it from the instructor.  The PSP course provides students with data on their own work.  Even if you are the best lecturer in the world, the students learn more from their data than they learn from you.  The experience of using data to manage and plan their personal work convinces them that the PSP can help them to produce better results.

Your job as an instructor is to facilitate this process.  Explain the material in the lectures, lead the students through the exercises, and review and grade their work.  By showing them how to follow the PSP practices, and by identifying and correcting any misunderstandings and problems, you help them properly follow the PSP methods.  As a result, their data demonstrates how this process works for them.

## 1.5.2	Handling Skeptics

Skeptics are often the best PSP students, even though they can often be annoying and ask difficult and embarrassing questions.  Skeptics are curious and thinking.  They don’t believe something because you tell them or because they read it.  They need evidence.  The PSP strategy for handling skeptics is to do your best to answer questions but to appeal to their curiosity and skepticism.  Encourage them to direct their curiosity toward their data rather than toward you.  After they start using their data to answer their own questions, help them interpret the results.  With a few exceptions, skeptics become the strongest supporters of the PSP and TSP after they become convinced.  Welcome them.

## 1.5.3	The Evolutionary PSP Process

The evolving PSP process introduces the PSP’s methods in relatively simple and easy-to-understand steps [Humphrey 2005].  Each step of the PSP process builds on prior steps.  Each step also shows the students how to handle many of the problems that they have encountered while completing the programming exercises.

## 1.5.4	The Classroom Lectures

The PSP course lectures provide an opportunity for you to explain the basic PSP material to the students.  The lectures also give the students an opportunity to ask questions about the various PSP methods.  While the material in the lectures is covered in the textbook, not all students complete the textbook reading assignments. Many of those who do complete the reading assignments find that the material is so different from their prior experiences, they cannot grasp it by reading alone.  Therefore, an important part of the classroom lectures is to reinforce the reading assignments through discussion and interaction.

## 1.5.5	The Classroom Exercises

While students generally find the PSP practices simple once they have used them, the practices often seem complex and time consuming to the uninitiated.  It is therefore helpful to conduct some brief class exercises during the lectures.  During these exercises, the students should actually work through a simple problem that illustrates the particular PSP method being introduced.  While doing so, the students should also use the PSP support tools that they plan to use to complete the programming exercises.  Example exercises could be time and defect recording, conceptual design, code review, or state machine verification.

## 1.5.6	The Classroom Tutorials and Quizzes

There are two strategies for ensuring that students understand how to use the PSP data to plan and manage their personal work.  However, each of these strategies has advantages and disadvantages.  One approach is to have the students first complete each of the required calculations at least once without tool support.  For example, with this strategy, the support tool would not calculate the To-Date% figures the first time they are introduced with PSP0.  However, it would then complete these calculations for PSP0.1 and all subsequent process steps.

While this approach has the advantage of exposing student misunderstandings, it has two disadvantages.  First, it reinforces initial misconceptions that the PSP involves a lot of paperwork.  Second, it requires considerably more work from the instructor in grading these initial assignments.  The other strategy is to have the support tool automatically complete all of the required calculations but to use classroom tutorials and quizzes to verify student understanding.  With this strategy, you will not waste time teaching the students how to do something that they won’t need to do in the future.  While this approach is much easier for the students, it requires that you present a brief tutorial on each new method and verify student understanding, either during the tutorial or with a brief quiz.

While this guide assumes that you will follow the latter approach and verify understanding during the tutorials, you can use whichever method you find most appropriate.  You will, of course, have to use a PSP support tool that supports the teaching strategy you select.

## 1.5.7	The PSP Programming Exercises

The programming exercises provide the truly unique aspect of the PSP course.  By using the PSP methods they have just learned to write a moderately simple program, the students not only learn the method, they also obtain data on their personal work.  The feedback provided by these personal data is the most compelling evidence the students can get on the effectiveness of the PSP methods for them.

## 1.5.8	The Report Exercises

By merely gathering data, students will begin to understand their personal performance.  However, to truly understand the data and to see how these data can be most helpful, the students must analyze their data.  By completing the standard PSP report exercises, the students generally get this understanding.  These reports are described in Chapters 5, 7, and 9 of this guide.

## 1.5.9	Gathering Defect Data

Since the PSP uses data to help the students do better work, it is essential that they gather complete and accurate data.  While gathering time data is rarely a problem, defect data are often a source of complaints, particularly compile defect data.  Emphasize to students that these data are important and that they are required to successfully complete the course.

# 1.6	Learning Statistical Methods

In addition to providing experience with the PSP methods and generating feedback data, the initial PSP exercise sets also expose the students to statistical principles that are a fundamental part of the PSP methods.  For example, by writing a program that calculates the linear regression parameters for their personal data, students simultaneously create a program and gain an understanding of linear regression.

Since it is important that the students understand a few basic statistical methods, either use a PSP exercise set that uses pertinent statistical topics or add tutorial or class exercise material that familiarizes students with correlation, linear regression, the prediction interval, and multiple regression.

# 1.7	Using Other Programs

While most programs that developers can produce in about three to five hours could be used for the PSP exercises, choose easily defined programs to avoid requirements misunderstandings.  Including imprecise or changing requirements in the PSP exercises increases the time required to do the exercises and introduces a degree of variability that makes both individual and class data difficult to interpret and use. Mathematical exercises, similar to those provided by at least one of the basic PSP exercise sets, are good examples of exercises that meet these criteria.

Also, students who are working engineers should not use programs that they must write as part of their jobs. The PSP course requires that students use new and unfamiliar methods when writing programs. Developers are uniformly unwilling to do this when writing programs on the job.

While it is important for students to learn about the general imprecision and changeability of requirements, that is not the purpose of this course.  Further, including imprecise or changing requirements in the PSP exercises would likely increase the time required to do the exercises and introduce a degree of variability that would make both individual and class data harder to interpret and to use.

# 1.8	The PSP Quality Focus

Since this course focuses on using data to achieve high quality personal work, it is important that the students are required to do quality work.  For example, they must properly gather and record all of the required data and should produce high quality programs and reports.

Explain the following PSP grading guidelines to the students at the beginning of the course and repeat the explanation as often as needed to get consistently high-quality work.

- Make sure that the students understand that quality work is expected and that poorly done work will be rejected and must be redone.

- When the students do not know how to do something, help them.  They should only turn in work that is neat, in the proper order, and correct.

- While the students should turn in their work on time, it is more important that it be correct.

- In academic courses, tell the students that you will not even grade their assignments until they are submitted properly.

- Follow a grading strategy that initially insists on quality data and then progresses to the use, interpretation, and internalization of lessons based on these data.

- Treat each student as if he or she has a hidden talent that should be revealed.  The course and the data will help you to do this.

- While you may never recognize the students’ unique talents, try to help them better appreciate their own capabilities.

# 1.9	PSP Course Support Tools

Students can complete the PSP course with no tool support whatever, but this involves considerable manual data recording, calculation, and management. Even fairly rudimentary tool support can greatly accelerate and simplify these activities.  However, no tool can completely eliminate the need for students to record data, analyze these data, and use the data to plan and manage their work.  The SEI has developed a basic tool to support the PSP course. It is available at the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  Also available at that site is a tool to support instructors with analyzing, tracking, and displaying class data and progress.

# 1.10	Exercise Kits

As previously noted, classroom exercises and tutorials are essential for teaching the PSP methods.  The SEI has developed a family of exercises and tutorials, which are listed with a brief description, on the SEI’s TSP/PSP Web site.  As suitable new class exercises and tutorials become available, they are also listed.  While the SEI reviews exercises and tutorials that are submitted by third-party sources, it makes no guarantee regarding their use, suitability, or efficacy.

# 1.11	Assignment Kits

During the PSP course, students are required to complete a number of programming and report exercises.  As noted in the strategy discussion in the beginning of this chapter, merely reading the textbook or listening to the lectures has not proven to be an effective way to learn the PSP methods.  After extensive experience with teaching these methods and from the course data on several thousand experienced software developers, it is clear that a high percentage can learn the PSP methods in a class where they complete the ten A-series programming exercises and five report exercises described in the initial PSP textbook, A Discipline for Software Engineering [Humphrey 1995].

Groups have experimented with limited exercise sets, but there are not yet sufficient data to demonstrate their effectiveness.  Therefore, it is recommended that students complete at least eight programming exercises and the full set of report exercises.

The SEI encourages organizations to submit alternate exercise kits but will not list them unless they are accompanied by a complete set of support materials and data that demonstrate their effectiveness.

# 1.12	PSP Process Materials

PSP process materials include forms, scripts, templates, standards, and instructions.  Copies of these materials can be obtained from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  As described in the textbook, the PSP process is introduced in evolutionary steps.  To facilitate learning, each process step is upwardly compatible with all previous steps and the process additions are denoted by bold italic text.  This convention is also followed within the PSP process materials.

2.	General Teaching Suggestions

Instructors have had the most success teaching this course by focusing on the process used to complete the course exercises rather than primarily on the programs produced.  The key lessons for the students are how to gather process data and how to use these data to improve the way they work.  While the students must produce working programs, it is best to assume that they know how to write the programs and to focus primarily on process quality and process data.

In PSP courses taught to date, students have said that periodic class review of data on their work helped them to see the benefits of using the PSP methods and to appreciate the advantages of following disciplined personal practices.  Suggestions on the data to present and review with each lecture are included in Chapter 3 of this instructor’s guide.

To emphasize the importance of quality, insist that the students submit quality work as defined in section 1.8 on page 11.  If they are not sure how to complete an assignment, they should ask questions first and then complete the work correctly.  While it is important to submit the homework on time, quality work is more important, even if it must be late.

Properly prepared students do not typically have trouble writing the programming exercises, but they are often confused about how to use the PSP methods and data.  When students encounter difficulties, the suggested approach is for them to do the work as best they can, and then to check with you before turning in their assignments.  If an assignment is not done correctly, have the student correct it before submitting it.  By using this approach, after only one or two assignments, students realize that they save time by doing their work correctly.  Thereafter, the quality of their work is generally excellent.

Assignment kits emphasize to the students that they must follow the assignment specifications.  The kits specify the programs to write, the process to use in writing these programs, the way in which the results are to be reported, and the order of submission for the materials in the reports.  Grading and data analyses are much easier when the students submit their assignments in the specific format and order.

It is also important to analyze the students’ data after each assignment.  Rapid feedback is an essential part of teaching the PSP methods.  Grade the assignments when they’re submitted and then promptly examine the data.  While it only takes a few minutes to grade and assess the data for each student assignment, these tasks can become major chores if you delay them for even a few assignments.  This also deprives the students of essential feedback about the work they have completed.

The PSP tools, described in section 1.9 on page 12 of this guide, automatically generate a wide variety of analyses and graphic presentations for displaying the data of each student and for the class as a whole.  By using these tools, you can readily present charts of overall class performance on any selected metric.  This helps students understand how they are doing individually and how their performance compares to that of the whole class.  Please refer to section 3.1 for guidelines for showing student data.

The course should honor each student’s individuality.  Each student has strengths and weaknesses and individual performance varies widely depending on skill levels and the tasks assigned. Thus, do not grade students on absolute performance. Emphasize improvement and the extent to which students analyze their data and use these analyses to affect their behavior.  Your objective is to encourage them to do quality work, follow the process, and strive to improve their performance.

Finally, the course does not require that students work alone.  While they must complete their own work, they can get help.  They must, however, note that they did get help, report the time involved, and document the changes made as a result.

To the extent practical in a class environment, this course presents a realistic view of software development in an industrial setting.  While professional developers are responsible for completing their own work, they often get support from their associates.  Such collaboration should be actively encouraged, as long as it does not prevent students from learning through their own experience.  Students can ask for advice and guidance, but they must make their own plans, develop their own programs, gather their own data, and produce their own assignment reports.

# 2.1	Industrial PSP Course Scheduling Suggestions

The PSP course has been taught in many configurations in both universities and industry.  The following paragraphs describe some of the more common course configurations.

The most common industrial configuration is a two-week format with a several-week break in between.  In the first week, cover the first overview lecture followed by five PSP lectures.  In the second week, cover the next overview and five more PSP lectures.  The students can generally complete three or four of the programming assignments during each week’s scheduled classes and must finish them along with the interim and final reports after they return to work.  Usually, some special management and instructor effort is required to permit students to complete all of the coursework on the job. When an entire project team takes the course together, a just-in-time strategy with the two-week course configuration has been most successful.  Then shortly after completing the course, they launch their first TSP team and start using the PSP on the job.

Alternative course structures depend on the availability of instructors and students. For example, students could devote one or two days a week to the course and continue working the rest of the time.  This model is not typically successful, largely because the students are often required to meet all of their other commitments in three or four days a week instead of five.  This not only increases their pressure at work, it provides them limited time outside of the classroom to complete the PSP assignments.  While all organizations are reluctant to interrupt development work for two weeks, many have concluded that if they want the developers to learn and use the PSP in a reasonable period of time, it is most cost effective to use the two-week configuration or something similar.

# 2.2	Academic PSP Course Scheduling Suggestions

The PSP has been taught as both a one-semester and a one-quarter university graduate or undergraduate course.  The principal limitation in scheduling the PSP course offering is the students’ programming skills.  Also, the mathematics requirements of the PSP programming assignments can sometimes be too challenging for beginning students.  A fundamental problem with teaching the full PSP course too early in the curriculum is that the students cannot yet appreciate many of the problems that the PSP is designed to address.  Under these circumstances, students are much more likely to react negatively to the amount of required course work.  Since students are increasingly exposed to software engineering issues during high school or summer activities, the PSP materials will likely soon be suitable for first-year students.  Also consider using the simpler introductory PSP textbook now available for first-year students [Humphrey 1997].

To be most successful, the PSP should be integrated into the software curriculum with the students being required to use PSP methods in their other classes.  While this approach requires that many of the faculty understand and support the PSP, it does generally produce graduates who have the skills to become certified by the SEI as PSP practitioners and to use these methods in their subsequent jobs.  This makes them more attractive job candidates.

# 2.3	General Assignment Guidelines

Students need copies of the PSP process materials to complete the course assignments for each assignment and process level.  These materials are found in the assignment kits available at the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.

Perform the following steps to distribute and collect assignment kits:

- For each assignment, make a copy of the appropriate kit for each student.

- Have the students submit copies of their assignment reports.

- When grading the assignments, write comments on the copies and return them to the students.

- If students are to correct and resubmit their work, have them return the marked-up copies of the assignment reports together with the corrected copies.

Note that since most PSP support tools produce the required process forms with the calculations completed correctly, the students do not need to complete them by hand.

# 2.4	General Grading Guidelines

The grading philosophy suggested for this course is as follows.

- The process data are complete.  The first priority is to ensure that the process data have been entered completely and correctly.  Since, without correct data, the rest of the PSP process will be largely ineffective, this is the first and most important grading priority.

- The process data are accurate and self-consistent.  While this is generally more difficult to determine, it is usually possible to spot most inconsistencies when you know what to look for.  For example, if a developer takes 20 to 30 or more minutes in compiling, but reports no compile defects, he or she is probably not recording all or even any of the defects found.

- The exercise reports are submitted in the proper order and format.  Some students submit the process data in random order and others produce fancy bound reports.  In either case, the students should be told to submit only the required materials and in the correct order.  If they can’t follow such a simple specification, the odds of them following the more complex specifications later in the course are low.

- Historical data are used in planning the work. After students learn to gather complete and accurate data, they generally see the benefits of using the available data for planning future work.

- Historical data are consistently used to evaluate and improve the process.  While this is the real objective of the course, the prior items are important prerequisites.

Quality data are an absolute prerequisite to an effective PSP course. If students’ data are inferior, their learning experience will suffer.

If you are consistent and thorough in your grading, students will generally produce correct results after a single reminder.  You can then focus your attention on the more substantive new topics for each process version.  Note that on the grading checklists, you can easily identify the new items because they are shown in bold italic text.  To help the students to do correct work, suggest that they not submit each assignment until they have reviewed the grading comments for the preceding one.

It is helpful to grade homework by performing the following steps:

- Check that all the forms are present and in the proper order.  When the forms are not submitted in the proper order, you waste time searching through random piles of paper to find the data you need to grade and analyze.

- Check each form to ensure that the data are complete and readable.

- Check the data items on each form to ensure that they are self-consistent.

- Check the data dependencies among the forms to ensure that they are self-consistent.

- Check that the data are properly used.

After students begin to consistently submit quality work, the initial steps of this process take only a few moments per assignment. The grading discussions for each process level suggest the proper items to check for that process level.

3.	Interpreting Class Data

One of the most important objectives of the PSP course is to convince students that using the PSP methods will help them to do better work.  That is why it is important to provide them with frequent feedback on their personal work and on overall class results.

# 3.1	Class Data Feedback

After the first lecture, try to present available class data to the students every day if possible.  However, do not present anything until you have enough data so that no individual’s performance is visible.  The PSP guidelines for showing student data are as follows.

- Respect students’ individuality.  All students are different, so making comparisons among them is counterproductive.  The objective is to help each student maximize his or her potential to do high quality and productive work.

- Respect students’ data.  Data are private.  No student’s data should be shown to anyone else under any conditions.  Students may show their own data to anyone they choose, but you should not.

- Remain neutral. Do not even hint that a particular student has done unusually good or poor work.

Table 3.1 lists the different kinds of data that are appropriate for each lecture.  While you may choose to not show all of these data at every class, I have never had students complain about seeing too much data.  At the end of the course, give the students copies of a final set of the overall data on class performance.

Charts that show the class maximum, minimum, and average values for the data listed in Table 3.1 can be produced by using the SEI PSP instructor support tool.  It’s usually a good idea to point out to students that the maximum and minimum values on the charts reflect the work of different people on each program.  First, check to ensure that this is the case for your class, but for reasonably homogeneous classes of ten or more students, usually no individual’s performance is consistently the best or the worst for all of the programs or measures.

# 3.2	Class Feedback Charts

The following paragraphs discuss each of the class feedback charts that can be generated by using the SEI PSP support tool and the data listed in Table 3.1.

### Time Range

The Time Range chart shows the class average, minimum, and maximum times spent developing each of the programs in hours.  This range is usually very large because of the many possible ways to write programs and because of the wide range in student ability.  This range is of general interest, but it is not useful as an indicator of student performance.

Table 3.1 Suggested Data to Show with Each PSP Lecture

| Lecture Number | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Time Range | x | x | x | x | x | x | x | x | x |
| Time Error | x | x | x | x | x | x | x | x | x |
| Size Range |  | x | x | x | x | x | x | x | x |
| Size Error |  | x | x | x | x | x | x | x | x |
| Size Time |  | x | x | x | x | x | x | x | x |
| Compile Time |  |  | x | x | x | x | x | x | x |
| Test Time |  |  | x | x | x | x | x | x | x |
| Total Defects |  |  | x | x | x | x | x | x | x |
| Compile Defects |  |  | x | x | x | x | x | x | x |
| Test Defects |  |  | x | x | x | x | x | x | x |
| Compile vs. Test Defects |  |  |  | x | x | x | x | x | x |
| Design Defects |  |  |  | x | x | x | x | x | x |
| Design Review Defects |  |  |  | x | x | x | x | x | x |
| Code Defects |  |  |  | x | x | x | x | x | x |
| Code Review Defects |  |  |  | x | x | x | x | x | x |
| Total COQ |  |  |  |  | x | x | x | x | x |
| Appraisal as a % of COQ |  |  |  |  | x | x | x | x | x |
| A/FR |  |  |  |  | x | x | x | x | x |
| Yield |  |  |  |  | x | x | x | x | x |
| Defects per Hour |  |  |  |  | x | x | x | x | x |
| Test Defects vs. A/FR |  |  |  |  | x | x | x | x | x |
| Productivity |  |  |  |  |  |  | x | x | x |
| Size vs. Productivity |  |  |  |  |  |  | x | x | x |
| Productivity vs. A/FR |  |  |  |  |  |  | x | x | x |
| Yield vs. A/FR |  |  |  |  |  |  | x | x | x |
| Yield vs. Productivity |  |  |  |  |  |  | x | x | x |

### Time Error

The Time Error chart shows the error in the time estimates as a percentage of the estimate, and displays the class minimum, maximum, and percentage error for the total of the class estimates and actuals.  That is, with data on four student programs, the chart shows the total of the development time estimates for the four programs compared to the total of the actual time spent developing the programs.  The maximum and minimum values are also shown for each program.  Again, the students are generally surprised at the accuracy of the composite time estimate for the total class.  This indicates the potential value of independently-made estimates, particularly when they are based on historical data and are made using sound estimating methods.

### Size Range

The Size Range chart shows the class average, minimum, and maximum for the added and modified sizes of the programs.  Even with the simple PSP exercise programs, the students have considerable flexibility in how they design each program.  Size ranges of three to one or more are common.  When the size of any of the programs is below about 50 LOC, check that the students are actually writing the programs instead of using available mathematical library functions.

### Size Error

The Size Error chart shows the percentage error for the class minimum, maximum, and total of the class size estimates and actuals for added and modified size.  For example, with data on four students’ programs, the total value is for the sum of the size estimates for the four programs compared to the total of the actual sizes for the same four programs. The principal point to be made with this chart is that the composite class estimate is generally much more accurate than any of the individual estimates.

### Size vs. Time

The Size vs. Time chart shows the added and modified size and the time in hours for each program for the total class.  Each plot point indicates the degree to which development time relates to that program’s size.  Again, composite class data show a poor correlation, but individual students can usually observe a fairly close relationship for their personal data.  The principal lesson is that high correlations are likely for individual data but not for composite class or team data.

### Compile Time

The Compile Time chart shows the percentage of total development time spent in compilation.  Programs written using high-quality processes usually require less compile time.  If many of the students use development environments that do not have a compile phase, show these data for only those students that use compiling.  However, only do so if there are enough of these students so that those individuals cannot be singled out.

### Test Time

The Test Time chart shows the percentage of development time spent in test.  This percentage is a simple indicator of process quality.  Lower test times indicate fewer test defects, higher product quality, and higher process quality.

### Total Defects

The Total Defects chart shows the class average, minimum, and maximum for the total number of defects found during program development per KLOC of added and modified code.  An objective of the course is to increase the students’ sensitivity to defects, thereby convincing them to be more careful in their work.  The total number of defects/KLOC should gradually decline throughout the course.  While this is usually the case, there is often a temporary upward step with the first PSP2 program.  This may indicate that the students are finding a higher percentage of defects and that the finished programs are of higher quality.

### Compile Defects

For those students that have a compile phase, the Compile Defects chart shows the number of defects found in compilation per KLOC of added and modified code and displays the class average, minimum, and maximum values for each program.  One course objective is to motivate students to strive for clean compilations on the first try, resulting in higher quality programs.  If many of the students use development environments that do not have a compile phase, show these data for only those students that use compiling.  However, only do so if there are enough of these students so individuals cannot be singled out.

### Test Defects

The Test Defects chart shows the number of defects found in test, per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  A key quality message of the PSP course is that the number of test defects indicates the number of defects remaining in a program.  This is because test processes generally miss a percentage of a program’s defects.  Thus, the objective is to have as few test defects as possible, resulting in a low number of defects in the finished product.

### Compile vs. Test Defects

The Compile vs. Test Defects chart displays the number of compile and test defects for the entire class plotted on x-y axes.  It indicates the relationship between compile and test defects.  Again, composite class data show a poor correlation, but individual students can usually observe a fairly close relationship for their personal data.  The implication is that to reduce the number of test defects, students should strive to reduce the number of compile defects.

### Design Defects

The Design Defects chart shows the number of defects injected during design per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  For most PSP classes, the number of design defects is fairly small compared to the number of coding defects.

### Design Review Defects

The Design Review Defects chart shows the number of defects found during design reviews per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  A PSP course objective is to maximize the percentage of design defects that are found in design reviews.

### Code Defects

The Code Defects chart shows the number of defects injected in the coding phase, per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  Students are often surprised at how many code defects they inject.  They also find that with modest care they can significantly reduce this number.

### Code Review Defects

The Code Review Defects chart shows the numbers of defects found during code reviews, per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  A PSP course objective is to maximize the percentage of coding defects that are found in code reviews.

### Total Cost of Quality

The cost of quality (COQ) measure displays the percentage of a developer’s total development time that is spent on quality-related activities.  The components of COQ are prevention costs, appraisal costs, and failure costs.  Total COQ is the sum of these three costs. For individual developers, this value is generally fairly flat throughout the PSP course.  This indicates that the PSP strategy of increasing prevention and appraisal costs and decreasing failure costs does not appreciably change a developer’s overall development costs.  However, developers find when they use these methods on larger projects, the resultant higher-quality products have far lower final testing costs and, therefore, much lower total COQ.

### Appraisal Cost as a % of COQ

The appraisal COQ chart shows the percentage of total COQ time that is spent performing appraisal activities.  In the PSP, this is the time spent in design and code reviews.  Appraisal COQ is generally very low at the beginning of the course, but then jumps abruptly for the exercises that use PSP2 and PSP2.1.

### Failure Cost as a % of COQ

Failure COQ is typically relatively flat for the PSP0 and PSP1 exercises and then drops sharply for the PSP2 and PSP2.1 exercises.

### A/FR

The appraisal to failure ratio, A/FR, indicates the effectiveness of the developer’s appraisal activities.  If appraisal time is inadequate or not properly used, failure costs will not drop significantly and A/FR remains relatively low.  Conversely, very large A/FR values could indicate that a developer was spending an unnecessarily large amount of time in reviews.  The A/FR, yield, and review rate measures should be used together to draw conclusions in each specific case.  A/FR is calculated as:

A/FR=(time in code reviews + time in design reviews)/(time in compile + time in test)

### Process Yield

Process Yield denotes the percentage of defects that are removed before the first compile, and shows the class average, minimum, and maximum values for each program.  Convincing students to increase their personal process yield should be one of your highest priority quality objectives for the PSP course.  Process yield is calculated as:

Process Yield=100*(defects removed prior to compile)/(defects injected prior to compile)

If the students’ environments do not have a compile phase, process yield is calculated as yield before the first build and test.

### Code Review Rate vs. Process Yield

The code review rate is typically shown in LOC per hour, although other measures should be used if many of the students are using other size measures.  This chart compares the code review rate with process yield for each program.  While the data are widely scattered for both individuals and overall classes, they usually show that high review rates are associated with low yields and vice versa.

### Defects Per Hour

The Defects Per Hour chart shows the rate of defect discovery measured in defects per hour for design review, code review, compile, and test.  It displays the class average for each of these rates for each program.  These data demonstrate that testing is an inefficient way for developers to spend their time.  Defects per hour are calculated by dividing the number of defects found in a phase by the time in hours spent in that phase.  This calculation is done for design review, code review, compile, and test.

### Test Defects vs. A/FR

The Test Defects vs. A/FR chart shows, for each program, the test defects per KLOC compared to the A/FR achieved for that program.  High A/FR values are associated with low numbers of test defects, while with low A/FR values there are many programs with high numbers of test defects.

### Productivity

The Productivity chart shows the students’ productivity measured in lines of code per hour and displays the class average, minimum, and maximum values for each program.  While students should strive for high productivity, few see significant productivity increases or decreases during the PSP course.  On average, class productivity is fairly flat.  This means that on average, the students are introduced to the PSP’s disciplined engineering methods at little or no net cost to productivity.

### Size vs. Productivity

The Size vs. Productivity chart displays development productivity versus program size on an x-y plot.  The chart generally does not show any discernable trend.

### Productivity vs. A/FR

This chart compares the productivity and A/FR for each student and program plotted on x-y axes.  The intent is to show the degree to which higher values of A/FR impact development productivity.  Many students are surprised to find that their productivity does not decrease and often increases with increased A/FR.

### Yield vs. A/FR

The Yield vs. A/FR chart displays process yield versus A/FR plotted on x-y axes for all of the programs written by the entire class.  While the numbers may not correlate well for the entire class, more experienced developers generally find that higher yields accompany higher values of A/FR.

### Yield vs. Productivity

The Yield vs. Productivity chart shows process yield versus productivity in an x-y plot.  Productivity should be viewed as a long-term objective.  The more immediate objective of this course is to improve basic engineering practices without greatly impacting productivity.

4.	Teaching PSP0 Topics

This chapter covers the objectives for this initial PSP process, describes why understanding this process level is particularly important in learning the PSP, and lists the knowledge the students should gain after listening to the PSP0 lectures and using PSP0 to write one program.  It assumes that you have read the textbook, PSP: A Self-Improvement Process for Software Engineers, and have completed both the PSP Engineer’s course and the PSP Instructor’s course.

The chapter also briefly describes the two lectures that the SEI makes available for introducing the PSP course and the PSP0 process. It also references the various tutorial and exercise materials used to teach PSP0, available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html. The latter sections of the chapter explain how to grade the PSP0 assignments.

# 4.1	PSP0 Objectives

The PSP0 process lecture and exercises focus on achieving six principal objectives.

- Showing students how to follow a simple, generic process while writing the PSP exercise programs.

- Starting students measuring the time they spend and the defects they inject and remove while writing programs.

- Showing students how to determine the likely distribution of their time among process phases.

- Establishing an initial baseline for determining how their personal performance changes during the course.

- Providing the foundation for the subsequent PSP process levels and exercises.

- Introducing the PSP support tool and providing initial experience using it.

Since the PSP0 process level plays such an important role in teaching the PSP, and because there is so much material to cover, do not include additional materials.

The students acquire the following knowledge and capability from the PSP0 lectures and by successfully completing the PSP0 exercises and tutorials.

- What a process is and how to use a defined and measured process.

- How to measure task time and why it is important to do so.

- How to measure the defects they inject and remove while writing programs.

- How long it takes to write programs and how their time is distributed among process phases.

- Initial time data to use in planning future programming exercises.

- The numbers and types of defects they inject and remove in various process phases.

- Initial defect data used for later quality analysis.

- Benefits of doing their work correctly the first time.

# 4.2	PSP0 Lecture: Course Overview Part I

The opening PSP lecture includes a course overview, summarizes the class ground-rules, and provides the schedule for the first five days of the course.  The key topics in the overview lecture are discussed in the sections below.

## 4.2.1	Opening Exercise

The opening exercise provides a forum in which students can discuss software development issues in their organizations, assuming that the students are professional developers and that they have issues to discuss.  For academic courses, use this discussion period to address topics of concern, such as:

- Why are they are taking the PSP course?

- What do they expect to gain from the course?

- How do they expect to use what they learn in their careers?

If the class contains a mix of university students and professional developers, consider asking the developers to discuss the issues they face and to share their experiences with and answer questions from the full-time students.  Regardless of the attendee mix, keep the discussion informal and call on both the outspoken and quiet attendees.  The objective is to have everyone participate and express his or her views.

## 4.2.2	Course Ground Rules

Another important objective of the overview lecture is to establish the course ground rules.  The topics included are

- course prerequisites

- course objectives

- your ground rules for interacting with the students

- your availability to the students

- the handling of incorrect work (return it for correction and resubmission)

- what you expect from the students

- how you will grade their work

This is an opportune time to entertain questions about the effort that is required from the students to complete the course.

## 4.2.3	Course Agenda

Explain the class schedule and answer questions about the topics that are covered, when they are covered, and why they are covered in a specific order.

## 4.2.4	Questions

Below are some examples of commonly asked PSP0 questions and answers.

Q: Why do we need to write programs to learn the PSP?

A:  The PSP course teaches you how to follow a planned, managed, and quality controlled personal process.  To do this, you must actually use such a process.

Q:  But couldn’t we use a simpler process than writing programs?

A:  While this course could theoretically be taught with any process, the software development process is sufficiently rich and complex to provide convincing data with a few simple exercises.  Other processes would likely take a great many more data points and a lot more time to provide similar results.

Q:  I use agile methods in my work.  Can I use them in the PSP course?

A:  While agile methods are compatible with the PSP and TSP, this course is not designed to use them.  You should use more traditional software development methods to write the exercise programs and then later use agile methods with your TSP team.  The material to teach PSP courses with agile methods are not currently available with the support you would need to do the programming exercises.

Q:  Why isn’t the design material taught first?  Since software development projects typically start with design, why does design come near the end of the course?

A:  As you will see, design is in large part, a quality issue.  Further, without high quality coding practices, the value of sound design is significantly reduced.  Therefore, the PSP introduces the design topics after you have learned to use quality coding practices.

Q:  Then, why isn’t quality taught first instead of planning?

A:  To appreciate the importance of the PSP quality methods, you need personal defect data.  With the relatively small PSP programs, that requires data from three or more exercises.  Rather than requiring you to write more programs, the course was designed to provide these defect data from the exercises that teach the PSP planning methods.

Q: Since the compiler finds syntax defects, why should I record the compiler defects?

A:  There are two reasons.  First, by merely recording these data you will become more aware of your mistakes and make fewer of them.  Second, your principal concern is with the mistakes you make.  Since most programming mistakes produce at least some defects of types that are often missed by the compiler, not recording compile defects will omit a lot of potentially useful information about the kinds of mistakes you make.

# 4.3	PSP0 Lecture: Introduction to the PSP and TSP

The introduction lecture explains why the PSP and TSP processes are needed and provides an overview of the PSP.  The TSP is described in the final course lecture.  The main topics of the PSP0 lecture are described in the following sections.

## 4.3.1	The Changing World of Software Engineering

This lecture explains that software projects have grown larger, more complex, and more demanding every year.  To address the growing challenge of software development, software engineers need improved skills and capabilities.  The TSP shows teams how to address these challenges at a project level and the PSP prepares developers to be effective TSP team members.

## 4.3.2	PSP Principles

The lecture next summarizes the basic principles behind the PSP and lists the skills the PSP course provides its graduates.  Because it is important for students to understand and agree with these principles, encourage class discussion.

## 4.3.3	PSP Process Overview and Course Logic

This brief overview shows the students what is coming in the PSP course. It describes the various parts of the PSP course and the material covered in each part.

## 4.3.4	Typical PSP Class Results

The results presented are based on data from 8,100 programs written in PSP classes.  Point out that there has been a lot of experience with the PSP course and that it is known to work.  It has also been shown to be effective at improving the personal performance of developers who use it properly.

# 4.4	PSP0 Process Tutorial

When students are asked to do something new or unfamiliar, reinforce the lecture by including a process tutorial.  Tutorial materials are available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  During the tutorial cover the PSP0 Process forms and scripts and using the PSP Course Support Tool to record time data, defect data, and calculate derived measures.

# 4.5	PSP0 Programming Exercise Assignment

Assign only one programming exercise for the PSP0 process.  Completing more than one exercise is not recommended because only one is needed to establish an initial baseline.  Thereafter, it is important for students to measure program size as well as time and defects.  Suitable first programs are available at the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.

When making this assignment, it is usually best to start with a brief workshop that explains the program requirements, works through an example of any non-trivial mathematical logic, and walks the students through planning to develop their programs.  Thoroughly cover the assignment report specifications provided in the assignment kit and emphasize that the students must turn in copies of all the required forms.  Also explain that these forms can be printed from the PSP support tool.  Finally, consider the points covered in section 4.7 of this chapter, “PSP0 Tips and Hints.”

# 4.6	Grading PSP0 Assignments

The assignment evaluation checklist for the PSP0 programming exercises is available at the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  The PSP0 items to check are discussed in this section.

## 4.6.1 	Program and Test Result

Since this is not a programming course, the grading of the program and test results needs to ensure that the program generates the correct results and has been exercised on all the required tests.

Also, review the program listing to verify that an appropriate program was written and that it appears to be complete and working.  If you suspect that there are problems, ask the student for a brief demonstration.

## 4.6.2	Time Recording Log

The most typical problems that you’ll encounter with students using the Time Recording log are that they forget to make entries while doing the work or that they only do so after finishing their program.  When students record the times after the work is done, the values are usually round numbers.  If you insist that the students enter the time data properly with PSP0, entering time data will not usually be a problem for subsequent process levels.

There should be Time Recording log entries for each phase and the sequence of entries should conform to the PSP0, allowing for the possibility of iteration within the development phase. However, it would, for example, be unrealistic to have a design phase immediately followed by a test phase without a code phase (and possibly a compile phase depending on the programming environment being used). The first plan should be Plan and the last phase should be PostMortem.

Time Recording log entries should not overlap. While it is not strictly necessary to have Time Recording log entries in time order, doing so is more likely to indicate that the student is recording activity as it occurs.

## 4.6.3	Defect Recording Log

The main problem with the Defect Recording log is that students refuse to enter any defect data.  If this is the case, either convince these students to start recording defect data, at least during the course, or remove them from the class.

Another common problem is that students don’t bother entering the defect data when they find the defects and then try to enter the data later.  This usually results in them not recording most of their defect data.

The Defect Recording log is a common source of problems, not because it is difficult but because students often omit part of the data or make incomplete entries.  Good defect data are required for later parts of the course.  If you do not insist on students entering good defect data now, it will be much harder to get them to enter quality defect data later.

The injected and removed phases should be checked for consistency with the defect type and the defect description.

## 4.6.4	Project Plan Summary

Do not check the entries in the Project Plan Summary that are calculated by the students’ support tool, but check any values directly entered (such as planned total time) or any manual calculations the students make.  If the results are incorrect, ask them how they arrived at the numbers used in the form and correct any misunderstandings.  Then ask them to correct and resubmit the assignment report.

## 4.6.5	Consistency Checks

On the PSP0 Project Plan Summary, check that the data look reasonable.  The following paragraphs describe typical consistency problems.

Check for consistency between the time and defect data.

- The time spent in the compile and test phases is consistent with the find and fix time for the defects found in that phase. Query students where the difference is more than a few minutes. Encourage them to prepare for testing in the design and coding phases (for example, preparing test data) so that the compile and test time accurately reflects the failure time for the assignment.

- The order of the defect entries is consistent with the order shown by the phase entries in the time log.

- Where the programming work took two or more days, check that the defect phases entered in a day are consistent with the phase entries in the time log.

- Check for consistency between the time and defect logs and the Project Plan Summary. While these values are mostly transferred automatically, occasionally students edit the summary values or provide inconsistent copies of documents.

## 4.6.6	General

Verify that the student did his or her own work.  While cheating is rare, it is possible, particularly when students are not qualified or are taking the course under duress.  A simple check of the program listings and PSP forms usually reveals instances of copying.

# 4.7	PSP0 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP courses and from analyzing the data gathered from thousands of PSP class programs. Consider these points as you give lectures, answer questions, and advise students.

## 4.7.1	Program Complexity

Most students write reasonably sized PSP assignment programs but some can be overly ambitious.  This can often be the case with experienced developers who are accustomed to handling error problems, providing sophisticated user interfaces, or preventing security vulnerabilities.  While sound programming practices are important, the PSP exercise programs are class exercises that will not be reused.  The students do not need to produce anything more than a basic working program that handles normal input, error, and operating conditions.  It doesn’t need to be designed to be bulletproof or to handle unusual situations.  Emphasize that programs of 50 to 100 LOC are usually adequate.

## 4.7.2	Very Small Programs

Many modern programming environments include a wide variety of mathematical and other embedded functions.  While using embedded functions for some program actions is appropriate, they should not be used to write the principal functions of the exercise program.  When students use such functions, they can write many of the PSP exercises in fewer than ten LOC.  This takes too little time and is of no pedagogical value.  If students use these functions, require them to modify their program to implement the principal exercise functions themselves.  If the programs are smaller than 50 LOC and take less than a couple of hours to write, the students are not likely to learn the necessary lessons from the exercise.

## 4.7.3	Quality

A fundamental point to emphasize at every opportunity is that the PSP is a process for producing quality work.  This requires that the process data be of high quality, that the programs the students produce are of high quality, and that the students submit quality exercise reports.  If you require quality work from the beginning, you will not likely have many problems.  However, if you do not start by insisting on quality work, you will likely have quality problems throughout the course.

## 4.7.4	Disruptive Students

Occasionally, students are enrolled in PSP classes either over their objections or without proper prior discussion or preparation.  If such students are outspoken or appear to be working against the objectives of the course, take them aside to discuss the issue.  If the student is not willing to take the course and to complete the required work, insist that he or she be removed from the class.  With a negative attitude, the student will not gain anything from taking the course and is likely to cause problems with the other students.  If you compromise on this point, the course will likely fail, even for the students who are willing to do the work.  Then you will be blamed for the failure.

5.	Teaching PSP0.1 Topics

This chapter discusses the objectives for the PSP0.1 process and lists the knowledge the students should possess after listening to the PSP0.1 lectures and using PSP0.1 to write one or more programs. It assumes that the students have completed the PSP0 material covered in the prior chapter and have started developing a program using the PSP0 process. It briefly describes common questions and issues you may encounter while teaching the PSP0.1 process.

The chapter briefly describes the lecture that the SEI makes available for the PSP0.1 process. It also references the various tutorial and exercise materials used to teach PSP0.1, available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html. The latter sections of the chapter explain how to grade the PSP0.1 assignments.

# 5.1	PSP0.1 Objectives

The PSP0.1 process lecture and exercises focus on achieving six principal objectives.

- Explaining the principles of process measurement and the basic PSP measures.

- Explaining why size measures are useful for making project estimates and plans.

- Describing the PSP size measures and the criteria used for selecting a size measure.

- Describing the principles and methods for developing program size counters.

- Showing students how to use PSP size-accounting.

- Producing a program that students can use to measure the sizes of the programs they develop.

The students acquire the following knowledge and capability from the PSP0.1 lectures and by successfully completing the PSP0.1 exercises and tutorials.

- measurement principles

- why size-measurement is important

- how to select a program size measure

- why counting and coding standards are needed for program size-measurement and how they are developed

- how to develop a program to measure program size

- how to track program size changes by using the PSP size-accounting framework

# 5.2	PSP0.1 Lecture: Process Measurement

The PSP0.1 lecture covers the topics described in this section.

## 5.2.1	Process Measurement Principles and Objectives

Begin the PSP0.1 lecture with an overview of process measurement principles and objectives and then describe various types of measures.  These opening topics provide students with an understanding of why the specific PSP measurements are needed, how these measurements are made, and why the PSP measures are accurate, precise, and useful.

## 5.2.2	The PSP Measures

The PSP Measures portion of the lecture describes the three basic PSP measures, the goals of these measures, and some questions that they can be used to answer.  Then it briefly summarizes some of the more useful PSP-derived measures that can be obtained by using these basic measures.

## 5.2.3	Size Measure Criteria

A substantial portion of this lecture is devoted to size-measurement criteria because these criteria are particularly important in establishing the PSP planning strategy. You may find that students tend to forget this aspect of the PSP measures and later object to the use of LOC as a size measure in the PSP course. During the lecture, emphasize that most projects use multiple size measures to plan and track their work so they must be able to use many different size measures.  For example, they need measures for requirements, designs, code, and documentation, among other things.

For most students, the lines of code (LOC) measure is the simplest and easiest one to use for the PSP programming exercises, but no one has to use it.  However, if students want to use some other measure, they must define it. You can help them to do this, but they will have to do extra work to define and evaluate the measure that they use.

## 5.2.4	Counting Program Size

The students must understand how to measure program size.  To provide a size-measurement tool, the PSP programming exercises usually require students to write at least one program that measures program size.  If students do not write such a program, you must provide them with a size-measurement tool they can use to measure their work throughout the course.  If students are confused about how to write a size-measurement program, work with them to resolve the issues so they will be able to produce a useful size-measurement tool.

Professional software engineers usually use more sophisticated size-measurement programs that can count additions, changes, and deletions to measure the size of larger programs. Depending on the development environment being used, such tools are often available.

## 5.2.5	Size-Accounting

Although the PSP size-accounting principles are relatively simple, they are a new concept to most students and thus can be confusing.  If students are still confused about any aspects of size accounting after the lecture, ask them to work through one or more size-accounting exercises.

## 5.2.6	Questions

The most commonly asked questions for the PSP0.1 lecture usually concern LOC, alternative size measures, and how to distinguish between base and reused code. Below are some example questions and answers about these topics.

Q:  I’m used to writing programs in SQL and don’t want to use LOC.  What can I do?

A:  The textbook includes an extensive discussion of this subject in Chapter 3.  Read that chapter before writing the exercise program.  To develop your own size measure, identify the elements of your programs that can be counted and write a program to count them.  Write the program to count each of the element types separately.  Then determine which combination of the element count types produces the most reliable correlation between size and time.  You can try several combinations of these measures while writing your first several PSP exercise programs before deciding.  The data generated when writing the exercise programs will guide you in selecting the most suitable counting standard.  The textbook gives some examples of how to do this.

Q:  It seems that base code and reused code is the same thing.  For example, if I reuse Program 1 to write Program 3, would Program 1 be reused or base code?

A:  According to the PSP convention, if you are modifying and enhancing an existing program, the original unmodified program is considered base code.  There is, however, an exception.  Only if the base program was designed to be a reusable program and if you do not make any changes to that code, is it considered reused code.  The reason for this distinction is that in most cases, developers write new programs by modifying and enhancing existing ones.  They typically start by developing a small core portion of the program as “version one” and then follow a cyclic process to add new code to this base with each successive cycle.  Since the original core of code for cycle one was the first step in this cyclic process, it is considered base and not reused code.  This type of cyclic approach is a recommended strategy for developing the larger PSP programming exercises.

# 5.3	PSP0.1 Process Tutorial

When students are asked to do something new or unfamiliar, reinforce the lecture by including a process tutorial.  Tutorial materials are available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  During the tutorial, describe the new entries included in the PSP0.1 forms and scripts, how to calculate the size entries listed in the Project Plan Summary, and size- accounting.

# 5.4	The Size-Measurement Report Assignment

The size-measurement report assignment requires students to produce a size-measurement standard for the programs that they write.  They need this standard to produce the report and to complete the size-measurement programming assignment.  If the students all write their programs in languages where LOC is an appropriate size measure, a single, simple size-measurement example or exercise should be sufficient.  However, if some of the students are unable or unwilling to use LOC, you should develop a special tutorial in advance that shows how to count the sizes of programs written in the languages that these students are using.  If you do not prepare a special tutorial, expect to spend a significant amount of time coaching students while they try to write a size-measurement program.

# 5.5	The Coding Standard Report Assignment

The coding-standard report assignment asks the students to produce a coding standard that is tailored to the size-measurement standard they produced with the size-measurement report.  A brief review and discussion of this assignment is usually adequate.

# 5.6	PSP0.1 Programming Exercise Assignments

Assign at least one programming exercise for the PSP0.1 process.  If the course schedule permits, a second PSP0.1 exercise provides the students additional experience with making size and time estimates. The SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html, provides a number of suitable programming exercises.

When assigning this programming exercise, start with a brief workshop that explains the program requirements, walks through an example of any non-trivial mathematical logic, and demonstrates for the students how to plan their programming work.  Also, review the assignment report specification that is included in the assignment kit again and emphasize any areas that were problematic in previous assignments.

# 5.7	Grading the Size-Measurement Report Assignment

The size-measurement report assignment requires students to develop a size-counting standard.  This standard can be completely or partially patterned on the standards in the textbook.  The students do not need to produce an original standard.  Your grading approach should focus on the degree to which the standards are complete and adequately cover the needs of the programming languages the students use for the course.

# 5.8	Grading the Coding Standard Report Assignment

The coding standard report guides the students in developing quality programs that can be counted by the size counters they develop.  This standard does not need to be original, but it should include the basic elements of the example standard provided with the assignment kits.  When grading this assignment, your principal concern is that students follow the standards they produce.

# 5.9	Grading PSP0.1 Programming Assignments

The assignment evaluation criteria for the PSP0.1 programming exercises are the same as those for PSP0, with some additions.  Additional criteria are denoted by bold italic text on the grading checklist.  The PSP0.1 checklist is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.  The PSP0.1 items to check are discussed in this section.  Refer to the previous chapter for a discussion of the PSP0 criteria.

When grading the PSP0.1 programs, focus on the new items, as well as on those that students found difficult in earlier assignments.  However, check all the PSP0 process level items to ensure that students do not regress.

## 5.9.1	Project Plan Summary

It is not necessary to verify the numerous Project Plan Summary entries that are calculated by the students’ support tool.  However, you must verify any manual calculations made by students.  If the results are incorrect, ask the students how they arrived at the numbers they used in the form.  Also verify that the planned times for each phase are distributed in proportion to the To Date % value produced by the PSP0 program and that the planned and actual size values are reasonable.

## 5.9.2	The PIP Form

The PIP form provides evidence that students are thinking about the process and how it works for them.  Ensure that a PIP form has been completed for each assignment and that it includes insightful comments.

The PIP form should capture the student’s ideas about aspects of the process that are not working well and how the process might be improved, or aspects that are working well and how to reinforce those aspects. It is an opportunity for personal reflection. Encourage students to go beyond just technical programming issues in their PIPs to include their process behavior.

## 5.9.3	Consistency Checks

Repeat the consistency checks you performed for the PSP0 programs for the PSP0.1 programs, starting with a review of the PSP0.1 Project Plan Summary to determine if the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Finally, check the students’ time and defect logs and ask them to explain any unusual values.

# 5.10	PSP0.1 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP courses and from analyzing the data gathered from thousands of PSP class programs. Consider these points as you give lectures, answer questions, and advise students.

Distinguishing between planned and actual size often confuses students. During planning, students estimate the base, deleted, added, modified, and reused size elements, then they calculate the total size and added and modified size by using these estimates.  For actual size, the PSP-specified size-counting programs only produce values for total program size and total base size.  Students should also have previously counted their reusable programs.  They must then manually count the deleted and modified code and calculate the added, modified, and added and modified values by using the measured values.

The objective of the PSP0.1 process is to establish a size-measurement capability.  After students produce useful size-counting tools, they often want to measure other programs they have written or programs written by other developers in their organizations.  Encourage this early interest, because it helps to maintain students’ interest in the PSP and to build an appreciation for how the PSP data can help them to do better work.

6.	Teaching PSP1 Topics

This chapter discusses the objectives for the PSP1 process and lists the knowledge the students should possess after listening to the PSP1 lectures and using PSP1 to write one or more programs. It assumes that the students have completed the PSP0.1 material covered in the prior chapter and have started developing a program using the PSP0.1 process. It briefly describes common questions and issues you may encounter while teaching the PSP1 process.

The chapter briefly describes the lecture that the SEI makes available for the PSP1 process. It also references the various tutorial and exercise materials used to teach PSP1, available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html. The latter sections of the chapter explain how to grade the PSP1 assignments.

# 6.1	PSP1 Objectives

The PSP1 process lecture and exercises focus on achieving five principal objectives.

- Explaining size-estimating principles.

- Describing the PROBE method and its principal elements.

- Explaining what conceptual design is and how to produce one.

- Introducing proxies and explaining how they are used in size estimating.

- Showing how PROBE uses linear regression to make statistically sound estimates.

The students acquire the following knowledge and capability from participating in the PSP1 lectures and from successfully completing the PSP1 exercises and tutorials.

- How size estimates are made and why they should be made with statistically sound methods.

- What the PROBE method is and how its principal elements relate.

- What the conceptual design is and why it is needed.

- What proxies are and how they help in making estimates.

- How to determine the linear regression parameters for a set of time and size data.

# 6.2	PSP1 Lecture: Estimating with PROBE I

The PSP1 PROBE I lecture covers the topics described in this section.

## 6.2.1	Planning Overview

The PSP1 lecture begins with a description of the project-planning framework and explains the planning process and the principles behind it.  Size estimating is next discussed and includes the principles of estimating.  In this discussion, emphasize the role of data and how each estimate provides the data students use to improve estimating accuracy.  Also emphasize the role historical data plays in making sound and balanced estimates.

## 6.2.2	The PROBE Estimating Method

The lecture next describes the elements of the PROBE estimating method, followed by a brief overview of conceptual design.  During this discussion, emphasize the role of the conceptual design and how it differs from the real design.

## 6.2.3	Estimating Proxies

The lecture describes estimating proxies by using the example of proxies in building construction.  It then describes the criteria for a good size-estimating proxy and shows students how to use these criteria to develop their own proxies.

## 6.2.4	Estimating Program Size

The final part of the lecture discusses linear regression and how it helps in making accurate size and time estimates.  Stress that linear regression is just a mathematical method and that while it can be very helpful, it can produce misleading results if not used properly.

## 6.2.5	Questions

The most commonly asked questions for the PSP1 lecture usually concern balanced estimates, the part-size tables, conceptual design, and the comparison of PROBE with other estimating methods.  Below are some example questions and answers about these topics.

Q:  Why does PROBE produce balanced estimates?

A:  Using data from your own work is the key to making accurate, balanced estimates with the PROBE method.  However, you must use the data in a statistically sound way.  You start by creating a conceptual design that divides the planned product into parts.  You then use historical data to estimate the sizes of parts of the new program that are similar to parts of programs that you have developed in the past.  Next, assume that the new parts will have the same average size as similar parts that you have already developed.  After you have made a number of estimates in this manner, on average, your estimates will be correct and balanced.

Q:  The sizes in the size table in the textbook look too small to me.  Do I have to use the values in that table?

A:  No, you can use whatever size data seem most appropriate for your program, but you must use a size table.  If you do not have enough data to create a size table, you must use the table in the textbook until you have data from enough programs to produce a table of your own.  Then you should build your own table and use it.

Q:  How does conceptual design differ from real design?  Why not just make the real design?  Then you’d have a better design and a better estimate.

A:  That is correct.  If you first produced the real design and used it for estimating, you would almost certainly have a more accurate estimate.  That also holds true for estimating implementation time.  If you wrote and tested the program, your estimate would be very accurate, but it would merely be a record of historic fact.  In the PSP course, our goal is to make accurate estimates before actually doing any of the work.  To make the estimate, you must have an idea of what you intend to build and the parts with which you intend to build it.  You create the conceptual design to help you identify and estimate the sizes of these parts.  While producing the actual design may produce a better estimate, it would not build your estimating skills.

Q:  In my organization, we use function points to make size estimates.  Could I use the function point method instead of PROBE?

A:  While you could use the function-point method with the PSP and TSP, you must use the PROBE method in this course.  The function point and PROBE estimating methods are similar in several ways.  They both use proxies as an intuitive framework for estimating size and they both use defined methods for combining the proxy data to produce the estimate.  One difference, however, is that the PROBE proxies are physical program entities that can be measured, while the function point proxies are not.  After completing the course, you can use the function point method if you find it helps you to make better estimates.

# 6.3	PSP1 Process Tutorial

When students are asked to do something new or unfamiliar, augment the lecture with a process tutorial.  Tutorial materials are available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.

In this tutorial, you should describe the new entries included in the PSP1 forms and scripts and any new process elements.  The main addition to the PSP1 Project Plan Summary is the measure for productivity in size units per hour.  The new process elements for PSP1 are the Test Report template, Size Estimating template and PROBE calculation worksheet.  Walk the students through a simple example that shows them how to use the support tool to use the PROBE method.  Cover recording both plan and actual size and time data.

# 6.4	PSP1 Programming Exercise Assignments

Assign at least one programming exercise for the PSP1 process.  If the course schedule permits, assigning one or more additional PSP1 exercises provides the students with additional data on their work and enables them to become more experienced with the PROBE estimating method. The SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html, provides a number of suitable programming exercises.

When assigning this exercise, start with a brief workshop that explains the program requirements, walks through an example of any non-trivial mathematical logic, and demonstrates for the students how to plan their programming work.  Also, again review the assignment report specification that is included in the assignment kit and emphasize any areas that were problematic in previous assignments.

# 6.5	Grading PSP1 Programming Assignments

The assignment evaluation criteria for the PSP1 exercises are the same as those for PSP0.1, with some additions.  Again, additional criteria are denoted by bold italic text on the grading checklist.  The checklist is available at the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  The PSP1 items to check are discussed in this section. Refer to the previous chapters for discussions of the PSP0 and PSP0.1 criteria.

When grading the PSP1 programs, focus on the new items, as well as on those that students found difficult in earlier assignments.  However, check all the PSP0 and PSP0.1 process items to ensure that students do not regress.

## 6.5.1	Project Plan Summary

With the introduction of the Size Estimating Template, the only value entered on the Project Plan Summary is the actual total program size (T).  The values of the other entries in the Project Plan Summary are calculated by the students’ support tool, so you probably do not need to verify them.  However, you must verify any manual calculations that the students make.  Also, check to make sure the planned productivity rate is consistent with the student’s past performance.  If the results are incorrect, ask them how they arrived at the numbers used in the form and resolve any problems.

## 6.5.2	Size Estimating Template

First, ensure that all of the required plan and actual size values are correctly entered in the form.  A common mistake is to confuse base parts with parts additions and reused parts.  For example, if some base parts contain no modified or deleted code, ask the student why they are not treated as parts additions or reused parts.  Another common mistake occurs when parts additions are estimated and not developed, or developed but not estimated.

Also, verify that the type, items, relative size, and size entries for the parts additions are properly calculated and entered and that the students used a part-size table to make their estimates.  While students should create their own size tables after they have gathered enough data, they probably do not have enough programs to do so at this point.  Next, verify the method chosen on the PROBE Calculation worksheet satisfies its selection criteria (see the PROBE script for constraints on r2 and beta values).  Finally, check that the estimated and actual values from the PROBE Calculation Worksheet are entered in the proper places on the Project Plan Summary.

## 6.5.3	The Test Report Template

Check that the students’ test reports contain the required data for all tests that were run. Students should briefly describe the tests and document both the expected and actual results.  If a test was too complex to describe on the test report, the report should reference a document that describes the test in sufficient detail to repeat it if needed.

## 6.5.4	Consistency Checks

Repeat the consistency checks you performed for the previous process level for the PSP1 programs, starting with a review of the PSP1 Project Plan Summary to determine if the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Check the students’ time and defect logs and ask them to explain any unusual values. Also check that the estimated and actual values from the PROBE Calculation Worksheet are entered in the proper places on the Project Plan Summary. An important check is that that the actual Added (A) on the Planning Summary is close to and not less than the actual Based Added plus Parts Added (BA+PA) on the size estimating template. A discrepancy here indicates a problem with size accounting.

# 6.6	PSP1 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP courses and from analyzing the data gathered from thousands of PSP class programs. Consider these points as you give lectures, answer questions, and advise students.

Using the PROBE estimation with limited data is a common source of confusion.  When assigning the PROBE estimation exercise, emphasize that the students will not have enough data to use PROBE methods A or B.  In this case, students use PROBE method C, which is a simple productivity calculation that uses their size estimate and the average productivity for the programs they have developed to date.  If they are confused about how to use method C, walk them through one example of calculating estimated development time with their own data.

Students often fail to use their own data when estimating program size.  Most students continue using the tables in the textbook even after they have enough personal data to make a relative-size table of their own.  After they have written three or four programs, have them produce a simple table for their own programs. Then show them how they could have improved their estimating accuracy by using their own data.  In most cases, this simple change would have substantially reduced students’ estimating error.

7.	Teaching PSP1.1 Topics

This chapter covers the objectives for the PSP1.1 process and lists the knowledge the students should gain after listening to the PSP1.1 lectures and using PSP1.1 to write one or more programs.  It assumes that the students have completed the PSP materials covered in the previous chapters and have started developing a program using the PSP1 process. It briefly describes common questions and issues you may encounter while teaching the PSP1.1 process.

The chapter also briefly describes the lecture the SEI makes available for the PSP1.1 process. It also references the various tutorial and exercise materials used to teach PSP1.1, available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html. The latter sections of the chapter explain how to grade PSP1.1 assignments.

# 7.1	PSP1.1 Objectives

The PSP1.1 process lectures and exercises focus on achieving six principal objectives.

- Explaining what the prediction interval is, how it is determined, and how it is used.

- Showing how to determine the size ranges for a set of proxy size data.

- Describing the PROBE A, B, C, and D methods for estimating with limited data.

- Explaining how to combine the error ranges for multiple estimates.

- Describing the key issues to consider when using the PROBE method.

- Explaining how to produce and track plans.

The students acquire the following knowledge and capability from listening to the PSP1.1 lectures and from successfully completing the PSP1.1 exercises and tutorials.

- What a prediction interval is and how to determine it.

- How to develop the size ranges for a set of proxy data.

- How and when to use each of the PROBE A, B, C, and D estimating methods.

- How to combine the errors from multiple estimates.

- What task hours are.

- How to produce a schedule plan.

- What earned value is and how to use it in planning and tracking projects.

# 7.2	PSP1.1 Lecture: Estimating with PROBE II

The PSP1.1 PROBE II lecture covers the topics described in this section.

## 7.2.1	The Prediction Interval

The first PSP1.1 lecture begins with an explanation of the prediction interval (PI). Emphasize that the PI is a mathematically precise way to calculate likely estimate error, but it is not a prediction.  For example, the 70% prediction interval for 27 C++ program estimates shown in the PROBE II lecture has seven points outside of the PI range.  The seven points make up 25.9% of the total points, which is close to 30%.  However, with eight points, this percentage would be 29.6%.  While there is no way to predict the error for any estimate, as long as developers use consistent methods and data, the prediction interval provides a useful basis for judging the range of estimating error.

## 7.2.2	Organizing Proxy Data

The lecture next explains both the simple and the advanced methods for producing the relative-size table.  Emphasize that while the more sophisticated approach should slightly improve their estimating accuracy, the biggest single improvement will come from using data from their personal work.

## 7.2.3	Estimating with Limited Data

When describing the PROBE A, B, C, and D methods, students often have trouble understanding the concepts, so provide ample discussion time and walk them through one or more classroom exercises if needed.

## 7.2.4	Estimating Accuracy

Emphasize that not all estimating errors are bad.  Occasionally, when developers produce the actual design, they think of a better approach than the one they used for the conceptual design.  While this may result in a large estimating error, they should not be unhappy with the result.  Also point out that while they should understand how to combine multiple independent estimates, this is not something they will do during the PSP course.  For this course, they should understand the principles of combining estimates so they can better judge their estimating errors when they later work on team projects.

## 7.2.5	Estimating Considerations

Your objective for this portion of the lecture is to get the students to evaluate their own data and to build an intuitive understanding of the conditions that could cause any data-based estimating method to produce misleading results.  While using data helps them to make better estimates, they should understand the methods needed to consistently get the best results.

## 7.2.6	Questions

The most commonly asked questions for the PSP1.1 lecture concern using limited data, the relative-size table, and estimating for new development environments.  Below are some example questions and answers about these topics.

Q:  Can I use my PSP course data for estimating the projects I do at work?

A:  First, you must ensure that your PSP data are relevant to your working situation.  For example, if you must adhere to stringent specifications that could increase program size, you must either use data that are developed using the same specifications or make adjustments to your PSP data.  Of course, after you actually have data from your work environment, you should use it.  Also, experience shows that developer productivity is generally lower on the job than it is in the PSP class.  While there are many possible reasons, when developers are in a classroom environment, they have very few interruptions.  When you start measuring your time on the job, you will find that interruptions can waste a lot of time and seriously reduce productivity.

If you determine that the PSP course data are relevant, you can certainly use them for size estimating at work.  However, your productivity data will probably not be usable for anything but general guidance.  Regarding size data, use care when selecting the PROBE A, B, or C method.  If your work programs are much larger than the PSP exercises, use method C, regardless of how much data you have or its correlation.  Using methods A or B can produce misleading results for programs that are outside the range of the data used to generate the β parameters.

Q:  How many data points do I need to make my own relative-size table?

A:  With two data points, you have an average, a large, and a small value.  While that only provides one proxy type table for all programs, it is better than nothing.  After you obtain two data points on several proxy types, you can build a usable relative size table.  While gathering more part data would give you a broader and more representative set of size ranges, you can start with very little data and build on them.  If you have only one data point that is reasonably representative of your programming style, you can use it as an initial guideline for the average parts sizes for the next program.  With more data, of course, you can improve the table.

Q:  I use SEQUEL, C++, and a special application language at work. How can I use PROBE?

A:  The simplest way to address this situation is to make separate estimates for each language and environment.  This means that you should also develop a relative-size table and β parameters for each language and environment.

# 7.3	PSP1.1 Lecture: Using PSP Data

The second PSP1.1 lecture discusses how the PSP planning methods are used to plan larger projects. It covers the topics described in this section.

## 7.3.1	Using Personal Data

The objective of this part of the lecture is to explain to the students why the PSP planning methods will be useful in their future work.

## 7.3.2	Task and Schedule Planning

During this part of the lecture, introduce task and schedule plans, discuss project and period plans, and define task hours.  Then describe the steps for producing a project schedule.  Emphasize that, while the PROBE method sounds complex, most TSP support tools generate all of the required data after the basic size and task estimates are entered, the task order defined, and the task hours planned.

## 7.3.3	Project Tracking

Explain why it is important to track project status and how to use the earned value method to do so.  While students do not use earned value during the PSP course, they must understand the method when they later work on a TSP team.  Your objectives are to describe the earned-value method and to interest them in using it to track and manage their work in the future.

## 7.3.4	Questions

The most commonly asked questions for the second PSP1.1 lecture concern task time and earned value.  Below are some example questions and answers about these topics.

Q:  What are the typical weekly task hours for TSP teams in industry?

A:  While this varies considerably by organization and TSP experience, TSP teams typically start out averaging 10 to 12 task hours per week for each full-time developer.  With experience and management support, they can often increase to 15 to 18 task hours per week.  Occasionally, teams can achieve higher numbers.

Q:  I can’t imagine management in my organization agreeing to my working on projects only 10 to 12 hours a week.  How do teams address this issue?

A:  This is a common misunderstanding about task hours. Few people realize how much time developers typically spend every week on things other than project tasks.  With the TSP, teams measure task time so they have data to show how much time that they spend on various kinds of tasks.

For example, if management required you to work 40 task hours in a week, you would have to plan for everything you did.  While planning the project tasks would not be difficult, making an accurate plan for the time to handle e-mail, make out expense reports, take coffee breaks, attend meetings, provide assistance on prior projects, and do everything else you have to do would be next to impossible.  Task hours are a fairly predictable fraction of total work hours, so the task-hour planning strategy works well for organizations that use it.  The exception is for organizations that bill their time to clients.  In these organizations, developers track everything they do and they generally end up with many more than 10 to 12 billable hours a week.  However, by planning and tracking all of their non-task activities, they spend much more time planning and tracking their work and they are actually less productive.

Q:  It seems hard to believe that something as simple as earned value can produce accurate job-completion projections.  Are EV projections accurate and why?

A:  The earned-value method can be very accurate, but only under the right conditions.  First, the method assumes that your rate of earning value in the future will be about the same as in the past.  This requires that you and your team work on the project about the same amount of time every week in the future as you have in the past.  If you added or removed team members, you would have to adjust the EV projections.

The second and most important consideration for EV accuracy concerns plan accuracy.  For the EV method to be accurate, the planning errors for future phases must be similar to those for the completed phases.  While this holds true when projects are planned based on historical data, it is not generally true for most software projects.  The reason is that software projects typically use inaccurate size estimates, have only general productivity data, and try to meet unrealistic testing schedules.  Further, given the unreliable quality of most software at system test entry, testing time is unpredictable.  When developers use the TSP, create project plans based on historical data, and do quality work, their EV projections are surprisingly accurate.

# 7.4	PSP1.1 Process Tutorial

When students are asked to do something new or unfamiliar, augment the lecture with a process tutorial.  Tutorial materials are available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  During the PSP1.1 tutorial, you should describe the new entries included in the PSP1.1 forms and scripts and any new process elements.  The new process elements for PSP1.1 are the task and schedule templates.  If you thoroughly covered these templates during the second PSP1.1 lecture you only need to mention them during the tutorial.  The main addition to the PSP1.1 Project Plan Summary is new entries for the cost-performance index, % Reused, and % New Reusable.  Review these entries and explain their purpose and method of calculation.  If the students’ support tool calculates these values, walk through a brief class exercise where the students calculate the values by hand.  Otherwise, they will probably not understand what the values mean or how to use them.

# 7.5	PSP1.1 Programming Exercise Assignments

Assign at least one programming exercise for the PSP1.1 process.  If the course schedule permits, one or more additional PSP1.1 exercises would provide students with additional practice using PSP’s PROBE estimating method. The SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html, provides a number of suitable programming exercises.

When assigning PSP1.1 exercises, start with a brief workshop that explains the program requirements, walks through an example of any non-trivial mathematical logic, and demonstrates for the students how to plan their programming work.  Also, again review the assignment report specification that is included in the assignment kit and emphasize any areas that were problematic in previous assignments.

# 7.6	The Interim Report Assignment

The interim report assignment has the students define and document a process for analyzing their data and producing the report.  They then use this process to perform the analyses and to produce the report.  In producing this report, students are to analyze their size and time estimating data, examine their programming productivity, review their development time distributions, and analyze their defect data.  They are then to produce a report of these analyses.  The objective of the report is to establish a baseline against which they can measure and evaluate improvements in their personal performance.

When describing this assignment, emphasize the importance of producing a simple process and then using that process to guide and report on the work.  While process definition is not difficult, it does take practice to do it properly.  This exercise is the students’ opportunity to define a process in a learning environment.

The report data-analysis work should consume the bulk of the time required to complete the assignment, and it is adequately described in the assignment kit.  Have the students read through the assignment directions in class and ask questions about any aspects that are not clear.

# 7.7	The Design and Code Review Checklist Assignment

The design and code review checklists assignment requires that the students analyze their defect data to produce personal design review and code review.  Students need these checklists when they use the PSP2 and PSP2.1 processes to write programs.  Briefly discuss the checklist assignment and make sure students understand how to do the required work.  Also point out that the textbook discusses these checklists in Chapter 9.

# 7.8	Grading PSP1.1 Programming Assignments

The assignment evaluation criteria for the PSP1.1 exercises are the same as those for PSP1, with some additions.  Again, additional criteria are denoted by bold italic text on the grading checklist.  The PSP1.1 grading checklist is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.  The PSP1.1 items to check are discussed in this section. Refer to the previous chapters for discussions of the PSP0, PSP0.1, and PSP1 criteria.

When grading the PSP1.1 programs, focus on the new items as well as on those that students found difficult in earlier assignments.  However, check all the PSP0, PSP0.1, and PSP1 process items to ensure students do not regress.

## 7.8.1	Project Plan Summary

You do not need to check the Project Plan Summary entries calculated by the students’ support tool.  However, you must check any manual calculations made by the students.  If the results are incorrect, ask them to describe how they arrived at the numbers they used in the form.  Also verify that the planned times for each phase are distributed in about the proportion indicated by the To Date % value from the prior program, and that the planned and actual size values are reasonable.

Check the Cost-Performance Index (CPI) values to see how the students are performing and provide feedback that starts them thinking about what CPI means in terms of projects and management.  If the support tool does not automatically calculate the CPI values, verify that they are correct.

Also, check the % Reused and the % New Reusable values to determine if students are taking advantage of the potential reuse opportunities in the PSP exercises.  If not, urge them to do so.  It could save them a substantial amount of time, particularly for the remaining exercises.  If the support tool does not automatically calculate the % Reused and the % New Reusable values, verify that they are correct.

## 7.8.2	Consistency Checks

Repeat the consistency checks you performed for the previous process level for the PSP1.1 programs, starting with a review of the PSP1.1 Project Plan Summary to determine if the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Finally, check the students’ time and defect logs and ask them to explain any unusual values.

# 7.9	Grading the Interim Report Assignment

Grading the interim report focuses on three main concerns.

- Did students produce a usable process and then use it?

- Did they make a competent analysis of their data?

- Did they establish a clear and complete baseline for evaluating improvement?

This grading checklist for the interim report is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.

# 7.10	Grading the Design and Code Review Checklists

The grading checklist for the design and code review checklist is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.  Ensure that the student used their historical defect data to create checklist items that cover their highest priority defects.  Ensure that their defect analysis demonstrates a clear understanding of their data.

# 7.11	PSP1.1 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP courses and from analyzing the data gathered from thousands of PSP class programs. Consider these points as you give lectures, answer questions, and advise students.

At this point in the course, encourage students to start thinking about using the PSP on the job.  Outside of the class environment, they will need to design processes, analyze and use data, and deal with managers on management’s terms.  The interim report assignment is a student’s first step in preparing to transfer the PSP course skills to the workplace.  When discussing this report assignment, encourage students to think of it in practical terms, rather than as a way to complete a requirement for the PSP course.

8.	Teaching PSP2 Topics

This chapter covers the objectives for the PSP2 process and lists the knowledge the students should gain after listening to the PSP2 lectures and using PSP2 to write one or more programs.  It assumes that the students have completed the PSP materials covered in the previous chapters and have started developing a program using the PSP1.1 process. It briefly describes common questions and issues you may encounter while teaching the PSP2 process.

The chapter also briefly describes the lecture the SEI makes available for the PSP2 process. It also references the various tutorial and exercise materials used to teach PSP2, available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html. The latter sections of the chapter explain how to grade PSP2 assignments.

# 8.1	PSP2 Objectives

The PSP2 process lectures and exercises focus on achieving six principal objectives.

- Providing an overview of software quality and explaining the PSP quality focus.

- Describing the economics of software quality.

- Discussing defect removal methods.

- Introducing design and code reviews and explaining their principles and methods.

- Describing the PSP quality measures and showing how they are obtained and used.

- Describing the principles and general approach to defect prevention.

The students acquire the following knowledge and capability from listening to the PSP2 lectures and from successfully completing the PSP2 exercises and tutorials.

- Why defects are the principal quality focus of the PSP.

- Why testing alone cannot produce quality products.

- The relative costs of removing defects in reviews, inspections, unit testing, and system testing.

- What design and code reviews are, how they are performed, and why they are effective.

- What yield is and how process and phase yield differ.

- Principal elements of the COQ measures and how they are determined in the PSP.

- Why it is generally best to do code reviews before compiling or testing a program.

- How reviews differ from inspections.

- Why defect prevention is important and how it is typically performed.

# 8.2	PSP2 Lecture: Course Overview Part II

If the course format you are using has a break between the PSP1.1 and PSP2 topics, consider giving the PSP2 Course Overview lecture before the PSP2 Software Quality lecture.  The course overview discusses the remaining topics, reviews the class ground rules, and outlines the schedule for the final 5 days of the course.  The key topics of the overview lecture are described in this section.

## 8.2.1	Course Ground Rules

The course ground rules were covered in the opening lecture, but you should briefly repeat them to ensure that everybody remembers them.  The topics included are

- course prerequisites

- course objectives

- your ground rules for interacting with students

- your availability to students

- handling of incorrect work (return it for correction and resubmission)

- what you expect from students

- how you will grade their work

## 8.2.2	Course Agenda

Next, review the course schedule and give a brief overview of the topics that you will cover.  This is also an opportune time to ask students if they have any questions about the materials already covered, or about the plans for the final sessions.  Students rarely have questions at this point, but ask in case anyone does.

# 8.3	PSP2 Lecture: Software Quality

The Software Quality lecture covers the topics described in this section.

## 8.3.1	What Is Quality?

Your initial objective when giving this lecture is to explain that defect management is an important facet of software quality. Customers are not usually concerned about defects unless they cause problems, increase their costs, or delay their work.  However, defect management is enormously important to software developers.  Defects force them to rework old, defective code instead of developing new code.  They increase development costs and delay project schedules by weeks or months as developers fix defects in test.  As a result, most organizations spend half or more of their development time and effort fixing defects.

## 8.3.2	The Economics of Quality

An enormous amount of data show that removing defects before test is faster, cheaper, and more efficient than removing them in test.  Testing is essential, but it must be used properly.  Testing is best at finding those few complex system-level defects that are hard to identify in reviews and inspections.  For volume defect removal, however, testing is the wrong method to use.  With the PSP, developers learn that there are other more efficient methods to remove defects.  When developed with today’s common methods, even moderately sized programs have hundreds to thousands of defects that must be found and fixed.  In economic terms, when you must perform a task hundreds or thousands of times, it is wise to first determine the fastest and most effective way to do that task.  For volume defect removal, overwhelming evidence show that reviews are the fastest and most effective method.

## 8.3.3	Defect-Removal Methods

During this part of the lecture, describe the most common defect-removal methods and discuss their costs and effectiveness.  Explain to the students why some removal methods are more effective than others.  By using PSP data, they can analyze the effectiveness of various defect-removal methods and determine how to improve both the quality of their products and the productivity of their work.

## 8.3.4	Reviews

While design and code reviews are relatively simple in concept, they are not fully effective unless done properly.  Try to persuade the students to review their own work, but do not expect your lecture to convince them.  Developers are usually willing to do reviews in a class setting, but they must see their own data to appreciate the enormous benefits of doing thorough and complete reviews.  If you can convince them to do thorough reviews in the PSP class, they will have the data to convince them to do their reviews properly thereafter.

## 8.3.5	Design Reviews

Design reviews are discussed in the design verification lecture described in Chapter 9 of this guide, but during the PSP2 lecture, stress that effective design reviews require more than just reading the design with a checklist.  Effective design reviews require design analysis, which does take time.  The key consideration is economic.  Just how important is it to find the defects before test?  It is difficult to change the programmers’ common perception that their principal objective is to get programs into test as quickly as possible.  Instead, their objective should be to get defect-free programs into test as quickly as possible.

## 8.3.6	Quality Measures

Next, review all of the key PSP quality measures. Make sure that you spend enough time discussing yield to ensure that the students understand this measure and how to use it.

## 8.3.7	Reviewing Before Compile

During this discussion, you may find that students have strong opinions regarding whether or not to review their code before compiling. Do not allow the class to become polarized over this issue.  Increasingly, modern programming languages and environments do not have compile steps, so the debate would be pointless.  Your objective is to convince the students to thoroughly examine their designs and code before they submit them to test.  Unfortunately, experience shows that when developers compile their programs before reviewing them, once they get a clean compile, they assume that the program is defect-free and try to run a quick test.  This quick test normally reveals a single defect.  Then, after they fix that defect and run another quick test, there is just one more pesky defect, and then another, and then another.  By the time the program passes all tests, the developer has wasted a great deal of time.  The objective of this part of the lecture is to get the students to try reviewing first and to gather and use their own data when they do.  Then they can use these data to make sound decisions about what works best for them.

## 8.3.8	Defect Prevention

Explain to students that defect prevention is an integral part of the PSP.  Using a defined process, defect recording, sound plans, and improved design practices all reduce the likelihood of mistakes and improve product quality.  Therefore, these actions must be part of an overall defect prevention strategy.  However, even when developers use all of the PSP’s methods, they still inject defects.  The defect-prevention program is used to attack these residual problems.  While students will not specifically consider defect-prevention methods during the PSP course, they should consider using defect-prevention methods on their TSP teams.

## 8.3.9	Questions

The most commonly asked questions for the PSP2 Software Quality lecture concern recording defect data, using a debugger, and quality management.  Below are some example questions and answers about these topics.

Q:  Why should I bother recording the defects I find in compiling?   Since the compiler finds these defects, why do I care?

A:  Your real interest is in the mistakes you make that cause the defects, not in the defects.  With data, you can often figure out how to prevent mistakes.  The problem is that even your simple mistakes, like typos, misspellings, and omissions, sometimes produce defects that the compiler will miss.  Most of these defect types, when missed by the compiler, can be quickly found in test.  However, every so often, one gets past compiling and testing and causes untold user problems.  Unfortunately, there is no easy way to tell which mistakes will cause defects that the compiler will find and which produce defects that it will miss.  So, if you are trying to eliminate all of the defects from your finished products, you must gather data on the compile defects because they will provide clues that will help you to prevent about half of the mistakes that you make.

Q:  But if I do the review after compiling, I would only need to find the defects that the compiler missed.  Why doesn’t that work just as well?

A:  If you do equally thorough reviews before or after compile, it doesn’t matter when you do them.  However, the evidence is clear that when developers defer their reviews until after compile, the reviews are much less effective and program quality, development costs, schedule, and performance all suffer.  In the class, you are required to complete the reviews first.  Later, when you are working on a TSP team, you might want to have some team members do their reviews before they compile, and others do them afterward.  Then you can compare the quality of these two sets of programs and see which have the most defects in test.

Q:  I’ve got a marvelous debugger that has really accelerated my testing.  How can a code review be as fast or effective?

A:  There are two reasons.  First, a debugger can only track the progress of one test at a time.  This one test only covers one set of paths with one set of variables and parameters.  By using sound review practices, you can see all of the possibilities at once and see defects that you could not find without running the debugger with a large number of tests.  Second, to use a debugger properly, you must know the expected variable values at each step of the program.  If you are going to make a detailed enough analysis to determine all of these values, why not take a little more time and do a thorough review?  You can still use the debugger to check your results.  Debuggers can be very helpful for tracking down the occasional puzzling defect, but they are not an efficient way to find volumes of defects in testing.

Q:  My management doesn’t seem to care about quality.  Their only concern is releasing on schedule.  How do I convince them that quality is important?

A:  Regardless of appearances, your management almost certainly does care about quality; they just don’t understand the economics of quality and how quality work can save them time and money.  Suppose, for example, that you asked them, “Does the product have to work?”  They would likely get angry and say, “Of course it does.”  So quality is certainly important at the product level.  But few managers realize what poor quality practices cost them in time, money, and customer satisfaction.

There are a couple of ways to get managers to recognize the importance of quality.  The first and most effective way is to convince them to introduce the TSP and to attend the introductory executive seminar.  The other way is to gather test data and show them that test time is directly related to the number of test defects.  Since test time is often 30% to 50% of most project schedules, they should be interested in reducing test time.  This in turn requires that they reduce the number of test defects.  After managers understand this, the PSP and TSP methods will look more attractive.

# 8.4	PSP2 Process Tutorials

When students are asked to do something new or unfamiliar, augment the lecture with a process tutorial.  Tutorial materials are available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.

This tutorial should describe the new entries in the PSP2 forms and scripts and any new process elements.  The new process elements for PSP2 are design and code reviews, defect estimating, and several quality measures.  Since these new topics have all been covered in the previous lecture, a brief process overview should be adequate.

# 8.5	PSP2 Programming Exercise Assignments

Assign at least one programming exercise for the PSP2 process.  If the course schedule permits, one or more additional PSP2 exercises provides students with additional data on their work and gives them more practice with PSP’s PROBE estimating method and with design and code reviews. The SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html, provides a number of suitable programming exercises.

When assigning this exercise, start with a brief workshop that explains the program requirements, walks through an example of any non-trivial mathematical logic, and demonstrates for the students how to plan their programming work.  Also, again review the assignment report specification that is included in the assignment kit and emphasize any areas that were problematic in previous assignments.

# 8.6	Grading PSP2 Programming Assignments

The assignment evaluation criteria for the PSP2 exercises are the same as those for PSP1.1, with some additions.  Again, additional criteria are denoted by bold italic text on the grading checklist.  The PSP2 grading checklist is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.  The PSP2 items to check are discussed in this section. Refer to the previous chapters for discussions of the PSP0, PSP0.1, PSP1, and PSP1.1 criteria.

When grading the PSP2 programs, focus on the new items as well as on those that students found difficult in previous assignments.  However, briefly check all the PSP0, PSP0.1, PSP1, and PSP1.1 process items to ensure students do not regress.

## 8.6.1	Project Plan Summary

You do not need to check the Project Plan Summary entries calculated by the students’ support tool.  However, you must check any manual calculations made by the students.  If the results are incorrect, ask them to describe how they arrived at the numbers they used in the form.  Also verify that the planned times for each phase are distributed in about the proportion indicated by the To Date % value from the prior program, and that the planned and actual size values are reasonable.

Verify the planned and actual defect entries to ensure that the defect plans were based on actual data.  Also check that the planned and actual review rates were low enough to provide a suitable yield.  A common problem is that developers plan too little design review or code review time.  Emphasize that if they don’t plan to do quality work, they probably won’t.  The second and most serious issue is that students rarely spend the planned amount of time performing the reviews.  Check the actual review times for each assignment and, if they are too low, urge the students to spend more time in their reviews.

## 8.6.2	The PIP Form

When developers have low yields, they should identify the problem on their PIP forms and list planned actions to obtain better results in the future.  If they have not done this, reject their programming assignment and require that they add a completed PIP containing this information.  When they resubmit the assignment, check the PIP to make sure that the planned actions will likely improve their yield.  Don’t accept poor yield reviews without requiring that the student take corrective action!  Then check the next assignment to see if they actually did what they said they would do.

## 8.6.3	Consistency Checks

For the PSP2 programs, repeat the consistency checks you performed for the previous process level.  Start with a review of the PSP2 Project Plan Summary to determine if the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Finally, check the students’ time and defect logs and ask them to explain any unusual values.

In a sense, yield is a consistency issue.  If the students’ yields are low, it generally means that several parts of their processes are inadequate.  If this seems to be the case, check to see if they planned properly, updated the checklist, used the new checklist, and spent adequate time doing the review.  Once students take all of these steps, their yields should improve.

Another important consistency check is for defect-removal rates.  If students do not find about 2 to 3 defects per hour during design reviews or about 5 to 10 defects per hour during code reviews, they probably need guidance.

# 8.7	PSP2 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP courses and from analyzing the data gathered from thousands of PSP class programs. Consider these points as you give lectures, answer questions, and advise students.

The goal of PSP2 is to introduce design and code reviews.  Generally, when working on PSP2 assignments, students find few if any defects during design reviews.  This is usually for two reasons.  First, they do not have a very complete or precise design to review.  Second, their reviewing methods are probably still rudimentary.  They will not find many sophisticated design problems by merely reading through their designs with a checklist.  Instead, they must complete a careful design analysis.  Since design completeness and design analysis are the principal topics of the PSP2.1 lectures and exercises, there is no need to do more than mention them now.

The problem to focus on for PSP2 is code reviews with poor yields.  Consider two things in addressing this problem.  First, when students hurry through their reviews, they will get low yields.  Suggest that they plan a realistic amount of time for review and then keep reviewing until they have spent that amount of time.  They may have to repeat parts of their checklists but by forcing themselves to continue reviewing until they have spent the planned amount of time, they will slow down and do much better reviews.  Second, without constant reminders, students rarely update their checklists to take advantage of their latest defect data.  Consistently doing so can make a major difference in review yield.

9.	Teaching PSP2.1 Topics

This chapter covers the objectives for the PSP2.1 process and lists the knowledge the students should gain after listening to the PSP2.1 lectures and using PSP2.1 to write one or more programs.  It assumes that the students have completed the PSP materials covered in the previous chapters and have started developing a program using the PSP2 process. It briefly describes common questions and issues you may encounter while teaching the PSP2.1 process.

The chapter briefly describes the lectures the SEI makes available for the PSP2.1 process. It also references the various tutorial and exercise materials used to teach PSP2.1, available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html. The latter sections of the chapter explain how to grade PSP2.1 assignments.

# 9.1	PSP2.1 Objectives

The PSP2.1 process lectures and exercises focus on achieving eight principal objectives.

- Explaining the role of design in software development and why it is important.

- Showing how to precisely represent designs.

- Teaching design verification methods.

- Describing the issues involved in using PSP in practice.

- Providing students with the knowledge, experience, and conviction to continue using the PSP.

- Explaining the TSP process, its principles, and methods.

- Familiarizing students with their obligations as software professionals.

- Motivating some students to become PSP instructors and TSP coaches.

The students acquire the following knowledge and capability from listening to the PSP2.1 lectures and from successfully completing the PSP2.1 exercises and tutorials.

- Why design is important and how to precisely represent a design.

- What formal notations are, why they are important, and how to use a simple formal notation.

- How to use the PSP design templates to represent a design.

- Why and how to verify a design.

- How the PSP design templates relate to other software design methods.

- What the TSP is, where it can be used, and why it is effective.

- Students’ obligations as software professionals.

- Steps involved in becoming a PSP instructor and TSP coach.

- Why and how to become an SEI certified PSP practitioner.

# 9.2	PSP2.1 Lecture: Software Design I

The PSP2.1 Software Design I lecture covers the topics described in this section.

## 9.2.1	Design as a Learning Process

The opening section of this lecture should emphasize three main points:

- The best designers follow a dynamic process that leaps from level to level.

- A quality design must have a precise representation.

- The PSP has been designed to work with any design method.

Since developers often think of a process as constraining and limiting their creativity, encourage class discussion of these topics.

## 9.2.2	Design Completeness

During this part of the lecture, describe the logic behind the PSP design templates.  The simplicity of the PSP design logic is one of its major attributes.

## 9.2.3	Design Representation

Representing designs precisely substantially improves the quality of students’ work. Many different design representations exist. The method described in this lecture is a simplified version of the Z (pronounced “Zed”) notation.  While you should urge the students to use this notation when designing their exercise programs, they will likely encounter problems when doing so.  A design notation should be an aid to thought, but until students are fluent with the notation, it will not help them think and can actually slow them down.  However, they should practice using these methods where they can.  By doing so, they will gradually build the familiarity needed to use the notation more widely.  Emphasize that imprecisely represented designs often cause problems by introducing defects in an otherwise sound design and by making it difficult to identify flaws in a poor design.

## 9.2.4	The Operational Specification Template

Explain the Operational Specification Template (OST) by using an example and then ask the students to produce an OST for a specific program.  Note that they may need many OSTs to cover the key functions of a single program.  The OST can be particularly helpful for identifying a program’s error and exception conditions.

## 9.2.5	The Functional Specification Template

Use an example to explain the Functional Specification Template (FST) and then have the students produce an FST for a specific program.  Explain that the FST attributes can be used both to specify variables and parameters and to identify class relationships and inheritance.

## 9.2.6	The Logic Specification Template

Explain the Logic Specification Template (LST) by using an example and then have the students produce one for a specific program.  While reviewing the LST, explain the principles and methods of good pseudocode design.

## 9.2.7	Using Design Templates

After developers complete PSP training, they are often unsure how to use the PSP design templates when developing larger programs.  Your objective during this discussion is to provide them guidance on this question.

## 9.2.8	Questions

The most commonly asked questions for the PSP2.1 Software Design lecture concern agile methods, productivity, and UML.  Below are some example questions and answers about these topics.

Q:  Books about agile methods say to use the code as the design documentation and not to produce a lot of design documents.  What does the PSP say about this approach?

A:  Agile methods focus on designing small programs and, as pointed out in the PSP lecture and textbook, most developers can develop small programs without producing a documented design.  However, if you intend to use these smaller programs as parts of a larger system, you need documented designs, whether you use agile methods or not.  Too many people are involved in the design and implementation of large systems to rely on the code as the sole means of documentation.  It is often hard to decipher well-documented code, even if you were the developer.  Also, since source code comments rarely include high-level design topics, the lack of a documented design can cause confusion and mistakes.  So, if you only expect to work on small programs and if these programs will never be used as parts of larger systems, you do not need to worry about using the PSP design methods.  However, while in this class, you must use them.

Q:  You state that when I produce a design, my productivity will decrease.  How big of a drop is this?

A:  The data that show the impact of design on development time were gathered from over 8,000 programs that were written in PSP courses.  These data show that those who spent more time in design than in coding took an average of about 50% longer to write their PSP programs than those who spent little or no time in design.  Even though these results vary widely by individual and even by PSP exercise, the results are clear. Creating designs takes time and the benefits of the additional work are not usually apparent during the design-code-unit-test part of the development cycle.

If you want to produce a reasonably complete and documented design for your programs, you can expect to spend about 50% more time.  However, if a program is part of a larger system, the added time you spend on design is saved several times over in finding defects in integration test, system test, acceptance test, and use.  Therefore, before producing a design, consider whether the design documentation is worth the extra effort.  If you were developing small stand-alone programs, your principal benefit would be practice in producing quality designs.  If your programs must work in larger systems that must be safe, secure, reliable, or easily enhanced, then it is worth the effort to produce a documented design.

Q:  I use UML and would prefer to do my PSP exercise designs in UML, rather than with the PSP design templates.  Is this OK?

A:  During the PSP course, you should use the PSP design templates to record your designs.  However, the PSP does not specify the methods you can use to produce these designs.  If you want to produce the design with UML and then map that design onto the PSP templates, that is perfectly acceptable.  After you have a complete UML design, it is relatively easy to map it onto the PSP templates.  If you encounter problems, it is probably because your UML design is incomplete or contains errors.  Also, just by mapping your UML designs onto these templates, you will likely expose oversights and errors.  After the course, consider using the PSP templates to record and verify your designs, even when using UML.

# 9.3	PSP2.1 Lecture: Software Design II

The PSP2.1 Software Design II lecture covers the topics described in this section.

## 9.3.1	The Design Process

Begin the lecture by showing students how to use large-scale development practices to write small programs.  While the practices taught in the PSP course up to this point usually save time, this is not generally true for the PSP2.1 practices.  Most programmers can write small programs without producing a design.  However, designs are almost always needed for large systems.  To have the design skills they will later need, students should use the PSP design methods when developing the PSP2.1 exercise programs.  They should continue to use these methods whenever they can.

## 9.3.2	UML and the PSP

The PSP templates map directly to several of the Unified Modeling Language (UML) design diagrams.  This makes the PSP templates potentially useful as a simplified framework for introducing UML and as an aid for verifying UML designs.

## 9.3.3	State Machines

State machines are relative simple in concept, but can involve very complex logic.  Designs that use multiple system states are often defective because the design was not structured or analyzed as a state machine.  The advantage of treating programs as state machines is that the designs can be analytically verified.  However, the verification process can be complex and time-consuming for complex state machines.  But when a state machine is too complex to verify, it is probably too complex to test and should be redesigned.  Given careful thought, it is often possible to restructure large and complex multi-state systems into multiple, smaller state machines that can each be independently verified.

Using the PSP state-machine methods, students can analyze fairly complex systems and identify defects that other methods often overlook.  Spend the time needed for students to understand the principles and methods of state-machine design and analysis.  Then assign at least one classroom exercise on designing a simple state machine.

## 9.3.4	State-Machine Verification

During the design verification section of the PSP2.1 lecture, emphasize that creating a precise representation is essential before attempting design verification.  The SEI’s suggested State-Machine lecture includes one classroom exercise for verifying a state-machine design.  Work through this exercise and make sure that the students understand state-machine verification methods.

## 9.3.5	Questions

The most commonly asked questions for the PSP2.1 Software Design II lecture concern selecting states and analyzing state machines.  Below are some example questions and answers about these topics.

Q:  When designing a state machine, how do you decide how many states are needed and what they are?

A:  Unfortunately, there is no proven method for defining the states of a state machine.  In fact, there is no general method for simplifying state machines or even for determining if it can be simplified.  Therefore, you must try various alternative designs until you find one that does what you need, and is sufficiently simple and well structured so that it can be analyzed and tested.

Q:  Can you use these PSP state-machine methods to analyze existing programs?

A:  Yes, state machine design and verification methods can be used to analyze existing programs.  However, you will often find that it is difficult to identify the states in a state-machine program that was not developed with state-machine design methods.  This is because the states will probably not be explicitly identified.  Also, when the states of a state machine are hard to identify, it often means that possible states were overlooked.  Such programs are usually defective and extremely difficult to test and repair.  By developing a State Specification Template for such a program, you can identify its states and determine the state transitions.  You can then use the PSP state-machine verification methods to find and fix its defects.

# 9.4	PSP2.1 Lecture: Design Verification

The PSP 2.1 Design Verification lecture covers the topics described in this section.

## 9.4.1	The Need for Design Verification

This brief discussion is to describe the intent of the verification lecture, which is to expose students to various ways of finding design defects.  As previously stated, the principal question to answer when deciding whether or not to produce and verify a design is the cost versus benefit of doing so.  There is no way to answer this question in the abstract since the costs and benefits of a design depend on the product being developed, how it is to be tested and used, and the importance of finding every design defect.

## 9.4.2	Symbolic Execution

Symbolic execution is a conceptually simple, but specialized approach that can be very powerful.  Symbolic execution is particularly useful when used in conjunction with trace tables.  While this subject is not covered explicitly in the textbook, make sure the students know how to use symbolic execution in trace table analysis.

## 9.4.3	Execution Tables

The execution table provides a brute-force way to check logic.  It is straightforward and can quickly identify a surprising number of defects.  However, don’t spend much time explaining execution tables, as this discussion serves only as an introduction to the more general trace table method.  Do, however, walk through a simple exercise with the students to demonstrate how the method works.

## 9.4.4	Trace Tables

A trace table is an execution table with symbolic execution and case checking.  The principal advantage of the trace-table method is that it can cover a large number of possible tests with a single check.  In fact, just by setting up the trace table and defining all of the possible cases, developers often find more defects than they do during the actual verification step.  The trick with execution and trace tables is to produce a standard form and to make as many copies as needed to run all of the cases.  Filling in the variable values on these forms can then be done quite quickly and usually identifies design defects right away.  To show the students how simple and effective the trace-table method can be, assign a class exercise for a program that contains a subtle defect.

## 9.4.5	Verifying Program Correctness

While these verification proofs were first published many years ago, they still provide a useful mental framework for analyzing loop constructs.  One way to use these techniques is to think through the proof questions while designing loop structures.  This activity often helps students identify and prevent design problems.  These proof methods can also be coupled with the trace-table method whenever the proof questions require careful analysis.

## 9.4.6	Verification Discussion

Encourage students to ask questions and get them to try these verification methods in class.  They should consider using them whenever the logic of a construct is not obvious or when a design is known to be defective.

## 9.4.7	Questions

The most commonly asked questions for the PSP2.1 Design Verification lecture concern debuggers, complexity, and formal proofs.  Below are some example questions and answers about these topics.

Q:  The trace-table and execution-table methods look like manual debugging.  Why are they any better than just using the debugger?

A:  There are two main differences.  First, with a trace table, you must produce the trace-table form and define all of the logical cases.  Second, you must actually trace through the program a step at a time and determine exactly how the program is supposed to work.  While tracing the program’s actions involves the same steps that the debugger follows, the difference is that you are thinking through what the program does rather than just observing the debugger doing it.  The thinking is the important part.  For example, while analyzing a construct, you often see things that the debugger could not find, like an unanticipated exception condition.  Even though you never looked for this specific problem, thinking through the trace-table steps exposed it.

Q:  Wouldn’t the trace-table method be hard to use with a large or complex program?

A:  Yes.  The problem with all of the manual verification methods is that they are cumbersome, time-consuming, and error-prone when used with large programs.  But even then, these methods are much more efficient and cost effective than testing.  To verify really large programs, break them into smaller parts that you can verify.  While this is not always possible, it can be done more often than you might think.  Even when you cannot break a large program into multiple smaller parts, you can still usually isolate the troublesome logical constructs and check them with a trace table.  Even if each construct involves many hundreds to thousands of lines of code, the loop logic usually involves only a small percentage of the code.  In those cases, produce a simple pseudocode version of the significant logic and check it.  This is a very powerful way to check complex logic, particularly when you are making small modifications to large programs.  By decomposing the logic, you often find latent problems you could not find any other way.

Q:  How do the PSP methods compare to the formal proof methods that are taught in many computer science programs?

A:  They represent a small step in the direction of formality.  When you are familiar with formal methods and where they apply, you should certainly use them.  However, in this course, you must document your designs with the PSP design templates even if you use formal methods.  Without training and experience, most developers do not know how to use formal methods to write programs that they can formally verify.  The objective of the PSP design and verification lectures is to introduce a few basic formal concepts that developers can use with the programs they currently produce.

# 9.5	PSP2.1 Lecture: Using the PSP

The PSP2.1 Using the PSP lecture covers the topics discussed in this section.

## 9.5.1	Working on a TSP Team

Now that students have learned the PSP, the next challenge is to get them to apply it.  Individual developers can use the PSP in their personal work, but experience shows that few actually do so unless they work in a group where all of the members use the same methods.  This portion of the lecture explains what the TSP is, describes how it works, and explains why using the PSP on a TSP team is both enjoyable and rewarding for the developers and effective and efficient for their projects and management.

## 9.5.2	Being a PSP Instructor and TSP Coach

This lecture section provides a brief description of how to become a PSP instructor and a TSP coach.  The most effective way to give this lecture is for you to describe your experiences as an instructor and coach and explain why you find it to be a rewarding occupation.

## 9.5.3	Concluding Comments

The final lecture should start the students thinking about what they want in their professional life and, hopefully, to get them to consider the potential rewards of doing truly superior work.

## 9.5.4	Questions

The most commonly asked questions for the PSP2.1 Using the PSP lecture concern introducing TSP, large projects, and maintenance work. Below are some example questions and answers about these topics.

Q:  We don’t use the TSP in my organization.  What is the best way to introduce it?

A:  The best way is to get the SEI or one of its transition partners to meet with your management and explain the benefits of using the TSP.  If your management isn’t interested in such a meeting just yet, don’t give up.  Explain the methods to your peers and immediate management and gradually build support for piloting a TSP project in your organization.  With this support behind you, management is more likely to be interested.  Don’t get discouraged if this takes longer than you think it should.  Remember that every significant change starts with one person and you could be that one.

Q:  I can see how to use the TSP with a small team of a dozen or so developers, but my organization has a few really large projects.  Can the TSP be used there too?

A:  Yes.  The SEI has developed a multi-team version of TSP, called TSPm.  This process has been used with projects of close to 100 developers who are geographically dispersed.  It is designed for distributed team projects of up to about 150 to 200 members.  Beyond that, a more specialized process is needed.  The SEI can work with organizations to customize a process for large systems and to support its initial introduction to large project teams.

Q:  I do maintenance work.  Is there a TSP process that works in this environment?

A:  Yes.  There is a functional version of the TSP that is designed for groups of developers who do related, but relatively independent work.  Using a sports analogy, the traditional TSP is for groups that work like baseball or basketball teams where everyone is following a consistent set of rules and guidelines and striving for a common goal.  The functional TSP, or TSPf, is for teams that are more like track or wrestling teams.  In this case, the team shares a common facility and coach and even a common objective, but the individual members work independently.  While such groups typically provide support to each other, the members each work mostly by themselves.  If this describes your organization, the TSPf process is the appropriate one to use.

# 9.6	PSP2.1 Process Tutorial

When students are asked to do something new or unfamiliar, augment the lecture with a process tutorial.  Tutorial materials are available from the SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html.  This tutorial should describe the new entries in the PSP2.1 forms and scripts and any new process elements.  For PSP2.1, the new topics are the PSP2.1 process changes, design templates, and design verification methods.

The PSP2.1 process adds the four PSP design templates and a family of design verification methods.  Typically, these topics should all be accompanied by tutorial or classroom exercises.  The PSP2.1 process also includes an updated design review script and checklist that uses the PSP design templates and the verification methods covered in the lecture.  The following paragraphs describe some relevant exercises.

For each of the four PSP design templates, assign at least one exercise where the students produce a design and record it on the appropriate design template.  When producing this design, students must use the appropriate design template and should try to use the logic notation described during the state-machine lecture.  After they are done, ask one or two student volunteers to describe the designs they produced and then discuss them with the class.  Conclude the session by having students turn in their designs.  Review these exercise designs to identify areas where students had problems and if necessary, meet with specific students to make sure they know how to use the design template properly.

Assign at least one classroom exercise for each of the verification methods discussed in the lecture and ask one or more student volunteers to describe how they performed the verification.  Then hold a class discussion.  Conclude by having students turn in the completed exercises.  Check the results and if any students had trouble, meet with them to resolve the problems.

Since PSP2.1 introduces a number of cost-of-quality (COQ) measures that are calculated automatically by most PSP support tools, consider having a classroom exercise to verify that the students understand COQ and how its values are calculated.  This exercise can be very brief with a simple scenario giving the times and defect densities a developer had for each phase of a small project.  Then ask each student to calculate the % Appraisal COQ, % Failure COQ, A/FR ratio, and PQI.  Check that they all got the correct answer and, for any whom did not, clarify any confusion or misunderstanding.

The PSP2.1 process also introduces the upper and lower prediction intervals.  If students already wrote an exercise program to calculate the prediction interval, no additional classroom exercise is needed.  However, if they did not, assign a brief exercise that has students calculate the size and time prediction intervals for an example project plan.  To minimize the calculations involved, consider providing a worksheet that contains most of the calculated values, but requires students to use these numbers to calculate the range, UPI, and LPI values.

# 9.7	PSP2.1 Programming Exercise Assignments

Assign at least three programming exercises for the PSP2.1 process.  If the course schedule permits, one or more additional PSP2.1 exercises provides students with additional data on their work as well as more experience using PROBE, completing design reviews, doing code reviews, producing designs, and using design verification methods. The SEI’s TSP/PSP Web site, http://www.sei.cmu.edu/tsp/psp.html, provides a number of suitable programming exercises.

In making each assignment, start with a brief workshop that explains the program requirements, works through an example of any non-trivial mathematical logic and walks the students through planning their programming work.  Also, again review the assignment report specification in the assignment kit and emphasize any areas that were problems with prior assignments.

# 9.8	The Final Report Assignment

The final report assignment requires the students to update the process they used for the interim report and then use this process to perform the required analyses and produce the final report.  When producing the final report, students must complete all of the analyses called for by the assignment kit and use all of the data from all of the exercise programs they developed thus far.  The objective of this assignment is for the students to determine how the PSP impacted their personal performance and to consider how they will continue to improve in the future.  They should then set goals for the next stage of their personal improvement.

The report data-analysis work should take the bulk of the assignment time and it is adequately described in the assignment kit.  Have the students read over the assignment directions and ask questions about any aspects that are not clear.

# 9.9	Grading PSP2.1 Programming Assignments

The assignment evaluation criteria for the PSP2.1 exercises are the same as those for PSP2, with some additions.  Again, additional criteria are denoted by bold italic text on the grading checklist.  The PSP2.1 grading checklist is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.  The PSP2.1 items to check are discussed in this section. Refer to the previous chapters for discussions of the PSP0, PSP0.1, PSP1, PSP1.1, and PSP2 criteria.

When grading the PSP2.1 programs, focus on the new items, as well as those students found difficult in earlier assignments.  However, check the PSP0, PSP0.1, PSP1, PSP1.1, and PSP2 process items to ensure students do not regress.

## 9.9.1	Project Plan Summary

You do not need to check the Project Plan Summary entries calculated by the students’ support tool.  However, you must check any manual calculations made by the students.  If the results are incorrect, ask them to describe how they arrived at the numbers they used in the form.  Also verify that the planned times for each phase are distributed in about the proportion indicated by the To Date % value from the prior program, and that the planned and actual size values are reasonable.

With PSP2.1, four of the new items in the Project Plan Summary concern cost-of-quality.  If the students are using a support tool that calculates the COQ values, you do not need to verify the calculations.  However, it’s a good idea to review the COQ values to see what they tell you about a student’s work.  Then make appropriate comments regarding these values, particularly if A/FR is unusually low.

The other new PSP2.1 items the Project Plan Summary are the upper and lower prediction intervals.  Assuming that the students wrote an exercise program to calculate the prediction interval, they will know how this calculation is done so you do not need to check the values.  Do, however, comment on the values and what they imply about the student’s estimating ability and likelihood of overrunning a development plan.  Point out that by looking at their prediction intervals, they can determine the likelihood that they have made a serious under- or overestimate.

## 9.9.2	Consistency Checks

Repeat the consistency checks you performed for the previous process level for the PSP2.1 programs, starting with a review of the PSP2 Project Plan Summary to determine if the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Finally, check the students’ time and defect logs and ask them to explain any unusual values.

The new consistency item to consider for PSP2.l is the degree to which the students used the PSP design methods and templates, and whether they used any verification techniques while reviewing their designs.  It takes time for developers to build design and design review competencies, but the PSP course provides an opportunity for them to start.  Your guidance can help them to do so.

# 9.10	Grading the Final Report Assignment

Grading the final report focuses on three main concerns.

- Did the students produce a usable process and then use it?

- Did they perform a competent analysis of their data?

- Did they set realistic but challenging goals for personal improvement?

This grading checklist for the final report is available at the SEI’s TSP/PSP Web Site, http://www.sei.cmu.edu/tsp/psp.html.

# 9.11	PSP2.1 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP courses and from analyzing the data gathered from thousands of PSP class programs. Consider these points as you give lectures, answer questions, and advise students.

Keep in mind two very important things as you teach the PSP2.1 process: design is an investment and the principal objective is to get the students to use the PSP in practice.

## 9.11.1	Design as an Investment

Proper use of the PSP design and design verification methods improves product quality and, just as with code reviews, these methods take time to do correctly but save time in the long run.  However, design and design verification are different from code reviews in one important respect.  Most of the time developers save occurs after their work is complete, so many of them do not see a saving in their personal work, at least not until they work on a TSP team.  With the PSP, the easy part of quality management is reducing the volume of defects found in system testing.  However, after the high-volume defects are properly managed, a small number of residual design problems are left that are much more difficult to address.  These types of defects can be very expensive to find and fix in test and extraordinarily harmful when found by the program’s users.  One of the key challenges for the software community is moving beyond the simple code quality problems that are handled by PSP2 and on to the design-level quality issues that are more important and much more difficult to address.  This is the real message of PSP2.1, and it is a message you should impress on the students: the quality challenge for the future is to produce high quality designs.  Design quality is a long-term, life and death issue for the software profession.

## 9.11.2	Using the PSP in Practice

Convey to each student the message that producing quality work is the key to a happy and rewarding professional life.  The PSP provides the tools and framework for managing the quality of their personal work, but they must use these tools to reap the benefits.  By consistently using these methods, they will routinely meet their commitments and steadily improve their personal performance.  They will also have the satisfaction of producing truly superior products.  Your challenge as an instructor is to reach each student with this message and to motivate him or her to do truly superior work.  While you may not succeed every time, whenever you do, your reward will be the satisfaction of changing someone’s life.  That is the greatest reward a teacher can get.

References

| [Humphrey 95] | Humphrey, Watts S. A Discipline for Software Engineering. Reading, MA: Addison Wesley, 1995. |
| --- | --- |
| [Humphrey 97] | Humphrey, Watts S. Introduction to the Personal Software Process. Reading, MA: Addison Wesley, 1997. |
| [Humphrey 05] | Humphrey, Watts S. PSP: A Personal Improvement Process for Software Engineers. Reading, MA: Addison Wesley, 2005. |

®	Carnegie Mellon is registered in the U.S. Patent and Trademark Office by Carnegie Mellon University.

SM 	Personal Software Process and PSP are service marks of Carnegie Mellon University.

SM 	Team Software Process and TSP are service marks of Carnegie Mellon University.