# Instructor’s Guide

PSP Fundamentals

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to PSP Instructors

Table of Contents

1 Introduction	1

1.1 PSP Fundamentals Course Goals	1

1.2 The PSP Fundamentals Course Strategy – Learn By Doing	2

1.3 PSP Fundamentals Course Overview	2

1.4 The PSP Quality Focus	5

1.5 PSP Fundamentals Course Support Tools	5

1.6 A Self-Teaching System	6

1.7 Handling Skeptics	6

1.8 The PSP Learning Strategy	6

1.9 Gathering Data	6

2 General Teaching Guidelines	7

2.1 Scheduling the Course	7

2.2 Preparing to Teach	7

2.3 Class Discussions	7

2.4 General Assignment and Exercise Guidelines	8

2.5 Dealing with Students who are falling behind	8

2.6 Surfing the internet – Class Distractions	9

2.7 Disruptive Students	9

2.8 Handling Tough Questions	9

2.9 General Grading Guidelines	9

3 Interpreting Class Data	12

3.1 Class Data Feedback	12

3.2 Compiling Class Data	12

3.3 Class Feedback Charts	13

4 Blended Learning	18

5 Day 1	19

5.1 Introduction to Blended Learning	19

5.2 Course Overview	19

5.3 Lecture 1: Introduction to the PSP	20

5.4 PSP0 Tutorial	20

5.5 PSP0 Tips and Hints	21

5.6 Program 1: Mean and Standard Deviation	22

5.7 Grading PSP0 Assignments	22

6 Day 2	25

6.1 Class Data Feedback	25

6.2 Lecture 2: Fundamental Planning Concepts	25

6.3 Coding Standard Assignment	26

6.4 PSP1 Tutorial	26

6.5 Program 2: Program Size Counter	27

6.6 Grading PSP1 Assignments	28

6.7 PSP1 Tips and Hints	30

7 Day 3	31

7.1 Class Data Feedback	31

7.2 Lecture 3: Software Quality	31

7.3 Review Checklists Assignment	33

7.4 Code Review Exercise	33

7.5 PSP2 Tutorial	34

7.6 Program 3: Correlation and Significance	34

7.7 Grading PSP2 Assignments	34

7.8 PSP2 Tips and Hints	36

8 Day 4	38

8.1 Class Data Feedback	38

8.2 Lecture 4: Task and Schedule Planning	38

8.3 Program 4: Relative Size Table	39

8.4 Grading Program 4	39

8.5 Program 4 Hints and Tips	40

9 Day 5	41

9.1 Class Data Feedback	41

9.2 Capstone Exercise	41

9.3 Lecture 5: TSP Launch and Overview	42

10 Frequently Asked Questions (FAQs)	44

10.1 Day 1 FAQs	44

10.2 Day 2 FAQs	45

10.3 Day 3 FAQs	47

11 References	49

# Introduction

This guide provides teaching suggestions and links to support materials for teaching the PSPSM Fundamentals course.  This guide is written to be a reference for SEI-Authorized PSP Instructors.  It assumes that the instructor is already familiar with the PSP and focuses on how to teach the PSP to others.

The suggestions in this guide are based on the experiences of instructors at the Carnegie Mellon® Software Engineering Institute (SEI) and those of many other experienced instructors who have taught the SEI’s Personal Software Process (PSP) methodology to thousands of students and professional software developers.

A transition guide has been developed for those instructors teaching previous versions of the PSP for Engineers course.  The transition guide (Transition Guide) is included in the instructor support materials.

For information about using the SEI’s course delivery system to teach PSP Fundamentals, refer to the Instructor tutorial available from the SEI Learning Portal, http://learning.sei.cmu.edu.

This Instructor’s Guide contains eleven chapters. This introductory chapter provides an overview of the PSP Fundamentals course strategy and principles, a list of available support materials, guidance on where to obtain these materials, and suggestions on how to use them.  Chapter 2 provides general teaching suggestions, and Chapter 3 describes the PSP class data and the importance of providing frequent feedback to students.  Chapter 4 describes the course management system that supports PSP Fundamentals.  Chapters 5 through 9 provide day by day teaching suggestions for each lecture, exercise, report, and programming assignment.  Chapter 10 provides answers to frequently asked questions grouped by day of instruction.  Chapter 11 is a list of references.

## PSP Fundamentals Course Goals

The purpose of the PSP Fundamentals course is to provide students with a broad overview of PSP knowledge and skills to enable them to participate effectively on a TSP team.  A second course, PSP Advanced, follows.  The purpose of PSP Advanced is to provide an in-depth understanding of PSP so that the students are able to expand and extend PSP principles and concepts.  Together the two courses cover the PSP Body of Knowledge and prepare students for the PSP Developer Certification exam.  Both courses use the textbook PSP: A Self-Improvement Process for Software Engineers by Watts Humphrey.

The specific course objectives are to

- Teach students how to use PSP with limited data (e.g. no statistical analysis) for basic development work

  - follow a process

  - collect accurate, complete, and consistent time, size, defect, and schedule data

  - estimate size and effort using PROBE methods C and D

  - complete a project plan

  - conduct personal design and code reviews

  - complete a task and schedule plan

  - use Earned Value (EV) tracking

- Prepare students to participate on a TSP launch.

## The PSP Fundamentals Course Strategy – Learn By Doing

The course strategy is based on these fundamental principles:

- Software professionals will better understand what they do if they define, measure, and track their work.

- They will then have a defined process structure and measurable criteria for evaluating and learning from their own and others’ experiences.

- With this knowledge, they can select those methods and practices that best suit their particular tasks and abilities.

- By using a customized set of orderly, consistently practiced, and high-quality personal practices, developers will be more effective members of their development teams and projects.

The ultimate objective of the PSP is to demonstrate to these students with data on their own work that the PSP’s practices will help them to improve their personal performance as working developers.  The programming assignments also give the students an opportunity to practice and master the PSP knowledge and skills.

## PSP Fundamentals Course Overview

The diagram below provides an overview of the PSP Fundamentals course.

Figure 1. PSP Fundamentals Course Overview

The course is composed of six basic parts: lectures, process tutorials, programming assignments, report assignments, exercises, and class feedback sessions.  The following paragraphs identify the characteristics of each part.

### Lectures

The purpose of the course lectures is to explain the basic PSP principles and procedures while the tutorials focus on how to follow the PSP procedures.  The lectures also give the students an opportunity to ask questions about the various PSP methods.  While the material in the lectures is covered in the textbook, not all students complete the textbook reading assignments.  An important part of the classroom lectures is to reinforce materials through discussion and interaction.

### Process Tutorials

The purpose of the process tutorials is to prepare the students to follow that process to complete a programming assignment.  The tutorials are structured to introduce a PSP process step and to demonstrate usage of the PSP tool.  While some of the materials are effectively communicated through slides, in many cases the students need to complete a “hands-on” experience in the support tool.  Specific guidance on how to conduct each tutorial is included in this guide.  Please refer to each specific process tutorial in the day by day guidance sections.

### Assignments versus Exercises

The primary difference between assignments and exercises is that assignments are graded by the instructor.  Exercises have exercise answers, while assignments do not.  The exercise guidelines allow the students to work together in small groups and class discussions, and to learn from each other.  When they complete and submit their assignments, the students should be given individual feedback and coaching on their personal performance from the instructor.

### Programming Assignments

The programming assignments provide the unique aspect of the PSP Fundamentals course.  Students learn PSP methods in the course and apply them immediately to write moderately simple programs.  The programs serve to reinforce classroom learning.  Assignment kits emphasize to the students that they must follow the assignment specifications.  The kits specify the programs to write, the process to use in writing these programs, and the way in which the results are to be reported.  For the mathematical programs, a completed example is included in each assignment kit.  The examples provide the students with step-by-step guidance (and intermediate values) on how to complete the programs.  The examples also explain the required program calculations as simple sequences of arithmetic operations.  Instructors need to tailor their explanation of the programming assignments to each class and to each student.  The skills that students gain through properly completing the programming assignments are exactly those that they will need as members of TSP teams.  The course is designed to maximize the amount of time that students get to practice this skills set and therefore there are four programming assignments.  There is one programming assignment for each PSP0 and PSP1 and two programming assignments for PSP2.  Writing two programs with PSP2 allows students to practices the breadth of all PSP skills and also allows student to experience using a process without major changes.

### Report Assignments

The purpose of the report assignments is for the students to develop process elements, required to implement the PSP, specifically the personal review checklists and the coding standard.  The reports are handed-in as part of the appropriate programming assignments.

### Exercises

Exercises help to ensure understanding of the lecture content.  They are an opportunity for the instructor to lead a class discussion of the problems presented by the exercise scenarios.  It is especially important that the instructors are well prepared for these exercises, as their effectiveness depends greatly upon your ability to focus the class discussion upon the exercise objectives.

### Class Feedback Sessions

The purposes of the class feedback sessions are to

- review class data

- establish a benchmark of what is possible

- teach students how to read the charts on their own data

- explain the underlying data used on charts

- explain how to interpret and use derived measures

- address misunderstandings and common errors

- share lessons learned

- keep the focus on process

- have informal discussions about individual reactions to following a process

- help the students to appreciate the range of skills involved in developing software, to understand their personal strengths and weaknesses, and to see how to improve their personal performance.

Class data demonstrates the effectiveness gained by introducing new process steps to the PSP.  Class discussions provide the forum for students to learn from each other.

## The PSP Quality Focus

Since this course focuses on using data to achieve high quality personal work, it is important that the students be required to do quality work.  For example, they must gather and record all of the required data and should produce high quality programs and reports.

Explain the following guidelines to the students at the beginning of the course and repeat the explanation as often as needed to get consistently high-quality work.

- Make sure that the students understand that quality work is expected and that work done poorly will be rejected and must be redone.

- When students do not know how to do something, help them.  They should only turn in work that is correct.

- While the students should turn their work in on time, it is more important that it be correct before turning it in.

- Tell the students that you will not grade their assignments until they are submitted properly.

- Follow a strategy that demands the submission of quality data from the outset and then progresses to the use, interpretation, and internalization of lessons based upon these data.

- Treat each student as if (s)he has a hidden talent that should be revealed.  The course and the data will help you to do this.

- While you may never recognize unique talents, try to help each student achieve a better appreciation of his or her capabilities.

## PSP Fundamentals Course Support Tools

Instructor materials for PSP Fundamentals include two tools.  The student tool (called the PSP workbook) supports data recording, calculation, and management. It accelerates and simplifies these activities.  Remind students that no tool can completely eliminate the need to record data, analyze these data, and use the data to plan and manage their work, nor should a tool be used without understanding the relationships between the data and the values that are derived from those data.   The tool contains the correct process steps for the four programming assignments of the PSP Fundamentals course.  The instructor tool supports analyzing, tracking, and displaying class data and course progress.

## A Self-Teaching System

Most developers need to learn the PSP by taking the course, but the instructor only facilitates the learning process.  The PSP Fundamentals course provides students with the data on their own work, and when properly coached, the students will learn more from their data and experiences than they will learn from the instructor.

Your job as an instructor is to facilitate this process.  Explain the material in the lectures, lead the students through the exercises and assignments, and review and grade their work.  By showing them how to follow the PSP practices, and by identifying and correcting any misunderstandings and problems, you help them learn the PSP.  Having the students use these processes repeatedly, demonstrates how the process can work for them.

## Handling Skeptics

Skeptics are often the best PSP students, even though they can be annoying and ask difficult and embarrassing questions.  Skeptics are curious and thinking.  They don’t believe something because you tell them or because they read it.  They need evidence.  The PSP strategy for handling skeptics is to do your best as the instructor to answer questions, but to appeal to their curiosity and skepticism.  Encourage them to direct their curiosity toward their data rather than toward you.  You’ll first have to convince them to follow the process and gather that data, which can be a daunting but necessary task.  After they start using their data to answer their own questions, you can help them interpret the results.  After they become convinced, skeptics are often the strongest supporters of the PSP and TSP.  Welcome them.

## The PSP Learning Strategy

The evolving PSP process introduces the PSP’s methods in relatively simple and easy-to-understand steps.  Each step of the PSP process builds on prior steps.  Understanding the learning for each level will help the students to build the proper foundation.

- PSP0 – developers learn to follow a process and gather data.

- PSP1 – developers learn to build plans.

- PSP2 – developers learn how to build high quality parts and programs.

## Gathering Data

Since the PSP uses data to help the students do better work, it is essential that they gather complete and accurate data.  Emphasize to students that these data are important and that they are required to complete the course successfully.

# General Teaching Guidelines

This section provides guidance on how to teach the class and on how to address the most common problems you will face as an instructor.

## Scheduling the Course

PSP Fundamentals is designed as a one-week course.  The agendas, lectures, exercises, and assignments all assume that the course will be taught over five consecutive days.  Classes on the first four days have a lab session that begins in the early afternoon.  On those days students can work in the classroom or at some other location if they prefer.  However, it is strongly recommended that they do the work in the classroom setting so they can get instructor guidance and they do not get distracted until they have completed their PSP assignments.  The class on the fifth day is scheduled to end at 2:30 PM.

It might be possible to have the class meet once a week, so that students in the class are not away from their work for a full week.  This model has not been particularly successful, largely because all of their other work commitments must be squeezed into three or four days a week instead of five.  This not only increases their pressure at work, but also provides limited time to complete all of their PSP Fundamentals coursework on the job.  With sufficient planning, a project team can take the PSP Fundamentals course together, participate in a TSP launch soon afterwards, and start using PSP on the job.

## Preparing to Teach

A course checklist has been developed to help you prepare for course delivery.  The course checklist is part of the collateral materials.  The course checklist takes the instructor through all the procedural steps necessary to schedule and set-up a class.  To prepare to teach, complete the following steps.

- Read the instructor’s guide for the specific topic area.  Some instructors find it useful to conduct a dry-run, especially the first time they prepare to teach a particular topic.

- Review the applicable textbook and the course materials.  Think about how to make the course content motivating to the class.  Also, think about how you will relate the topics to each other.

- Review the tutorials and prepare to lead the class through the tutorial materials.

- Review the assignments and prepare to lead the class through the assignment materials.

- Review the exercises and prepare to discuss of the code review and capstone exercises.

## Class Discussions

There are many places in the course materials where questions are posed to the class.  The instructor should pose the question to the class and give the students time to document their answers.  The instructor should then ask students to share their answer and document them on a white board or flip chart.  The instructor should encourage class participation but must also manage discussion time to ensure that all materials are covered.

## General Assignment and Exercise Guidelines

The materials needed to complete assignments and exercises are available in printable PDF documents.  These files are available through the Blended Learning system.  The instructor should encourage the students to print out the exercise and assignment materials.

## Dealing with Students who are falling behind

It is important to keep all students on schedule.  When students fall behind, there are many negative consequences.  The lecture materials will no longer relate to what the student is doing and the students will not have the experience needed to fully benefit from the next lecture, tutorial and exercise.  This will put the student further behind.  If they don’t finish their assignments that week, then they have to try to “make time” to complete the course after returning to work.  Interacting with the instructor after the class is more time consuming and less effective than face to face contact.  Many students who have significant amounts of work to complete at the end of the class week do not finish the course.  This results in a negative experience for the student and a loss of investment time and money for the company.

To keep the class on schedule, the instructor should carefully monitor class progress and make adjustments throughout the week.  The instructor should start this process on the afternoon of the first day.  The instructor should walk around the class on Monday afternoon to see where all of the students are.  If a student is struggling, the instructor should understand why and address that problem.  Typically students fall behind for four reasons.

First, the program assignment could be too difficult for that student or the student is making it too difficult.  For each programming assignment, this guide has simplifying guidelines.  If the student is making the assignment too hard by over-engineering a solution, simply remind the student that this is a process class, not a programming class.

Second, the student is not “doing it right the first time.”  This is reflected when the student has many re-submits per assignments.  Students need to realize how much of your and their time is wasted by resubmits.  The instructor should discuss what quality means in this course.  It could be that the student is making too many assumptions and that (s)he needs to be reminded to confirm his/her assumptions before proceeding.

Third, the student might be intimidated by the math in the programming assignments.  In this case, take the time to walk the student through the worked out arithmetic example to make the student comfortable with the mathematics.  The same is true with the string processing in assignment 2, students may need additional explanation from the instructor.

Fourth, the student may not have the ability to complete the programming assignments.  Either the student doesn’t have programming skills or the student is working in a programming environment (s)he is unfamiliar with.  If the student is working in an unfamiliar programming environment, have him/her switch to a language with which (s)he is comfortable.  If the student lacks programming skills, suggest that (s)he takes the Introduction to Personal Process course.  If the instructor chooses to continue with a student with poor programming skills, both the instructor and the student must realize that this could be very time consuming.

No matter what the cause, instructors should promptly identify students who are falling behind so the problems can be addressed in time.

## Surfing the internet – Class Distractions

The instructors must immediately address the issue of class distraction.  If the instructor does not address this issue it is likely that students will miss important details and many will fall behind.  There are several tried and true techniques for addressing distracted students.  One technique is to put questions to the class and target those who are not paying attention.  A second technique is to keep the lectures lively and interesting.  Work hard to relate the materials to real world experiences and keep the class engaged in class discussions.  A third technique is to openly discuss the issue with the class.  A last ditch effort is to single people out and asking them to close their computers.  These same techniques can be used for conversations between students.

## Disruptive Students

Occasionally, students are enrolled in PSP classes either over their objections or without proper prior discussion or preparation.  If such students are outspoken or appear to be working against the objectives of the course, take them aside to discuss the issue.  If the student is not willing to take the course and to complete the required work, insist that (s)he be removed from the class.  With a negative attitude, the student will not gain from taking the course and will likely cause problems for other students.  If you compromise on this point, the course will likely fail, even for those students who are willing to do the work.  This would be an instructor failure.

## Handling Tough Questions

Sometimes you will get hard questions or questions for which there is no right answer.  In these cases, explain the purpose of the data and ask the student to consider different ways to address the issue.  Emphasize the importance of gathering relevant data and figuring out the solution that works best for each case.

## General Grading Guidelines

Instructors have had the most success teaching PSP Fundamentals by focusing upon the process used to complete the course assignments rather than upon the programs produced.  The key lessons for the students are in how to gather process data and in how to use these data to improve the way they work.  Although students must produce working programs, it is best to assume that they know how to write the programs and to focus primarily upon process quality and process data.

The grading philosophy suggested for this course is as follows.

- The process data are complete.  The first priority is to ensure that the process data have been entered completely and correctly.  Since, without correct data, the rest of the PSP process will be largely ineffective, this is the first and most important grading priority.

- The process data are accurate and self-consistent.  While this is generally more difficult to determine, it is usually possible to spot most inconsistencies when you know what to look for.  For example, if a developer takes an hour or more in unit test, but reports a defect fix time of ten or fifteen minutes, (s)he is probably not recording all of the defects found or may not understand how to record defect fix time.

- Historical data are used in planning the work. After students learn to gather complete and accurate data, they generally see the benefits of using their data for planning future work.

High quality data is an absolute requirement to an effective PSP Fundamentals course.  If the quality of a student’s data is poor, that student’s learning experience will suffer.

When the instructors are consistent and thorough in their grading, students will generally produce correct results after a single reminder.  The instructors can then focus their attention on the more substantive new topics for each process version.  Note that on the grading checklists, the new items are easily identifiable because they are shown in bold italics text.  To help students do correct work, they should not submit an assignment until they have reviewed the grading comments for the preceding one, which stresses the importance of timely feedback on assignments.

It is helpful to grade homework by performing the following steps:

- Follow the steps in the Grading Checklist.  It is structured in a sequence that has been shown to assist in rapid and complete grading.

- Check each form to ensure that the data are complete.

- Check the data dependencies among the forms to ensure that they are self-consistent.  An example dependency is that Added LOC on the Project Plan Summary should be compared to Actual Added Parts TOTAL on the Size Estimating Template.  Criteria for this comparison are shown on the Grading Checklist.

- Check that the data are used properly.

In many cases, the instructor won’t be able to tell if process data are correct or not.  All the instructor can do in these cases is to point out that some data look incorrect.  Experience shows that problems are solved best on face to face discussions.  The instructor should ask the student to explain what (s)he is doing.

After students consistently begin to submit quality work, the initial steps of this process should take only a few minutes per assignment. The grading discussions for each process level suggest the proper items to check for that process level.

To emphasize the importance of quality, the instructor should insist that the students submit quality work as defined in section 1.4.  If they are not sure how to complete an assignment, they should ask questions first and then complete the work correctly.  While it is important to submit the homework on time, quality work is more important, even if it must be late.

Students who are fluent in a programming language and use a familiar development environment do not typically have trouble writing the programming assignments.  Students who are not working as developers may struggle with the exercises. However, regardless of their programming competency, they may be confused about how to use the PSP methods and data.  When students encounter difficulties, the suggested approach is for them to do the work as best they can and then to check with you before turning in the assignments.  If an assignment is not done correctly, have the student correct it before submitting it.  By using this approach, students realize after only one or two assignments that they save time by doing their work correctly.  Thereafter, the quality of their work is generally excellent.

It is also important to analyze student data after each assignment.  Rapid feedback is an essential part of teaching the PSP methods.  Grade the assignments when they are submitted and then promptly examine the data.  It is a time consuming task to grade and assess the data for each student assignment that becomes nearly impossible to catch up on if the instructors delay grading even a single assignment.  Delays also deprive the students of essential feedback about the work they have completed.

The course should honor each student’s individuality.  Each student has strengths and weaknesses and individual performance varies widely, depending upon skill level and the task assigned. Thus, do not grade students on absolute performance.  Emphasize improvement and the extent to which students analyze their data and use these analyses to affect their behavior.  Your objective is to encourage them to do quality work, follow the process, and strive to improve their performance.  However, when you review class data you should expect to see the trends described in section 3 of this guide.  You should use the class data as a way of reviewing your teaching strengths and weaknesses.

# Interpreting Class Data

One of the most important objectives of the PSP Fundamentals course is to convince students that using the PSP methods will help them to do better work.  That is why it is important to provide them with frequent feedback on their personal work and on overall class results.

## Class Data Feedback

After the first lecture, try to present class data to the students every day if possible.  However, do not present anything until you have enough data so that no individual’s performance is visible.  The PSP guidelines for showing student data are as follows.

- Respect students’ individuality.  All students are different, so making comparisons among them is counterproductive.  The objective is to help each student maximize his or her potential to do high quality and productive work.

- Respect student data.  Data are private.  No student’s data should be shown to anyone else under any conditions.  Students may show their own data to anyone they choose, but you should not.

- Remain neutral. Do not hint that a particular student has done unusually good or poor work.

Table 3.1 lists the different kinds of data that are appropriate for each lecture.  While you may choose not to show all of these data at every class, students have never complained about seeing too much data.  At the end of the course, give the students copies of a final set of the overall data on class performance.

Charts that show the class maximum, minimum, and average values for the data listed in Table 3.1 can be produced by using the PSP instructor support tool.  It’s usually a good idea to point out to students that the maximum and minimum values on the charts reflect the work of different people on each program.  First, check to ensure that this is the case for your class, but for reasonably homogeneous classes of ten or more students, usually no individual’s performance is consistently the best or the worst for all of the programs or measures.

## Compiling Class Data

The instructor support tool provides an import function to aid with consolidating class data.  However, in some classes you will find that it is undesirable to include all students’ data in the class data.  If a student is using a language where the size measure is different from everyone else’s, this can artificially skew the class data.

In very small classes, you might not be able to illustrate concepts adequately due to limited data.  In this case it is perfectly acceptable to include student data from other classes.  Just let the current class know what you have done and why.

## Class Feedback Charts

The following paragraphs discuss each of the class feedback charts that can be generated by using the SEI PSP workbook and the data listed in Table 3.1. Note that some of the data are not suggested for PSP Fundamentals.  They will be introduced and shown in PSP Advanced.

### Number of Assignments Submitted

This graph depicts the progress that students are making in the course.  It shows the number of students who have received approval for each assignment.  It should not be used to imply that some students always complete their assignments on time or that others are chronically behind.

### Actual Development Time

The Time Range chart shows the class average, minimum and maximum times spent developing each of the programs in hours.  This range is usually very large because of the many possible ways to write programs and because of the wide range in student ability.  This range is of general interest, but it is not useful as an indicator of student performance.

| Day | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- |
| Number of assignments submitted | x | x | x | x |
| Actual development time | x | x | x | x |
| Time estimating error |  | x | x | x |
| Design time | x | x | x | x |
| Compile time | x | x | x | x |
| Test Time | x | x | x | x |
| Actual size |  | x | x | x |
| Size estimating error |  | x | x | x |
| Size vs. development time |  | x | x | x |
| Total defects |  | x | x | x |
| Defects injected in design |  |  | x | x |
| Defects injected in coding |  |  | x | x |
| Defect removal rates |  |  | x | x |
| Compile defects vs. test defects |  |  | x | x |
| Defects found in design review |  |  | x | x |
| Defects found in code review |  |  | x | x |
| Defects found in compile |  | x | x | x |
| Defects found in test |  | x | x | x |
| Yield |  |  | x | x |
| Productivity |  |  | x | x |
| Yield vs. productivity |  |  | x | x |

Table 3.1. Class Data Reference

### Time Estimating Error

The Time Error chart shows the error in the time estimates as a percentage of the estimate, and displays the class minimum, maximum, and percentage error for the total of the class estimates and actuals.  That is, with data on four student programs, the chart shows the total of the development time estimates for the four programs compared to the total of the actual time spent developing the programs.  The maximum and minimum values are also shown for each program.  Again, the students are generally surprised at the accuracy of the composite time estimate for the total class.  This indicates the potential value of independently-made estimates, particularly when they are based on historical data and are made using sound estimating methods.  When historical data are not used, common biases often lead to large composite errors.

### Design Time

The Design Time chart shows the percentage of total development time spent in design.  For PSP Fundamentals, students are allowed to use whatever design techniques that they have brought to the course, so they may vary widely.  The PSP programs are small, so design is not a significant part of the effort.  Nevertheless, in projecting this graph you should reiterate the importance of design.  You can mention several times during the class data presentation that design is a major topic in the PSP Advanced course.

### Compile Time

The Compile Time chart shows the percentage of total development time spent in compilation.  Programs written using high-quality processes usually require less compile time.  If many of the students use development environments that do not have a compile phase, show these data for only those students that use compiling.  However, only do so if there are enough of these students so that individuals cannot be identified.

### Test Time

The Test Time chart shows the percentage of development time spent in test.  This percentage is a simple indicator of process quality.  Lower test times indicate fewer test defects and higher product quality. This indicates higher process quality.

### Actual Size

The Size Range chart shows the class average, minimum, and maximum for the added and modified sizes of the programs.  Even with the simple PSP exercise programs, the students have considerable flexibility in how they design each program.  Size ranges of three to one or more are common.  When the size of any of the programs is below about 50 LOC, check that the students are actually writing the programs instead of using available mathematical library functions.

### Size Estimating Error

For added and modified size, the Size Error chart shows the error percentage for the class minimum, maximum, and class total of the size estimates and actuals.  For example, with data on four students’ programs, the total value is the sum of the size estimates for the four programs compared to the total of the actual sizes for the same four programs. The principal point to be made with this chart is that the composite class estimate is generally much more accurate than any of the individual estimates.

### Size vs. Development Time

The Size vs. Time chart shows the added and modified size and the time in hours for each program for the whole class.  Each plot point indicates the degree to which development time relates to that program’s size.  Composite class data show a poor correlation, but individual students can usually observe a fairly close relationship for their personal data.  The principal lesson is that high correlations are likely for individual data but not for composite class or team data.  The instructor should explain that the correlation for the class is often poor because class data are often for programs written in different languages and students generally have very different productivity rates.

### Total Defects

The Total Defects chart shows the class average, minimum, and maximum for the total number of defects found during program development per KLOC of added and modified code.  An objective of the course is to increase the students’ sensitivity to defects, thereby encouraging them to employ quality methods in their work.  The total number of defects/KLOC should gradually decline throughout the course.  While this is usually the case, there is often a temporary upward step with the first PSP2 program.  This may indicate that the students are finding defects that they would have missed previously and that their finished programs are now of higher quality.  This is why teams of PSP trained developers typically reduce the number of defects found in system test by 80% or more, with comparable reductions in testing times.

### Defects Injected in Design

The Design Defects chart shows the number of defects injected during design per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  For most PSP classes, the number of design defects is fairly small compared to the number of coding defects.  Note that “design defects” as described here refer to defects injected in the design phase.  Until they start using sound design methods, most developers will do most of their design work and inject most design-type errors during the code phase.

### Defects Injected in Code

The Code Defects chart shows the number of defects injected in the coding phase, per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  Students are often surprised at how many code defects they inject.  They also find that with modest care they can significantly reduce this number.

### Defects Removal Rates

The Defects per Hour chart shows the rate of defect discovery measured in defects per hour for design review, code review, compile, and test.  It displays the class average for each of these rates for each program.  Defects per hour are calculated by dividing the number of defects found in a phase by the time in hours spent in that phase.  This calculation is done for design review, code review, compile, and test.  These data demonstrate that testing is an inefficient way for developers to spend their time.

### Compile vs. Test Defects

The Compile vs. Test Defects chart displays the number of compile and test defects for the entire class plotted on x-y axes.  It indicates the relationship between compile and test defects.  Again, composite class data show a poor correlation, but individual students can usually observe a fairly close relationship for their personal data.  The implication is that to reduce the number of test defects, students should strive to reduce the number of compile defects.

### Defects Found in Design Review

The Design Review Defects chart shows the number of defects found during design reviews per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  While students develop a personal design review checklist and review their designs, typically this phase will not find very many defects.  That is because students are not developing reviewable designs.  This is a main topic in PSP Advanced course.

### Defects Found in Code Review

The Code Review Defects chart shows the number of defects found during code reviews, per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  This is another focal point for the PSP Fundamentals course to maximize the percentage of coding defects that are found in code reviews.

### Defects Found in Compile

For those students that have a compile phase, the Compile Defects chart shows the number of defects found in compilation per KLOC of added and modified code and displays the class average, minimum, and maximum values for each program.  One course objective is to motivate students to strive for clean compilations on the first try, resulting in higher quality programs.  If many of the students use development environments that do not have a compile phase, show these data for those students that use compiling.  Do so only if there are enough of these students so individuals cannot be singled out, however. When there is a mixture where some of the programming environments do have a compile phase, and some don’t, the chart will show zero compile defects for those environments with no compile phase.

### Defects Found in Test

The Test Defects chart shows the number of defects found in test, per KLOC of added and modified code, and displays the class average, minimum, and maximum values for each program.  A key quality message of the PSP Fundamentals course is that the number of test defects indicates the number of defects remaining in a program.  This is because test processes generally miss a percentage of a program’s defects.  In test, defects tend to mask other defects and high defect density in test tends to reduce the test yield.  Thus, the objective is to have as few test defects as possible, resulting in a low number of defects remaining in the finished product.  This assumes, of course, that the testing process is competently performed and the defect data are properly recorded.

### Yield

Process Yield denotes the percentage of defects that are removed before the first compile or program build step, and shows the class average, minimum, and maximum values for each program.  One of the instructor’s principal objectives is to convince students to increase their personal process yield.

### Productivity

The Productivity chart shows the students’ productivity measured in lines of code per hour and displays the class average, minimum, and maximum values for each program.  While students should strive for high productivity, few see significant productivity increases and many may see decreases during the PSP Fundamentals course.  In learning the PSP, students are both building new skills and performing additional tasks.  While these new tasks will quickly improve the predictability and quality of their work, students usually have to write ten or more programs with the PSP before they see productivity improvements.

### Yield vs. Productivity

The Yield vs. Productivity chart shows process yield versus productivity in an x-y plot.  Productivity should be viewed as a long-term objective.  The more immediate objective of this course is to improve basic engineering practices while gradually improving productivity.

# Blended Learning

The instructors are authorized to teach PSP Fundamentals only as an online course with a course management system provided by the SEI Learning Portal.  The approach taken to instruction is called Blended Learning because it is a blend of real-time instruction (synchronous learning) and work that is performed at a pace that is convenient and comfortable for students (asynchronous learning).  Asynchronous learning includes access to course materials, submission of assignments, and feedback from the instructors – all provided by the Blended Learning system.

The lectures and tutorials are delivered in the usual manner, although students will not have paper copies of course materials available to them.  They will be able to follow the lecture slides and retrieve assignment kits directly from the course management system.  Completed assignments will be submitted via the course management system.  Instructors will provide feedback on assignments by completing the usual grading checklist.  After grading a student assignment, the instructor will be able to return it to the student via the course management system.

Authorization to use the SEI Learning Portal course management system will be given to instructors after they complete the PSP Instructor Tutorial online training course that is offered through the SEI Learning Portal.  In this way the instructors will interact with the system as students to gain sufficient mastery of the system to use it for teaching the PSP Fundamentals course.

On the first day of the course, instructors should walk the class through the basics required for using the SEI Learning Portal at the beginning of the class.

For information about using the SEI Learning Portal to teach PSP Fundamentals, refer to the PSP Instructor Tutorial available through the SEI Learning Portal, http://learning.sei.cmu.edu.

# Day 1

This chapter covers the content of the first day of PSP Fundamentals.  The day consists of an introduction to Blended Learning and a course overview, followed by a lecture that introduces the PSP and a tutorial on PSP0.  The tutorial introduces the PSP0 process and the PSP workbook.  The first programming assignment is then introduced.

## Introduction to Blended Learning

SEI makes the PSP Fundamentals course available only via the SEI Learning Portal.  The skills that students must have in order to use the SEI Learning Portal are

- login to the system and manage their account

- navigate through the system

- complete and submit course assignments

- review feedback from the instructor and track their progress

- communicate with the instructors

The instructors must ensure that all the students have the aforementioned skills at the beginning of the class to shortcut many questions about the use of the SEI course management system.  This will help ensure that students can concentrate upon the process skills being taught, rather than trying to figure out how to use the course management system.

## Course Overview

In the course overview the instructors become acquainted with the class, help students understand the purpose of the PSP Fundamentals course, and learn what they can expect to get from the course.

The overview begins with introductions by the instructors and students.  The instructors introduce themselves, describe their backgrounds and explain how they became involved with the PSP and TSP.  If TSP has helped them and/or their company be more productive, produce higher quality products, or reduce costs, then this is a good opportunity to say so.

The students should also introduce themselves and discuss their expectations for the class and the language they will use.  The instructor should write all course expectations on a flip chart and address any mismatched expectation.  It’s helpful to identify students using the same language so they can help each other.

In the overview, the instructors present the challenges generally faced by software developers.  This is the time to mention that developers must establish credibility with management.  Several slides describe how credibility comes from setting, keeping, and exceeding the expectations that they have personally set with their management.  The final slide then explains that the TSP process guides developers in establishing and meeting management expectations.

The remainder of this session introduces the ground rules for the course and the agenda for each day.  The instructors should then state their expectations for the class: each day the class will start on time, distractions will be held to a minimum, and assignment submissions should be correct and complete.

## Lecture 1: Introduction to the PSP

The goal of this lecture is that students understand an example personal process and how it can be effective for them as software developers.

The lecture begins with a class discussion of what students know about the way they currently perform.  This discussion should draw out their personal experiences with different employers.  In this discussion, the instructors should help students see that, although they may have a sense of how they perform, they probably don’t have much specific knowledge.

After helping students see that they don’t truly understand their personal performance, the discussion should then transition to process definition and personal processes.

After motivating the reasons for using a personal process, the PSP is introduced as a personal process for writing software.  Elements of the PSP such as scripts, forms, process measures, standards, etc. are introduced.  The reasons for having a “good” process are presented to help the instructors make the case that PSP can be effective for improving software work.

The lecture concludes by describing how students learn the PSP and showing some course results.

## PSP0 Tutorial

The PSP0 tutorial prepares students to follow the PSP0, and to use the student workbook, to complete programming assignment 1.  The tutorial covers a PSP0 overview, objectives of PSP0, its process phases, how PSP0 and cyclic development are complementary, and the process elements of PSP0.  In describing the process phases the instructors should state whether a compile phase is required or the circumstances where it may not be needed.  Emphasize that cyclic development is encouraged. Be prepared to answer questions about various coding styles such as coding, compiling and testing a few lines of code at a time.

Next the tutorial describes the student workbook.  Students should have already downloaded the tool from the Blended Learning system.  The tutorial describes the basics for installing and starting the tool.  This is best done (slides 10-16) by having the students open their tool and discussing the topics from a tool vantage point.

The next section of the tutorial (slides 17-33), describes the steps in the PSP0 process and how the data is entered and tracked in the student workbook.  Only the features used for the current process level are described.  Students learn this material best by trying to do things with their tool.  However, make sure that the points on the slides are covered and that students understand the importance of following the written process scripts.

The tutorial ends with a discussion of errors that students frequently make when doing the first assignment.  The goal is to prevent these errors before students use the process and workbook for the first time.  If these errors are not prevented, the students will take excessive time completing the first assignment.

## PSP0 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP Fundamentals courses and from analyzing the data gathered from thousands of PSP class programs. Instructors should consider these points as they give lectures, answer questions and advise students.

### Program Complexity

Most students write reasonably sized PSP assignment programs but some can be overly ambitious.  This can often be the case with experienced developers who are accustomed to handling error conditions, providing sophisticated user interfaces, or preventing security vulnerabilities.  While sound programming practices are important, the PSP exercise programs are class exercises that will not be reused.  The students do not need to produce anything more than a basic working program that handles normal input, simple error, and operating conditions.  These programs need not be designed to be bulletproof or to handle unusual situations.  Emphasize that development times that average between two to five hours are usually adequate.

### Very Small Programs

Many modern programming environments include a wide variety of mathematical and other embedded functions.  While using embedded functions for some program actions is appropriate, they should not be used to write the principal functions of the programming assignment.  When students use such functions, they can write many of the PSP exercises in fewer than ten LOC.  This takes too little time and is of no pedagogical value.  Mention this point when you give the assignment and insist that students code the principal assignment functions themselves, otherwise their work would be rejected.  If the programs are smaller than 50 LOC and take less than a couple of hours to write, the students will not likely learn the necessary lessons from the assignment.

### Quality

Emphasize at every opportunity that the PSP is a process for producing quality work.  This requires that the process data be of high quality, that the programs the students produce are of high quality, and that the students submit quality reports.  When instructors insist on receiving quality work from the beginning, there will not likely be many problems.  However, if this requirement is relaxed, the class is likely to have quality problems throughout the course.

## Program 1: Mean and Standard Deviation

The first programming assignment uses PSP0 to write a program to calculate the mean and standard deviation of a set of values.  It is usually best to start with a brief workshop to explain the program requirements, work through an example of mathematical computations, and walk the students through planning to develop their programs.  Although data entry from a file is not required, it is recommended.  Manual entry takes excessive amounts of time and is subject to error.  Also, subsequent assignments will require similar test data.

Instructors should check throughout the afternoon lab session that all students are on schedule.  If students are falling behind, consider simplifying the assignment for them.  For example, this assignment can be simplified by changing the data structure from a linked list to a variable or fixed array.  Also, some students may require additional instructions on opening and reading from a file.

## Grading PSP0 Assignments

The SEI course management system provides a grading checklist for use by instructors when grading student assignments.  Each item on the checklist has a cell for a checkmark to indicate that the requirement has been satisfied.  The grading discussion in this guide is in the same organization as the grading checklist.

### General

Refer to section 2.9, General Grading Guidelines, for general guidance on grading.

The students feel that their hard work is being recognized when they receive positive written comments from their instructors.  This feedback should be summarized at the top with each assignment.

In grading PSP0 assignments, ensure that students are following scripts and collecting complete, consistent and accurate time and defect data.  Students will resist tracking their data as they work because initially it will feel awkward.  The instructors must insist that students collect complete data and after one or two programs they will establish a habit and the time and defect logs will reflect that.

Verify that the students did their own work.  While cheating is rare, it is possible, particularly when students are not qualified or are taking the course under duress.  A simple check of the program listings and PSP forms usually reveals instances of copying.

Finally point out that even a little data gives a lot of insight into performance.  Are they surprised at how they spend their time?  Did one defect take a significant percentage of development time?  Motivate the student to improve.

### Program and Test Results

A review of the program listing will verify that an appropriate program was written and that it appears complete and working.  If you suspect problems, invite students to briefly demonstrate their programs.  Since this is not a programming course, only grade the program and test results to ensure that the program generates the correct results and has been exercised on all the required tests.  Note that “incorrect” or “close enough” results will cause incorrect results on subsequent programs since the earlier programs are reused in later assignments.  Some “close but not perfect” results in later programs are due to the poor precision of earlier programs.

### Time Recording Log

Typical problems encountered in using the Time Recording Log are forgetting to make entries while doing the work or only doing so after finishing the programs.  When they record times after the work is done, the values are usually integers.  If instructors insist with the first assignment that students enter the time data properly, entering time data will not usually be a problem thereafter.

The Time Recording Log should show entries for each phase of PSP0.  The sequence of entries should conform to the PSP0, allowing for the possibility of iteration within the development phase. It would be unrealistic, however, to have a design phase immediately followed by a test phase without a code phase (and possibly a compile phase, depending on the programming environment being used). The first phase should be Plan and the last phase should be Postmortem.

Time Recording Log entries should not overlap. While it is not necessary to have entries in time order, doing so is more likely to indicate that the student is recording activity as it occurs.

Instructors should encourage the use of the “Comments” field for interruption classification and other useful information, displaying a good account of how the time was spent. The comments are a great source of data for analysis and improvement ideas.

The many checks about whether the time data is reasonable include

- when the student is working (late hours during a class night)

- very small or very, very large increments

- counting time inconsistently, sometimes include research, sometimes don’t

- inserting interruptions as a separate entry (adds interrupt time to the development time instead of subtracting)

- confusing process phases versus activities e.g. compiling in compile phase versus compiling in test phase

The time log will help the instructor understand if the student is following the script.  If the students have trouble figuring out how to track their time or confuse phases with activity, they are probably not following the scripts.  It will help to have a class discussion about the importance of consistent data and how that data can be used.

### Defect Recording Log

A common initial problem with the Defect Recording log is for students to not enter any defect data.  Either students refuse to collect defect data or they forget to.  When students do not record their defects, tell them that collecting defect data is required to complete the class.  Usually this is enough to get them to comply.  If students forget to record defects, have them enter their defect data as best they can remember.  Most students will struggle with collecting size and defect data on the initial programs, but by diligently reviewing their assignments and requiring corrections, this problem will go away with the later assignments.  Instructors should address this problem early on and stress the importance of recording “all” of the defect data.  Generally, students will be averaging around 100 defects per KLOC.  Some students will have much higher and much lower defect densities.  Defect density also depends upon the language and development environment the student is using.  Always bring suspicious data to students’ attention.

The Defect Recording Log is a common source of problems, not because it is difficult but because students often omit part of the data or make incomplete entries.  Good defect data are required for later parts of the course.  For instance, good defect descriptions are required for effective review checklists and quality PIPs.  If students do not start recording good defect data from the outset, it will be much more difficult to get them to enter quality defect data later.

The injected and removed phases should be checked for consistency with the defect type, the defect description, and the time log data.  Some students will complain that the defect types are not applicable to their programming environment.  When this is the case, have them adopt the closest types, and then consistently use these types throughout the course.

### Project Plan Summary

Remind students that plan time is entered in minutes rather than hours.  Besides checking the math, look at the plan summary data and ask the students if they are surprised about how they spend their time.

### Consistency Checks

In evaluating the students’ work, employ consistency checks to ensure that the data shown on the PSP0 Project Plan Summary are reasonable.

Checking for consistency between the time and defect data:

- The time spent in the compile and test phases should be consistent with the find and fix time for the defects found in that phase. Question students where the difference is more than a few minutes. Encouraged them to prepare test cases and test data in the design phase.  Preparing the test cases during the design phase usually results in better designs.

- The order of the defect entries should be consistent with the order shown by the phase entries in the time log.

- Where the programming work took two or more days, the defect phases entered in a day should be consistent with the phase entries in the time log.

- Check the consistency between the time and defect logs and the Project Plan Summary.  While data from time recording log is transferred automatically to the summary sheet, the sum of defect fix times in a phase is not checked by the tool against the total time spent in that phase.  Instructors should verify the consistency of defect fix times and total time spent in a phase.  Another reason for inconsistency is the fact that some of the students occasionally edit the summary values or provide inconsistent copies of documents.

# Day 2

This chapter covers the second day of PSP Fundamentals.  Day 2 begins with a discussion of the previous day’s assignment.  Following that discussion is a lecture on planning with the PSP and a tutorial on PSP1.  The second programming assignment is then described.

## Class Data Feedback

The class data feedback should always start with positive comments from the instructor.

In this session the class discusses their reaction to the first day of training.  Most students should have completed program 1 and received instructor’s feedback.  This is an opportunity for students to discuss the lessons that they have learned from doing the first assignment.  It is also the instructors’ chance to discuss what they have seen in the student work they have graded.  Plan to discuss one or more or all of the following topics.

- Difficulty following a process/script

- state of the program vs. state of the programmer

- forgetting to track time or defects

- not recording all defects

- over-designing/over-implementing a solution

- not being consistent with types

- good vs. poor defect descriptions, describing symptoms rather than the root cause

Frequently reiterate that PSP Fundamentals is a process course not a programming course.

The instructor tool is used to collect and present data about student work.  Table 3.1 on page 13 lists the data to be presented on day 2 of the course.  That list is also included in the class materials.

The student tool also provides the analysis charts so that students can see data on their own performance.

## Lecture 2: Fundamental Planning Concepts

This lecture helps students learn about planning and how the PROBE method can help them to estimate their work.

The lecture begins with two motivating questions.

- Why are plans needed?

- What are the steps in planning?

In each case the “textbook answer” is presented on the following slide.  Before showing the slide, have the students discuss these questions and their answers.

Then present the PSP planning framework.  Spend enough time on this slide to explain the new terminology, the conceptual design, resources, and process analysis.  Note that this lecture is mostly about two boxes on the framework: conceptual design and estimate size.

To help them understand the estimation problem, the conceptual design is shown with the analogy of estimating the size of a house in the early stages of planning.  From there the analogy is carried to software, so rooms of a house become “parts” of a program, and historical data about room size become data about LOC.

PROBE is introduced as a formal way to estimate software size using historical data.  Proxies are described, and a table of proxy sizes is presented.  Note the example used to explain the principals of PROBE in the case between “number of items” and “part size” to “number of rooms” and “room size” is to reinforce the analogy between estimating the size of construction and of a program.

Caution students against jumping into size estimation without understanding what makes a good size estimate.  Size accounting should be repeatable, so students are introduced to the necessity for a precise measure and for use of a counting standard.

Terms such as base, added, deleted, modified, etc., are also introduced in this lecture.  Emphasize the difference between the types of LOC.  Although a slide describes the differences between the types of LOC, students are often confused when trying to apply the definitions.  Take the time to give examples of base code and reused code.  Tell students that for the first two programming assignments they will probably have no base code and no reused code.

The lecture ends by presenting the PSP Planning Framework for a second time.  This is to reiterate the part of the framework that has been presented and to indicate that other parts of the framework will be covered later.

## Coding Standard Assignment

The coding standard assignment is for students to create a coding standard for the language that they are using in the course.  The assignment objectives are to establish a consistent set of coding practices, provide criteria for judging code quality, and ensure consistent with LOC counts.  The coding standard should ensure that each physical LOC should contain one logical LOC.  Students are provided a sample coding standard for C++ as a starting point.  The assignment is to be submitted with Program 2.

## PSP1 Tutorial

The purpose of the PSP1 tutorial is to prepare the students to follow the PSP1 process, using the student workbook, to complete programming assignment 2.  The tutorial consists of an overview of PSP1, a planning scenario for a developer named JD, and introduction of the PIP form and the Test Report Template.

The tutorial takes the students through the planning process to both reinforce the lecture and ensure that the students are comfortable using the student workbook.  The example also includes recording actual size data.

For the class exercise students make a separate copy of their student workbook so they can practice working in the tool without disrupting their class data.  The tutorial leads a developer through the planning process, from conceptual design through a completed plan summary.  Use the slide materials as a guide to show the students a display of the student workbook and then illustrate how to record actual size data in the tool.

Introduce the PIP form is in this tutorial.  The tutorial slide shows the form, but the instructor should have good examples of PIPs and be prepared to discuss them.  Students will generally respond with good PIPs after being motivated by the instructor and seeing examples of good and poor PIPs.  The example PIPs should relate to the work the students have just completed, so a PIP about collecting good defect and time data would be appreciated.  Another good way to engage the class would be to ask the students for PIP ideas about better collecting data. An example could be keeping the script handy so the students always know what phase they are in to track time data consistently.  A PIP can also be very personal, such as the time of day the student works.  Some students find that working very late at night is not effective and that they actually save time by going to sleep and starting fresh in the morning.  “Trying harder” and “being more careful” are examples of poor and unacceptable PIPs.  “Trying harder” is actually saying “what I’m doing is not working, so I’m going to do more of it faster!”  A PIP must be both specific and actionable.  The bottom line is that the difference between a poor process and one that is convenient and easy to use (operation) concern the small details.

The Test Report Template is also introduced in this tutorial.  Point out that the test reports are also useful for design and regression testing.  The report should include enough information so the student can run the test to get the expected results.  The test report should include information such as which input file produces the expected results, precision of the input data and expected results, what data to input when prompted by the program, etc.  Explain that the tool provides multiple “pages” for test reports and that there should be a “page” for each test case.

## Program 2: Program Size Counter

The programming assignment uses PSP1 to write a program to create a program size counter.  Emphasize that the students should create their coding standard before beginning to write the program.  Keep in mind that the complexity of the coding standard will have a direct impact on the complexity of the programming assignment.  They will then be able to write a program size counter that is consistent with the way they will be working.  Stress two points for this assignment.  First, this is not an assignment to write a recursive descent parser.  For some students strategically placed comments that indicate the beginning of a new method in a class may make the assignment a reasonable one for their programming abilities.  Second, the students should pay careful attention to the test requirements and design their program accordingly.  It is often very useful for students and instructors to have the students include line numbers in the submitted source listings to facilitate a manual count of program size.  This method helps the students check if their line counting logic is working, and it makes the instructors’ review of program test results both easier and faster.

For students who are falling behind, this assignment can be simplified by having the students use tokens to mark the beginning and end of parts and items.  The students should already know how to open and read from a file, but they may need additional support in parsing text.

## Grading PSP1 Assignments

### General

Refer to section 2.9, General Grading Guidelines, for general guidance on grading.

Again, remember to provide written positive feedback and summarize your feedback at the top of the checklist.  Reiterate that the focus of PSP1 is having a defined estimating process that produces unbiased estimates.

When grading the PSP1 programs, focus on the new items, as well as on those that students found difficult in earlier assignments.  However, all the PSP0 process items must be checked to ensure that students do not regress.

### Program and Test Results

Check that the students have followed their coding standards.  Standards must be operational. They should help to do the work. Moreover, it is an exceedingly bad precedent to create standards, scripts, or guidelines that are not used. Something worth doing, is worth doing well.  If it’s not worth doing well, it’s not worth doing at all.  If the standard doesn’t help, the student should create a PIP.

Programming assignment 2 uses PSP1 and it is one program that the students use throughout the remainder of PSP Fundamentals course and also during the PSP Advanced course.  It is essential that this program works correctly and provides accurate counts.  .  The time invested in checking the correctness of this program will eliminate many issues that would otherwise come up in later assignments.

### The Test Report Template

Check that the students’ test reports contain the required data for all the tests that were run.  The students should describe the tests, document both the expected and the actual results, and turn in source listings for programs 1 and 2.

### Size Estimating Template

Since size estimating is the main change in PSP1, spend time in reviewing and understanding the student’s size estimating performance.  Performance improves with a combination of intended practice and feedback.   The size estimating objective is to be consistent.  Consistency is achievable by following a defined estimating process and basing estimates on historical data.  Focus on specific problem areas and point them out to the student.

For example, some students may be good at estimating new parts with their errors in the estimates of deleted and modified LOC.  Some students may be good at estimating the items listed on their size estimating template, but the size estimating template may not include everything e.g. main.  Convince the students that size estimating is an important part of the process and it is a skill that they need to practice to improve.  Some students may never become very good size estimators but they can learn to make balanced or unbiased estimates.  They should all seek ways to improve their estimating ability.

All of the required plan and actual size values must be correctly entered in the form.  A common mistake is to confuse base parts with parts additions and reused parts.  For example, if some base parts contain no modified or deleted code, ask the student why they are not treated as parts additions or reused parts.  Another common mistake occurs when parts additions are estimated and not developed, or developed but not estimated.  The same is true when a reused part has to be modified.

Also, verify that the type, items, relative size, and size entries for the parts additions are calculated and entered properly and that the students used the part-size table to make their estimates.  While students should create their own size tables after they have gathered enough data, they probably will not have enough programs to do so at this point.  Next, verify that PROBE method C or D was used for estimation.

Another way to check that the estimates are reasonable is to cross check that the planned productivity rate is reasonable for the student.

### Project Plan Summary

Size data is now included on the project plan summary.  Check to make sure that plan and actual data are entered correctly.   Also, check to make sure the planned productivity rate is consistent with the student’s past performance.  If the results are incorrect, ask the student how (s)he arrived at the numbers used in the form and resolve any problems.  Please note that size data is entered for assignment 1 but does not appear on Project Plan Summary for assignment 1.

### Consistency Checks

Repeat the consistency checks performed for the previous process level for the PSP1 programs, starting with a review of the PSP1 Project Plan Summary to determine whether the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Check the students’ time and defect logs and ask them to explain any unusual values. Also, check that the estimated and actual values from the PROBE Calculation Worksheet are entered in the proper places on the Project Plan Summary. An important check is that the actual Added (A) on the Planning Summary is close to and not less than the actual Based Added plus Parts Added (BA+PA) on the size estimating template. A discrepancy here indicates a problem with size accounting.  Note that the value of actual Added (A) on the Project Plan Summary is derived after actual Total (T) has been entered.  Some lines in the source code, such as the class declarations remain outside of the parts, it is therefore possible for Actual Added to exceed PS+BA.  If students have a discrepancy between the Project Plan Summary and the Size Estimating Template it is often because the way they are counting the actual sizes of program parts for the Size Estimating Template doesn’t agree with the way they are counting total size for the Project Plan Summary.

## PSP1 Tips and Hints

Distinguishing between planned and actual size often confuses students. During planning, students estimate the base, deleted, added, modified, and reused size elements and then calculate the total size and added and modified size by using these estimates.  For actual size, the size counter that they construct for Assignment 2 only counts the total size and number of parts in a program.  They must count manually the size of reused code and deleted and modified code and also calculate the size of added, modified, and added and modified code by using their manual size counts.

Using the PROBE estimation with limited data is a common source of confusion.  Explain that method C is a simple productivity calculation that uses their size estimate and the average productivity for the programs they have developed to date.  If they are confused about how to use method C, walk them through one example of calculating estimated development time with their own data.

# Day 3

This chapter covers the content of the third day of PSP Fundamentals.  The overall topic for day 3 is program quality.  The lecture helps students to understand the concept of quality and techniques they can use to produce high quality software.  The review checklist assignment describes how personal checklists are used in the PSP and the procedure for developing them.  A code review exercise is then conducted, followed by the PSP2 tutorial.  The day ends with the assignment of Program 3.

## Class Data Feedback

In this session discuss the class reaction of the first two days of training.  Most students should have completed program 2 and received the instructor’s feedback.  This is an opportunity for students to discuss the lessons that they have learned from doing the first two assignments.  It is also the instructors’ chance to discuss what they have seen in the student work they have graded.  Plan to discuss one or more or all of the following topics.

- not following their coding standard

- focusing on estimating accuracy over estimate balance. To achieve unbiased estimates students should be experiencing a balance between over and under estimated parts

- focusing estimating accuracy for only one data point (e.g. how is CPI?)

- not establishing a habit of data collection

- misunderstanding iterative development (they think they have to use waterfall process)

- some understanding of personal performance

  - average, max, and min productivity

  - how do I spend my time?

  - how should I spend my time?

  - what is the quality of my code?

  - how predictable/consistent is my process?

- recognizing personal strengths and weaknesses

- PIPs to prevent or mitigate common problems

If students are falling behind or have many resubmits, hold a class discussion to address the issue with the class.  Re-emphasize the purpose of the class and insist that assignments been correct the first time.  The longer the instructor waits to address this issue, the less likely they are to have a high assignment completion rate.  For struggling students, refer to the section on “Dealing with Students who are falling behind” for guidance on adjusting the programming assignments.

Use the instructor tool to collect and present data about student work.  Table 3.1, page 13, lists the data to be presented on day 3 of the course.  That list is also included in the class materials.

## Lecture 3: Software Quality

This lecture helps students to understand the economics of software quality and that they are personally responsible for the quality of the software that they produce.

The initial objective in giving this lecture is to explain that defect management is an important facet of software quality. Customers are not usually concerned about defects unless the defects cause problems, increase their costs, or delay their work.  However, defect management is enormously important to software developers.  Defects force them to rework old, defective code instead of developing new code.  Defects increase development costs and delay project schedules by weeks or months as developers fix defects in test.  As a result, most organizations spend half or more of their development time and effort fixing defects.

The lecture begins with a motivating question “What does quality mean to you?”  Have students talk about this before moving on to the next slide.  Get lots of ideas about what quality means before presenting the definition that’s used for the PSP.  After the discussion the lecture moves on to defining quality and showing how PSP focuses upon defect management.  In particular, the lecture emphasizes that developers need to remove their own defects and learn to prevent reoccurrences of the kinds of defects they have injected into their previous work.

The next slide points out that quality is an economic issue because of the way many software developers attempt to achieve quality.  An enormous amount of data show that removing defects before test is faster, cheaper, and more efficient than removing them in test.  Testing is essential, but it must be used properly because it is inefficient.  Testing should verify that all defects have been removed.  Testing becomes less effective as defect density increases.  Defects often mask other defects.  Repairing trivial defects takes time that could be used to test for more subtle defects.  The primary message of this part of the lecture is that late defect removal adds cost and reduces the effectiveness of the development process.

Instructors can motivate the transition back to the lecture slides with the question “If not testing, then what?”  This can lead to the concept of managed quality and early defect removal.  The lecture then describes different types of appraisals with slides on personal reviews, review checklists, and reviews before inspections.  The final slide in this section emphasizes the differences between testing and appraisals to help emphasize appraisals as a technique for managing quality.  This is followed by several graphs and tables that demonstrate the effectiveness of appraisals versus testing.

The next discussion is on the need for an objective quality assessment.  First, describe what objective means, and then discuss when the objective measure is needed.  Most people will agree that the best time to have an objective measure is after the author has had an opportunity to remove defects and before expensive defect removal methods are employed.  The last discussion is on tools that can be used to objectively measure product quality.

During this discussion, some students will have strong opinions about whether or not to review their code before compiling.  Do not to allow the class to become polarized over this issue.  Increasingly, modern programming languages and environments do not have compile steps, so the debate would be pointless.  Instead, focus the discussion on the need for an objective quality measure and the timing of that measure.  The main point is to get the students to agree to try the process as defined, to collect data, and then to decide.

The PSP quality measures (yield, review rate, defect injection and removal rates, defect-removal leverage) are mentioned here because it is essential for the students to understand them to manage quality.  Definitions are given in the PSP2 tutorial.

The lecture ends by reminding students that they are personally responsible for the quality of the components they produce.  It is the quality of the process they use and their commitment to process discipline that determines product quality.

## Review Checklists Assignment

The review checklist assignment has students create design and code review checklists based on their historical defect data.  The goal of the assignment is to produce checklists that enable the students to achieve high yields.  The students are asked to analyze the defects that they injected in their two programs to guide them in constructing the review checklists.  Sample checklists (design review and code review) for C++ are included in the assignment kit.  Remind students that the sample checklists may have little relevance to their defects and that their checklist items must be based upon the defects they have recorded during their previous programming assignments.  Students should submit their review checklists with this and all future programming assignments.  Instructors should not allow the students to submit the example checklists.  They must use their own defect profile and update their checklists throughout the course.  Point out that updates to checklists can be used for PIPs.

## Code Review Exercise

The code review exercise gives the students practice conducting a personal review by following a script and using a code review checklist.  The exercise starts by reviewing the entry criteria for the code review script.  Inform the students that, for the purposes of this exercise, the design is not included, but that designs typically are part of code reviews. The source listings of four files are provided.  This is a good time to talk about how much code should be reviewed at a time.  Walk through the first checklist item. Explain that they can use a check or can track captures and escapes.  Let each student conduct his or her own review (about 30 minutes).  At the end, chart (CodeReviewChart.xls) how many defects were found and the time each student required to perform the review and handout the exercise answers (Code Review Answers.doc.) Talk about the benefit of tracking captures and escapes.  Have a class discussion about their experiences using the checklist and looking for one checklist item at a time.  Also, discuss the defect types, pointing out that compilers or static analysis tools are not very good at detecting certain defect types.  Finally, discuss the last two steps of the review checklist and the exit criteria.  Make the point that the review phase is not over until the defects are fixed and verified.

## PSP2 Tutorial

The purpose of the PSP2 tutorial is to prepare students to follow the PSP2 process, using the student workbook, to complete programming assignment 3. The tutorial begins by describing the objectives of PSP2 and the process changes introduced in PSP2.  This is a good time to reiterate the progressions of PSP0, PSP1, and now PSP2.  A recap should discuss what was introduced in PSP0 and PSP1 and that PSP2 introduces quality management.

Walk through the use of the new PSP elements in the PSP workbook.  Students should follow along by making entries in a workbook on their computers.  After estimating development time, students estimate review time, total defects, and defects injected and removed by phase.  Also point out that the tool calculates planned defect removal efficiency and leverage, test defects per KLOC, total defects per KLOC, and yield.  Show students where these values appear in the tool.  Since this is the first time these terms have appeared, it is important that students see how values are derived and where the derived value appears in the tool.  Also prepare an example to go through the derivations of these quality measures with the class.

## Program 3: Correlation and Significance

The programming assignment is to use PSP2 to write a program to calculate the linear regression parameters and correlation coefficients for pairs of data values.  The concepts in this assignment are more difficult than in the two previous ones, although the values can be calculated with a simple arithmetic procedure.  Demonstrate how the values are calculated by the assignment kit with sample calculations.  Draw on a flip chart the relationship of 0 and  1 to the pairs of data values.  Then describe how rx,y relates to the picture you have drawn.  Note that use of Program 1 as base is encouraged.  (Some students may have constructed code for Program 1 that can be reused, rather than modified.)

For students who are falling behind, the only way to simplify this assignment is to have the student closely follow the worked examples and develop their programs in small iterations.  The students should be advised to use variable or fixed arrays instead of linked lists.

## Grading PSP2 Assignments

### General

Refer to section 2.9, General Grading Guidelines, for general guidance on grading.

Again, remember to provide written positive feedback and summarize your feedback at the top of the checklist.  Reiterate that the focus of PSP2 is having a process that consistently produces high quality products.

When grading the PSP2 programs, focus on the new items, as well as on those that students found difficult in earlier assignments.  However, all the PSP0 and PSP1 process items must be checked to ensure that students do not regress.

### Project Plan Summary

Project Plan Summary entries that are automatically calculated by the PSP workbook need not be checked and verified by the instructors.  Planned and actual defect entries need verification to ensure that the defect plans were based on actual data.  Also, planned and actual review rates should be low enough to provide a suitable yield.  A common problem is that students plan too little design review or code review time.  Emphasize that, if they don’t plan to do quality work, they probably won’t get high yields.  The second and more serious issue is that students rarely spend the planned amount of time performing the reviews.  Students should be urged to spend more time in their reviews when actual review times for each assignment are too low.  Research has shown that checklists are effective when each item is given conscious consideration. Rapid review of a checklist is ineffective. Simply reading code is ineffective. Consider strategies such as selecting an item and reviewing the code from bottom to top to prevent a cursory reading of the text.

Check the CPI.  Often students have problems estimating effort for a particular program, but their CPI across several programs is good.  This illustrates the point that breaking estimates into multiple parts and making balanced estimates produces more accurate results.

### The PIP Form

When students have low yields (based on individual performance), they should identify the problem on their PIP forms and list planned actions to obtain better results in the future.  If they have not done this, reject their programming assignments and require them to add completed PIPs containing this information.  When they resubmit the assignment, check the PIPs to make sure that the planned actions will likely improve their yields.  Don’t accept poor yield reviews without requiring the student to take corrective action!  Then check the next assignment to see if they actually did what they said they would do.  Suggestions to slow down review rates to improve yield include

- taking a break between development and review phases

- including more detail to the review checklist

- reviewing in smaller pieces

- reviewing at a time of day where the student is most alert

- ensuring that the student is reviewing for each checklist item separately

- identifying the review steps that previously missed defects and performing them more slowly and carefully

- the key to high-yield reviews is for the students to plan a realistic amount of time for review and then keep reviewing until they have spent that amount of time

### Design and Code Review Checklists

Personal reviews are the major change in PSP2 and enough time should be spent to ensure that the students properly conduct their reviews.  Make sure the checklists are based on the students’ historical data and have the students submit their defect logs as part of their assignments.  Check that the students are conducting reviews properly and using the checklists appropriately.  If students are reviewing too fast, look at the suggestions in the PIP section above on how to slow down review rates.  Motivate students to feel personally responsibility for the work they produce.

### Consistency Checks

For the PSP2 programs, repeat the same consistency checks for the previous process level.  Data entered into the Size Estimating Template are transferred to the Project Plan Summary, however, students who attempt to change their workbooks after marking a program complete may corrupt the workbook data base.  When they do, the values on the Size Estimating Template may not be consistent, and the values on the Process Plan Summary may not agree with those on the Size Estimating Template.

First, review the PSP2 Project Plan Summary to determine that the data are reasonable.  Also, verify that the planned times and sizes are reasonably consistent with the actual size and time relationships for previously written programs.  Similarly, ensure that the relationships between the actual size, time, and defect data are reasonable.  If any of the consistency checks reveal significant discrepancies, the data likely contain errors or were made up.  Finally, check the students’ time and defect logs and ask them to explain any unusual values.

In a sense, yield is a consistency issue.  If the students’ yields are low, it generally means that several parts of their processes are inadequate.  If this seems to be the case, check that they planned properly, updated their checklists, used the new checklists, and spent adequate time doing the reviews.  Once students take all of these steps, their yields should improve.

Another important consistency check is of the defect-removal rates.  If students do not find about two to three defects per hour during design reviews or about five to ten defects per hour during code reviews, they probably need guidance.

## PSP2 Tips and Hints

Below are some hints and tips that are based on our experiences teaching many PSP Fundamentals courses and from analyzing the data gathered from thousands of PSP class programs. Instructors should consider these points as they give lectures, answer questions, and advise students.

The goal of PSP2 is to introduce design and code reviews.  Generally, when working on PSP2 assignments, students find few if any defects during design reviews.  This is usually for two reasons.  First, they do not have a very complete or precise design to review.  Second, their reviewing methods are probably still rudimentary.  They will not find many sophisticated design problems by merely reading through their designs with a checklist.  Instead, they must complete a careful design analysis.  That topic will be taught in the PSP Advanced course.

The problem to focus on for PSP2 is code reviews with poor yields.  Consider two things in addressing this problem.  First, when students hurry through their reviews, they will get low yields.  Suggest that they plan a realistic amount of time for review and then keep reviewing until they have spent that amount of time.  They may have to repeat parts of their checklists but by forcing themselves to continue reviewing until they have spent the planned amount of time, they will slow down and do much better reviews.  Second, without constant reminders, students rarely update their checklists to take advantage of their latest defect data.  Doing so consistently can make a major difference in review yield.

# Day 4

This chapter covers the content of the fourth day of PSP Fundamentals.  The overall topic for day 4 is task and schedule planning and tracking.  After the class data feedback discussion, the lecture shows students how to build and track against task and schedule planning using earned value.  These skills are shown to be important for working on a team.  Programming assignment 4 is then introduced.  There are no more process tutorials.

## Class Data Feedback

In this session the class reaction of the first three day of training is discussed.  Most students should have completed program 3 and received instructor’s feedback.  This is an opportunity for students to discuss the lessons that they have learned from doing the three assignments.  It is also the instructors’ chance to discuss what they have seen in the student work they have graded.  Plan to discuss one or more or all of the following topics.

  - how to slow down a personal review

  - what’s missing from designs

  - why designing while coding is error-prone and deprives the student of the design review phase – think of PSP as a system of filters and the consequence of removing one of those filters

  - the power of a common vocabulary to share with co-workers

  - updating checklists

The instructor tool is used to collect and present data about student work.  Table 3.1, page 13, lists the data to be presented on day 4 of the course.  That list is also included in the class materials.

## Lecture 4: Task and Schedule Planning

The goal of this lecture is that students understand task and schedule planning and tracking.  While task and schedule planning is not a big topic in PSP, it is in TSP.  After showing students how to build task and schedule plans and how to track their work against the plan, they are then shown how teams can use earned value for tracking team status against the plans and for projecting project completion.

The lecture begins with a class discussion on “Why do we need good plans?”  The slide has seven additional questions on it.  All of these questions are about the reason that developers need good plans.  Engage the class on these questions and pose additional questions during the discussion session.

The question “What are the characteristics of a good plan?” follows.  The answers should be documented on the white board.  Some of the expected answers are

- Lists all tasks that need to be completed.

- Uses estimates based on historical data.

- Is based on available project hours.

- Can be used to understand the impact of changes.

- Is used to guide the developer’s daily work.

- Allows the developer to easily evaluate progress against a plan.

- Allows the developer to easily and regularly estimate a completion date.

- Allows the developer to coordinate interdependent task with others.

- Allows the developer to articulate the scope of work to be performed to others.

The lecture introduces task and schedule planning and earned value as a way to measure progress against a plan.  The “rules” of earned value are made clear, so that earned value tracking will be unambiguous.  The slides show an example of using earned value to track a plan and estimate a completion date for an individual’s project.  The lecture slides also show how to recalculate the value earned by task when plans change.

Next is a discussion of task and schedule planning and plan tracking by teams.  Sample Week forms from a TSP workbook are shown, and questions are asked about how to interpret the data.  Be prepared to discuss these slides.  In some cases, you will need to do some real-time calculations, so prepare calculations in advance.  Some instructors may find it more useful to prepare lecture notes to hand out in place of real-time calculations.

## Program 4: Relative Size Table

Students are asked to use PSP2 to write a program that computes representative values for relatives sizes (very small, small, medium, large, and very large) for a set of data.  The data are assumed to be log-normally distributed.  The discussion in the assignment kit demonstrates how to transform a data set that is log-normally distributed into a data set that is normally distributed.  After calculating the standard deviation for the transformed data set, the representative values for very small, small, etc., can be transformed back into the original domain.

Mention that this is the source of the values in the C++ proxy table that is given in the PSP workbook.  Draw some pictures to help explain the transformations.

Program 4 tends to be one of the smaller programs.  Typically students who get to this point in the class complete this assignment without much delay.

Since the process is the same for Program 4 the PSP2 Tips and Hints shown in section 7.8 are applicable to the development of this program.

## Grading Program 4

Refer to section 2.9, General Grading Guidelines, for general guidance on grading.  Students use PSP2 to complete programming assignment 4, refer to section 7.7 Grading PSP2 Assignments for grading guidance.  Using the same process is an excellent opportunity for students to benefit from previous feedback and to grow comfortable following a process without major changes.  You should expect to see productivity and quality improvements, be sure to point these out to students.  PSP skills improve with practice and most students’ data will show that their improvement has not yet hit a plateau.  Point this out to the students.

## Program 4 Hints and Tips

Since program 4 uses PSP2, refer to section 7.8 PSP2 Tips and Hints.

# Day 5

This chapter covers the content of the fifth day of the PSP Fundamentals course.  The principal topic for day 5 is a capstone exercise pulling together all of the PSP concepts.  The final topic is TSP Overview lecture to prepare the students for a TSP project launch.

## Class Data Feedback

In this session the class reaction to the first four days of training is discussed.  Most students should have completed program 4 and received the instructor’s feedback.  This is an opportunity for students to discuss the lessons that they have learned from doing the four assignments.  It is also the instructors’ chance to discuss what they have seen in the student work they have graded.  Plan to discuss one or more or all of the following topics.

  - how to slow down a personal review

  - what’s missing from designs

  - why designing while coding is error-prone

  - when you design during coding you also deprive yourself of the design review phase – think of PSP as a system of filters and the consequence of removing one of those filters

  - the power of a common vocabulary to share with co-workers

  - updating checklists

Students have used PSP 2 for the third and fourth programs.  Thus, there are no new process elements to be discussed today, so the same graphs are displayed in the PSP instructor tool as were displayed on day 4.  Point out that with no new process changes, trends may become more apparent after four programs.

The instructor tool is used to collect and present data about student work.  Table 3.1 lists the data to be presented on day 5 of the course.  That list is also included in the class materials.

## Capstone Exercise

This exercise is a multi-part case study exercise about a developer, Otto, using PSP2.  The purpose of this exercise is to bring together all of the parts of the PSP into one project and show how these data might be used in an industrial setting.  Also, the exercise illustrates the consequences of quality and plan management in both positive and negative ways.

The principal objective of this module is to give the students a feel for what it is like to use PSP.  This exercise gives students experience in

- evaluating PSP plans

- using process data to understand the status of a project

- using process data to improve

Each part of this exercise is conducted by breaking the class into groups of 4 to 6 individuals and having each group review the material in the exercise workbook, come to a group consensus on what they find/recommend, and prepare a flipchart with their findings.  As the groups review the data, circulate around and check with the groups to make sure they are not having problems.

In preparing for this exercise for the first time, the instructors should

- Run through the exercise as a student, if they haven’t already done so.

- Read through the exercise answer (Capstone Answers.doc) and make sure they are comfortable with the data.

- Based on the class and configuration, define small groups/teams and determine how much time can be spent in small group discussions and overall class discussions.

## Lecture 5: TSP Launch and Overview

The purpose of the lecture is for students to have a high-level understanding of the TSP, understand how PSP fits into the TSP, and understand their responsibilities as team members before and during a launch.

The lecture begins by reflecting back upon some of the problems that were mentioned in the introductory lecture on the first day.  It demonstrates that problems faced by teams are quite similar to problems faced by individual developers and that the consequences are equally problematic.

The lecture then shows how TSP addresses the problems highlighted in the first slide of the lecture. It demonstrates how TSP fits with the PSP, shows how the measures of the TSP are the same basic measures as those of the PSP, describes team data, and covers the TSP launch process.

Next, the lecture describes how a team performs its planning, how individual plans are merged into an overall plan, and how the team tracks its performance against its plan.

The next discussion is about how teams manage quality.  Graphs from the TSP workbook demonstrate how teams can view their quality plan and track their quality performance against it.

The next part of the lecture describes how teams work.  In particular, the objectives of the weekly team meeting are described.

Remember that many (perhaps all) of the students in the class will soon become members of a TSP team.  The goal of this lecture is for them to understand that the PSP knowledge and skills that they have learned in PSP Fundamentals will apply to their TSP teamwork even on their first day on a team.  For this reason the instructors should use their TSP team experiences to help relate this lecture to the students’ work environment.

The slide about PSP Advanced can be used to point out to the class that they have not learned all there is to learn about PSP.  Students in the class who want to learn more about PSP, become certified, or become a PSP Instructor or TSP Coach will need to take the PSP Advanced course.

On the evaluation slide, the students are to complete the SEI evaluation form.  The students should follow the directions on this slide to complete and return the evaluation form to the SEI.  Additionally, instructors should conduct an interactive postmortem and gather and forward notes to SEI to help improve the course materials and to improve the presentation of the materials.

# Frequently Asked Questions (FAQs)

## Day 1 FAQs

Q: Can I use my work assignments instead of the programming assignments?

A: Students should not use programs that they must write as part of their jobs.  Since developers are uniformly unwilling to try new and unfamiliar methods on production code, the risk is too high that they will not use the PSP properly.  Also, this would involve a tremendous amount of overhead for the instructor to develop minimum test requirements and expected results.

Q: Why do we need to write programs to learn the PSP?

A:  The PSP Fundamentals course teaches you how to follow a planned, managed, and quality controlled personal process.  To do this, you must actually use such a process.

Q:  But couldn’t we use a simpler process than writing programs?

A:  While this course could theoretically be taught with any process, the software development process is sufficiently rich and complex to provide convincing data with a few simple exercises.  Other processes would likely take a great many more data points and a lot more time to provide similar results.

Q: Why do I have to write these mathematical programs?

A: The programming assignments have been chosen because they

- are straightforward to define

- avoid requirements misunderstanding

- can be done in about three to five hours.

The programs are mathematical because they satisfy these criteria.  Including imprecise or changing requirements in the PSP programs would increase the time required to write the programs and introduce a degree of variability that would make both individual and class data difficult to interpret and use.  While it is important for students to learn about the general imprecision and changeability of requirements, that is not the purpose of this course.

Q:  I use agile methods in my work.  Can I use them in the PSP Fundamentals course?

A:  While agile methods are compatible with the PSP and TSP, this course is not designed to use them.  The phases used in this course designed to separate and measure rework.  An agile process can be instrumented, but phases will not have the same interpretation.  For pedagogical reasons, we should use the phases as designed for this course and then later consider using agile methods with your TSP team.  The materials to teach PSP Fundamentals courses with agile methods are not currently available with the level of support you would need to do programming assignments.

Q:  Why isn’t quality taught first instead of planning?

A:  To appreciate the importance of the PSP quality methods, you need personal defect data.  With the relatively small PSP programs, that requires data from three or more programs.  Rather than requiring you to write more programs, the course was designed to provide these defect data from the programs that teach the PSP planning methods.

Q: Since the compiler finds syntax defects, why should I record the compiler defects?

A:  There are two reasons.  First, by merely recording these data you will become more aware of your mistakes and make fewer of them.  Second, your principal concern is with the mistakes you make.  Since most programming mistakes produce at least some defects of types that are often missed by the compiler, not recording compile defects will omit a lot of potentially useful information about the kinds of mistakes that you make.

Q: I developed a prototype, how do I track this time?

A: Ask the student what script they were following when they developed the prototype.  If the student is not following a script, then you need to determine which phase the student was in when the work was done.  In most cases, a prototype is developed to understand how something works so that a proper design can be established.  You should point out the difference between prototype code and production code.  Do you require prototype code to adhere to your coding standard?  Does your prototype code have to be robust?  Does your prototype code have to be industrial strength?  However in some cases, the developer is designing while coding and in that case all of their time is tracked to the coding phase.  The answer depends on the specific situation so make sure the students know how the data will be used so that they can make the right decisions for themselves.

## Day 2 FAQs

Q:  I’m used to writing programs in SQL and don’t want to use LOC.  What can I do?

A:  The textbook includes an extensive discussion of this subject in Chapter 3.  Read that chapter before writing the exercise program.  To develop your own size measure, identify the elements of your programs that can be counted and write a program to count them.  Write the program to count each of the element types separately.  Then determine which combination of the element count types produces the most reliable correlation between size and time.  You can try several combinations of these measures while writing your first several PSP exercise programs before deciding.  The data generated when writing the programs will guide you in selecting the most suitable counting standard.  The textbook gives some examples of how to do this.

Q:  It seems that base code and reused code is the same thing.  For example, if I reuse Program 1 to write Program 3, would Program 1 be reused or base code?

A:  According to the PSP convention, if you are modifying and enhancing an existing program, the original unmodified program is considered base code.  There is, however, an exception.  Only if the base program was designed to be a reusable program and if you do not make any changes to that code, is it considered reused code.  The reason for this distinction is that in most cases, developers write new programs by modifying and enhancing existing ones.  They typically start by developing a small core portion of the program as “version one” and then follow a cyclic process to add new code to this base with each successive cycle.  Since the original core of code for cycle one was the first step in this cyclic process, it is considered base and not reused code.  This type of cyclic approach is a recommended strategy for developing the larger PSP programming assignments.

Q:  Why does PROBE produce balanced estimates?

A:  Using data from your own work is the key to making accurate, balanced estimates with the PROBE method.  However, you must use the data in a statistically sound way.  You start by creating a conceptual design that divides the planned product into parts.  You then use historical data to estimate the sizes of parts of the new program that are similar to parts of programs that you have developed in the past.  Next, assume that the new parts will have the same average size as similar parts that you have already developed.  After you have made a number of estimates in this manner, on average, your estimates will be correct and balanced.

Q:  The sizes in the size table in the textbook look too small to me.  Do I have to use the values in that table?

A:  No, you can use whatever size data seem most appropriate for your program, but you must use a size table.  If you do not have enough data to create a size table, you must use the table in the textbook until you have data from enough programs to produce a table of your own.  Once you have enough data to build your own table and use it, you can go in the student workbook, click on Size Measures tab, select “LOC” and click on Open Size Measure button, and on the next screen click on Update button.

Q:  How does conceptual design differ from real design?  Why not just make the real design?  Then you’d have a better design and a better estimate.

A:  That is correct.  If you first produced the real design and used it for estimating, you would almost certainly have a more accurate estimate.  That also holds true for estimating implementation time.  After you wrote and tested the program, your estimate would be very accurate, but it would merely be a record of historic fact.  In the PSP Fundamentals course, our goal is to make accurate estimates before actually doing any of the work.  To make the estimate, you must have an idea of what you intend to build and the parts with which you intend to build it.  You create the conceptual design to help you identify and estimate the sizes of these parts.  While producing the actual design may produce a better estimate, it would not build your estimating skills.  The purpose is to produce a reasonable estimate in the development process when it is most needed and useful, rather than a better estimate at a later, but less useful time.

Q:  In my organization, we use function points to make size estimates.  Could I use the function point method instead of PROBE?

A:  While you could use the function-point method with the PSP and TSP, you must use the PROBE method in this course.  The function point and PROBE estimating methods are similar in several ways.  They both use proxies as an intuitive framework for estimating size and they both use defined methods for combining the proxy data to produce the estimate.  One difference, however, is that the PROBE proxies are physical program entities that can be measured, while the function point proxies are not.  After completing the course, you can use the function point method if you find it helps you to make better estimates.

## Day 3 FAQs

Q:  Can I use my PSP Fundamentals course data for estimating the projects I do at work?

A:  First, you must ensure that your PSP data are relevant to your working situation.  For example, if you must adhere to stringent specifications that could increase program size, you must either use data that are developed using the same specifications or make adjustments to your PSP data.  Of course, after you actually have data from your work environment, you should use it.  Also, experience shows that developer productivity is generally lower on the job than it is in the PSP class.  While there are many possible reasons, when developers are in a classroom environment, they have very few interruptions.  When you start measuring your time on the job, you will find that interruptions can waste a lot of time and seriously reduce productivity.

If you determine that the PSP Fundamentals course data are relevant, you can certainly use them for size estimating at work.  However, your productivity data will probably not be usable for anything but general guidance.  Regarding size data, use care when selecting the PROBE method.  If your work programs are much larger than the PSP exercises, use method C until you have historical data for similar sized programs. Do this regardless of how much data you have or its correlation.

Q:  How many data points do I need to make my own relative-size table?

A:  With two data points, you have an average, a large, and a small value.  While that only provides one proxy type table for all programs, it is better than nothing.  After you obtain two data points on several proxy types, you can build a usable relative size table.  While gathering more part data would give you a broader and more representative set of size ranges, you can start with very little data.  If you have only one data point that is reasonably representative of your programming style, you can use it as an initial guideline for the average parts sizes for the next program.  With more data, of course, you can improve the table.

Q:  I use SQL, C++, and a special application language at work. How can I use PROBE?

A:  The simplest way to address this situation is to make separate estimates for each language and environment.

Q:  Why should I bother recording the defects I find in compiling?   Since the compiler finds these defects, why do I care?

A:  Your real interest is in the mistakes you make that cause the defects, not in the defects.  With data, you can often figure out how to prevent mistakes.  The problem is that even your simple mistakes, like typos, misspellings, and omissions, sometimes produce defects that the compiler will miss.  Most of these defect types, when missed by the compiler, can be quickly found in test.  However, every so often, one gets past compiling and testing and causes untold user problems.  Unfortunately, there is no easy way to tell which mistakes will cause defects that the compiler will find and which produce defects that it will miss.  So, if you are trying to eliminate all of the defects from your finished products, you must gather data on the compile defects because they will provide clues that will help you to prevent about half of the mistakes that you make.

Q:  If I perform a review after compiling, I would only need to find the defects that the compiler missed.  Why doesn’t that work just as well?

A:  If you do equally thorough reviews before or after compile, it doesn’t matter when you do them.  However, the evidence shows that when developers defer their reviews until after compile, the reviews are much less effective and program quality, development costs, schedule, and performance all suffer.  In the class, you are required to complete the reviews first.  Later, when you are working on a TSP team, you might want to have some team members do their reviews before they compile, and others do them afterward.  Then you can compare the quality of these two sets of programs and see which have the most defects in test.

Q:  I’ve got a marvelous debugger that has really accelerated my testing.  How can a code review be as fast or effective?

A:  There are two reasons.  First, a debugger can only track the progress of one test at a time.  This one test only covers one set of paths with one set of variables and parameters.  By using sound review practices, you can see all of the possibilities at once and see defects that you could not find without running the debugger with a large number of tests.  Second, to use a debugger properly, you must know the expected variable values at each step of the program.  If you are going to make a detailed enough analysis to determine all of these values, why not take a little more time and do a thorough review?  You can still use the debugger to check your results.  Debuggers can be very helpful for tracking down the occasional puzzling defect, but they are not an efficient way to find volumes of defects in testing.

Q:  My management doesn’t seem to care about quality.  Their only concern is releasing on schedule.  How do I convince them that quality is important?

A:  Regardless of appearances, your management almost certainly does care about quality; they just don’t understand the economics of quality and how quality work can save them time and money.  Suppose, for example, that you asked them, “Does the product have to work?”  They would likely get angry and say, “Of course it does.”  So quality is certainly important at the product level.  But few managers realize what poor quality practices cost them in time, money, and customer satisfaction.

There are a couple of ways to get managers to recognize the importance of quality.  The first and most effective way is to convince them to introduce the TSP and to attend the introductory executive seminar.  The other way is to gather test data and show them that test time is directly related to the number of test defects.  Since test time is often 30% to 50% of most project schedules, they should be interested in reducing test time.  This in turn requires that they reduce the number of test defects.  After managers understand this, the PSP and TSP methods will look more attractive.

# References

| [Humphrey 95] | Humphrey, Watts S. A Discipline for Software Engineering. Reading, MA: Addison Wesley, 1995. |
| --- | --- |
| [Humphrey 97] | Humphrey, Watts S. Introduction to the Personal Software Process. Reading, MA: Addison Wesley, 1997. |
| [Humphrey 05] | Humphrey, Watts S. PSP: A Personal Improvement Process for Software Engineers. Reading, MA: Addison Wesley, 2005. |

®SM 	Personal Software Process and PSP are service marks of Carnegie Mellon University.

®	Carnegie Mellon is registered in the U.S. Patent and Trademark Office by Carnegie Mellon University.