Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# A Strategy for Mentoring Students on PROBE

The purpose of this memo is to describe a strategy for mentoring students to help them get good results using the PSP PROBE estimating technique. The technique involves using proxies and historical size and effort data to estimate the size and effort for software projects.

Both the PROBE time and size estimates are determined by first estimating the proxy size (denoted as E on the size estimating template) and then are calculated using regression coefficients derived from historical data.

In order to get good time estimates or good size estimates, the student must first get the proxy estimating working and then accumulate enough data to get the regression working. The proxies represent the component “parts” of the solution that will perform the work. Proxies can be roughly estimated in size (for example, small, medium, large).  When appropriate parts have been identified and sized, PROBE will, with sufficient data, lead to accurate planned size and effort projections. So when students are not getting good size or time estimates with PROBE, the first place to start is by examining how well they followed each part of the proxy estimating process.

There are three basic steps to the proxy estimating process. The first step is creating a conceptual design which identifies the parts needed to build the program. These parts are the proxies in PROBE. This is not a High Level Design, but serves only to help understand the problem conceptually.  For example, one might identify the parts as classes without describing the class interfaces or data structure.   The second step is estimating the relative size of each proxy by assigning a type and relative size to each proxy. The third step is to determine the estimated size by using the size from a relative size table that has rows for each proxy type and columns for each relative size category.

### The Conceptual Design.

The first thing to check is the conceptual design. The common problems are failing to identify needed parts, identifying parts not actually needed, incorrectly assigning relative size, and inaccurate conversion from the relative to estimated size.  Some questions to ask include

- Were all the parts needed for the solution identified in the conceptual design?

- Were parts identified that weren’t needed?

- Is the conceptual design detailed enough?

One part with multiple methods or no parts and only Base additions will seldom result in good proxy estimates in the PSP class. This is because to get good overall proxy size estimates, students need multiple parts with some over estimated and some under estimated so the errors tend to cancel. To achieve this in the PSP class, where the programs are small, students should generally treat each method in a class as a separate part. However, this should not be taken to an extreme; you don’t want to end up with dozens of parts. Trivial methods should not be included. Somewhere in the neighborhood 6 to 12 parts is fine. If the conceptual design seems to be complete and at the right level of detail, then the next thing to look at is the typing and relative sizing of the parts.

### Type and Relative Size.

Most students use the relative size table from the book which has 6 types and 5 relative size categories. Most students don’t have problems typing the parts but occasionally some misunderstand the types. Some students have trouble with picking the relative size category. This is easy to identify because the actual size turns out to be much different than the estimate. When a part turns out to have a very large actual size (>100), it is likely the student didn’t take the conceptual design to a low enough level.

### Estimated Proxy Size.

Another problem you may find is that the student is not using numbers from the table, but instead entering their best guess for the proxy size. This should not be done because it will likely cause the student’s estimating process to become unstable. Learning and improvement requires feedback from a stable process providing consistent results. The student should use values from the standard relative size table until they have enough data to build their own size table.

One last potential problem could happen; the relative size table from the book may not work for the student. This is apparent when most of the added part actual sizes are much larger than the estimated part sizes. Another indication is that the beta1 value for method A is around 2 or larger. What is happening here is that the student’s coding style produces larger sized parts than the relative size table. If the students have enough parts data in the PSP tool, they can create a new relative size table from their own data (look under the size measure tab). This will often solve the problem. The alternative is to continue using the book relative size table and ignore the recommendation that beta1 should be less than 1.5.

Now, if the student has a good conceptual design (the right level and has not missed parts), has typed and sized the parts correctly, and the relative size table matches the student’s coding style; the sum of the added parts estimate should be close to the sum of the actual added parts size.  This being the case, and assuming the student isn’t classsifying all the additions as Base additions (discussed above), the student should have a good estimated proxy size, designated as E in the size estimating template. The estimated proxy size (E) is the basis for the second part of PROBE that applies the size and time regression coefficients, beta0 and beta1, to arrive at the size estimate and time estimate for the program.

### Estimated Size.

Let’s discuss the size estimate first. If the estimated proxy size (E) is good, but the size estimate isn’t; the problem most likely is the historical data used in the regression. The options here are to (1) look for outliers in the data, (2) use method C or D, or (3) get more data. The good news is that if the students are doing well with size estimating, their size estimating will get better as they get more data and start removing the older poorer data.

### Estimated Time.

Now let’s discuss the time estimate. If the estimated proxy size (E) is good but the time estimate isn’t, then there are two major possibilities: (1) there is not a correlation between their actual size and actual time, or (2) their historical data is not representative of their current process.  This second one is only a temporary problem; their time estimates will improve as they gather more data and eliminate the outliers or obsolete data.

The first one is a temporary show stopper; if the student doesn’t have a correlation between actual size and actual time, their time estimating will not be good. So, what do they do if they don’t have a correlation between actual size and actual time? It means their total productivity has a high variation. The first thing is to figure out what’s causing that. It could be many things including the process changes introduced during the class. A good way to look for the cause is to chart time (minutes or hours)/KLOC by phase for all the programs.

Looking at this chart may help them identify where in their process the variation in productivity is occurring and thus narrow their search for the root cause. For instance the above chart shows that the design phase has grown significantly, peaking with program 6. And the test phase, since program 4, has been highly variable.  It is likely that process changes will be needed to fix the problems identified so this may take some time before a size time correlation is achieved. However, this is necessary in order to get time estimating working. As long are there significant variations in their productivity, their time estimating accuracy will also show significant variation.