## Slide 1
PSP Instructor Training
Lecture: Using the PSP
Notes: <number>

## Slide 3: Lecture Topics
Working on a team
What is the TSP?
The TSP Launch
Working on a TSP project
Notes: <number>

## Slide 4: Working in Teams
Successful teams are both satisfying and rare.
Although many teams come close to meeting their product and business goals, they often do so at the expense of the team members.
We describe a team that works together smoothly and efficiently as being a “jelled team.”
“A jelled team is…greater than the sum of its parts… and the enjoyment people derive from the work is greater than you would expect.”
- Peopleware, DeMarco and Lister
Notes: <number>

## Slide 5: Why Do Teams Succeed or Fail?
A team’s success or failure is often attributable to the ability of individuals to work together as a team.
Technical issues are generally not as important to team success as non-technical issues and “people” issues.
People issues are often caused by non-technical issues that produce frustration, anger, and other behaviors that are disruptive to the team.
Notes: <number>

## Slide 6: Key Non-technical Issues
Some key non-technical issues that affect teams are
  poor leadership
  non-supportive work environment
  lack of clear or shared understanding of individual responsibilities
  unclear goals or priorities
  forced commitments
  undefined or unplanned approach to the work
  unrealistic expectations
  lack of discipline or commitment
When these issues are not addressed by the team or management, team performance suffers.
Notes: <number>

## Slide 7: Team-building Takes Time
The ability of a team to work together effectively develops over time.
Teams generally begin with
  diverse goals
  no clear sense of responsibilities
  vague ideas of the product to be built
  different approaches to the work
In time, team members converge on a mutual understanding of these factors and can achieve their best performance.
Under normal circumstances, the evolution of a successful team can take months or even years.
Notes: <number>

## Slide 8: Accelerating Team-building -1
Artificially-jelled teams can be built quickly through “team-building” exercises.
  retreats, seminars, workshops
  games (paintball, laser tag, etc.)
  contrived challenges (e.g., blind obstacle courses)
Team-building activities are unlikely to produce long-term team success unless they address real workplace issues.
  common understanding of roles, goals, products
  management support of team needs
The TSP is an effective way of building jelled teams quickly.
Notes: <number>

## Slide 9: Accelerating Team-building -2
The TSP addresses the need for
  teams who can build quality products within cost and schedule constraints
  building teams quickly and reliably
  optimizing team performance throughout a project
  accelerating process improvement
  making use of mature processes normal and expected
Notes: <number>

## Slide 10: What is the TSP?
The TSP is a framework and a process structure for building and guiding engineering teams.
The TSP contains
  a team-building process that builds shared goals, commitments, and cohesion
  a team-working process that guides the team’s engineering processes and practices
A prerequisite for TSP teams is mastery of the software engineering and process skills taught in the PSP course.
Notes: <number>

## Slide 11: The TSP -1
The TSP uses a team-directed approach to team management.
It works best for
  integrated product teams
  teams with 3 to 15 members
It can be applied to projects that involve both new development and enhancement.
Notes: <number>

## Slide 12: The TSP -2
The TSP was designed for groups of people who
  are working together towards a common objective
  do interdependent work
  have been trained to use the same methods for planning, tracking, and managing their work
  depend on and support each other
  need to act, feel, and think like a close-knit group
It includes process elements that facilitate successful team-building.
  personal discipline: responsibility for quality
  common understanding of team goals, roles, and work processes
  techniques to manage the work to a successful conclusion
Notes: <number>

## Slide 13: The Need for Personal Discipline
Teams need people with good professional skills, but building successful high-performance teams requires more than just technical ability.
Successful high-performance teams are built of members who are committed to the concept of personal discipline.
Personal discipline means that all team members understand their own abilities and can make realistic commitments to each other and to management.
Team members develop personal discipline by learning the principles of the Personal Software Process.
Notes: <number>

## Slide 14: The PSP
The PSP shows developers how to
  measure and manage their personal work
  use data to make sound plans
  manage the quality of their work
  produce quality products on predictable schedules
The essential elements of the PSP are
  performance measures
  estimating and planning skills
  quality management skills
Notes: <number>

## Slide 15: The TSP Strategy
The TSP strategy improves performance from the bottom-up.
Team
Member
Skills
Team
Building
Team
Management
Process discipline
Performance measures
Estimating & planning skills
Quality management skills
Goal setting
Role assignment
Tailored team process
Detailed balanced plans
Team communication
Team coordination
Project tracking
Risk analysis
Personal Process
TSP
Notes: <number>

## Slide 16: The TSP Process Structure
TSP projects can start on any phase or cycle.
Each phase or cycle starts with a launch or re-launch.
The strategy is to
  develop in increments
  use multiple cycles
  work-ahead
TSP permits whatever process structure that makes the most business and technical sense.
Development
phase
or cycle
Development
phase
or cycle
Phase or cycle
Postmortem
Development
phase
or cycle
Launch
Re-launch
Project
Postmortem
Lessons, new goals, new requirements, new risk, etc.
Business and technical goals
Estimates, plans, process, commitment
Work products, status, metrics, results
Notes: <number>

## Slide 17: The Overall Plan and Cycle Plans
Launch
Cycle 1 Postmortem
Overall Plan (for entire project)
Cycle 1 Plan
Cycle 2 Plan
Cycle 3 Plan
Cycle N - 1
Plan
Cycle N
Plan
Re-Launch
Cycle 2 Postmortem
Re-Launch
Re-Launch
Re-Launch
Project Postmortem
Cycle 3 Postmortem
Cycle N-1 Postmortem
Notes: <number>

## Slide 18: Cycle Plan
Cycle N Plan
Team
Member A
Team
Member B
Team
Member D
Team
Member C
Work
Package 1
Work
Package 2
Work
Package 3
Work
Package
4
Work
Package
5
Work
Package
6
Work
Package
8
Work
Package
7
Work
Package
N-1
Work
Package N
Notes: <number>

## Slide 19: Individual Plans
Work
Package
N
How big is it? How long will I take to build it?
What steps will I take to build it?
How well will it work when it is built?
Personal Planning Framework
Personal Process Framework
Personal Quality Framework
Personal Process
Notes: <number>

## Slide 20: When to Launch
A launch or relaunch occurs
  at the beginning of every project phase
  when substantive changes to the plan are required
A launch may also be needed when new members are added to the team.
  familiarize them with the team processes
  integrate them into the team’s plans
  get their agreement with the goals
Notes: <number>

## Slide 21: Purpose of the TSP Launch
The purpose of the launch is to establish a common team understanding of the following project elements:
  management’s goals for the project
  team and team members’ goals
  the roles that the team members will perform
  the development work to be done
  the processes that the team will use
  the plan for doing the work
  the management and customer reporting system
  the ongoing team communication process
Notes: <number>

## Slide 22: The TSP Launch -1
The TSP launch is a workshop used to kick off each project phase.
The team leader and all team members participate.
The launch workshop is considered to be part of the project work.
The launch workshops are planned and tracked.
Notes: <number>

## Slide 23: The TSP Launch -2
During the launch workshop, the team produces a comprehensive plan for their work.
The launch workshop accelerates team building. It builds
a common understanding of the job
agreement on how to do the work
commitment to a team plan
management support for the plan
the products needed to get management support
Notes: <number>

## Slide 24: The TSP Launch Products
Business needs
Management goals
Product requirements
Team goals
Conceptual design
Planned products
Size estimates
Task hour plan
Schedule plan
Earned-value plan
Team strategy
Team process
Team roles
Task plans
Detailed plans
Quality plan
Risk evaluation
Risk mitigation plans
Alternate plans
Notes: <number>
Commitments are often made when little is know about a project.
“If you can’t plan early, plan often”
- Humphrey
A plan is a snapshot of what needs to be done.
  Based on what you know at the time.
  Should be revisited when new information is gained.
  Adjustments can be made if early warning is given.
The intent is not to continuously reset the end dates, but to continuously reexamine the amount of work left to do to reach the end date.
The TSP development strategy encourages
  incremental development
  iterative development
  multiple builds or cycles
  working ahead

## Slide 25: The TSP Launch Process
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A qualified coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: <number>

## Slide 26: Purpose for Meeting 1
The purpose for meeting 1 is for
  organizational and project management to describe the project objectives and management goals to the team
  team members to understand what the team is supposed to do
  the team-building process to begin
  the commitment process to begin

## Slide 27: Purpose of Meeting 2
The purpose of launch meeting 2 is to organize the team by
  setting project goals
  selecting team roles
Project goals provide a common objective for the team.
Team roles provide a defined and accepted working framework for team members.

## Slide 28: Meeting 3 – The What and the How
In meeting 3, the team accomplishes three important prerequisites to building the team plan.
  identifies all of the “work” the team needs to do
  identifies the “strategy” the team will use to develop the product
    Integration strategy
    Test strategy
    Development strategy
  identifies or defines the “processes” the team will follow to do the work
Project strategy
Process, support
List of products
Development strategy
Conceptual
design

## Slide 29: Meeting 4 - Build the Overall Plan
In launch meeting 4, the team creates the overall plan.
  the estimated sizes of the products and services to be produced (how big is the job)
  the tasks needed to do the work (with effort estimates)
    next-phase tasks, detailed to the work step level
    later phases at a high level
  the estimated team hours available each week for the work
  an initial schedule for the project
The team may consider alternative plans if management goals are not met.
Overall plan
Available time
Estimate resources
Define tasks
Estimate size

## Slide 30: Project Size Estimate
TSP teams typically document their size estimates in a TSP support tool.
The size estimates look like the following:
Notes: <number>

## Slide 31: Team Task and Resource Plan
The task list includes the product assembly, process phase, task, team assignment, estimated size, and development time.
Notes: <number>

## Slide 32: Meeting 5 - Build a Quality Plan
In launch meeting 5, the team builds a quality plan that estimates the
  number of defects that will be injected in each phase
  number of defects that will be removed in each phase
  quality (defect density) of the final products & services
  quality (process quality index) of the development process
The team ensures that the plan meets the quality goals.
Quality plan
Quality goals
Defects injected
Defects removed

## Slide 33: Quality Plan
To make the quality plan, the team enters defect-injection and yield data and the TSP support tool calculates the defects injected and removed by phase.
Notes: <number>

## Slide 34: Meeting 6 - Build Individual Work Plans
In launch meeting 6, the team allocates tasks to the team members, who build individual work plans for their tasks for the next phase.
In building their plans, the team members
  refine size and effort estimates using their own data and processes
  break tasks to the granularity of around 10 task hours per task or less
  estimate their own available task hours for each week
  create an earned-value plan
The team reviews individual plans and balances workloads across all team members.
Balanced
plan
Allocate tasks
Individual plans
Balance workload

## Slide 35: TSP Plans
Overall team plan
  top-down
  optimal
  all phases
Individual plans
  bottom-up
  detailed
  next-phase only
Next-phase team plan
  consolidated
  balanced
  realistic
  next-phase only
Individual plan
Individual plan
Individual plan
.
.
.
Next-phase team plan
Overall team plan
Meeting 4
Meeting 6
Notes: Show files in folder of the overall and individual and consolidate plans.
This meeting will produce individual and team detailed next phase plan.
  The overall plan should be at a level of detail consistent with the information the team has at that time.
  Next phase plans need to be at a level where 2 to 4 tasks can be scheduled and completed each week.
  Detailed tasks should be in the 8 to 10 hour range.
  This level of granularity will allow the team to track earned value accurately.
Once the plan is detailed, balanced, and consolidated, the team has the most realistic plan that they can produce, without adjusting for risk.

## Slide 36: Meeting 7 - Risks
In launch meeting 7 (Script LAU7), the team identifies and assesses risks to the team meeting its plan.
The risks are documented in the team’s plan.
Risks are assigned to team members to track during the project.
The team identifies mitigation and recovery strategies for high-priority risks.

## Slide 37: Meeting 8 - Prepare Management Briefing
In launch meeting 8, the team prepares a presentation on the plan for management.
If the team’s plan does not meet management’s goals, the team generates alternate plans to come closer to or meet management’s goals by
  adding more resources
  delivering a reduced-functionality initial version, followed later by a full-functionality version(s)

## Slide 38: Meeting 9 - Management Review
In launch meeting 9, the team presents its plan (and alternatives, if any) to management and answers questions.
Management determines whether
  the plan is based on sound estimates, historical data, and a quality process
  the team believes in their plan
  the plan or an alternative meets the business need
Management
  approves the plan or an alternative
  asks the team to look at a different alternative

## Slide 39: TSP Launch Postmortem
The launch postmortem is to
consolidate the plan and launch data
review the launch process and produce PIPs
discuss open issues and agree on how to handle them
The final launch steps are to
assign responsibility for the project notebook
assign responsibility for handling the PIPs
file launch data in the project notebook
complete launch evaluation forms
submit the launch data and evaluations to the SEI
Notes: <number>

## Slide 40: After the Launch
TSP projects are self-directed. Being a self-directed project means that the team manages itself by
  following the processes they defined
  maintaining and tracking their individual and team plans
  managing the quality of their work
  working aggressively to meet team goals
The team must also show management and the customer that they are managing themselves.
  frequently report status and progress
  anticipate, plan for, and report on project risks
The TSP team roles and the TSP weekly team meeting are mechanisms which enable self-direction.
Notes: <number>

## Slide 41: Team Member Roles -1
Team self-management responsibilities are shared among team members through defined team member roles, such as:
Roles should be tailored to meet the needs of the team. In addition to these roles listed above, others may be needed to address specific project needs.
Planning Manager | Design Manager
Quality Manager | Test Manager
Process Manager | Customer Interface Manager
Support Manager | Implementation Manager
Notes: <number>

## Slide 42: Team Member Roles -2
The development roles are
  Customer interface manager – focal point for requirements and customer-related issues
  Design manager – establishes design standards and guides the design work
  Implementation manager – defines the implementation standards and handles implementation issues
  Test manager – ensures that test issues are properly considered and handles test planning and coordination
The TSP support roles are
  Planning manager – helps the team maintain, track, and report on the plan and plan status
  Process manager – guides the process definition work, handles PIPs, and monitors process data
  Quality manager – reviews process and product quality and monitors team inspections
  Support manager – ensures that proper support tools and aids are available and handles support issues
Notes: <number>

## Slide 43: Team Member Roles -3
Team member roles are not time consuming.
Each team member should have a team member role in addition to their normal responsibilities.
All team roles should
  get team input on their decisions
  perform their role duties promptly and professionally
All team members should
  follow disciplined personal practices
  plan, track, and manage their personal work
  support and contribute to the team
Notes: <number>

## Slide 44: The Team Leader’s Role
Normally, the team leader does not take one of the eight team roles.
The team leader’s job is to
  coach the team
  provide management support
  guide the team in doing their work
  establish and maintain high standards for the work
  make the team accountable for problem solving
  support the team-directed management concept
Notes: <number>

## Slide 45: The Weekly Team Meeting
The weekly team meeting keeps the project on track by reviewing status and planned work for the team and each team member on a weekly basis.
The meeting objective is to ensure that all team members
  understand current project status
  know what tasks are next
  are aware of everyone’s status and progress
  know the status against the quality plan
  discuss actions needed to ensure high quality
  understand the key project issues and risks
  participate in key team decisions
Notes: <number>

## Slide 46: TSP Project Tracking -1
Each team member is responsible for
  gathering data on their work
  ensuring the quality of the work that they produce
  tracking status against their personal plan
  keeping the team informed on their personal status
Project tracking in the TSP uses the following metrics
  product size (how big is the product being built)
  time (in minutes per task)
  defects injected and removed (by phase)
  schedule planning/tracking with earned value
The detailed team and individual plans facilitate precise project tracking.
Notes: <number>

## Slide 47: TSP Project Tracking -2
Quality
summary
Schedule
status
Team Member A
Product
summary
Enter defects
by component
and phase
Enter
size by
component
Enter
week of task
completion
Enter
time by
task
Updated team and
individual task, schedule,
and quality plans
Team task
and schedule
summary
Task status
Team Member A
Notes: <number>

## Slide 48: WEEK -1
Notes: <number>

## Slide 49: WEEK -2
Notes: <number>

## Slide 50: TSP Analysis Charts -1
Notes: <number>

## Slide 51: TSP Analysis Charts -2
Notes: <number>

## Slide 52: TSP Analysis Charts -3
Notes: <number>

## Slide 53: TSP Analysis Charts -4
Notes: <number>

## Slide 54: What Makes TSP Unique
You may already be using some of the planning, tracking, and quality management practices in the TSP.
What makes the TSP unique is that all these practices are integrated into an operational framework that addresses
  Planning
  Tracking
  Quality
  Measurement
  Tool
  Training
  Team building
And that framework cannot only be used at the project level, but at an individual team member level to guide day-to-day work.
Notes: <number>

## Slide 55: Messages to Remember
To be successful, teams need
  clear goals and roles
  agreed-upon processes and plans
On self-directed teams, the members
  own their own processes and plans
  understand their goals and roles
  voluntarily commit to their goals
  believe their commitments are achievable
The TSP launch builds self-directed teams.
Team members of self-directed teams practice disciplined personal processes.
Notes: <number>