Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Checklists

All TSP Checklists are listed.

| Checklist Abbreviations | Checklist Name | Page Reference |
| --- | --- | --- |
| PREPL | TSP Launch Preparation Checklist | 2 |
| PREPR | TSP Relaunch Preparation Checklist | 4 |

TSP Launch Preparation Checklist - PREPL

| Purpose |  | To guide launch preparation activities |  |
| --- | --- | --- | --- |
| Weeks Prior to Launch | Step | Description | Completed |
| 6-8 | Prelaunch Package Sent | The launch coordinator has received and reviewed the prelaunch package. |  |
| 6 | Project Identified | The TSP project has been identified. |  |
| 6 | Responsible Person Identified | A person has been named as responsible for launch preparation for the project. |  |
| 4 | Team Ready | The team members and team leader are identified and have scheduled the launch period on their calendars so that they are available for the entire launch period. |  |
| 2 | Launch Preparation Package Distributed | The launch coordinator has received, reviewed, and distributed the launch preparation package to new teams or team members. |  |
| 2 | Team Member Training Completed | - All software developers on the team have completed PSP training. - All other team members have completed team member training. |  |
| 2 | Management Training Completed | - The team leader has completed TSP or PSP management training. - All involved managers and executives have completed TSP or PSP management training. |  |
| 2 | Attendance Confirmed | All launch participants know the attendance guidelines and are scheduled to attend. - The management, marketing, and other interested parties attend launch meetings 1 and 9. - The team leader and team members attend meetings 1 through 9, and the launch postmortem. |  |
| 2 | Schedule Finalized | - All team members and the team leader are committed to attend launch meetings 1 through 9 and the launch postmortem, and management and marketing representatives are prepared and available for meetings 1 and 9. |  |
| 2 | Facilities for Meetings 1 and 9 Confirmed | - The room for launch meetings 1 and 9 is large enough to hold all the team members, management representatives, and observers. - A projector and screen are available. - The room is available for the mornings of days 1 and 4. |  |

(continued on next page)

TSP Launch Preparation Checklist - PREPL (continued)

| Weeks Prior to Launch | Step | Description | Completed |
| --- | --- | --- | --- |
| 2 | Facilities for Meetings 2 through 8, and Launch Postmortem Confirmed | For days 1, 2, 3, and 4 (if needed) the following facilities are available. - a conference room with desk-size working space for each team member, the team leader, and launch coaches - one or more personal computers with the Microsoft Office 2000 - two flip-chart easels and a whiteboard with pads and markers - a PC-compatible projector |  |
| 2 | Process Review Scheduled | All new TSP team members are scheduled to attend a TSP process review and workshop for the rest of day 4, after all other launch meetings. |  |
| 2 | Team Preparation Package Distributed | The team leader and all of the team's members have been given the team and team leader workshop preparation packages, respectively. |  |
| 2 | Management Preparation Package Distributed | The senior manager has been given the senior management workshop preparation package. |  |
| 2 | Marketing Preparation Package Distributed | The senior marketing manager has been given the marketing management workshop preparation package. |  |
| 2 | Other Attendee Preparation Package Distributed | Any other attendees have been given the other attendee workshop preparation package. |  |
| 2 | Catering Confirmed (optional) | For days 1, 2, 3, and 4 (if needed), the following catering is planned. - morning and midmorning break - working lunch - mid-afternoon break - A working dinner may be needed for days 1, 2, or 3. |  |
| 2 | Launch Notebooks Distributed | The launch notebooks have been distributed to all team members and the team leader. |  |

TSP Relaunch Preparation Checklist - PREPR

| Purpose |  | Use this checklist to guide relaunch preparation activities |  |
| --- | --- | --- | --- |
| Weeks Prior to Launch | Step | Description | Completed |
| 6 | Project Identified | The TSP project has been launched and is ready for relaunch. |  |
| 6 | Responsible Person Identified | A person has been named as responsible for relaunch preparation for the project. |  |
| 4 | Team Ready | The team members and team leader are identified and available for the entire relaunch period. |  |
| 4 | Postmortem Scheduled | All team members and the team leader are scheduled to complete a Postmortem (script PM), for the current Launch/Phase, prior to the relaunch. |  |
| 2 | Relaunch Preparation Package Distributed | All team members have received, reviewed, and distributed the relaunch preparation package(s). |  |
| 2 | Team Member Training Done | - All new software engineers have completed PSP training. - All other new members have completed team member training. |  |
| 2 | Management Training Done | - The team leader has completed TSP or PSP management training. - All involved managers and executives have completed TSP or PSP management training. |  |
| 2 | Attendance Confirmed | All relaunch participants know the attendance guidelines and are scheduled to attend. - The TSP team, management, marketing, and other interested parties attend relaunch meeting 1. - Team members attend meetings 2 through 7, and the relaunch PM, with no observers. |  |
| 2 | Schedule Finalized | - All team members and the team leader are committed to attend relaunch meetings 1 through 7 and the relaunch postmortem. |  |
| 1 | Launch Notebooks Distributed | The launch notebooks have been distributed to all team members and the team leader. |  |
| 1 | Team Preparation Package Distributed | The team leader and all of the team's members have been given the team and team leader workshop preparation packages, respectively. |  |
| 1 | Other Attendee Preparation Package Distributed | Any other attendees have been given the Other Attendee Workshop Preparation Package. |  |

(continued on next page)

TSP Relaunch Preparation Checklist - PREPR (continued)

| Weeks Prior to Launch | Step | Description | Completed |
| --- | --- | --- | --- |
| 1 | Meeting 1 Facilities Confirmed | - The room for relaunch meeting 1 is large enough to hold all team members, management representatives, TSP coach(es), and observers. - A projector and screen are available. - The room is available for the morning of day 1. |  |
| 1 | Facilities for Meetings 2 through 7 and Launch Postmortem Confirmed | - For days 1, 2, and 3 (if needed), the following facilities are available. - a conference room with desk-size working space for each team member, the team leader, and TSP coaches - one or more personal computers with the Microsoft Office - two flip-chart easels and a whiteboard with pads and markers - a PC compatible projector |  |
| 1 | Catering Confirmed (optional) | For days 1, 2, and 3 (if needed), the following are planned. - refreshments at start and for a mid-morning break - soft drinks for a mid-afternoon break - working lunch - a working dinner (pizza?) may be needed for day 1 |  |
| 1 | Final Report Completed | The final project report (script PM) for the current Project/Phase/Cycle, has been completed and filed in the project notebook. |  |