Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Forms

All the TSP forms are given here in the alphabetical order of their abbreviations. Each form has an instruction that is on the immediate following page.

| Form Abbreviation | Form and Instructions Name | Page Reference |
| --- | --- | --- |
| CHECKTMDR | Checkpoint Team Member Data Review | 2 |
| DEFECT | Defect Reporting Form | 7 |
| GOAL | Team Goals | 9 |
| INS | Inspection Report | 11 |
| INV | Process Inventory | 13 |
| ITL | Issue/Risk Tracking Log | 15 |
| LOGD | Defect Recording Log | 17 |
| LOGT | Time Recording Log | 19 |
| MTG | Meeting Report Form | 21 |
| PIP | Process Improvement Proposal | 23 |
| ROLE | Team Roles | 25 |
| ROLEMX | Role Assignment Matrix | 27 |
| SCHED | Schedule Planning Template | 29 |
| STRAT | Strategic Planning Form | 31 |
| SUMDI | Defects Injected Summary | 33 |
| SUMDR | Defects Removed Summary | 35 |
| SUMP | Plan Summary Form | 37 |
| SUMQ | Quality Summary Form | 40 |
| SUMS | Program Size Summary | 43 |
| SUMT | Development Time Summary Form | 45 |
| SUMTASK | Task Plan Summary | 47 |
| TASK | Task Planning Template | 49 |
| TESTLOG | Test Log | 51 |
| WEEK | Weekly Status Report | 53 |

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR

| Team Member Name: |  |
| --- | --- |
| Team Name: |  |
| Role: |  |
| Date Checkpoint Review Conducted: |  |
| Coach Name: |  |

| Time Logging | Observations |
| --- | --- |
| Are times mostly recorded as the work is done? |  |
| Is interrupt time tracked appropriately? |  |
| Is comment field used to help guide and remind member of work? |  |
| Other observations and questions for team member |  |

| Defect Logging | Observations |
| --- | --- |
| Do all defects have required data? |  |
| Were defect injected before they were removed? |  |
| Does every defect have a fix time? |  |
| Do defects injected in compile and tests have fix numbers? |  |
| Are defects adequately described? |  |
| Are defect types consistent with descriptions? |  |
| Are defect types consistent with phase injected? |  |
| Are defect types assigned consistently? |  |
| Other observations and questions for team member |  |

| Defect Log and Time Log Consistency | Observations |
| --- | --- |
| Are defects being recorded for personal reviews and inspections? |  |
| Are defects being recorded for tests? |  |
| Are defects removed consistent with compile and test phase time and program size? |  |
| Is total compile defect fix times less than compile time? |  |
| Is total test defect fix times less than test time? |  |
| Are defect dates and phases consistent with the time log? |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Tasks | Observations |
| --- | --- |
| Are all tasks < one week of effort in the next 2-4 weeks? |  |
| Are all tasks following a process as defined in the PSSP? |  |
| Is the number of open task hours < 5% of the plan? |  |
| Are all open tasks hours < one week of effort? |  |
| Other observations and questions for team member |  |

| Schedule | Observations |
| --- | --- |
| Is vacation or other significant things scheduled? |  |
| Is the next launch or re-launch scheduled? |  |
| Other observations and questions for team member |  |

| Quality | Observations |
| --- | --- |
| Are actual phase yields close to or exceeding plan yields? |  |
| Are actual defect injections lower than or close to planned inject rates? |  |
| Are review rates appropriate? |  |
| Do designs conform to team design standards? |  |
| Does code conform to team coding standards? |  |
| Is their evidence that checklists are being used in personal reviews? |  |
| Are review rates for inspections appropriate? |  |
| Are checklists being used in performing inspections? |  |
| Are Process Quality Indicator ratios close to expected? |  |
| Are the actual phase yields reasonable? |  |
| Are checklists up to date? |  |
| Are reviews and inspections being done properly? |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Week | Observations |
| --- | --- |
| Is current plan date not > 1 week later than baseline date? |  |
| Is predicted date not > 2 weeks later than baseline date? |  |
| Is growth > 5% of plan? |  |
| Are schedule hours this cycle to date < 10% of plan? |  |
| Are to date hours for task completed > 10% of plan? |  |
| Are milestone dates being met? |  |
| Other observations and questions for team member |  |

| Summary Data | Observations |
| --- | --- |
| Are actual sizes being recorded? |  |
| Other observations and questions for team member |  |

| Project Overview | Observations |
| --- | --- |
| Baseline Plan End Date |  |
| Current Plan End Date |  |
| Predicted End Date |  |
| Earn Value Per Week (are most weeks ahead or behind baseline?) |  |
| Did the current plan change a lot from the baseline? |  |
| How many actual hours are ahead of / behind plan? |  |
| Defects removed by phase (are they tracking defects? How does actual defects removed by phase compare to plan?) |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Role Data | Observations |
| --- | --- |
| Is the team member performing all the responsibilities outlined in the role specification? |  |
| Is the team member meeting the expectations of the role established during the launch/relaunch? |  |
| Is the team member performing the role specific work defined during the launch/relaunch? |  |
| Other observations and questions for team member |  |

TSP Checkpoint Team Member Data Review Form Instructions – Form CHECKTMDR

| Purpose | - To provide the TSP coach a mechanism for systematically reviewing team member data and recording one-on-one interview discussions with team members |
| --- | --- |
| General | - The coach is responsible for ensuring that confidentiality is maintained. No individual statements by any individual team member are to be reported to anyone else. Only issues that are shared by multiple team members are to be reported. - In general, the analysis of team member data is very context sensitive. Thus, the review of team member data should generate many questions that only the team member themselves can answer. Only after the context of the data is understood can true conclusions be made about the data. - The questions provided in this form are designed to systematically walk the coach through the TSP data. It is not a complete list of questions. Other questions can and should be asked. - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter team member’s name. - Enter name of the team the member’s data is associated with. - Enter the team member’s role assignment(s). - Enter date(s) checkpoint review was conducted. - Enter the name of the TSP Coach performing the checkpoint. |
| TSP Coach | - Review team member data and record answers to questions provided and observations made while analyzing the team member’s TSP data in the space provided. - When analysis is complete, meet with team member to discuss observations and answer questions discovered while analyzing the team member’s data. Questions about the team member’s data can best be answered by showing the team member the data in question directly in the TSP tool. - Record information provided by the team member during the interview process in the “Other observations and questions for team member” space provided. - After all data analysis and interviews are completed, consolidate finding in a Checkpoint Report (see TSP Checkpoint Report Guideline). - Answer any questions the team member might have about the data or processes being used. |

TSP Defect Report - Form DEFECT

| Problem Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Originator |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |
| Product |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Phase |  |  |  |  |  |
| Problem Record |  |  | Number |  |  |  | Severity |  |  |  |  |  |  |  |  |  | Category |  |  |  |
| Problem Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Briefly describe the problem encountered and its impact. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Include or attach sufficient data to recreate the problem. Where you know a fix, describe it. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total time spent on problem (hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Member |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  |
| Product |  |  |  |  |  |  |  |  |  |  |  |  |  | Component |  |  |  |  |  |  |
| Defect Number |  |  |  |  |  |  | Defect Type |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase Injected |  |  |  |  |  |  | Phase Removed |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Size (LOC) |  |  |  |  |  |  | Team Member Fix Time |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Defect No. |  |  |  |  |  |  | Fix Category |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Describe the changes made as completely as possible, including affected programs, dependencies, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| When fix completed and reviewed, submit this form to the change control board. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Control No. |  |  |  |  |  |  |  | Date Verified |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Distributed |  |  |  |  |  |  |  | Date Installed |  |  |  |  |  |  |  |  |  |  |  |  |
| Notification |  |  |  |  |  |  |  | Date Closed |  |  |  |  |  |  |  |  |  |  |  |  |
| Prerequisites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defect Report Instructions - Form DEFECT

| Purpose | - Record program problem and fix data on this form. - Use the form for all defects reported during integration testing, system testing, acceptance testing, and customer installation and use. |
| --- | --- |
| General | - This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Problem Report | In completing the problem report, the problem originator enters - his/her name and the date - the name and/or number of the product component and/or module where the problem was encountered - the phase where the problem was found (system test, use, etc.) |
| Problem Record | - Number: enter a serial identification number for each problem. - Severity: the problem originator enters the severity. - C (critical): System operation is not possible. - S (serious): System operation is possible but limited. - U (usable): The problem can be bypassed - M (minor): The problem is not operationally significant. - Category: the team member making the fix enters the category. - V (defect): a valid software defect - D (duplicate): a previously reported defect - I (invalid): any other problem report - Invalid categories - user error: the user made an error in using the system. - non-software problem, e.g. hardware or other software - a product suggestion |
| Problem Description | - Describe the problem in as much detail as possible. - Provide system or application data for problem recreation. - If you know a fix or bypass, describe it. - Record the total time spent on the problem. |
| Fix Report | - In completing the fix report, the development team member enters - his/her name and the date - the product name and the component or module fixed - the defect number, type, phase injected, and phase removed - the total time diagnosing and fixing the problem and fix size - If it is a fix defect, the team member records the prior fix number. - The team member enters the fix category. - major: any change that will affect the program source - minor: any change that will not affect the program source |
| Fix Description | - Describe the defect and fix in sufficient detail to permit later analysis to determine problem cause and problem prevention. - Note any dependencies on fixes, features, or configuration. |
| Fix Control | Use the bottom section of the form for tracking and managing the fix process. |

TSP Team Goals - Form GOAL

| Name |  | Date |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Launch/Phase |  |  |  |  |  |
|  |  |  |  | Measures |  |  | Tracking |
| Goal |  |  |  | Goal |  | Actual | Responsibility |

TSP Team Goals Instructions - Form GOAL

| Purpose | Use this form to record the team's goals. |
| --- | --- |
| General | This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Goal-setting Process | In establishing goals, follow these guidelines. - Start with management's and marketing’s or customer’s stated goals. - Identify implied goals. - Define the team goals required to meet the stated and implied goals. |
| Implied Goals | Some goals seem too obvious to state. Examples include: - Produce a product that works reliably and consistently. - Provide a product that is safe, does not damage people or property, and is protected against anticipated failures. - Respond to customer requests with sufficient reports and information to keep them satisfied with the team's work. |
| Team Goals | In establishing goals, examine each stated and implied goal and ask what would have to happen for this result to be assured. - What must the team do to assure that this goal is met? - Define team goals that require that these actions be taken. |
| Example Team Goals | - Provide a highly usable and convenient system. - Deliver the product on time and at planned costs. - Produce a defect-free product. - Reduce development cycle time. - Keep management and the customer fully informed of project status. |
| Measures: Goal | Try to define one or more measurements for every goal. - Sometimes, the goal will be readily measurable. - Often, indirect or opinion measures will be needed. - For every goal, specify how to determine if it was met. |
| Example Measures | Possible measures for the above example goals include, - Establish user performance targets and run usability tests to measure the performance and reaction of typical users. - Measure cost and schedule performance against the plan. - Set percent defect free (PDF) targets and track through development, test, acceptance, and use. - Measure how often specific managers must ask about project status rather than being informed in advance. |
| Measures: Actual | At project completion or whenever the data are available, measure and enter actual performance against each goal. |
| Responsibility | - Name the team member or role manager responsible for tracking and reporting on each goal. - In the weekly meeting, report status against all goals as soon as performance measures are available. |

TSP Inspection Report - Form INS

| Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  |  |  |  |  |  |  |  |  |  | Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Product |  |  |  |  |  |  |  |  |  |  | Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Moderator |  |  |  |  |  |  |  |  |  |  | Producer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inspection Summary |  |  |  |  |  | Product Size |  |  |  |  |  |  |  |  | Size Measure |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Defects for A |  |  |  |  |  | Total Defects for B |  |  |  |  |  |  |  |  |  |  |  |  | C (# common) |  |  |  |  |  |  |  |  |
| Total Defects (AB/C) |  |  |  |  |  | Number Found (A+B-C) |  |  |  |  |  |  |  |  |  |  |  |  | Number Left |  |  |  |  |  |  |  |  |
| Meeting Time |  |  |  |  |  | Total Inspection Hours |  |  |  |  |  |  |  |  |  |  |  |  | Overall Rate |  |  |  |  |  |  |  |  |
| Reviewer Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  | Defects |  |  |  |  | Preparation Data |  |  |  |  |  |  |  |  |  |  |  |  | Est. |  |
|  |  |  |  |  |  |  |  | Major |  |  | Minor |  | Size |  |  |  |  | Time |  |  |  | Rate |  |  |  | Yield |  |
| Totals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Defect Data |  |  |  |  |  |  | Defects |  |  |  | Reviewers (finding major defects) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Defect Description |  |  |  |  |  | Maj |  | Min |  |  |  |  |  |  |  |  |  |  |  |  |  | A |  |  |  | B |
| Page Totals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Page Unique Defects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Inspection Report Instructions - Form INS

| Purpose | - Use this form to gather and analyze inspection data. - These data must be gathered during the inspection as they cannot generally be obtained later. |
| --- | --- |
| General | - Record the preparation data at the beginning of the inspection meeting. - Complete the inspection data at the end of the inspection meeting. - It is helpful to have line and page numbers on the printed product text. |
| Major/Minor Defects | - Major defects: where the fix will change the design or code - Example: a requirements defect necessitating code changes - Example: a coding change requiring an added semicolon - Minor defects: all other defects - Example: a comment, documentation, or code format change |
| Header | - Enter your name, the project name, team name, and the date. - Enter the names of the moderator and producer. - Also enter the product and the process phase it is in or completing. |
| Reviewer Data: Preparation | - For each reviewer, enter the reviewer’s name and preparation time. - the major and minor defects the reviewer found in preparation - the LOC, lines, or pages each reviewer inspected (to save time, reviewers may concentrate on program sections) - the preparation rate in LOC, pseudocode lines, or pages per hour - Also calculate and enter the total preparation time, total major and minor defects found, and overall preparation rate. |
| Reviewer Data: Yield | At the end of the inspection, calculate the team and reviewer yields. |
| Product Size | - For requirements or high-level design inspections, enter the text pages. - For detailed design inspections, enter the LOC or pseudocode lines. - For source code inspections, enter the source LOC. |
| Defect Data: Reviewers | In the first row below the “Reviewers” heading, enter the name or initials of each reviewer who participated in the inspection. |
| Defect Data: No. | - Enter a number for each defect found in the inspection. - It is most convenient to use the document line and page number. |
| Defect Data: Defect Description | - Describe defects and check whether major (Maj) or minor (Min). - For major defects, check the column for each reviewer who found that defect during inspection preparation. |
| Summary: Estimate Remaining Defects | - After all defects are entered, count the major defects each reviewer found that no other reviewer found (the reviewer's unique defects). - Identify the reviewer who found the most unique defects. - Check the defects that reviewer found in column A. - In column B, check all the defects found by the other reviewers. - Count the common defects (C for common) between columns A and B. - The estimated number of defects in the product is AB/C. - Round fractional results to the nearest integer. - The number of defects found in the inspection is A+B-C. - The number remaining is: total less the number found: (AB/C)-A-B+C. - This defect estimate is only reliable when all the numbers A and B are greater than 4 and A-C, and B-C are both greater than 1. - Even with these criteria, total defect error is likely to be 10% or more. - Generally, the larger these numbers, the more reliable the estimate. - If A=B=C, you have likely found all the defects. - If several reviewers found the same largest number of unique defects, repeat these calculations, using each of these reviewers as A, and use the largest resulting number as the total defect estimate. - Enter total meeting time, inspection hours, and inspection rate. |

TSP Process Inventory - Form INV

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

(If you need additional space, use another inventory sheet.)

(List the elements in categories such as forms, scripts, standards, text pages, etc.)

|  |  | Work Units |  |  |  | When |  | Est. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Process Elements |  | Mod. |  | New |  | Needed |  | Hours |  | Team Member |
| Totals |  |  |  |  |  |  |  |  |  |  |

TSP Process Inventory Instructions - Form INV

| Purpose | Use this form for - listing needed scripts, forms, standards, or other work products - specifying when those items are needed - recording the estimated size of the item and the time for developing or obtaining it - assigning a team member to obtain or develop each item |
| --- | --- |
| General | - In making the inventory, group the processes or other items in categories. - Since it generally takes a different amount of time to develop elements in each category, the data from this form will help you make more accurate estimates in the future. - When making detailed plans, team members should include these items in their personal task plans. - This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Process Elements | List the process elements you plan to develop or modify. |
| Size | Determine and record the number of elements or pages to be - modified - newly developed |
| When Needed | Enter when each element will be needed, either by a date or by a process phase. |
| Estimated Hours | List the estimated hours of work required to develop, modify, or obtain each item. |
| Team member | Enter the name of the team member who will either develop the element or otherwise obtain it for the team. |
| Total | Total the estimated size and time data by element category. |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Issue and Risk Tracking Log Instructions - Form ITL

| Purpose | - Use this log to record and track project risks and issues. - Risks or issues may affect the team or may be personal. - Risks are uncertainties; they may or may not happen. - Issues are certainties; without action, they will happen. |
| --- | --- |
| General | - For both risks and issues record - a description of the risk or issue - who is responsible for tracking each risk or issue (owner) - data on each risk or issue, including when it is resolved - For risks, conduct a risk evaluation. - Use H, M, and L for high, medium, or low evaluations. - Evaluate the risk in terms of likelihood and impact. - Generally the impact evaluation is relative to schedule, but other project or product factors could be examined, e.g. cost, performance, usability, maintainability, etc. - A priority of HM would be a risk with a high likelihood of occurring and a medium impact on the project. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Issue/Risk Tracking | - Keep a master copy of the completed risk and issue logs in the project notebook. - In each weekly meeting, each team member reviews the status of the risks and issues he or she is responsible for. - In the weekly meetings, set review priorities based on issue/risk priority, flag date, and chronological age. - For each new phase, review the flagged items for the phase. - Note that this form is typically used as a template in a spreadsheet or database. |
| No. | Assign a control number to each risk and issue. |
| Date | Enter the date on which the risk or issue was entered in the ITL system. |
| Personal/Team | Enter an P for a personal risk or issue and a T for a team risk or issue. |
| Risk/Issue | Enter an R for a risk or an I for an issue. |
| Impact | For risks, enter the impact to the project if the risk occurs. - H (High): high impact to the project - M (Medium): medium impact to the project - L (Low): low impact to the project |
| Likelihood | For risks, enter the likelihood that the risk will occur. - H (High): high likelihood of occurring - M (Medium): medium likelihood of occurring - L (Low): low likelihood of occurring |
| Owner | Name the team member who is tracking the risk or issue. |
| Description | - Describe the risk or issue as clearly as possible. For example - a change to be made or interface to be checked - a requirements question to answer - a possible delay in obtaining a support tool - Describe the risk or issue completely enough to permit you or someone else to later take the needed action. |
| Follow-up Date | Note the date when the risk or issue should be reviewed. |
| Resolved | Record the date on which the risk or issue was resolved. |

| TSP Defect Recording Log - Form LOGD Defect Types |  |
| --- | --- |
| 10 Documentation | 60 Checking |
| 20 Syntax | 70 Data |
| 30 Build, Package | 80 Function |
| 40 Assignment | 90 System |
| 50 Interface | 100 Environment |

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| Project |  |  |  |  |
| Part/Assembly |  |  |  |  |

|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defect Recording Log Instructions – Form LOGD

| Purpose | - Use this form to hold data on the defects you find and correct. - Keep separate logs for each program, component, or module. - These data are used to complete form SUMP. - For integration, system test, and user-reported defects, also use form DEFECT. |
| --- | --- |
| General | - Record each defect separately and completely. - If you need additional space, use another copy of the form. - This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, and date. - For larger programs, keep a separate LOGD form for each component or module. |
| Date | Enter the date you found the defect. |
| Number | - Enter the defect number. - For each program or module, use a sequential number starting with 1 (or 001, etc.). |
| Type | - Enter the defect type from the defect type list summarized in the top left corner of the LOGD form. - Use your best judgment in selecting which type applies. |
| Assembly | Enter the assembly name |
| Inject | - Enter the phase when this defect was injected. - Use your best judgment. |
| Remove | - Enter the phase during which you fixed the defect. - This will generally be the phase when you found the defect. |
| Fix Time | - Enter the time you took to find and fix the defect. - This time can be determined by stopwatch or by judgment. |
| Fix Defect | - If you or someone else injected this defect while fixing another defect, record the number of the improperly fixed defect. - If you cannot identify the defect number, enter an X. |
| Description | Write a succinct description of the defect that is clear enough to later remind you about the error and help you to remember why you made it. |

TSP Time Recording Log - Form LOGT

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  |  |  |

| Assembly | Phase | Task | Start Date and Time | Stop Date and Time | Int. Time | Delta Time | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |

TSP Time Recording Log Instructions – Form LOGT

| Purpose | - Use this form to record the time spent on each project task. - Either keep one log and note the task and product element for each entry, or keep separate logs for each major task. |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Record all the time you spend on the project. - Record the time in minutes. - Be as accurate as possible. - If you need additional space, use another copy of the form. - If you forget to record the starting, stopping, or interruption time for a task, promptly enter your best estimate. |
| Header | - Enter your name and the date. - Enter the project name. |
| Assembly | Enter the assembly name. |
| Phase | Enter the name or other designation of the phase or step you worked on, e.g. Requirements, Design, Test. |
| Task | Enter the task name. |
| Start Date and Time | Enter the date and time when you start working on a task. |
| Stop Date and Time | Enter the date and time when you stop working on that task. |
| Interruption Time | - Record any interruption time that was not spent on the task - If you have several interruptions, enter their total time. - You may enter the reason for the interrupt in comments. |
| Delta Time | Enter the clock time you actually spent working on the task, less the interruption time. |
| Comments | Enter any other pertinent comments that might later remind you of any unusual circumstances regarding this activity. |

TSP Meeting Report - Form MTG

| Name |  |  |  |  | Date |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | Location |  |  |  |  |  |  |
| Meeting Date |  | Start Time |  |  |  | End Time |  |  |

| Subject/Purpose |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Attendees |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  |  |  |  |  |
| Plan | Start |  | Stop |  | Topics |  | Discussion Leader |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  | Who |  | When |

TSP Meeting Report Instructions – Form MTG

| Purpose | To record meeting arrangements and results |
| --- | --- |
| General | - Complete the header, purpose, and agenda portions of this form in advance of the meeting. - At the beginning of the meeting, determine who will handle the timekeeper and recorder roles. - For more space, attach another form or separate sheets. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name and the date you filled out the form. - Enter the name of the chairperson. - Enter the planned meeting time and location. |
| Subject/Purpose | - Name the type of meeting: weekly team, status, review, etc. - Succinctly describe the meeting’s purpose. - If you cannot briefly describe what the meeting is to accomplish, reconsider holding the meeting. |
| Attendees | - List the planned meeting attendees. - You must know in advance who will chair the meeting. |
| Meeting Roles | - The chairperson leads the discussion and ensures that the meeting process and agenda are followed. - The chairperson also ensures that the meeting roles are assigned at the beginning of the meeting. - The timekeeper records the actual meeting times and helps the chairperson keep the meeting on schedule. - The recorder ensures that all conclusions, decisions, and planned actions are understood, and documented. - The recorder completes the meeting report form and gives it to the chairperson. - The chairperson prepares and distributes the meeting report. - In most cases, a completed copy of the MTG form is an adequate report. |
| Agenda | - List the agenda topics with times and discussion leaders. - All discussion leaders must know their agenda topics in advance. - If you need additional space, use another form or attach a separate sheet with the agenda. |
| Decisions, Actions, and Key Information | - For all decisions, actions, and key information, clearly and completely list - what is to be or was done - who made the decision or will take the action - what information was provided by whom - when the actions are to be taken - Where additional data are needed, attach separate sheets |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |

TSP Process Improvement Proposal Instructions - Form PIP

| Purpose | - To provide a way to record process problems and improvement ideas - To provide an orderly record of your process improvement ideas for use in process improvement |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Use the PIP form to - record process improvement ideas as they occur to you - establish priorities for your improvement plans - describe lessons learned and unusual conditions - Keep PIP forms on hand while using the TSP. - Record process problems, even without proposed solutions. - Submit the PIPs for use in process improvement. |
| Header | - Enter your name and date. - Provide your e-mail address and organization in case there are any questions. |
| PIP Number | Use for your own identification purposes. |
| Priority | - Indicate if PIP priority is urgent, important, or routine. - Explain the reason for this priority under “Improvement Benefits.” |
| PIP Title | - Create a title for the PIP. |
| Improvement Description | - Describe your proposed improvement as explicitly as possible. |
| Process Elements Impacted | - Where you can, reference the specific process elements impacted and the changes suggested. |
| Improvement Benefits | Describe the benefits you expect from this change. Be as specific as possible. - the difficulties overcome - the impact on the product, the process, and you |
| When Completed | - Keep a copy for your records. - Submit a copy to your team’s process manager or PIP coordinator. |
| Process Manager or PIP Coordinator | - Review all PIPs. - Evaluate the PIP. - Estimate implementation effort. - Enter PIP into LOGPIP and allocate unique PIP Control #. - Enter date received. - Decide whether to accept the PIP, return it for more information, or defer it. - Notify the author of the disposition and, if returned, the information needed. - Submit approved PIPs to the Process Group for action. |

TSP Team Role Assignments - Form ROLE

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Team Member Roles |  | Requirements | Design | Implementation | Integration and Test |
| --- | --- | --- | --- | --- | --- |
| Official Team Leader | P |  |  |  |  |
|  | A |  |  |  |  |
| Customer Interface | P |  |  |  |  |
| Manager | A |  |  |  |  |
| Design Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Implementation | P |  |  |  |  |
| Manager | A |  |  |  |  |
| Planning Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Process Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Quality Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Support Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Test Manager | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P | Principal responsibility for the role |  |  |  |
|  | A | Alternate responsibility for the role |  |  |  |

TSP Team Role Assignments Instructions - Form ROLE

| Purpose | This form holds data on the team role assignments. |
| --- | --- |
| General | - Make team role assignments during launch and relaunch. - Enter the names of those assigned the principal and alternate responsibilities for each role. - Every team member should have at least one principal or alternate team role. - Update the form during relaunch or when roles change. - Use form ROLEMX if necessary to help make role selections. - See ROLE specification for the role responsibilities. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Team Member Roles | List any other role assignments at the bottom of the form. |
| Team Leader | - The team leader - serves as the project and team manager - obtains project staffing, makes job assignments, approves plans, reports status, and arranges for needed support - leads the launch and relaunch meetings - supports and guides the team members in doing their jobs - usually has no other team role. |
| Customer Interface Manager | - The customer interface manager - manages requirements issues and changes - ensures that all requirements assumptions are verified - leads usability, installation, documentation, and training plans |
| Design Manager | - The design manager - leads the design work and controls design changes - sets the design standards and specifications |
| Implementation Manager | - The implementation manager - leads the implementation work - sets the implementation, size, and performance standards |
| Planning Manager | - The planning manager - guides estimating, planning, tracking, and risk management - establishes the standard planning framework used for developing the team and personal plans - consolidates the team members' plans into the overall team plan |
| Process Manager | - The process manager - leads the process and procedure definition work - manages the PIP process - owns and maintains the team processes |
| Quality Manager | - The quality manager - develops and tracks the quality plan and analyzes quality data - moderates team inspections or obtains a moderator - alerts the team and management to likely quality problems |
| Support Manager | - The support manager - establishes the development system - operates the configuration management, change management, and issue tracking systems |
| Test Manager | - The test manager - ensures that testing issues are considered in every phase - leads test planning, measuring, tracking, and management |
| Team Member | All team members do design, implementation, and testing work and support other team members as needed. |

TSP Role Assignment Matrix - Form ROLEMX

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Team Member Roles Team Members | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Process Manager | Quality Manager | Support Manager | Test Manager |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

TSP Role Assignment Matrix Instructions - Form ROLEMX

| Purpose | This form is used by the team to select team role assignments. |
| --- | --- |
| General | - Make team role assignments during launch and relaunch. - Record the names of those assigned the principal and alternate responsibilities for each role in form ROLE. - Every team member should have at least one principal or alternate team role. - See ROLE specification for the role responsibilities. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Team Member Roles | - The standard TSP role assignments are listed across the top of the form. - List any other role assignments in the blank spaces at the right of the form. |
| Team Leader | - The project leader or team manager is typically designated by management before the project starts. - The team leader usually has no other team role. |
| Team Members | List the team members in the left-hand column of the form. |
| Initial Role Selection | - Have each team member identify the two roles he or she would prefer to have. - Label these roles with 1 or 2 for the first or second choice. - For small teams, make a larger number of initial selections. |
| Initial Role Entry | For each team member, mark a 1 or 2 by the two roles selected by that team member (or 3, etc. for smaller teams). |
| Unique Role Identification | - Where a team member is the only one to select a role, that team member gets that assignment. - Where a team member has two or more unique roles, he or she may choose which one to take. |
| Choice Elimination | - When a team member's role has been selected, cross off all other choices for that team member. Also cross off all selected roles. - Next, note which team members now have unique roles selected and make appropriate assignments. - Continue this process until either all roles have been selected or no unique choices remains. |
| Duplicate Role Choices | - Where two or more team members select the same roles, they decide with the team's assistance which will have the role. - Where they cannot agree, the team leader, with the team's assistance, makes the final selection. |
| Unselected Roles | Similarly, where no roles have been selected, volunteers are requested from those team members with no or the fewest roles. |
| Alternate Roles | - After the roles have been selected, select an alternate for each role. - The role alternate backs up the role manager when needed. - Be guided by the team members' preferences in assigning the alternate roles. |

TSP Schedule Planning Template - Form SCHED

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

|  |  | Plan |  |  | Actual |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week No. | Date | Task Direct Hours | Cumulative Hours | Cumulative Planned Value | Task Hours | Cumulative Hours | Week Earned Value | Cumulative Earned Value |

TSP Schedule Planning Template Instructions - Form SCHED

| Purpose | - To record the estimated and actual hours expended by calendar period - To relate the task planned value to the calendar schedule - To calculate adjusted planned and earned values when tasks change |
| --- | --- |
| General | - Expand this template or use multiple pages as needed. - Complete in conjunction with the task planning template. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Week No. | - From the project start, enter a week number, typically starting with 1. - For very small projects, it may be more convenient to use days instead of weeks. |
| Date | - Enter the calendar date for each week. - Pick a standard day in the week, for example, Monday. |
| Plan: Task Direct Hours | - Enter the planned number of task project hours you expect to spend each week. - Consider non-work time such as vacations, holidays, etc. - Consider other committed activities such as e-mail, courses, meetings, and other projects. |
| Plan: Cumulative Hours | Enter the cumulative planned hours through each week. |
| Plan: Cumulative Planned Value | - For each week - take the plan cumulative hours from the SCHED template - on the TASK template, find the task with nearest equal or lower plan cumulative hours and note its plan cumulative value - enter this cumulative value in the SCHED template for that week - if the cumulative value for the prior week still applies, enter it again |
| Actual | - During development, enter the actual direct hours, cumulative hours, and cumulative earned value for each week. - Determine status against plan by comparing the cumulative planned value and the actual cumulative earned value. |

TSP Strategy Recording - Form STRAT

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

|  |  | Cycle LOC |  |  | Cycle Hours |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Component, Element, or Feature | 1 | 2 | 3 | 1 | 2 | 3 |
| Totals |  |  |  |  |  |  |  |

TSP Strategy Recording Instructions - STRAT

| Purpose | - Use this form to record strategic decisions. - Use it during strategy development to allocate product functions to development cycles. - Also use it during high-level design to allocate SRS functions to components. |
| --- | --- |
| General | - This form provides a way to record strategic decisions. Use it or any other format that contains the same data. - If you need space for more functions or cycles, use additional form copies. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Reference | Use this column to list the need statement, SRS paragraph, sentence number, or other reference for the functions. |
| Component, Element, or Feature | In this column, list the principal product components, elements, or features to be included in the product in each development cycle. |
| Cycle LOC | - Use these columns for the estimated LOC or other size measure for each function. - Enter the size estimated for each function under the number of the development cycle that will include that function. - If you plan to implement a function partially in two or more cycles, enter the estimated new and changed size for each cycle. |
| Cycle Hours | - Use these columns for the estimated time required to develop each function. - Enter the time estimated for each function under the number of the cycle where you plan to include that function. - If you plan to implement a function partially in two or more cycles, enter the estimated development time for each cycle. |

| TSP Defects Injected Summary - Form SUMDI Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

| Phase Parts |  | Requirements |  | Requirements Inspection |  | High-level Design |  | HLD Inspection |  | Detailed Design |  | Detailed Design Review |  | Detailed Design Inspection |  | Code |  | Code Review |  | Compile |  | Code Inspection |  | Unit Test |  | Build and Integration |  | System Test |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defects Injected Summary Instructions - Form SUMDI

| Purpose | - This form summarizes the data for estimated and actual defects injected. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the defect-injected data from a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the defects-injected entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Phase | The phases of the development process are listed across the top of the form. |
| Parts | List the name or number of each module, component, product, or subsystem in the left column. |
| Columns | Under each phase heading, enter, for each part, the number of defects injected in that phase. |
| Total | At the bottom of the form, enter the totals of the defects injected in all the parts in that phase. |

| TSP Defects Removed Summary - Form SUMDR Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

| Phase Parts |  | Requirements |  | Requirements Inspection |  | High-level Design |  | HLD Inspection |  | Detailed Design |  | Detailed Design Review |  | Detailed Design Inspection |  | Code |  | Code Review |  | Compile |  | Code Inspection |  | Unit Test |  | Build and Integration |  | System Test |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defects Removed Summary Instructions - Form SUMDR

| Purpose | - This form summarizes the data for estimated and actual defects removed. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the defect-removed data from a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the defects-removed entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Phase | The phases of the development process are listed across the top of the form. |
| Parts | List the name or number of each module, component, product, or subsystem in the left column. |
| Columns | Under each phase heading, enter, for each part, the number of defects removed in that phase. |
| Total | At the bottom of the form, enter the totals of the defects removed in all the parts in that phase. |

TSP Plan Summary - Form SUMP

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Summary | Plan |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |
| LOC/Hour |  |  |  |  |  |  |  |
| % Reuse (% of Total LOC - T) |  |  |  |  |  |  |  |
| % New Reuse (% of N&C LOC - N) |  |  |  |  |  |  |  |
| Product Size | Plan |  |  |  | Actual |  |  |
| Requirements pages (SRS) |  |  |  |  |  |  |  |
| High-level design pages (SDS) |  |  |  |  |  |  |  |
| Detailed design lines |  |  |  |  |  |  |  |
| Base LOC (B) (measured) |  |  |  |  |  |  |  |
| Deleted LOC (D) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Modified LOC (M) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Added LOC (A) |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |
| Reused LOC (R) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Total New & Changed LOC (N) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |
| Total LOC (T) |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |
| Total New Reuse LOC |  |  |  |  |  |  |  |
| Estimated Object LOC (E) |  |  |  |  |  |  |  |
| Size UPI (70%) |  |  |  |  |  |  |  |
| Size LPI (70%) |  |  |  |  |  |  |  |
| Time in Phase (hours) | Plan |  | Actual |  |  |  | Actual % |
| Launch and planning |  |  |  |  |  |  |  |
| Requirements |  |  |  |  |  |  |  |
| System test plan |  |  |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |  |  |
| Relaunch and planning |  |  |  |  |  |  |  |
| High-level design |  |  |  |  |  |  |  |
| Integration test plan |  |  |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |  |  |
| Relaunch and planning |  |  |  |  |  |  |  |
| Detailed design |  |  |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |  |  |
| Test development |  |  |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |
| Code review |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |
| Code inspection |  |  |  |  |  |  |  |
| Unit test |  |  |  |  |  |  |  |

(continued on next page)

TSP Plan Summary - Form SUMP (continued)

| Part/Assembly |  | Date |  |
| --- | --- | --- | --- |

| Time in Phase (hours) (Continued) | Plan |  | Actual |  | Actual % |
| --- | --- | --- | --- | --- | --- |
| Relaunch and planning |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Postmortem |  |  |  |  |  |
| Total |  |  |  |  |  |
| Time UPI (70%) |  |  |  |  |  |
| Time LPI (70%) |  |  |  |  |  |
| Defects Injected | Plan |  | Actual |  | Actual % |
| Requirements |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |
| High-level design |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |
| Detailed design |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |
| Code |  |  |  |  |  |
| Code review |  |  |  |  |  |
| Compile |  |  |  |  |  |
| Code inspection |  |  |  |  |  |
| Unit Test |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Total Development |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  | Actual % |
| Requirements |  |  |  |  |  |
| System test planning |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |
| High-level design |  |  |  |  |  |
| Integration test planning |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |
| Detailed design |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |
| Test development |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |
| Code |  |  |  |  |  |
| Code review |  |  |  |  |  |
| Compile |  |  |  |  |  |
| Code inspection |  |  |  |  |  |
| Unit Test |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Total Development |  |  |  |  |  |
| Acceptance test |  |  |  |  |  |
| Product life |  |  |  |  |  |

TSP Plan Summary Instructions – Form SUMP

| Purpose | - This form holds plan and actual data for parts or assemblies. - An assembly could be a system with multiple products, a product with multiple components, or a component with multiple modules. - A part could be a module, component, or product. - Note: the lowest-level parts or modules typically have no system-level data (i.e. requirements, high-level design, or system test). |
| --- | --- |
| General | - Where possible, make estimates based on your own historical data. - Where data are not available, use the PLAN standard for guidance. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Summary | - For CPI, use the sums of planned and actual development times for all products developed in this system to date. - Enter the new and changed LOC per hour planned, the actual for this product, and the rate for all products at this level to date. - CPI = (To Date Planned Time)/(To Date Actual Time). - Reuse percent is reuse LOC as a percent of total LOC. - New Reuse percent is new reuse LOC as a percent of new and changed LOC. |
| Product Size | - For text and designs, enter only the new and changed size data. - For program parts or assemblies, enter all the indicated LOC data. |
| Time in Phase | - Enter estimated and actual time by phase. - For higher-level assemblies, enter the sums of the plan and actual times for the parts (from SUMT). - For the lowest-level parts, these values come from the TASK template. - Actual Percent: Enter the percent of the actual development time by phase. |
| Defects Injected | - Enter estimated and actual defects injected by phase from form SUMDI. - For assemblies, enter the total of the plan and actual defects injected for its parts. For modules, enter the defect data directly. - Make the defect estimates while producing the quality plan. - Actual Percent: Enter the percent of the actual defects injected by phase. |
| Defects Removed | - Enter estimated and actual defects removed by phase from form SUMDR. - For assemblies, enter the total of the plan and actual defects removed for its parts. For modules, enter the defect data directly. - Make the defect estimates while producing the quality plan. - Actual Percent: Enter the percent of the actual defects removed by phase. |

TSP Quality Summary - Form SUMQ

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Percent Defect Free | Plan |  | Actual |
| --- | --- | --- | --- |
| In compile |  |  |  |
| In unit test |  |  |  |
| In integration test |  |  |  |
| In system test |  |  |  |
| In acceptance test |  |  |  |
| In one year of use |  |  |  |
| In product life |  |  |  |
| Defect/Page |  |  |  |
| Requirements inspection |  |  |  |
| HLD review |  |  |  |
| HLD inspection |  |  |  |
| Defects/KLOC |  |  |  |
| DLD review |  |  |  |
| DLD inspection |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Total development |  |  |  |
| Acceptance test |  |  |  |
| Product life |  |  |  |
| Total |  |  |  |
| Defect Ratios |  |  |  |
| Code review/Compile |  |  |  |
| DLD review/Unit test |  |  |  |
| Development Time Ratios (%) |  |  |  |
| Requirements inspection/Req. time |  |  |  |
| HLD inspection/HLD time |  |  |  |
| DLD/code |  |  |  |
| DLD review/design |  |  |  |
| Code review/code |  |  |  |
| A/FR |  |  |  |
| Personal Review Rates |  |  |  |
| DLD lines/hour |  |  |  |
| Code LOC/hour |  |  |  |
| Inspection Rates |  |  |  |
| Requirement pages/hour |  |  |  |
| HLD pages/hour |  |  |  |
| DLD lines/hour |  |  |  |
| Code LOC/hour |  |  |  |

(continued on next page)

TSP Quality Summary - Form SUMQ (continued)

| Part/Assembly |  | Date |  |
| --- | --- | --- | --- |

| Defect Injection Rates | Plan |  | Actual |
| --- | --- | --- | --- |
| Requirements |  |  |  |
| HLD |  |  |  |
| DLD |  |  |  |
| Coding |  |  |  |
| Compile |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Defect Removal Rates | Plan |  | Actual |
| Requirements |  |  |  |
| System test planning |  |  |  |
| Requirements inspection |  |  |  |
| HLD |  |  |  |
| Integration test planning |  |  |  |
| HLD inspection |  |  |  |
| DLD review |  |  |  |
| Test development |  |  |  |
| DLD inspection |  |  |  |
| Code |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Phase Yields | Plan |  | Actual |
| Requirements inspection |  |  |  |
| HLD inspection |  |  |  |
| DLD review |  |  |  |
| DLD inspection |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Process Yields | Plan |  | Actual |
| % before compile |  |  |  |
| % before unit test |  |  |  |
| % before build and integration |  |  |  |
| % before system test |  |  |  |
| % before system delivery |  |  |  |

TSP Quality Summary Instructions – Form SUMQ

| Purpose | - This form holds plan and actual quality data for parts or assemblies. - An assembly could be a system with multiple products, a product with multiple components, or a component with multiple modules. - A part could be a module, component, or product. - Note: the lowest-level parts or modules typically have no system-level data (i.e., requirements, high-level design, or system test). |
| --- | --- |
| General | - Where possible, establish goals based on your own historical data. - Where data are not available, use the QUAL standard for guidance. - In planning, follow script LAU5 to make the quality plan. - This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Percent Defect Free (PDF) | - Set the percent defect free (PDF) plan values in the project launch. - At phase completion, enter the actual PDF values. - PDF does not apply to modules or lowest-level parts. - For program assemblies, compute PDF from form SUMDR. |
| Defects/page and Defects/KLOC | - Set the defect/page and defect/KLOC plan values in the launch. - After development, calculate the actual values. For modules, calculate directly; for assemblies, calculate from the forms SUMS and SUMDR. |
| Defect Ratios | - From the defects/KLOC values, calculate the defect ratios. - When compile or unit test defects are 0, enter "inf." |
| %Development Time Ratios | - Calculate the planned and actual ratios from form SUMP. - During development, monitor these planned and actual ratios to ensure the work meets the team quality goals. |
| A/FR | - For A/FR, use detailed design and code review and inspection times divided by compile and unit test times. - Use the sum of personal review and team inspection times. |
| Review and Inspection Rates | - From forms SUMT and SUMS, calculate the indicated planned or actual review and inspection rates. - During development, monitor these planned and actual rates to ensure that the work meets the team quality goals. |
| Defect Injection and Removal Rates | - Based on the quality plan, establish standard team rates. - As you gather actual data, compute the actual defect injection and removal rates for each phase. - For modules, compute the values directly. - For larger program assemblies, compute the values from the forms SUMT, SUMDI, and SUMDR. |
| Yield | - In planning, use historical data to estimate the yield values needed for each defect-removal phase. - After each phase, calculate the estimated yield values. - Update these values as development progresses. - For modules, compute the yield values directly. - For larger program assemblies, compute the yield values from SUMDI and SUMDR. |

| TSP Product Size Summary - Form SUMS Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

|  |  |  |  | Size Category |
| --- | --- | --- | --- | --- |

| Product or Part Names |  | Size Measure |  | Base |  | Deleted |  | Modified |  | Added |  | Reused |  | New and Changed |  | Total |  | Total New Reuse |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Totals |  | Text Pages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | HLD Pages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | DLD Lines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | LOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Product Size Summary Instructions - Form SUMS

| Purpose | - This form summarizes the data for program size. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the size data for a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the size entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Header | - Enter your name, the date, project, and launch phase. - Name the assembly that contains these parts. - For part level, enter whether module, component, product, or sub-system data are summarized in the form. |
| Product or Part Names | List the name or number of each module, component, or other product in the left column. |
| Size Measure | - Enter the size measure for the product in each row. - Example measures are text pages, HLD pages, DLD pseudocode lines, and LOC. |
| Size Category | - For planned size, under each size category, for each part - Enter the estimated Base, Deleted, Modified, Added, Reused, and Total New Reuse size. - Calculate New and Changed size (Added + Modified) categories. - Calculate the Total size (Base - Deleted + Added + Reused). - For actual size, under each size category, for each part - Measure and enter the estimated Base, Deleted, Modified, Added, Reused, and Total New Reuse size. - Calculate New and Changed size (Added + Modified) categories. - Calculate the Total size (Base - Deleted + Added + Reused). |
| Total | - At the bottom of the form, enter the totals of each size measure. - Be careful not to double count the base size measure when several parts have been developed from the same base. - Also, when products are developed in cycles, check that the base or reused code are not double counted. |

| TSP Development Time Summary - Form SUMT Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

| Phase Parts |  | Launch and Planning |  | Requirements |  | System Test Planning |  | Requirements Inspection |  | Relaunch |  | High-level Design |  | Integration Test Planning |  | HLD Inspection |  | Relaunch |  | Detailed Design |  | Detailed Design Review |  | Test Development |  | Detailed Design Inspection |  | Code |  | Code Review |  | Compile |  | Code Inspection |  | Unit Test |  | Relaunch |  | Build and Integration |  | System Test |  | Postmortem |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Development Time Summary Instructions - Form SUMT

| Purpose | - This form summarizes the data for estimated and actual development time. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the development time data for a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the phase time entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Phase | The phases of the development process are listed across the top of the form. |
| Parts | List the name or number of each module, component, product, or subsystem part in the left column. |
| Columns | Under each phase heading, enter, for each part, the plan or actual time for that development phase. |
| Total | At the bottom of the form, enter the total development time for all parts in that phase. |

TSP Task Plan Summary - Form SUMTASK

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Products of the task |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task users/customers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall requirements/message |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specifications/constraints |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Product elements |  | Size Unit |  |  |  |  | Plan Units |  |  |  |  | Plan Rate |  |  |  |  | Plan Time |  |  |  |  |  |  | Act. Units |  |  |  | Act. Time |  |  |  |  |  |  |  |  | Act. Rate |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase |  |  |  | Plan |  |  |  |  |  |  |  |  |  | Actual |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  | Base Times |  |  |  |  |  |  |  |
| Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outline/High-level design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer review and correct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft/Detailed-level design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer review and correct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement/Rewrite |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer review and correct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test/Trial use |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total time (minutes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total time (hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Task Plan Summary Instructions - Form SUMTASK

| Purpose | - To facilitate planning and tracking task activities - Use this form for tasks that take more than about 10 hours. - This form is for those general tasks which are large enough to warrant detailed project plan summaries. |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Product of the Task | Describe the product to be produced by this task: i.e., test scripts, requirements documents, database designs, etc. |
| Task Users/Customers | - Note who will use or be the customer for this product. - For example, if it is a process, the team will use list "team." |
| Overall Requirements/ Message | - Briefly list the product requirements. - If the product is a document, give a brief outline of the principal topics or document sections. - For a process, list its principal steps and elements. |
| Specifications/ Constraints | - Summarize any special task or product constraints. - For example: prerequisites, page limits, number of slides, etc. |
| Product Elements | - List the various product elements to be produced. - Give the size unit for each element type. - Estimate the development rate in minutes per unit. - Estimate the new and changed units per element type and the time. - Record the actual units, time, and rate when done. |
| Time in Phase | - Record the plan and actual times for the task phases. - Where some phases are not appropriate or differ from those in the form, make appropriate changes. |
| % and Base | When your personal plan contains tasks of more than 10 hours, use % and Base Times columns to divide tasks into smaller steps. |
| Percent (%) | The percent of time you typically plan for each task phase. |
| Base Times | - Using the phase % values, allocate the original total estimated task time among the phases. - Since the base times add up to the original estimate, using these values will preserve the original earned value plan. |
| Example | Suppose, during the launch, you planned a task to take 30 hours, and had not then divided it into smaller time steps. - You now estimate the task to take 50 hours. - Your current phase estimates in hours are planning: 2, research: 10, design: 5, implementation: 12, review: 6, peer review: 8, trial: 6, and postmortem: 1. - These percents are respectively 4, 20, 10, 24, 12, 16, 12, 2. - In “Base Times”, enter 1.2 for planning (4*30/100), 3 for research (10*30/100), etc. - To preserve your earned value plan, enter new rows for these tasks and times and set the original 30 hour estimate to 0. |

TSP Task Planning Template - Form TASK

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Task |  |  | Plan |  |  |  |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase | Part | Task Name | Number of Team members | Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value - PV | Cumulative PV | Hours | Cumulative EV | Week No. |
| Totals |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Task Planning Template Instructions - Form TASK

| Purpose | - To estimate the development time for each project task - To compute the planned value for each project task - To estimate the planned completion date for each task - To provide a basis for tracking schedule progress even when the tasks are not completed in the planned order |
| --- | --- |
| General | - Complete the SCHED and TASK templates together. - Expand this template or use multiple pages as needed. - Include every significant task. - Use task names and numbers that support the activity and are consistent with the project work breakdown structure. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Task | - Enter the project phase for each task. - Enter the product, part, or assembly to which the task relates. - Enter task names and/or numbers in the order in which you expect to complete them. - Select tasks that have explicit completion criteria, i.e., plan completed, program compiled and defects corrected, etc. |
| Plan: No. of Team members | Enter the number of team members who will equally share in this task. If their individual times will differ, use different task names. |
| Plan: Hours | Enter the total planned hours for each task. |
| Plan: Cumulative Hours | Enter the cumulative sum of the total planned hours. |
| Plan: Units | For each product produced, enter the units of the size measure, i.e., LOC, KLOC, pages, classes, scripts, etc. |
| Plan: Size | For each task, enter the size of the product produced, if any. |
| Plan Week | - On form SCHED, find the plan cumulative hours entry that equals or just exceeds each cumulative hours entry on this form. - The week number in that row of the form SCHED is the plan week number for the task on form TASK. - If several weeks on the schedule template have the same cumulative value, enter the earliest week number. - Pick the plan date as the Monday of the week during which completion for that task is planned. |
| Plan: Planned Value (PV) | - Total the planned hours for all tasks. - Find the percent each task's planned hours are of total hours. - Enter this percent as the planned value for each task. |
| Plan: Cumulative PV | - Enter the cumulative sum of the planned values. |
| Actual: Hours | - When a task is completed, enter the hours spent on the task. |
| Actual: Cumulative Earned Value (EV) | - Each week, total the EV for all completed tasks and enter that total beside the latest completed task. - Also enter the weekly and cumulative total EV on form SCHED. |
| Actual: Week No. | - As a task is completed, enter the week number it was completed. |

TSP Test Log - Form TESTLOG

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Test Log Instructions – Form TESTLOG

| Purpose | - To report test data and results. |
| --- | --- |
| General | - You need test data to improve the testing processes. - the tests run - how long they took to run - the numbers and types of defects found - You also need to demonstrate the benefits of a quality process. - the testing time required to produce a workable product - the numbers of defects found in the product - the relative costs of fixing defects in test as opposed to earlier in the development process - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Date | Enter the date each test was run. |
| Test | - Uniquely identify each test. - Use the same name or number as in the test plan. |
| Product | Name the product being tested. |
| Test Time | - Enter the test time. - Start: when the test was started - Stop: when the test was stopped, either because it finished successfully or it was interrupted for any program or test-related reason - Delta time: the time between starting and stopping the test. |
| Problems | - Enter the number of test problem reports. - If one or more problems is determined to be a defect, note that under comments. |
| Comments | Briefly note the test results. For example: - the test finished successfully - the test was completed, but the result was incorrect - the test failed with 3 problems, 1 defect - where possible, give additional information on test results, test configuration, or anything else that would permit reproducing the test results. |

TSP Weekly Status Report - Form WEEK

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Week No. |  |

| Weekly Data |  |  |  | Planned |  |  |  | Actual |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project hours for this week |  |  |  |  |  |  |  |  |  |
| Project hours this phase to date |  |  |  |  |  |  |  |  |  |
| Earned value for this week |  |  |  |  |  |  |  |  |  |
| Earned value this phase to date |  |  |  |  |  |  |  |  |  |
| Non earned-value project tasks |  |  |  |  |  |  |  |  |  |
| Role Tasks Completed |  | Hours |  | Earned Value |  |  |  | Planned Week |  |
| Totals |  |  |  |  |  |  |  |  |  |
| Development Tasks Completed |  | Hours |  | Earned Value |  |  |  | Planned Week |  |
| Totals |  |  |  |  |  |  |  |  |  |
| Other Project Activities This Week |  |  |  |  |  |  | Hours |  |  |
| Totals |  |  |  |  |  |  |  |  |  |
| Risk/Issue Tracking |  |  |  |  |  |  |  |  |  |
| Risk Name |  | Status |  |  |  |  |  |  |  |
| Issue Name |  | Status |  |  |  |  |  |  |  |

TSP Weekly Status Report Instructions - Form WEEK

| Purpose | Use this form to prepare your weekly status reports. |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Complete a copy of this form each week and give it to the planning manager before the weekly meeting. - The planning manager prepares the team summary form. - Role tasks are those tasks you perform for a team assigned role such as planning manager, quality manager, etc. - Development tasks are those tasks you perform while developing the product such as designing, coding, or inspecting. |
| Header | Enter your name, project name, date, and the week number reported. |
| Weekly Data | - Enter the hours you actually spent on the project this week and the hours you planned to spend. - Enter the actual and planned cumulative hours you have spent on this phase of the project. - Enter the earned value planned for the week and your actual earned value. - Enter your cumulative earned value planned and actual for the project phase to date. - Note: the team may choose to track time and earned value for the entire project to date, rather than just for the current phase. |
| Role Tasks Completed | For each of your team roles: - Enter the name of each task you completed this week. - Enter the total time you spent on each of these tasks. - Enter the week number when you planned to finish the task. - Total the week’s earned value. |
| Development Tasks Completed | For your development work: - Enter the name of each task you completed this week. - Enter the total time you spent on each of these tasks. - Enter the week number when you planned to finish the task. - Total the week’s earned value. |
| Other Project Activities | For any other project work that is not on the task schedule: - Enter the activity on which you spent time this week. - Enter the total time you spent on each of these activities. |
| Risk/Issue Tracking | - For the risks you track, summarize the status and any important changes or exposures for this week. - For the issues you track, summarize the status and any important changes this week. |