Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Workshop Handouts - Meeting 1

| Contents Page | Element |
| --- | --- |
|  | Launch Workshop |
| 2 | Meeting Report - Launch Meeting 1 (partially completed) |
| 3 | TSP Meeting Roles and Responsibilities |
| 4 | TSP General Meeting Process - Script MTG |
| 5 | TSP Meeting Report Form Instructions - Form MTG |
| 6 | TSP Team Launch - Script LAU |
| 7 | TSP Launch Meeting 1 - Script LAU1 |
| 8 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 9 | TSP Issue and Risk Tracking Log Instructions - Form ITL |
| 10 | TSP Process Improvement Proposal - Form PIP (blank) |
| 11 | TSP Process Improvement Proposal Instruction - Form PIP |
| 12 | Product Discussion Guidelines |
| 13 | Senior Management Goals Discussion Guidelines |
| 14 | Team Leader Meeting 1 Discussion Guidelines |
| 15 | Team Member Meeting 1 Discussion Guidelines |
| # 16 | Relaunch Workshop |
| 16 | Meeting Report - Relaunch Meeting 1 (partially completed) |
| 17 | TSP Team Relaunch - Script REL |
| 18 | TSP Relaunch Meeting 1 - Script REL1 |
| 19 | TSP Overview slides |

Meeting Report - Launch Meeting 1

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 1: To overview the TSP workshop, to |  |  |  |  |  |  |  |
| describe TSP, and to review marketing's and management's need for the project |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 30 |  |  |  |  | Launch overview |  |  |  |  | TSP Coach |  |
| 25 |  |  |  |  | Business need for the project |  |  |  |  | Management |  |
| 25 |  |  |  |  | The desired product |  |  |  |  | Marketing |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

TSP Meeting Roles and Responsibilities

| Objective | By consistently following the defined meeting script and roles, team meetings will be shorter and more productive. |
| --- | --- |
| General | See script MTG for guidance on running meetings. |
| Chairperson | The meeting chairperson - produces the meeting agenda - sets the meeting time and location - arranges for facilities - selects the meeting timekeeper and recorder - keeps the meeting on schedule and focused on the agenda - defers off-the-point items and has the recorder note them for later attention - ensures that all attendees get a chance to state their views - ensures that all items are covered or otherwise handled - ensures that a final meeting report is produced, distributed, and filed in the project notebook |
| Recorder | The recorder - records meeting decisions: who and what - records planned actions: who, what, and when - checks each decision and planned action to ensure that the attendees agree with the report's wording - produces a summary meeting report (form MTG) - checks the report with the chairperson to ensure that it is complete and correct - provides the report to the chairperson for distribution and filing in the project notebook |
| Facilitator/ Timekeeper | The facilitator/timekeeper - helps the chairperson maintain a productive atmosphere - assists in keeping the discussion factual and objective - prevents the meeting from becoming personal or destructive - alerts the chairperson when the discussion deviates from the agenda - informs the chairperson when an agenda item is nearing the end of its allotted time - records the actual meeting times for each agenda item - provides time data to the recorder for the meeting report |
| Attendees | Each meeting attendee - prepares for the meeting - supports the facilitator/timekeeper in maintaining a productive atmosphere - contributes to the discussion whenever he or she has something relevant to say - volunteers for meeting roles and action items as needed |

| TSP General Meeting Process - Script MTG |  |
| --- | --- |
| Purpose | Use this script as a guide in planning and conducting meetings; it will help you hold useful meetings in a minimum time. |
| Entry Criteria | - You need a meeting and know who should attend. - Form: MTG - Specification: NOTEBOOK |
| General | Meetings can be held to - resolve issues or make decisions - inform or educate - produce work products; i.e., a design, plan, process, or standard |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Preparation | In planning a meeting, complete form MTG. - What is the meeting’s purpose? Write it down. - What outcome do you want? Be specific. - Who should attend the meeting and why? - What topics should be covered? - Who should present what and for how long? - Are discussion periods needed and for how long? - Are decisions needed, on what, and by whom? - Set the agenda topics, times, and speakers. - Are actions desired after the meeting? - List the data needed: responsibilities, dates, resources, etc. - After ensuring that the key attendees can attend, schedule the meeting. - Check facilities: setup, equipment, supplies, refreshments, etc. - Provide each attendee a completed copy of form MTG. |
| 2 | Meeting Roles | Select the meeting roles (specification Meeting Roles). - The chairperson leads the meeting. - The timekeeper keeps the meeting on schedule. - The recorder notes meeting decisions and actions and helps to write the meeting report. |
| 3 | Meeting Introduction | - Review the meeting purpose and agenda. - Check for any changes in the purpose or agenda. |
| 4 | The Meeting | During the meeting, all attendees should do the following. - Follow the agenda. - When important topics are raised that are not on the current subject, defer them to later in the agenda or to another meeting. Record the deferred topic on a visible chart, white board, etc. - Be specific on each decision: what was decided and by whom. - Be clear on each planned action: who will do what and when. - Give everyone an opportunity to contribute and speak up. |
| 5 | Meeting Conclusion | - The recorder reviews and confirms the decisions and actions. - Briefly review the meeting process for suggested improvements. |
| 6 | Meeting Report | Promptly issue the meeting report (form MTG). The recorder - lists the purpose, attendees, and results - describes decisions made, and by whom - documents pending actions: what, when, and by whom - verifies with the attendees that the report is correct and complete |

| Exit Criteria | The meeting was held and the meeting report was issued and filed in the project notebook. |
| --- | --- |

TSP Meeting Report Instructions – Form MTG

| Purpose | To record meeting arrangements and results |
| --- | --- |
| General | - Complete the header, purpose, and agenda portions of this form in advance of the meeting. - At the beginning of the meeting, determine who will handle the timekeeper and recorder roles. - For more space, attach another form or separate sheets. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name and the date you filled out the form. - Enter the name of the chairperson. - Enter the planned meeting time and location. |
| Subject/Purpose | - Name the type of meeting: weekly team, status, review, etc. - Succinctly describe the meeting’s purpose. - If you cannot briefly describe what the meeting is to accomplish, reconsider holding the meeting. |
| Attendees | - List the planned meeting attendees. - You must know in advance who will chair the meeting. |
| Meeting Roles | - The chairperson leads the discussion and ensures that the meeting process and agenda are followed. - The chairperson also ensures that the meeting roles are assigned at the beginning of the meeting. - The timekeeper records the actual meeting times and helps the chairperson keep the meeting on schedule. - The recorder ensures that all conclusions, decisions, and planned actions are understood, and documented. - The recorder completes the meeting report form and gives it to the chairperson. - The chairperson prepares and distributes the meeting report. - In most cases, a completed copy of the MTG form is an adequate report. |
| Agenda | - List the agenda topics with times and discussion leaders. - All discussion leaders must know their agenda topics in advance. - If you need additional space, use another form or attach a separate sheet with the agenda. |
| Decisions, Actions, and Key Information | - For all decisions, actions, and key information, clearly and completely list - what is to be or was done - who made the decision or will take the action - what information was provided by whom - when the actions are to be taken - Where additional data are needed, attach separate sheets |

| TSP Team Launch - Script LAU |  |
| --- | --- |
| Purpose | To guide teams in launching a software-intensive project |
| Entry Criteria | - The launch preparation work has been completed (PREPL, PREPT). - All team members and the team leader are committed to attend launch meetings 1 through 9 and the launch postmortem, and management and marketing representatives are prepared and available for meetings 1 and 9. - A certified TSP coach is on hand to lead the launch process. |
| General | Day; 1; 2; 3; 4. Timing; 8:30-6:45; 8:00-5:00; 8:30-5:30; 8:30-4:30. Meetings; 1, 2, and 3; 3 (cont.), 4, 5, and 6; 6 (cont.), 7 and 8; 9 and PM. Notional schedule can be compressed or extended to meet scope of launch |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Project and Management Objectives | Hold team launch meeting 1 (script LAU1). - Review the launch process and introduce team members. - Discuss the project goals with management and marketing. |
| 2 | Team Goals and Roles | Hold team launch meeting 2 (script LAU2). - Define and document the team's goals. - Allocate team roles among team members. |
| 3 | Project Strategy and Support | Hold team launch meeting 3 (script LAU3). - Produce a system conceptual design, and, if needed, a fix list. - Determine the development strategy and products to be produced. - Define the development process to be used. - Produce the process and support plans. |
| 4 | Overall Plan | Hold team launch meeting 4 (script LAU4). - Develop size estimates and the overall team plan. |
| 5 | Quality Plan | Hold team launch meeting 5 (script LAU5). - Develop the quality plan. |
| 6 | Balanced Plan | Hold team launch meeting 6 (script LAU6). - Allocate work to team members. - Produce bottom-up next-phase or cycle plans for each team member. - Produce a balanced next-phase or cycle plan for the team and each team member. |
| 7 | Project Risk Analysis | Hold team launch meeting 7 (script LAU7). - Identify and evaluate project risks. - Define risk assessment checkpoints and responsibilities. - Propose mitigation actions for near-term, high-impact risks. |
| 8 | Launch Report Preparation | Hold team launch meeting 8 (script LAU8). - Prepare a launch report for management. |
| 9 | Management Review | Hold team launch meeting 9 (script LAU9). - Review the launch report with management. - Discuss project risks, responsibilities, and planned actions. |
| PM | Launch Postmortem | Hold team launch postmortem meeting (script LAUPM). - Gather launch data and produce a launch report. - Put the launch report in the project notebook. - Assess the launch process and prepare PIPs. |

| Exit Criteria | - The launch is completed with documented team and team member plans. - Team roles, goals, processes, and responsibilities are defined. - Management agrees with the team plan, or resolution actions have been identified and responsibilities assigned. - The launch data are in the project notebook (NOTEBOOK specification). |
| --- | --- |

| TSP Launch Meeting 1 - Script LAU1 |  |
| --- | --- |
| Purpose | To review management goals and product objectives with the team |
| Entry Criteria | - The team and team leader are prepared. - All participants are present (TSP coach, team members, team leader, management and marketing representatives). - Forms: MTG, ITL, PIP |
| General | Meeting 1 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | TSP and Launch Overview Meeting Role Assignments | The TSP coach leads the meeting (script MTG). The coach - describes the TSP launch process and the launch products - reviews the TSP team roles - reviews the meeting roles and assigns a timekeeper and recorder (specification ROLE) - discusses the work to be done in this meeting |
| 2 | Project Goals | A senior management representative - describes the business reasons for wanting to do this project - describes the business goals for the project - answers the team's questions |
| 3 | Goal Questions | The team members should satisfy themselves that they understand the project goals (Team Member Meeting 1 Discussion Guidelines). - management's goals for the project - the reasons for these goals - how management will measure goal attainment - management's minimum and ideal goals for the project |
| 4 | Product Objectives | A marketing or customer representative - describes the characteristics of the desired product - summarizes the customers' needs for the product - compares these needs with competitive offerings - answers the team's questions |
| 5 | Product Questions | The team members should satisfy themselves that they understand the product objectives (Team Member Meeting 1 Discussion Guidelines). - users' and customer's needs - any items that are especially important to the customer |
| 6 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - saves the completed form MTG to give to the planning manager in launch meeting 2 |

| Exit Criteria | - Launch meeting 1 activities have been completed. - The team understands the customer's needs and management's goals. - All of the team's questions have been answered, or actions are planned to get answers for the team. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Issue and Risk Tracking Log Instructions - Form ITL

| Purpose | - Use this log to record and track project risks and issues. - Risks or issues may affect the team or may be personal. - Risks are uncertainties; they may or may not happen. - Issues are certainties; without action, they will happen. |
| --- | --- |
| General | - For both risks and issues record - a description of the risk or issue - who is responsible for tracking each risk or issue (owner) - data on each risk or issue, including when it is resolved - For risks, conduct a risk evaluation. - Use H, M, and L for high, medium, or low evaluations. - Evaluate the risk in terms of likelihood and impact. - Generally the impact evaluation is relative to schedule, but other project or product factors could be examined, e.g. cost, performance, usability, maintainability, etc. - A priority of HM would be a risk with a high likelihood of occurring and a medium impact on the project. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Issue/Risk Tracking | - Keep a master copy of the completed risk and issue logs in the project notebook. - In each weekly meeting, each team member reviews the status of the risks and issues he or she is responsible for. - In the weekly meetings, set review priorities based on issue/risk priority, flag date, and chronological age. - For each new phase, review the flagged items for the phase. - Note that this form is typically used as a template in a spreadsheet or database. |
| No. | Assign a control number to each risk and issue. |
| Date | Enter the date on which the risk or issue was entered in the ITL system. |
| Personal/Team | Enter an P for a personal risk or issue and a T for a team risk or issue. |
| Risk/Issue | Enter an R for a risk or an I for an issue. |
| Impact | For risks, enter the impact to the project if the risk occurs. - H (High): high impact to the project - M (Medium): medium impact to the project - L (Low): low impact to the project |
| Likelihood | For risks, enter the likelihood that the risk will occur. - H (High): high likelihood of occurring - M (Medium): medium likelihood of occurring - L (Low): low likelihood of occurring |
| Owner | Name the team member who is tracking the risk or issue. |
| Description | - Describe the risk or issue as clearly as possible. For example - a change to be made or interface to be checked - a requirements question to answer - a possible delay in obtaining a support tool - Describe the risk or issue completely enough to permit you or someone else to later take the needed action. |
| Follow-up Date | Note the date when the risk or issue should be reviewed. |
| Resolved | Record the date on which the risk or issue was resolved. |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |

TSP Process Improvement Proposal Instructions - Form PIP

| Purpose | - To provide a way to record process problems and improvement ideas - To provide an orderly record of your process improvement ideas for use in process improvement |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Use the PIP form to - record process improvement ideas as they occur to you - establish priorities for your improvement plans - describe lessons learned and unusual conditions - Keep PIP forms on hand while using the TSP. - Record process problems, even without proposed solutions. - Submit the PIPs for use in process improvement. |
| Header | - Enter your name and date. - Provide your e-mail address and organization in case there are any questions. |
| PIP Number | Use for your own identification purposes. |
| Priority | - Indicate if PIP priority is urgent, important, or routine. - Explain the reason for this priority under “Improvement Benefits.” |
| PIP Title | - Create a title for the PIP. |
| Improvement Description | - Describe your proposed improvement as explicitly as possible. |
| Process Elements Impacted | - Where you can, reference the specific process elements impacted and the changes suggested. |
| Improvement Benefits | Describe the benefits you expect from this change. Be as specific as possible. - the difficulties overcome - the impact on the product, the process, and you |
| When Completed | - Keep a copy for your records. - Submit a copy to your team’s process manager or PIP coordinator. |
| Process Manager or PIP Coordinator | - Review all PIPs. - Evaluate the PIP. - Estimate implementation effort. - Enter PIP into LOGPIP and allocate unique PIP Control #. - Enter date received. - Decide whether to accept the PIP, return it for more information, or defer it. - Notify the author of the disposition and, if returned, the information needed. - Submit approved PIPs to the Process Group for action. |

Product Discussion Guidelines

Launch Meeting 1

Purpose: In this meeting, a knowledgeable manager discusses the product or product release to be produced.  The discussion objective is to provide all team members with a common understanding of what is expected of the future product.

Discussion leader:  This discussion is led by a manager who understands the desired product, what the customer and anticipated users intend to do with this product, and the kind of product management wishes to produce.  This manager may personally present the material or have others do so.

#### Discussion guidelines:  The following topics should be covered in whatever order the discussion leader deems appropriate.

- Who the customer is

- Why the customer wants the product

- The principal product functions

- The ideal set of product functions and characteristics

- The minimum acceptable set of product functions and characteristics

- How the work relates to other products and projects

- An overview of the key competitive offerings (when appropriate)

- Respond to the team’s questions about the product, the customer, or management’s objectives

Intended result: After this discussion, the team should appreciate management’s and the customer’s/user's desires and be able to proceed with development planning. The team will be able to make better business/function/technical tradeoffs throughout the project, and produce a more desirable product.  The team members will also be better equipped to handle unanticipated problems, capitalize on new opportunities, and seek appropriate guidance when needed.

Senior Management Goals Discussion Guidelines

Launch Meeting 1

Purpose:  In launch meeting 1, a senior manager meets with the team to describe the organization’s goals and to answer the team’s questions.

Discussion leader:  The senior manager who knows why this project was undertaken should lead this discussion.  Ideally, this would be the executive who originally decided to launch the project.

#### Executive discussion:  The executive should cover the following topics in whatever order seems most appropriate.

- The organization’s overall business objectives

- Why the business decided to undertake this project

- What the business wishes to gain from doing this project

- How the executive would characterize a fully successful result

- What this project will lead to if fully successful

- How the executive would characterize a minimally acceptable result

- What resources are available and planned for this project

- Respond to the team’s questions about the business, its goals, and this project

Team discussion:  The team may ask questions about the goals and what they mean for the team’s work.  At the conclusion of this discussion, the team should understand the following.

- Management’s ideal and minimum goals for the project

- The resources planned and available for the work

- Any business or other constraints on the project

Intended result:  As a result of this discussion, the team should fully appreciate why the business has undertaken this project and what a successful outcome will mean to the organization.

Team Leader Meeting 1 Discussion Guidelines

Launch Meeting 1

Purpose:  In launch meeting 1, senior managers describe the desired product and the organization’s goals for the project.  They will also answer the team’s questions. The objective of meeting 1 is to provide the background you need to intelligently balance conflicting user, business, and technical needs.

Discussion format:  The product discussion will be led by a manager who understands the desired product and what the customer and anticipated users intend to do with this product.  A senior manager will explain why the project is being undertaken, how it fits into the business plan, and what a successful outcome will mean to the business.

#### Discussion attitude:  Products are often needed sooner than they can be produced, and all organizations want to minimize cost.  It is possible that management will want an outcome which you cannot achieve.  Under these conditions, it is important that you start the planning process with a positive attitude.

- You must make it clear that you will devise the best plan you possibly can.

- If this plan does not meet management's needs, you will try to rework it so it does. If management does not believe you are trying to meet their needs, they are not likely to accept your plan.

- In asking questions, try to be positive.  Ask management what they want and explore how to achieve it.  Do not discuss how difficult the job looks or the problems you anticipate.

- Ask about alternatives, such as added resources or expert assistance.

- Regardless of how impossible the task may appear, you cannot know what is possible until you produce a plan.

Discussion approach:  You are in a tricky position in this meeting, since the team views you as part of management and management views you as part of the team.  You do not want to change either perception.  Your objectives are as follows.

- Make sure you understand management's needs and desires.

- Get your team to ask the questions.

- Before the meeting is over, you want to be satisfied that all the team members fully understand what is wanted and why.

To meet these objectives, ask the team for questions instead of asking them yourself.  You might even plant some of your questions with the team in advance.  You could also ask leading questions so that the team members end up asking what you want to know.  However, try to get them to speak up.  It will make them feel better about the meeting and may even expose some important concerns.

Desired outcome:  At the end of the meeting, you and all team members should understand what management wants and be able to make a plan that best meets management’s needs.  While this plan may not fully meet management’s stated needs, it will come as close as you and your team possibly can.

Team Member Meeting 1 Discussion Guidelines

Launch Meeting 1

Purpose:  In launch meeting 1, senior managers describe the desired product and the organization’s goals for the project.  They will also answer the team’s questions. The objective of meeting 1 is to provide the background you need to intelligently balance conflicting user, business, and technical needs.

Discussion format:  The product discussion will be led by a manager who understands the desired product and what the customer and anticipated users intend to do with this product.  A senior manager will explain why the project is being undertaken, how it fits into the business plan, and what a successful outcome will mean to the business.

#### Discussion attitude:  Products are often needed sooner than they can be produced, and all organizations want to minimize cost.  It is possible that management will want an outcome that you cannot achieve.  Under these conditions, it is important that you start the planning process with a positive attitude.

- You must make it clear that you will devise the best plan you possibly can.

- If this plan does not meet management's needs, you will try to rework it so it does. If management does not believe you are trying to meet their needs, they will not likely accept your plan.

- In asking questions, try to be positive.  Ask management what want and explore how to achieve it.  Do not discuss how difficult the job looks or the problems you anticipate.

- Ask about alternatives, such as added resources or expert assistance.

- Regardless of how impossible the task may appear, you cannot know what is possible until you produce a plan.

Potential Questions:  Some potential questions for management are the following.

- Should you consider delivering the product in versions, and what initial functions would make the most sense?

- In balancing cost, schedule, and product function, can they suggest trade-off priorities?

- Why did they pick the schedule they did?  Would they like it sooner and what would it mean if it was later?

- If your plan is early, should you consider reducing resources, and if late, should you consider adding people?

- In adding more people, could you get them early enough so they could be PSP trained?

- To shorten the schedule, should you consider early or overlapping involvement of other groups, such as testing or manufacturing?

Desired outcome:  At the end of the meeting, you should understand what management wants and be able to make a plan that best meets their needs.  While your plan may not fully meet management’s stated needs, it will come as close as you possibly can.

Meeting Report - Relaunch Meeting 1

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  |  |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Relaunch Meeting 1: To overview project status and to |  |  |  |  |  |  |  |
| Introduce new team members. |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 10 |  |  |  |  | Introduce new team members |  |  |  |  | Team Leader |  |
| 40 |  |  |  |  | Project status update |  |  |  |  | Team Leader |  |
| 15 |  |  |  |  | Goal performance and goal update |  |  |  |  | Team Leader |  |
| 15 |  |  |  |  | Management update |  |  |  |  | Team Leader |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSP Team Relaunch - Script REL |  |
| --- | --- |
| Purpose | To guide integrated teams in relaunching a software-intensive project |
| Entry Criteria | - The relaunch preparation work has been completed (PREPR, PREPT). - The team leader has prepared the project status report. - The team leader and team members are available for the entire relaunch. - A certified TSP coach is on hand to lead the relaunch. - The updated project notebook is available. - Note: to meet aggressive schedules, the next phase may be relaunched before the postmortem for the current phase. |
| General | If there are significant project changes, follow script LAU. Timing; Day; 1; 2; 3. Meeting; 1, 2, and 3; 4 and 5; 6, 7, and PM. Notional schedule can be compressed or extended to meet scope of relaunch. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Project Status and Objectives | Hold team relaunch meeting 1 (script REL1). - Review the relaunch process and introduce new team members. - Review the project status to date. - Understand management's goals for the project. |
| 2 | Team Goals and Roles | Hold team relaunch meeting 2 (script LAU2). - Update and document the team's goals. - Allocate team roles among team members. |
| 3 | Project Strategy and Support | Hold team relaunch meeting 3 (script LAU3). - Update the system conceptual design, and, if needed, a fix list. - Update the development strategy and products to be produced. - Review and update the development process to be used. - Review and update the process and support plans. |
| 4 | Overall Plan | Hold team relaunch meeting 4 (script LAU4). - Develop or update the size estimates and overall plan. |
| 5 | Quality Plan | Hold team launch meeting 5 (script LAU5). - Update the quality plan. |
| 6 | Balanced Plan | Hold team relaunch meeting 6. (script LAU6.). - Allocate work to team members. - Produce bottom-up next-phase plans for each team member. - Produce a balanced next-phase plan for the team and each team member. |
| 7 | Project Risk Analysis | Hold team relaunch meeting 7 (script LAU7). - Identify and evaluate any new project risks. - Define risk assessment checkpoints and responsibilities. - Propose mitigation actions for near-term, high-impact risks. |
| 8 | Launch Report Preparation | There is no relaunch meeting 8. |
| 9 | Management Review | There is no relaunch meeting 9. |
| PM | Launch Postmortem | Hold team launch postmortem meeting (script LAUPM). - Gather launch data and produce a launch report. - Put the launch report in the project notebook. - Assess the launch process and prepare PIPs. |

| Exit Criteria | - The relaunch is completed. - Team roles, goals, processes, responsibilities, and plans are defined. - The relaunch data are in the project notebook (specification NOTEBOOK). |
| --- | --- |

| TSP Relaunch Meeting 1 - Script REL1 |  |
| --- | --- |
| Purpose | To review project status and update the team on any customer requirements or management goal changes |
| Entry Criteria | - The team and team leader are prepared. - All participants are present (TSP coach, team members, team leader). - Forms: MTG, ITL, PIP |
| General | Meeting 1 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Relaunch Overview | The TSP coach - reviews the relaunch process and the products to be produced - discusses the work to be done in this meeting |
| 3 | New Members | The team leader introduces new team members. |
| 4 | Project Status | The team leader presents a full project status report to the team and TSP coach (specification STATUS). - schedule status versus plan - actual earned value and task hour performance versus plan - actual size and time data versus plan - quality performance versus plan |
| 5 | Goal Performance | - The team leader reviews the team's quality, schedule, and cost performance versus goals. - Where performance fell short, the team discusses recovery options. - Where performance met or exceeded goals, the team discusses improvement opportunities. |
| 6 | Management Update | The team leader describes any changes in management's goals for the project. - reasons for any goal changes - how management will measure goal attainment - answers questions on the goals |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - saves the completed form MTG to give to the planning manager in launch meeting 2 |

| Exit Criteria | - Relaunch meeting 1 activities have been completed. - The team fully understands project status and any changes in management's goals. - All of the team's questions have been answered, or actions are planned to get the answers for the team. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |