Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Workshop Handouts - Meeting 3

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Meeting 3 (partially completed) |
| 3 | TSP Launch Meeting 3 - Script LAU3 |
| 5 | TSP Process Inventory - Form INV (blank) |
| 6 | TSP Process Inventory Form Instructions - Form INV |
| 7 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 8 | TSP Process Improvement Proposal - Form PIP (blank) |
| 9 | TSP Strategy Recording - Form STRAT (blank) |
| 10 | TSP Strategy Recording Instructions - STRAT |

Note: for meeting 3, the TSP launch and relaunch processes are the same.

Meeting Report - Launch Meeting 3

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 3: To produce the project conceptual design and strategy, |  |  |  |  |  |  |  |
| and the process and support plans |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 50 |  |  |  |  | Produce the product conceptual design |  |  |  |  | Design Manager |  |
| 45 |  |  |  |  | Define the development strategy |  |  |  |  | Team Leader |  |
| 30 |  |  |  |  | ### List the products to be produced |  |  |  |  | Team Leader |  |
| 40 |  |  |  |  | Define the development process |  |  |  |  | Process Manager |  |
| 20 |  |  |  |  | Produce the process plan |  |  |  |  | Process Manager |  |
| 20 |  |  |  |  | Produce the support plan |  |  |  |  | Support Manager |  |
| 10 |  |  |  |  | Define the CCB membership |  |  |  |  | TSP Coach |  |
| 10 |  |  |  |  | Define role tasks and weekly status |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |
| Development strategy (form STRAT) |  |  |  |  |  |  |  |  |  |  |  |
| Process and support plans (form INV) |  |  |  |  |  |  |  |  |  |  |  |
| Size summary (form SUMS) |  |  |  |  |  |  |  |  |  |  |  |

(Use additional form copies if needed.)

| TSP Launch Meeting 3 - Script LAU3 |  |
| --- | --- |
| Purpose | To help the team produce the development strategy, development process, and support plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented project goals and team roles are available. - Forms: INV, ITL, MTG, PIP, STRAT, SUMS, SUMTASK |
| General | Meeting 3 generally takes from 3 to 5 hours, depending on project status, product complexity, team size, and the team's TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Product Conceptual Design | The design manager leads the team in - producing a conceptual design - defining the principal product components, elements, or features of the conceptual design - making a gross size estimate of each component, element, or feature |
| 4 | Development Strategy | - The team leader leads the team in establishing the project strategy. In developing the project strategy, the team considers - the gross size of each principal product component, element, or feature - whether the product should be developed in one or multiple versions - the general content of each development version - the number of development cycles, and estimated size and hours of each - whether prototypes are needed, when they are needed, and their purpose - The results, principal product components or elements, estimated size and development hours, and development cycle, are recorded on form STRAT. |
| 5 | Products Produced | - The team leader leads the team in defining the work products to be produced for the next phase or cycle, and all subsequent phases or cycles. These items are recorded on form SUMS. Examples include - prioritized list of fixes to the existing product - requirements documents and specifications - design documents and specifications - prototypes - principal product elements or components - installation, user, and maintenance manuals - test programs, scripts, data, and plans - When defining the principal product elements or components, use a level of detail that is appropriate for the phase being planned. Subsystems or components are sufficient for the requirements and high-level design phases, and modules or objects may be needed for the implementation phase. The items on form STRAT may be used as a starting point and may be further refined as needed. |

(continued on next page)

| TSP Launch Meeting 3 - Script LAU3 (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 6 | Development Process | - The process manager leads the team in defining the development process. - Define the overall development process up to final delivery. - principal process phases - major activities in each phase - items to be baselined at each phase - Refine the process steps for the next project phase or cycle to sufficient detail to support planning individual tasks that are 10 hours or less. - detailed steps required to produce each of the phase or cycle products - steps required to verify the quality of the inputs and the products - the point at which each product will be baselined - items to be baselined at each phase - Using form INV, make a plan to develop, modify, or obtain each missing development process element. Include the estimated size; estimated hours; the date, phase, or cycle when needed; and who will document the process. |
| 7 | Process Plan | - The process manager leads the team in identifying any other process elements that are needed. Examples include - design, code, size, naming, and message standards - guidelines for team processes and procedures; i.e. resolving issues, making decisions, approving standards - change control and change management procedures - Make a plan on form INV for each missing process element. |
| 8 | Support Plan | - The support manager leads the team in reviewing the available development and process support tools and facilities, and identifying any that are missing - requirements and design aids - editors, compilers, debug aids, testing tools - defect tracking, configuration management, issue tracking - LOC counting, difference counting, data analysis - Make a plan on form INV for obtaining each missing item. |
| 9 | CCB Membership | The TSP coach leads the team in identifying the membership of the configuration control board (CCB) and the CCB chair. - The support manager typically chairs the CCB. - Other typical members are the design manager, team leader, and customer interface manager. |
| 10 | Role Plan | The TSP coach leads the team in defining the tasks and weekly reporting for each role, and records the tasks on form INV. |
| 11 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 3 activities have been completed. - Development strategy is defined (form STRAT). - List of products to be produced has been recorded (form SUMS). - Overall and detailed development process steps are documented. - Process plan and support plan are documented (form INV). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

TSP Process Inventory - Form INV

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

(If you need additional space, use another inventory sheet.)

(List the elements in categories such as forms, scripts, standards, text pages, etc.)

|  |  | Work Units |  |  |  | When |  | Est. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Process Elements |  | Mod. |  | New |  | Needed |  | Hours |  | Team Member |
| Totals |  |  |  |  |  |  |  |  |  |  |

TSP Process Inventory Instructions - Form INV

| Purpose | Use this form for - listing needed scripts, forms, standards, or other work products - specifying when those items are needed - recording the estimated size of the item and the time for developing or obtaining it - assigning a team member to obtain or develop each item |
| --- | --- |
| General | - In making the inventory, group the processes or other items in categories. - Since it generally takes a different amount of time to develop elements in each category, the data from this form will help you make more accurate estimates in the future. - When making detailed plans, team members should include these items in their personal task plans. - This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Process Elements | List the process elements you plan to develop or modify. |
| Size | Determine and record the number of elements or pages to be - modified - newly developed |
| When Needed | Enter when each element will be needed, either by a date or by a process phase. |
| Estimated Hours | List the estimated hours of work required to develop, modify, or obtain each item. |
| Team member | Enter the name of the team member who will either develop the element or otherwise obtain it for the team. |
| Total | Total the estimated size and time data by element category. |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |

TSP Strategy Recording - Form STRAT

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

|  |  | Cycle LOC |  |  | Cycle Hours |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Component, Element, or Feature | 1 | 2 | 3 | 1 | 2 | 3 |
| Totals |  |  |  |  |  |  |  |

TSP Strategy Recording Instructions - STRAT

| Purpose | - Use this form to record strategic decisions. - Use it during strategy development to allocate product functions to development cycles. - Also use it during high-level design to allocate SRS functions to components. |
| --- | --- |
| General | - This form provides a way to record strategic decisions. Use it or any other format that contains the same data. - If you need space for more functions or cycles, use additional form copies. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Reference | Use this column to list the need statement, SRS paragraph, sentence number, or other reference for the functions. |
| Component, Element, or Feature | In this column, list the principal product components, elements, or features to be included in the product in each development cycle. |
| Cycle LOC | - Use these columns for the estimated LOC or other size measure for each function. - Enter the size estimated for each function under the number of the development cycle that will include that function. - If you plan to implement a function partially in two or more cycles, enter the estimated new and changed size for each cycle. |
| Cycle Hours | - Use these columns for the estimated time required to develop each function. - Enter the time estimated for each function under the number of the cycle where you plan to include that function. - If you plan to implement a function partially in two or more cycles, enter the estimated development time for each cycle. |