Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Workshop Handouts - Meeting 6

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Meeting 6 (partially completed) |
| 3 | TSP Launch Meeting 6 - Script LAU6 |
| 5 | TSP Plan Summary - Form SUMP (blank) |
| 7 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 8 | TSP Process Improvement Proposal - Form PIP (blank) |

Note: for meeting 6, the TSP launch and relaunch processes are the same.

Meeting Report - Launch Meeting 6

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 6: To produce a bottom-up plan for each team member |  |  |  |  |  |  |  |
| for the next phase or cycle |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 90 |  |  |  |  | Allocate next-phase tasks |  |  |  |  | Team |  |
| 70 |  |  |  |  | Team members produce individual plans |  |  |  |  | Team |  |
| 50 |  |  |  |  | Balance the team's workload |  |  |  |  | Team |  |
| 15 |  |  |  |  | Document the next-phase plan |  |  |  |  | Planning Manager |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |
| Completed and balanced plans for every engineer |  |  |  |  |  |  |  |  |  |  |  |
| (TASK and SCHED templates) |  |  |  |  |  |  |  |  |  |  |  |

(Use additional form copies if needed.)

| TSP Launch Meeting 6 - Script LAU6 |  |
| --- | --- |
| Purpose | To help the team produce a balanced next-phase or cycle plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented process, quality, and support plans are available. - Documented overall plan has been prepared. - Overall and next-phase or cycle effort estimates are available. - Forms: SCHED, TASK, INV, ITL, MTG, PIP, SUMP, SUMQ, SUMS |
| General | Meeting 6 generally takes 3 to 5 hours, depending on team size, project status, product complexity, and team TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Allocate Tasks to Team Members | - The team allocates the tasks for the next phase or cycle to individual team members using the following guidelines. - The team and team leader review the tasks for the next phase, and allocate these tasks among the team members. - The team may do load balancing during task allocation, or may do load balancing after each team member has produced their individual plans. - To maintain a balanced workload while allocating tasks, the team works through the plan one week at a time. - agrees on which team member will do each task - maintains a balanced workload among the team members |
| 4 | Build Bottom-up Plans | - Using personal data where possible, each team member - assesses his or her work and adds any role tasks - subdivides tasks longer than about 10 hours into smaller steps - produces personal task, schedule, and earned value plans |
| 5 | Review and Rebalance Team Workload | The planning manager leads the team review of the bottom-up plans. - ensures that the quality criteria are met - resolves conflicts, duplications, and critical path conflicts - rebalances tasks until a minimum schedule is achieved |
| 6 | Produce the Next-Phase or Cycle Development Plan | The planning manager combines the bottom-up plans and generates the consolidated next-phase or cycle team plan, which contains - consolidated team size estimates on form SUMS - combined team plan on TASK and SCHED forms - a team earned-value plan for tracking planned value, earned value, and projected earned value by week for the next phase or cycle - an optional Gantt schedule for the next phase or cycle - SUMP and SUMQ forms with size, resource, and quality data for the system and its components (as appropriate for the phase) - In the event that all cost, schedule, and functionality goals are not met, consider alternative plans (i.e., increase cost to meet schedule and functionality, or reduce functionality to meet cost and schedule constraints) to present to management. |

(continued on next page)

| TSP Launch Meeting 6 - Script LAU6 (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 7 | Launch Meeting Documentation | The recorder completed form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 6 activities have been completed. - Detailed next-phase plans for each team member and the team are documented (forms INV, SUMP, SUMQ, TASK, SCHED). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

TSP Plan Summary - Form SUMP

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Summary | Plan |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |
| LOC/Hour |  |  |  |  |  |  |  |
| % Reuse (% of Total LOC - T) |  |  |  |  |  |  |  |
| % New Reuse (% of N&C LOC - N) |  |  |  |  |  |  |  |
| Product Size | Plan |  |  |  | Actual |  |  |
| Requirements pages (SRS) |  |  |  |  |  |  |  |
| High-level design pages (SDS) |  |  |  |  |  |  |  |
| Detailed design lines |  |  |  |  |  |  |  |
| Base LOC (B) (measured) |  |  |  |  |  |  |  |
| Deleted LOC (D) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Modified LOC (M) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Added LOC (A) |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |
| Reused LOC (R) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Total New & Changed LOC (N) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |
| Total LOC (T) |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |
| Total New Reuse LOC |  |  |  |  |  |  |  |
| Estimated Object LOC (E) |  |  |  |  |  |  |  |
| Size UPI (70%) |  |  |  |  |  |  |  |
| Size LPI (70%) |  |  |  |  |  |  |  |
| Time in Phase (hours) | Plan |  | Actual |  |  |  | Actual % |
| Launch and planning |  |  |  |  |  |  |  |
| Requirements |  |  |  |  |  |  |  |
| System test plan |  |  |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |  |  |
| Relaunch and planning |  |  |  |  |  |  |  |
| High-level design |  |  |  |  |  |  |  |
| Integration test plan |  |  |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |  |  |
| Relaunch and planning |  |  |  |  |  |  |  |
| Detailed design |  |  |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |  |  |
| Test development |  |  |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |
| Code review |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |
| Code inspection |  |  |  |  |  |  |  |
| Unit test |  |  |  |  |  |  |  |

(continued on next page)

TSP Plan Summary - Form SUMP (continued)

| Part/Assembly |  | Date |  |
| --- | --- | --- | --- |

| Time in Phase (hours) (Continued) | Plan |  | Actual |  | Actual % |
| --- | --- | --- | --- | --- | --- |
| Relaunch and planning |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Postmortem |  |  |  |  |  |
| Total |  |  |  |  |  |
| Time UPI (70%) |  |  |  |  |  |
| Time LPI (70%) |  |  |  |  |  |
| Defects Injected | Plan |  | Actual |  | Actual % |
| Requirements |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |
| High-level design |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |
| Detailed design |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |
| Code |  |  |  |  |  |
| Code review |  |  |  |  |  |
| Compile |  |  |  |  |  |
| Code inspection |  |  |  |  |  |
| Unit Test |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Total Development |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  | Actual % |
| Requirements |  |  |  |  |  |
| System test planning |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |
| High-level design |  |  |  |  |  |
| Integration test planning |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |
| Detailed design |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |
| Test development |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |
| Code |  |  |  |  |  |
| Code review |  |  |  |  |  |
| Compile |  |  |  |  |  |
| Code inspection |  |  |  |  |  |
| Unit Test |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Total Development |  |  |  |  |  |
| Acceptance test |  |  |  |  |  |
| Product life |  |  |  |  |  |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |