Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Workshop Handouts - Meeting 7

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Meeting 7 ( partially completed) |
| 3 | TSP Launch Meeting 7 - Script LAU7 |
| 4 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 5 | TSP Process Improvement Proposal - Form PIP (blank) |

Note: for meeting 7, the TSP launch and relaunch processes are the same.

Meeting Report - Launch Meeting 7

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 7: To conduct a project risk assessment analysis and |  |  |  |  |  |  |  |
| produce a report on each high-priority risk |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 75 |  |  |  |  | Conduct project risk assessment |  |  |  |  | Team Leader |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |
| Completed list of risks with evaluations |  |  |  |  |  |  |  |  |  |  |  |
| Assignments for key risks |  |  |  |  |  |  |  |  |  |  |  |

(Use additional form copies if needed.)

| TSP Launch Meeting 7 - Script LAU7 |  |
| --- | --- |
| Purpose | To guide the team through a project risk assessment |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented overall and next-phase development plan are available. - Forms: ITL, MTG, PIP |
| General | - A risk is something that may or may not happen. Something that is certain is an issue, not a risk. - Meeting 7 generally takes 1 to 2 hours, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Risk Identification | The team leader asks the team to identify risks. - All team members participate in suggesting risks. - Use a brainstorm approach; i.e., do not evaluate risks during this step. - The process continues until no one can think of any more risks. - Record each risk to aid subsequent evaluation by the team. Use a flip chart or white board. |
|  | Impact Evaluation | For each risk, the team evaluates its likely impact. - Impact is high if the project schedule impact would be high. - Risks may also have medium or low schedule impact. - Note the impact evaluation. Use a flip chart or white board. |
|  | Likelihood Evaluation | For each risk, the team judges its likelihood. Likelihood is also measured as high, medium, or low. |
|  | Assign Risks | For the high and medium priority risks (i.e., high-high, high-medium, medium-high, or medium-medium), the team - assigns a member to track the risk - sets a date by which mitigation action must be taken - documents the risk, responsibility, and flag date on form ITL |
| 4 | Risk Mitigation | For the high and medium priority risks, identify those that are near-term. - Determine an effective mitigation plan. - Recommend actions to reduce or eliminate risk impact. |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 7 activities have been completed. - All risks and issues are documented (form ITL). - The high-priority risks have mitigation plans. - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |