Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Workshop Handouts - Meeting 8

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report Form - Launch Meeting 8 (partially completed) |
| 3 | TSP Launch Meeting 8 - Script LAU8 |
| 4 | TSP Management Briefing Guidelines |
| 5 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 6 | TSP Process Improvement Proposal - Form PIP (blank) |

Note: the TSP relaunch process has no meeting 8.

Meeting Report - Launch Meeting 8

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  |  | TSP Coach |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 8: To prepare for the management meeting |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start | Stop |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 60 |  |  |  |  | Plan the management meeting presentation |  |  |  |  | Team Leader |  |
| 15 |  |  |  |  | Allocation of meeting preparation tasks |  |  |  |  | Team Leader |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSP Launch Meeting 8 - Script LAU8 |  |
| --- | --- |
| Purpose | To guide the team in preparing for the management meeting (LAU9) |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - All team members have copies of - personal task and schedule spreadsheets - team task and schedule spreadsheets - project goals and role assignments - risk evaluation, assessments, and mitigation plans - Forms: ITL, MTG, PIP - Guideline: Management Briefing Guideline - Specifications: NOTEBOOK and STATUS |
| General | - In the management meeting (meeting 9), the team will - review the launch process and launch products - review the project plan and any questions or issues with this plan - demonstrate to management that they have made a thoughtful, realistic, and complete plan. - Meeting 8 generally takes 1 to 2 hours, depending on team size, project status, product complexity, and the team’s TSP experience. Additional time is needed to prepare materials for the management meeting (meeting 9). |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the objectives and procedure for the meeting, and describes the example contents of the management presentation. |
| 3 | Planning for the Management Meeting | - The team leader reviews each agenda item for the management meeting (guideline Management Briefing and script LAU9). - discusses the material to be covered - decides what to present and who will present it - assigns the preparation work to one or more team members - The team leader recommends what to present, but the team should be in agreement. |
| 4 | Management Meeting Preparation | The team leader summarizes - the work to be done - who will produce each item - the times when the items will be completed - who will present each item |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 8 activities have been completed. - The management meeting topics were decided and the preparation work planned. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

TSP Management Briefing Guidelines

| Purpose | To guide the team in preparing the management briefing |
| --- | --- |
| Agenda and Objectives | The team leader will present the - agenda for the management meeting - objectives for the meeting, including what is being asked of management Items required slides for the agenda and meeting objectives |
| Overview of Work Done | The team leader or a team member - presents a brief summary of the work done during the launch - describes the launch products produced - hands out a copy of the launch materials produced Recommended charts - brief summary of the launch work done - listing of the launch products produced Recommended presentation materials - cover page listing the project, date, team leader, team members, and handout contents - team role assignments - management's stated and implied goals and the team's goals - team Gantt-chart schedule - team TASK and SCHEDULE plans - team quality plan - team risk assessment |
| Team Goal and Plan Comparison | The team leader or a team member presents - management's stated and implied goals - the team's goals and goal measures - an overview of the team's plan, development strategy, and release plan - a comparison of the team's and management's goals Recommended charts - management's stated goals and implied goals - the team's goals - summary Gantt chart showing the key project dates - comparison of the team's plan to the goals |
| Alternate Team Plans (if applicable) | If the team's plan fails to meet management's stated goals, it is generally advisable to show - an alternate plan with additional resources - when the additional trained resources would be needed - how the added resources would improve goal performance Recommended charts - alternate plan - impact of added resources and when added resources are needed |
| Risks | The team leader or a team member describes - the risks identified by the team - the team's evaluation of the key risks - proposed mitigation actions for the key risks Recommended charts - each key risk, its evaluation, and the responsible team members - the proposed mitigation actions for each key risk |
| Conclusions | The briefing ends with a summary of the key plan elements and the briefing objective (to secure management commitment to the plan). |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |