Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Workshop Handouts – Launch Postmortem Meeting

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Postmortem Meeting (partially completed) |
| 3 | TSP Launch Postmortem Meeting - Script LAUPM |
| 4 | TSP Project Notebook - Specification NOTEBOOK |
| 5 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 6 | TSP Process Improvement Proposal - Form PIP (blank) |
| 7 | TSP Team Launch – Launch Participant Feedback Form |
| 11 | TSP Team Launch – TSP Coach Feedback Form |

Note: for the launch postmortem, the TSP launch and relaunch processes are the same.

Meeting Report - Launch Postmortem Meeting

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Postmortem Meeting: To conduct the launch postmortem |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 20 |  |  |  |  | Launch postmortem |  |  |  |  | TSP Coach |  |
| 10 |  |  |  |  | Prepare PIPs |  |  |  |  | TSP Coach |  |
| 15 |  |  |  |  | Launch evaluation |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSP Launch Postmortem Meeting - Script LAUPM |  |
| --- | --- |
| Purpose | To guide the team through the launch postmortem |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Team members’ personal task and schedule templates are available. - The planning manager has produced copies for the team of the - overall team task and schedule plan - team plan for the next phase - Forms: ITL, MTG, PIP - Specification: NOTEBOOK |
| General | - Timing - The launch postmortem meeting is held after meeting 9 on day 4, or at the end of day 3 right after meeting 8. - The PM generally takes about 1 hour, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Launch Postmortem | The planning manager reviews the launch data to ensure that - all required launch data are gathered and recorded - data are properly entered in the appropriate project forms and databases - responsibility is assigned for preparing the launch materials for entry in the project notebook (specification NOTEBOOK) |
| 4 | Prepare PIPs | The TSP coach leads the team through a process evaluation. - identify launch process problems or inconveniences - suggest process improvements and complete PIPs for these suggestions |
| 5 | Launch Evaluation | - The team and team leader complete the Launch Participant Feedback forms and submit a copy of these forms to the SEI. - The TSP coach completes the TSP Coach Feedback form and submits a copy of this form to the SEI. |
| 6 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch postmortem activities have been completed. - The management presentation has been added to the project notebook. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

TSP Project Notebook - Specification NOTEBOOK

| Purpose | To describe the contents of the project notebook |
| --- | --- |
| General | - The project notebook holds the complete project record. It should include all important project documents. - The notebook provides the historical record needed for future planning and analysis. |
| Notebook Format | The notebook format is not important. - Small project notebooks may be in a 3-ring binder. - Larger notebooks may be in one or more file folders. - For much larger notebooks, use summary and a database. |
| Outline | An outline of the notebook contents and item locations |
| Summary | Copies of completed system-level SUMP and SUMQ forms |
| Project Report | - The final project report (SUMMARY specification) - During the project, the NOTEBOOK file is a repository for documents to later include in the final report. |
| Task and Schedule Plans and Actuals | Include completed plan and actual resource and schedule data. - final completed TASK and SCHED templates - project's overall and detailed next-phase plans |
| Component Data | SUMP forms for all modules, components, products, subsystems, and the overall system |
| Quality Documents | - SUMQ forms for all modules, components, products, subsystems, and the overall system - Defect review records and forms (DEFECT and MTG forms) - Inspection reports (INS forms) |
| Risks and Issues | Include the initial and working risk and issue documents. - risk analysis and issue tracking reports and summaries - copies of the ITL issue and risk tracking forms - copies of risk analysis and issue resolution presentations - other risk analysis or issue resolution documents |
| Support Plans | Include the support plans. - build, integration, and system test plans - the process development plans and the processes used - the support development plans and a description of the support environment and tools used |
| Launch Summaries | Include the summary results of the project launches. - launch meeting reports and management presentation - team role assignments |
| Reports | Include copies of - all management and weekly meeting reports. - copies of any periodic management or customer reports - all cycle and project postmortem reports - all checkpoint reports |
| Working Documents | - System requirements specification (SRS) - Engineering requirements specification (ERS) - The conceptual design and development strategy - System design specification (SDS), (SRS/ERS traceability) - Design documents (EDS traceability) |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |
| No. |  | Date |  |  | Personal/Team |  | Risk/Issue |  | Impact |  | Likelihood |  | Owner |
| Description |  |  |  |  |  |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control # |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |