Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Launch Preparation Package

Senior Management

This package contains material you will need to prepare for the TSP Launch.  The elements contained are as follows.

| # Page | Launch Element |
| --- | --- |
| 2 | Senior Management Goals Discussion Guidelines |
| 3 | Senior Management Plan Review Guidelines |

Overview:  The TSP process guides your organization through planning and conducting a software intensive project.  Except for the opening and closing meetings which you attend, the team will be developing a detailed plan for their project.  Since this is demanding work that requires the full participation of all team members, no observers attend launch meetings 2 through 8 or the launch postmortem.

Your participation:  To launch teams properly, it is essential that they fully understand management's objectives for their projects.  That is why you are asked to describe and discuss management's objectives for this project at the opening launch meeting.  Suggestions for this discussion are given in the attached Senior Management Goals Discussion Guidelines on page (2 of this package).  At the end of the launch, the team will present their plan to you.  Again, it is important that you probe this plan to verify that it properly addresses your organization's needs.  Suggestions for this discussion are contained in Senior Management Plan Review Guidelines (on page 3 of this package).

Launch hours:  Your participation is essential at the opening launch meeting, which is scheduled from 8:30 AM to 10:00 AM of day 1.  Since this meeting could take longer, you should plan to spend the morning.  Generally, however, you will be free no later than 10:30 or 11:00 AM.

On launch day 4, your attendance is essential from 8:30 AM to 10:00 AM.  Again, the meeting could take longer, particularly if there are significant issues or problems.  While you should plan to be available until 12:00 noon of day 4, you will probably be free after 10:30 or 11:00 AM.

What to read and when:  Prior to launch meeting 1, you will find it helpful to read the Senior Management Goals Discussion Guidelines (on page 2 of this package).

Prior to launch meeting 9, you will also find it helpful to read the Senior Management Plan Review Guidelines (on page 3 of this package).

Other preparation guidelines:  If you wish to read the preparation guidelines for other launch participants, they are listed in the TSP Launch Preparation Package.  You can get a copy of this notebook from the person who is coordinating the launch preparations.

Senior Management Goals Discussion Guidelines

Launch Meeting 1

Purpose:  In launch meeting 1, a senior manager meets with the team to describe the organization’s goals and to answer the team’s questions.

Discussion leader:  The senior manager who knows why this project was undertaken should lead this discussion.  Ideally, this would be the executive who originally decided to launch the project.

#### Executive discussion:  The executive should cover the following topics in whatever order seems most appropriate.

- The organization’s overall business objectives

- Why the business decided to undertake this project

- What the business wishes to gain from doing this project

- How the executive would characterize a fully successful result

- What this project will lead to if fully successful

- How the executive would characterize a minimally acceptable result

- What resources are available and planned for this project

- Respond to the team’s questions about the business, its goals, and this project

Team discussion:  The team may ask questions about the goals and what they mean for the team’s work.  At the conclusion of this discussion, the team should understand the following.

- Management’s ideal and minimum goals for the project

- The resources planned and available for the work

- Any business or other constraints on the project

Intended result:  As a result of this discussion, the team should fully appreciate why the business has undertaken this project and what a successful outcome will mean to the organization.

Senior Management Plan Review Guidelines

Launch Meeting 9

Purpose:  In TSP launch meeting 9, the team leader presents the team's plan for your review and approval.

The team's objectives:  The team has worked to produce a thorough and responsible plan, and they would like you to understand and agree to it.  They may not have entirely met all your objectives, but they would like you to know that they have tried to do so.  Their plan rests on many estimates and assumptions, but they think it is the best plan that they can produce.  There is a lot that they do not know at this early point in the project, and their greatest concern is that they have overlooked some key activities.  While they feel this plan is aggressive, they would be happy if you approved it.

#### Your objectives:  You probably want to assure yourself that the team has done their best to meet your goals. One approach for doing this is as follows.

- Look for holes in the estimates and try to find extra or missing tasks.

- Understand the degree to which the team's estimates are based on historical data.

- Ensure that the plan has sufficient detail to guide the work.

#### Challenge the team members to show they can meet the plan.

Some probing questions:  Typical questions to ensure that the plan will meet your objectives might include the following.

- What are the size estimates for the principal products and how did you arrive at these estimates?

- How do you know if you have included all of the necessary tasks?

- What is the basis for your task estimates?

- How did the team arrive at the schedule?

- How did you estimate the number of weekly task hours?

- What could management do to help maximize your weekly task hours?

- Have you looked at alternative plans?

- Could you accelerate the schedule, and if so, what would it cost?

- What is your quality plan and how did you produce it?

- What are the key risks and your mitigation plans for them?

- Have you considered prototyping or reuse?

- What is the likely error in the size, time, and schedule estimates?

- When will you have learned enough to make a more accurate plan?

Desired outcome:  At the end of the meeting, you would like to understand the plan, be comfortable that it is the best plan you can expect, and know that the team is committed to meeting it, so that you can approve it.