Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Preparation Instructions

To ensure that your organization is properly prepared for the TSP launch workshop, it is important that you do the following as soon as possible.

- Appoint a launch coordinator who will handle the workshop preparation tasks and coordinate with the TSP launch coach.

- Give the attached launch preparation cover letter and checklist to the launch coordinator.

- Have the launch coordinator obtain answers to the questions on the attached project profile and provide them to the TSP launch coach as soon as possible.  The launch coach requires this information at least one month before the launch date.  If these questions are not answered in time, the launch workshop may have to be delayed.

- Have the launch coordinator follow the launch preparation cover letter and checklist to complete the arrangements for the launch workshop.

- The launch coordinator should contact the launch coach for answers to any preparation questions or issues.

#### TSP Project Profile Please provide the following information about the project to be launched and when completed, return this sheet to the TSP launch coach.

- The project name

- A brief description of the project and its status

- Names of all the team members on the project and their PSP/TSP training status. (For any team members who have not completed PSP/TSP training, please provide the date when that completion is planned.)

- Name of the project leader and the TSP training that he or she has completed. (If the project leader has not yet received TSP training, please provide the date when this training is planned.)

- Name, phone, business address, and e-mail address of the launch coordinator

TSP Launch Preparation Cover Letter

Preparation for a TSP launch involves the following steps.

- Check that all of the needed TSP materials are on hand.  The materials you need are

- Launch Checklist (Checklist PREPL)

- Launch Schedule

- Team Member Preparation Package (Launch Preparation Team Members.doc)

- Team Leader Preparation Package (Launch Preparation Team Leader.doc)

- Marketing Management Preparation Package(Launch Preparation Marketing.doc)

- Senior Management Preparation Package (Launch Preparation Senior Management.doc)

- Other Attendee Preparation Package (Launch Preparation Other.doc)

- TSP launch notebooks

- Tell the TSP coach that you have received the launch materials.

- The TSP launch notebooks should be on hand, but they are not needed until the opening day of the launch.

- Follow TSP Launch Preparation Checklist PREPL for a launch.  If this project has not previously had a launch, this is a launch.

- Make sure that all attendees are available for the launch during the times specified on the checklist.

- Make sure that all observers know they are only to attend the opening and closing launch meetings.  There are no observers for launch meetings 2 through 8.

- Distribute the appropriate preparation materials to the launch attendees at least a week before the start of the launch.

- Senior Manager:  TSP Launch Preparation Package Senior Management

- Marketing Manager: TSP Launch Preparation Package Marketing Management

- Team Leader:  TSP Launch Preparation Package Team Leader

- Team Member:  TSP Launch Preparation Package Team Members

- Other participant:  TSP Launch Preparation Package Other Attendees

- Make sure that the meeting facilities and catering (optional) are arranged.

- Inform the TSP coach that you are prepared for the launch.

TSP Launch Preparation Checklist - PREPL

| Purpose |  | To guide launch preparation activities |  |
| --- | --- | --- | --- |
| Weeks Prior to Launch | Step | Description | Completed |
| 6-8 | Prelaunch Package Sent | The launch coordinator has received and reviewed the prelaunch package. |  |
| 6 | Project Identified | The TSP project has been identified. |  |
| 6 | Responsible Person Identified | A person has been named as responsible for launch preparation for the project. |  |
| 4 | Team Ready | The team members and team leader are identified and have scheduled the launch period on their calendars so that they are available for the entire launch period. |  |
| 2 | Launch Preparation Package Distributed | The launch coordinator has received, reviewed, and distributed the launch preparation package to new teams or team members. |  |
| 2 | Team Member Training Completed | - All software developers on the team have completed PSP training. - All other team members have completed team member training. |  |
| 2 | Management Training Completed | - The team leader has completed TSP or PSP management training. - All involved managers and executives have completed TSP or PSP management training. |  |
| 2 | Attendance Confirmed | All launch participants know the attendance guidelines and are scheduled to attend. - The management, marketing, and other interested parties attend launch meetings 1 and 9. - The team leader and team members attend meetings 1 through 9, and the launch postmortem. |  |
| 2 | Schedule Finalized | - All team members and the team leader are committed to attend launch meetings 1 through 9 and the launch postmortem, and management and marketing representatives are prepared and available for meetings 1 and 9. |  |
| 2 | Facilities for Meetings 1 and 9 Confirmed | - The room for launch meetings 1 and 9 is large enough to hold all the team members, management representatives, and observers. - A projector and screen are available. - The room is available for the mornings of days 1 and 4. |  |

(continued on next page)

TSP Launch Preparation Checklist - PREPL (continued)

| Weeks Prior to Launch | Step | Description | Completed |
| --- | --- | --- | --- |
| 2 | Facilities for Meetings 2 through 8, and Launch Postmortem Confirmed | For days 1, 2, 3, and 4 (if needed) the following facilities are available. - a conference room with desk-size working space for each team member, the team leader, and launch coaches - one or more personal computers with the Microsoft Office 2000 - two flip-chart easels and a whiteboard with pads and markers - a PC-compatible projector |  |
| 2 | Process Review Scheduled | All new TSP team members are scheduled to attend a TSP process review and workshop for the rest of day 4, after all other launch meetings. |  |
| 2 | Team Preparation Package Distributed | The team leader and all of the team's members have been given the team and team leader workshop preparation packages, respectively. |  |
| 2 | Management Preparation Package Distributed | The senior manager has been given the senior management workshop preparation package. |  |
| 2 | Marketing Preparation Package Distributed | The senior marketing manager has been given the marketing management workshop preparation package. |  |
| 2 | Other Attendee Preparation Package Distributed | Any other attendees have been given the other attendee workshop preparation package. |  |
| 2 | Catering Confirmed (optional) | For days 1, 2, 3, and 4 (if needed), the following catering is planned. - morning and midmorning break - working lunch - mid-afternoon break - A working dinner may be needed for days 1, 2, or 3. |  |
| 2 | Launch Notebooks Distributed | The launch notebooks have been distributed to all team members and the team leader. |  |

Standard TSP Launch Workshop Schedule

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 1 |  |  |  |
| 8:30 | 10:00 | Meeting 1 | TSP and workshop overview Senior management discussion of the business need for the project Marketing discussion of the market need for the product Coach, team members, team leader, senior management |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 2 | Team roles and goals Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 2 (continued) | Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 6:45 | Meeting 3 | Strategy, process, and support planning Coach, team members, team leader |
| # Day 2 |  |  |  |
| 8:00 | 8:30 | Meeting 3 (continued) | Coach, team members, team leader |
| 8:30 | 10:00 | Meeting 4 | Overall project plan Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 4 (continued) | Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 1:30 | Meeting 4 (continued) | Coach, team members, team leader |
| 1:30 | 2:30 | Meeting 5 | Quality plan Coach, team members, team leader |
| 2:30 | 2:45 | Break |  |
| 2:45 | 5:00 | Meeting 6 | Detailed engineer and team next-phase plans, balanced plan Coach, team members, team leader |
| # Day 3 |  |  |  |
| 8:30 | 10:15 | Meeting 6 (continued) | Coach, team members, team leader |
| 10:15 | 10:30 | Break |  |
| 10:30 | 12:00 | Meeting 7 | Team risk assessment Coach, team members, team leader |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 2:30 | Meeting 8 | Management meeting planning Coach, team members, team leader |
| 2:30 | 2:45 | Break |  |
| 2:45 | 5:30 | Work period | Management meeting preparation Team members, team leader |
| # Day 4 |  |  |  |
| 8:30 | 10:00 | Meeting 9 | Senior management reviews the launch results Coach, team members, team leader, senior management |
| 10:00 | 10:30 | Break |  |
| 10:30 | 11:30 | Launch postmortem meeting | Launch postmortem Coach, team members, team leader |
| 11:30 | 12:30 | Lunch |  |
| 12:30 | 4:30 | TSP Process Review | Coach and all new team members |

TSP Relaunch Workshop Schedule

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 1 |  |  |  |
| 8:30 | 10:00 | Meeting 1 | Workshop overview Team leader review of project status and any changes in business goals Coach, team members, team leader, and other attendees as appropriate |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 2 | Team roles and goals Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 2 (continued) | Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 5:00 | Meeting 3 | Strategy, process, and support planning Coach, team members, team leader |
| # Day 2 |  |  |  |
| 8:00 | 10:15 | Meeting 3 (continued) | Coach, team members, team leader |
| 10:15 | 10:30 | Break |  |
| 10:30 | 12:00 | Meeting 4 | Overall project plan Coach, team members, team leader |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 3:30 | Meeting 4 (continued) | Coach, team members, team leader |
| 3:30 | 3:45 | Break |  |
| 3:45 | 4:45 | Meeting 5 | Quality plan Coach, team members, team leader |
| # Day 3 |  |  |  |
| 8:00 | 10:00 | Meeting 6 | Detailed engineer and team next-phase plans, balanced plan Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 6 (continued) | Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 2:30 | Meeting 7 | Team risk assessment Coach, team members, team leader |
| 2:30 | 2:45 | Break |  |
| 2:45 | 3:45 | Launch postmortem meeting | Launch postmortem Coach, team members, team leader |

Notional schedule; it can be compressed or extended to meet scope of launch.