Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Answers to the
Maintaining the Baseline Plan Exercise
Running the Project

TSP Coach Training

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

Not approved for public release.

Distribution controlled.

Answers to Maintaining the Baseline Plan Exercise

There is no right or wrong answer to this exercise. Your intuition, the facts, and the views of the team members will generally guide you to an effective solution to most team problems.

| #### The Facts | Even at this early project stage, the team’s weekly reports and the earned value charts provide a great deal of information. From these, you can determine the following facts. - All team members are spending less than their planned 20 hours per week. The total time spent is nearly 55 hours below plan. The ratio of planned to actual hours is 1.16. - The sum of the earned values for the engineers to date is 30.0, compared to 40.2 planned. The team has completed only about 75% of their planned work to date. - Within a few hours per week, every team member is working about the same amount of time (although team member B has put in the most hours to date). The problem does not seem to be that one member is not making an effort. - So far, the planned task hours are fairly close to the actual hours. The total hours spent on completed tasks is 303.8 hours (versus 293 hours planned), or about 4% more than the plan. - The project is more than a week behind schedule and, if the present rate of earning value continues, the earned value prediction is that it will finish this phase in week 20, as opposed to the planned week 13. The project should be viewed as potentially seven weeks behind schedule. |
| --- | --- |

| #### Considerations | In deciding how to react to the situation, consider the following. - The fewer task hours than planned (86.2% of planned) suggests a schedule growth of 16%. The greater number of task hours than planned for completed tasks suggests a 4% schedule growth. Combined, these two factors suggest a 20% schedule growth, but the earned value prediction suggests a 31% schedule growth. The difference is potentially because either there are some large partially-completed tasks or some of the team’s time is being spent on unreported tasks. You need to find out which is the case. Note that all tasks should be reported, even if they were not planned. - The engineers are spending a considerable amount of their normal 40-hour work week on non-project activities. While this is not unusual, you could get more time for the project if they could reduce this time. You need to determine what the engineers can do and what you could do to help them to improve their total weekly project hours. - Look at possibilities as to why the team is not getting the task hours. - Are the team members being pulled off to work on other tasks that are not in the plan? - Does the team not know how to write an SRS? |
| --- | --- |

| Alternative Actions | In deciding how to coach the team and what to do next, your principal alternatives are as follows. - Suggest that the team leader convince the team of the importance of getting back on schedule and work with them to set weekly goals for their hours and tasks. When the team or any engineer meets their goals, the team leader should make a big deal out of it. - Do nothing and wait a week or so to get more data. Make sure that the team understands the consequences of doing nothing. - Suggest that the team leader go to management with the problem and see what they suggest. - Suggest that the team leader direct the engineers to spend at least 20 hours every week and give them specific tasks to accomplish each week. |
| --- | --- |

| Comments on the Actions | Some of the key points on these actions are as follows. - Alternative 1 is the only real choice to get back on schedule. The team leader needs to motivate the engineers to work more hours and complete more tasks each week. To do this, she should act like a coach and strive to build team excitement. For example, if one engineer planned to complete a task by Wednesday, the team leader should stop by that afternoon to see how it is coming. She should be visible every day and show that she cares about every checkpoint and every goal. Also, consider posting the weekly hours or the earned value trend lines. However, in doing this, be careful not to compare the engineers’ performances. Work with the engineers and try to get each to do his/her very best each week. In addition, suggest that the team leader talk to her management to get their suggestions for ways to build team enthusiasm. - Action 2 would make sense only if the delay were due to a one-time event. In this case, there are no unique events. The project is in trouble. Delay would only make the problem harder to solve. - Action 3 is an abdication of authority. If the team leader goes to management at this point, she is saying that she does not know how to manage the team. You might suggest that the team leader have a private discussion with her immediate manager about the situation and her plans, but she should not ask for management help until she and the team have tried to fix the problem. - Action 4 is probably the worst choice. The reason is that the engineers gather all of the data that the team leader must use to enforce her directives. By being authoritarian, she loses their loyalty and makes avoiding her wrath more important than completing the project. This could cause them to take defensive measures, such as fudging their data, in order to protect themselves. They could appear to meet the directed goals, but this would not accelerate the project. If the team started fudging the data, then the team leader would have no reliable data for managing the project, and the work might slip schedule even faster without her knowing it. |
| --- | --- |