Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Student Workbook for the
Coaching the Team Leader Exercise

TSP Coach Training

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

Not approved for public release.

Distribution controlled.

TSP Coach Training

Coaching the Team Leader Exercise

Overview

| #### Exercise #### Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | Reference | 2 |
|  | Exercise Scenario One | 3 |
|  | Exercise Scenario Two | 4 |
|  | Exercise Scenario Three | 5 |
|  | Exercise Scenario Four | 6 |

| Exercise Objectives | At the end of this exercise, you will understand some of the issues involved in coaching the team leader. |
| --- | --- |

| #### Exercise #### Instructions | This exercise has four scenarios. - The students form teams and each team reviews one scenario. - Each team decides how to answer the exercise questions and prepares a five-minute presentation for the class. - The instructor leads a class discussion of each scenario. |
| --- | --- |

| #### Reference | Leading and Coaching Disciplined Teams: The Team Software Process (TSP) for Managers, Watts Humphrey, 2000 |
| --- | --- |

Continued on next page

Coaching the Team Leader Exercise

Scenarios

| #### Scenario One | Jan, the team leader, ran her small team like a military operation. Everyone participated during the team launch, but once the coach had left, Jan took charge. The weekly meeting was a command exercise. Every week before the meeting, Jan reviewed each team member’s weekly data. During the weekly meeting, instead of each team member reporting on their status, Jan questioned the team members who had not met their plans on why they had not met their plan. Jan did most of the talking, and there was little discussion. After a few weeks, Jan decided to change the project strategy. She told the engineers about the change, but she didn’t think a new plan was needed. She knew what everybody had to do, so she didn’t see why a plan was needed. Without a plan that they understood and believed, the engineers just did what they were told. A couple of weeks later, the coach visited Jan’s organization and found out what was happening. She talked to Jan’s manager and to the laboratory director. She did not have time to fix the problem, so she asked Jan’s managers to counsel Jan on how to run the project. Over the next week, the manager and laboratory director had several telephone conferences with the coach about Jan’s problems. After the second call, the coach realized that these managers were not going to counsel Jan -- they planned to fire her. It took several more phone calls before the coach could convince them not to fire Jan. |
| --- | --- |

| #### Questions for Discussion | Decide how to answer the following questions. - What is the problem with this team leader? - What mistakes did the coach make? - How should the coach have handled this situation? You have 15 minutes to arrive at a group conclusion and prepare a 5-minute presentation. |
| --- | --- |

Time:  20 minutes

Coaching the Team Leader Exercise

Scenarios, continued

| #### Scenario Two | Pat, the team leader, had not been an engineer and she was uneasy about her lack of software experience. Pat’s project had been launched successfully, but as the work progressed, Susan, the most experienced engineer on Pat’s team, did not use the TSP process or gather any data. The other engineers were concerned because they were religiously following the process and tracking their work. After several engineers complained to Pat, she decided to tell Susan to follow the process. Susan refused. She claimed that using the process and gathering the data would slow her down. Although Pat argued with Susan, she took no further action and Susan continued to ignore the process. Several months later, when Susan’s code was integrated and tested, there were so many problems that the team fell three weeks behind schedule. Also, by this time the other engineers’ performances were beginning to deteriorate because they were affected by Susan’s attitude. |
| --- | --- |

| #### Questions for Discussion | Decide how to answer the following questions. - What happened to this team? - How should Pat have handled this situation? - What should the coach do in this situation? You have 15 minutes to arrive at a group conclusion and prepare a 5-minute presentation. |
| --- | --- |

Time:  20 minutes

Coaching the Team Leader Exercise

Scenarios, continued

| #### Scenario Three | Although the organization had told Caroline, the coach, that they were fully prepared for the TSP launch, they were not. In launch meeting 2, the team told Caroline that the most experienced team member had been designated as the acting team leader. The permanent team leader, Marlene, had just been hired and would not start work until the Monday after the launch. Since they were already into the launch, Caroline decided to continue with the launch. At the management review meeting, management was annoyed that the team would not commit to support a customer demonstration in August. The earliest date to which the team would commit was in January. After some debate, the team’s plan was finally approved with the January date for the customer demonstration. When Marlene started work the following week, Caroline met with her and gave her an individual training course on the TSP and managing PSP-trained engineers. Marlene met with her supervisor and the company president. They told her that the company had to have software support for the customer demonstration in August. Marlene agreed that her team would provide the needed support by that date. When Marlene described this meeting to her team, the engineers felt betrayed. However, Marlene insisted that the August date was sacrosanct. Since Marlene, had not participated in the launch, she did not understand the team’s plan and did not know that the team should produce a new plan. Since none of the engineers explained this to her or offered to help, the team did not make a new plan. Without a new plan, the team continued to work to the old plan and essentially ignored Marlene. In every team meeting, Marlene talked about the August date and emphasized its importance, and the engineers listened politely without saying anything. Finally, in early July it became obvious that the team would not make the August date, and Marlene told management that the team could not support the customer demonstration until January. The company president was very unhappy. |
| --- | --- |

| #### Questions for Discussion | Decide how to answer the following questions. - What went wrong with this TSP project? - How should the coach have handled this? You have 15 minutes to arrive at a group conclusion and prepare a 5-minute presentation. |
| --- | --- |

Time:  20 minutes

Coaching the Team Leader Exercise

Scenarios, continued

| #### Scenario Four | Gwen, an external coach, arranged to do a TSP project with a client. Gwen discussed the PSP training requirements with the client and the client said they had arranged to have their engineers and mangers trained by an in-house authorized PSP instructor. Gwen showed up for the launch and the first meeting went fine, just like any other launch. However, in the second meeting, the team didn’t feel that they needed to set any goals. Management had told them what their schedule was and that was fine with them. As the team went through the role selection process, Alice, the team leader, insisted on taking the interface and design manager roles. The quality and test manager roles were given to group leaders outside the team. At the end of the first day of the launch, as Gwen was talking with one of the team members, she found out that none of the engineers had completed PSP training. In fact, they had attended only a couple days of the training, decided that it was too much work, and convinced their management to cancel the rest of the training. None of the managers had completed any training, either. Gwen thought about canceling the rest of the launch, but since everyone (including senior management) was assembled for the launch, and Gwen’s calendar was full for the next few months, she decided to proceed with the launch anyway. The next day in meeting 3, things continued to go downhill. Alice had already made a size estimate for the product, so when Gwen asked the team to estimate the product size, Alice convinced the team it was a waste of time since she had already completed this task. Next, Gwen tried to get the team to define their process. The team defined only their high-level process for the project phases of requirements, high-level design, implementation, and test. They didn’t feel that it was necessary to define any detailed work steps for the first phase, requirements. In meeting 4, Alice said that she already had a plan for the project with about 30 tasks and the team decided that plan was all the detail that they needed. Gwen tried to persuade the team to define their tasks in more detail, especially for the first phase. But since the company had always worked with this level of plan before, the team decided they didn’t need to go any further. The team completed the launch, but in the final plan, the engineers’ tasks were in increments of 50 to 130 hours, rather than in 10 hours or less as recommended by TSP. In the management review at the end of the launch, there was little discussion, since the plan was essentially the same plan that Alice had presented to management before the launch. |
| --- | --- |

| #### Questions for Discussion | Decide how to answer the following questions. - What went wrong with this TSP launch? - How should the coach have handled this? - What could the coach have done to prevent this situation? You have 15 minutes to arrive at a group conclusion and prepare a 5-minute presentation. |
| --- | --- |

Time:  20 minutes