## Index (hidden)
Index of Forms and Charts
FORMS | Description | CHARTS | Description
Launch Meeting/Planning Forms |  | Cumulative Earned Value | Cumulative Planned vs. earned vs. projected earned value
Use these forms to plan a new project |  | Earned Value per Week | Planned, earned, and projected value per week
Project | Project startup and summary form | Earned Value Trend | Cumulative Plan Value / Cumulateive Earned Value per week
Team | Team member summary | Cumulative Plan vs. Actual Hours | Cumulative planned vs. actual hours per week
Roles | TSPe role assignments | Plan vs. Actual Hours per Week | Planned vs. actual hours per week
Goals | Team goals | Percent Defect Free | Percent of components that are defect free by phase
SUMS | Size summary | Cumulative Defects Removed by Phase | Cumulative defects removed by phase for each component
Task | Task plan template | Defects Removed by Phase | Defects removed by phase for each component
Schedule | Schedule plan template | Defect Density by Phase | Defects per KLOC by phase for each component
|  | Review Rates | Inspection and review rates for each component
|  | Phase Yield | Phase yield for each component
|  | Process Yield | Process yield for each component
|  | Quality Profile | Five point quality profile for each component
|  | Time in Phase% | Percentage of time spent in each phase
|  | Defects Injected% | Percentage of defects injected in each phase
|  | Defects Removed% | Percentage of defects removed in each phase
Weekly Meeting/Tracking Forms
Use these forms for gathering data and tracking
TimeLog | Time recording Log
DefectLog | Defect recording log
Weekly meeting status report
Task | Task plan template
Schedule | Schedule plan template
Quality actuals for system and components
Resource actuals for system and components
Defects injected/removed for system and components
Standards
Phases | TSPe process phase standard
DefectTypes | Defect type standard
Copyright 1998 James W. Over

## TSPi Instructions (hidden)
TSP Support Tool Instructions
Strategy Development and Planning
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Before STRAT1 | Team Leader | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Before STRAT1 | Team Leader | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Before STRAT1 | Team Leader | Enter the role assignments on the Roles worksheet. | Roles!B2
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
STRAT1: Produce the Size Estimate | Planning Manager | Enter on the SUMS worksheet, the names and size estimates of all assemblies and parts for this cycle. | SUMS!B8
PLAN1: Produce the Task Plan | Planning Manager | Click the Generate Task List button to create a default task list. | Task!A8
PLAN1: Produce the Task Plan | Planning Manager | Revise the task list adding or deleting tasks as necessary. Then for each task, estimate the size where appropriate, the time, and the time for each engineer assigned to the task. | Task!A8
PLAN1: Produce the Schedule Plan | Planning Manager | Enter hours per week in the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
| Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate a schedule. | Task!A8
PLAN1: Quality Plan | Team | Before creating the quality plan, review the quality standard in the textbook.
PLAN1: Quality Plan | Quality/Process Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
PLAN1: Quality Plan | Quality/Process Manager | Enter estimated phase yields for each phase. | SUMQ!D55
PLAN1: Quality Plan | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
PLAN: Balance Workload | Planning Manager | Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the copies automatically. | Team!B2
PLAN: Balance Workload | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set their planned hours to zero). | Task!A8
PLAN: Balance Workload | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
PLAN: Balance Workload | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
PLAN: Balance Workload | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Weekly Tracking
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
STRAT, PLAN, REQ, DES, IMP, TEST, PM | All team members | During all TSPi phases, use the time log to record data on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
REQ, DES, IMP, TEST | All team members | During TSPi phases REQ, DES, IMP, and TEST, use the defect log to record data on each defect. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
Weekly | All team members | Click the Update Task and Schedule Plan button on the Task worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!C8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!A2
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!C8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Cycle Postmortem
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the cycle. | Project!Name

## TSP Instructions (hidden)
TSP Support Tool Instructions
Strategy Development and Planning
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Launch Meeting 2 | Launch Coach or Planning Manager | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the role assignments on the Roles worksheet. (Optional) | Roles!B2
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the team goals on the Goals worksheet. (Optional) | Goals!A3
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
Launch Meeting 3 | Launch Coach or Planning Manager | Enter all the software assemblies identified during this meeting. Enter the name, assembly/part flag, part of, and size measure. Requirements and High-Level Design documents may also be entered on SUMS. | SUMS!B8
Launch Meeting 4 | Launch Coach or Planning Manager | Enter on the SUMS worksheet, the size estimates of all software assemblies. | SUMS!B8
Launch Meeting 4 | Launch Coach or Planning Manager | Click the Generate Task List button to create an initial task list based on the assemblies on SUMS. | Task!A8
Launch Meeting 4 | Launch Coach or Planning Manager | Revise the initial task list by adding or deleting tasks as necessary. Then complete the estimate for each task by entering a size estimate, size measure, rate in units per hour, the estimated hours, and the number of engineers assigned to the task. | Task!A8
Launch Meeting 4 | Launch Coach or Planning Manager | Enter hours per week for the team on the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
Launch Meeting 4 | Launch Coach or Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate the overall plan. | Task!A8
Launch Meeting 5 | Team | Before creating the quality plan, review the quality guidelines in the TSP Launch Notebook
Launch Meeting 5 | Launch Coach, Planning Manager, or Quality Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
Launch Meeting 5 | Launch Coach, Planning Manager, or Quality Manager | Enter estimated phase yields for each phase. | SUMQ!D55
Launch Meeting 5 | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
Launch Meeting 6 | Launch Coach or Planning Manager | Enter the initials of the team member(s) assigned to each task in the resources column on worksheet Task. | Task!A8
Launch Meeting 6 | Launch Coach or Planning Manager | Enter the initials of the team member that owns each leaf assembly in the owner column on worksheet SUMS. Note that plan and actual size are copied from the owner's workbook to the team workbook during consolidation, so each leaf assembly MUST have an owner. | SUMS!B8
Launch Meeting 6 | Launch Coach or Planning Manager | Make 1 copy of the team workbook for the consolidated team plan. Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the engineer's copies automatically. | Team!B2
Launch Meeting 6 | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set the column Number of Engineers to 1). | Task!A8
Launch Meeting 6 | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
Launch Meeting 6 | Each engineer | Click the Update Task and Schedule Plan button on the Task Worksheet to generate your individual plan. Repeat the previous two steps until you are satisfied with the plan
Launch Meeting 6 | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
Launch Meeting 6 | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Launch Meeting 7 | Launch Coach or Planning Manager | Enter the team risks on the IRTL worksheet. (Optional) | IRTL!B7
Weekly Tracking
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
All | All team members | While working, use the time log to record time spent on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
All | All team members | While working, use the defect log to record each defect found. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
All | All team members | While working, use the issue/risk tracking log (IRTL) to record new issues and risks or to change status of existing issues or risks. | IRTL!B7
All | All team members | To review status against your plan select the Update item on the TSP Tools menu. | Project!B3
Weekly | All team members | Ensure that the completion data for all completed tasks has been entered, and all size, time, and defect data for the week have been entered.
Weekly | All team members | Review the task on worksheet Task and move all organize them into the following order. 1-completed tasks 2-tasks planned for the next two weeks 3-remaining tasks | Task!A8
Weekly | All team members | Click the Update Project button on the Task worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!A8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Prepare a weekly issue/risk report. The worksheet IRWeek contains the information for this reportt. | IRWeek!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!A3
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!A8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Prepare a weekly issue/risk report. The worksheet IRWeek contains the information for this reportt. | IRWeek!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Phase Postmortem
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the IRTL worksheet and print a copy of all team issues and risk | IRTL!B7
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the phase or project. | Project!Name

## Project
TSP | - Project Summary | [5 empty] | Plan | Actual | Phase | %
[6 empty] | Design/Code Time | 0.16392 | 0 | Management and Miscellaneous | 0.056064
Name | Consolidated | Date | 2026-07-29 |  |  | Code Review Time | 0.4456 | 0 | Code | 0.85229
Project | AIM | Start Date | 2010-01-25 |  |  | Compile Defects/KLOC | 0.39743 | 1 | Code Inspection | 0.09165
Team | AIM |  |  | Weeks Shown | 10 | Unit Test Ddefects/KLOC | 0.5744 | 1
Assembly |  | Cycle | 2 |  |  | Design Review Time | 0 | 0
Version: | TSP.20100105. ©2009 J. Over. | Today's Date Override |  |  |  | COMPILE | 3.4722
[6 empty] | CODEINSP | 2.7778
[6 empty] | UT | 2.0833
[6 empty] | IT | 0
[6 empty] | ST | 0
[6 empty] | 1 Year | 0
[6 empty] | Product Life | 0
[6 empty] | QPI | 0 | 0
Draw
Print
Use Time Log
Use Defect Log
Time and Defect Log Controls
Chart Controls
Max
Copy
Submit...
Team Folder

## Team
TSP Team Members - Form TEAM
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2
ID | Name | Initials | Phone | e-mail | Workbook Filename | Planned Tasks | Planned Task Hours | Planned Schedule Weeks | Planned End Date | Predicted End Date
1 | Team Member A | A |  |  | A.xls | 38 | 108.4 | 69 | 2010-05-24 | 2011-05-16
2 | Team Member C | C |  |  | C.xls | 100 | 160.7877 | 55 | 2010-04-26 | 2011-01-31
3 | Team Member B | B |  |  | B.xls | 102 | 286.1046 | 64 | 2010-05-10 | 2011-04-11
4 | Team Member F | F |  |  | F.xls | 40 | 189.2816 | 106 | 2010-06-07 | 2012-01-30
5 | Team Member D | D |  |  | D.xls | 113 | 333.5321 | 50 | 2010-05-17 | 2011-01-03
6 | Team Member G | G |  |  | G.xls | 91 | 162.7188 | 71 | 2010-06-14 | 2011-05-23
7 | Team Member E | E |  |  | E.xls | 33 | 45.6111 | 67 | 2010-05-31 | 2011-05-02
8
9
10
11
12
13
14
15
16
17
18
19
20
[6 empty] | 517 | 1286.4358 | 106 | 2010-06-14 | 2012-01-30
[6 empty] | Total |  | Max
Formulas:
Planned End Date = MAX(J8:[Planned End Date, row above])
Predicted End Date = MAX(K8:[Predicted End Date, row above])
Make Team Member Workbooks
Consolidation Mode
Consolidate Plans

## Goals (hidden)
TSP Team Goals - Form GOAL
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2 | Measure |  | Tracking
Stakeholder | Goal Desciption | Plan | Actual | Who | When

## Roles
TSP Team Member Role Assignments - Form ROLE
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2
Team Member Roles | Requirements | Design | Implementation | Integration and Test
Team Leader | G
C
Customer Interface Manager | G
A
Design Manager | D
C
Implementation Manager | B
D
Planning Manager | E
C
Process Manager | E
F
Quality Manager | C
E
Support Manager | D
B
Test Manager | A
F

## STRAT (hidden)
TSP Strategy Recording - Form STRAT
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2
Estimated Allocation to Development Cycle
|  |  |  | Estimated |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8
Ref. | Feature, Function, or Component | Description | Size Unit | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours

## INV (hidden)
TSP Process Inventory - Form INV
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2 | Estimate
|  | Size |  |  | Effort
Ref. | Work Element | Unit | New | Mod. | Hours | Due Date | Assigned To

## SUMP
TSP Plan Summary - Form SUMP
Name | Consolidated |  |  | Date | 2026-07-29
Team | AIM
Assembly |  |  |  | Cycle | 2
Program Size | Plan | Actual
Total Requirements Pages (SRS) | 605 | 11
Total HLD Pages (SDS) | 38 | 0
Total Detailed Design Lines
Base LOC (B) | 0 | 23617
Deleted LOC (D) | 0 | 79
Modified LOC (M) | 0 | 106
Added LOC (A) | 3170 | 350
Reused LOC (R) | 0 | 0
New and Changed LOC (N) | 3170 | 456
Total LOC (T) | 3170 | 23888
Total New Reuse LOC | 0 | 0
Estimated Object LOC (E)
Upper Prediction Interval (70%)
Lower Prediction Interval (70%)
Time in Phase (hours) | Plan | Actual | Actual%
Management and Miscellaneous | 394.16 | 155.2161 | 24.19%
Launch and Strategy | 0 | 0 | 0%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 0 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 0 | 0 | 0%
Detailed Design | 51.7222 | 52.7594 | 8.222%
DLD Review | 0 | 0 | 0%
Test Development | 0 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 363.5702 | 273.7331 | 42.66%
Code Review | 85.2671 | 61.8653 | 9.641%
Compile | 13.1081 | 2.4375 | 0.3798%
Code Inspection | 266.0573 | 77.1928 | 12.03%
Unit Test | 65.5405 | 11.6303 | 1.812%
Build and Integration Test | 0 | 0 | 0%
System Test | 11.22 | 0 | 0%
Documentation | 0 | 0 | 0%
Postmortem | 35.7903 | 6.8878 | 1.073%
Total | 1286.4358 | 641.7222 | 100%
Total Time UPI (70%)
Total Time LPI (70%)
Defects Injected | Plan | Actual | Actual%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 0 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 0 | 0 | 0%
Detailed Design | 38.7917 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 0 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 727.1404 | 80 | 100%
Code Review | 0 | 0 | 0%
Compile | 3.9324 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 4.3912 | 0 | 0%
Build and Integration Test | 0 | 0 | 0%
System Test | 0 | 0 | 0%
Total Development Defects Injected | 774.2557 | 80 | 100%
Defects Removed | Plan | Actual | Actual% |  |  | Phase | Plan | Actual
Planning | 0 | 0 | 0% |  |  | Planning | 0 | 0
Requirements | 0 | 0 | 0% |  |  | Requirements | 0 | 0
System Test Plan | 0 | 0 | 0% |  |  | System Test Plan | 0 | 0
REQ Inspection | 0 | 0 | 0% |  |  | REQ Inspection | 0 | 0
High-Level Design | 0 | 0 | 0% |  |  | High-Level Design | 0 | 0
Integration Test Plan | 0 | 0 | 0% |  |  | Integration Test Plan | 0 | 0
HLD Inspection | 0 | 0 | 0% |  |  | HLD Inspection | 0 | 0
Detailed Design | 0 | 0 | 0% |  |  | Detailed Design | 0 | 0
DLD Review | 27.1542 | 0 | 0% |  |  | DLD Review | 27.1542 | 0
Test Development | 0 | 0 | 0% |  |  | Test Development | 27.1542 | 0
DLD Inspection | 8.1463 | 0 | 0% |  |  | DLD Inspection | 35.3004 | 0
Code | 0 | 0 | 0% |  |  | Code | 35.3004 | 0
Code Review | 511.4422 | 43 | 53.75% |  |  | Code Review | 546.7426 | 43
Compile | 111.561 | 3 | 3.75% |  |  | Compile | 658.3036 | 46
Code Inspection | 78.0927 | 33 | 41.25% |  |  | Code Inspection | 736.3962 | 79
Unit Test | 34.0736 | 1 | 1.25% |  |  | Unit Test | 770.4698 | 80
Build and Integration Test | 3.0288 | 0 | 0% |  |  | Build and Integration Test | 773.4985 | 80
System Test | 0.60575 | 0 | 0% |  |  | System Test | 774.1043 | 80
Total Development Defects Removed | 774.1043 | 80 |  |  |  | Acceptance Test | 774.2027 | 80
Acceptance Test | 0.098435 | 0 |  |  |  | Product Life | 774.2557 | 80
Product Life | 0.053003 | 0
Summary | Plan | Actual
LOC/Hour | 2.4642 | 0.71059
CPI (Cost-Performance Index) |  | 2.0047
% Reuse | 0% | 0%
% New Reuse | 0% | 0%

## SUMQ
TSP Quality Plan - Form SUMQ
Name | Consolidated |  |  | Date | 2026-07-29
Team | AIM
Assembly |  |  |  | Cycle | 2
SYSTEM Percent Defect Free |  |  | Actual
In Compile |  |  | 91.67%
In Unit Test |  |  | 97.22%
In Build and Integration Test |  |  | 100%
In System Test |  |  | 100%
In Acceptance Test |  |  | 100%
In Product Life |  |  | 100%
Defects/Page |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0 | 0
Defects/KLOC |  | Plan | Actual
DLD Review |  | 8.566 | 0
DLD Inspection |  | 2.5698 | 0
Code Review |  | 161.3382 | 94.2982
Compile |  | 35.1927 | 6.5789
Code Inspection |  | 24.6349 | 72.3684
Unit Test |  | 10.7488 | 2.193
Build and Integration Test |  | 0.95544 | 0
System Test |  | 0.19109 | 0
Total Development |  | 244.1969 | 175.4386
Acceptance Test |  | 0.031052 | 0
Product Life |  | 0.01672 | 0
Total |  | 244.2447 | 175.4386
Defect Ratios |  | Plan | Actual
DLD Review/Unit Test |  | 0.79693 | 0
Code Review/Compile |  | 4.5844 | 14.3333
Development Time Ratios |  | Plan | Actual
REQ Inspection/Requirements |  | 0 | 0
HLD Inspection/High-Level Design |  | 0 | 0
Detailed Design/Code |  | 0.14226 | 0.19274
DLD Review/Detailed Design |  | 0 | 0
Code Review/Code |  | 0.23453 | 0.22601
Inspection/Review Rates |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0 | 0
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 37.1773 | 7.3709
Code Inspection |  | 11.9147 | 5.9073
A/FR |  | 4.467 | 9.8849
Phase Yields |  | Plan | Actual |  |  | Phase Yield Planning Guidelines
Planning |  | 0% | 0% |  |  | Planning | 0%
Requirements |  | 0% | 0% |  |  | Requirements | 0%
System Test Plan |  | 0% | 0% |  |  | System Test Plan | 0%
REQ Inspection |  | 70% | 0% |  |  | REQ Inspection | 70% | Not counting editorial comments
High-Level Design |  | 0% | 0% |  |  | High-Level Design | 0%
Integration Test Plan |  | 0% | 0% |  |  | Integration Test Plan | 0%
HLD Inspection |  | 70% | 0% |  |  | HLD Inspection | 70% | Using state analysis, trace tables
Detailed Design |  | 0% | 0% |  |  | Detailed Design | 0%
DLD Review |  | 70% | 0% |  |  | DLD Review | 70% | Using state analysis, trace tables
Test Development |  | 0% | 0% |  |  | Test Development | 0%
DLD Inspection |  | 70% | 0% |  |  | DLD Inspection | 70% | Using state analysis, trace tables
Code |  | 0% | 0% |  |  | Code | 0%
Code Review |  | 70% | 53.75% |  |  | Code Review | 70% | Using personal checklists
Compile |  | 50% | 8.108% |  |  | Compile | 50% | 90+ % of syntax defects
Code Inspection |  | 70% | 97.06% |  |  | Code Inspection | 70%
Unit Test |  | 90% | 100% |  |  | Unit test - at < 5 defects/KLOC | 90% | For high defects/KLOC - 50-75%
Build and Integration Test |  | 80% | 0% |  |  | Integration test at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65%
System Test |  | 80% | 0% |  |  | System test - at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65%
Acceptance Test |  | 65% | 0% |  |  | Acceptance test - at < 1.0 defects/KLOC | 65% | For high defects/KLOC - 30%
Process Yields |  | Plan | Actual
% Before Compile |  | 71.38% | 53.75%
% Before Unit Test |  | 95.65% | 98.75%
% Before Build and Integration Test |  | 99.51% | 100%
% Before System Test |  | 99.9% | 100%
% Before Acceptance Test |  | 99.98% | 100%
Defect Injection Rates (Defects Injected Per Hour) |  | Plan | Actual |  |  | Defect Injection Rates Planning Guidelines
Planning |  | 0 | 0 |  |  | Planning | 0
Requirements |  | 0.25 | 0 |  |  | Requirements | 0.25 | Only major defects
System Test Plan |  | 0 | 0 |  |  | System Test Plan | 0
REQ Inspection |  | 0 | 0 |  |  | REQ Inspection | 0
High-Level Design |  | 0.25 | 0 |  |  | High-Level Design | 0.25 | Only major defects
Integration Test Plan |  | 0 | 0 |  |  | Integration Test Plan | 0
HLD Inspection |  | 0 | 0 |  |  | HLD Inspection | 0
Detailed Design |  | 0.75 | 0 |  |  | Detailed Design | 0.75 | Only design defects
DLD Review |  | 0 | 0 |  |  | DLD Review | 0
Test Development |  | 0 | 0 |  |  | Test Development | 0
DLD Inspection |  | 0 | 0 |  |  | DLD Inspection | 0
Code |  | 2 | 0.29226 |  |  | Code | 2 | All defects
Code Review |  | 0 | 0 |  |  | Code Review | 0
Compile |  | 0.3 | 0 |  |  | Compile | 0.3 | Any defects
Code Inspection |  | 0 | 0 |  |  | Code Inspection | 0
Unit Test |  | 0.067 | 0 |  |  | Unit Test | 0.067 | Any defects
Build and Integration Test |  | 0 | 0 |  |  | Build and Integration Test | 0
System Test |  | 0 | 0 |  |  | System Test | 0
Defect Removal Rates |  | Plan | Actual
Planning |  | 0 | 0
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0 | 0
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0 | 0
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 0 | 0
DLD Inspection |  | 0 | 0
Code |  | 0 | 0
Code Review |  | 5.9981 | 0.69506
Compile |  | 8.5108 | 1.2308
Code Inspection |  | 0.29352 | 0.4275
Unit Test |  | 0.51989 | 0.085982
Build and Integration Test |  | 0 | 0
System Test |  | 0.053989 | 0
Transfer Defect Injection Rate Guidelines to Plan
Transfer Phase Yield Guidelines to Plan

## SUMS
TSP Size Summary - Form SUMS
| Name | Consolidated
| Team | AIM
| Date | 2026-07-29
| Cycle | 2 |  |  |  |  | Planned Size | [7 empty] | Actual Size | [7 empty] | Planned Defects Injected | [19 empty] | Actual Defects Injected | [19 empty] | Planned Defects Removed | [19 empty] | Actual Defects Removed | [19 empty] | Planned Time | [21 empty] | Actual Time
ID | Assembly, Sub-Assembly, or Part Name | (A)ssembly or (P)art | Parent Assembly Name | Owner | Size Measure | Estimating Assumptions | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Baseline Plan Date | Baseline Plan Hours
1 | Development | A | SYSTEM |  | LOC |  | 0 | 0 | 0 | 3170 | 0 | 3170 | 3170 | 0 | 23617 | 79 | 106 | 350 | 0 | 456 | 23888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254.7407 | 43.6937 | 13.1081 | 137.1369 | 65.5405 | 0 | 0 | 0 | 17.4775 | 6.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.9839 | 48.5025 | 2.4375 | 29.1431 | 11.6303 | 0 | 0 | 0 | 2.6422 | 2010-06-07 | 2501740.6395
2 | Development | A | SYSTEM |  | Text Pages |  | 14 | 4 | 10 | 311 | 0 | 321 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2083 | 0 | 0 | 0 | 67.8295 | 22.5318 | 0 | 30.6955 | 0 | 0 | 11.22 | 0 | 7.5906 | 38.7975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9725 | 0 | 0 | 0 | 13.6817 | 3.5894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 2501740.6395
3 | Development | A | SYSTEM |  | Req Pages |  | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4583 | 0 | 0 | 0 | 13.25 | 6.625 | 0 | 32.975 | 0 | 0 | 0 | 0 | 6.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8419 | 0 | 0 | 0 | 21.5772 | 2.6356 | 0 | 29.2506 | 0 | 0 | 0 | 0 | 2.1442 | 2010-06-07 | 2501740.6395
4 | Development | A | SYSTEM |  | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0833 | 0 | 0 | 0 | 9.5 | 4.75 | 0 | 25.75 | 0 | 0 | 0 | 0 | 1.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5725 | 0 | 0 | 0 | 9.805 | 3.9392 | 0 | 1.5989 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 2501740.6395
5 | Maintenance | A | Development |  | Text Pages |  | 14 | 4 | 10 | 206 | 0 | 216 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.0795 | 18.1568 | 0 | 17.5705 | 0 | 0 | 11.22 | 0 | 6.1323 | 38.7975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 928531.9978
6 | Maintenance | A | Development |  | LOC |  | 0 | 0 | 0 | 2918 | 0 | 2918 | 2918 | 0 | 23617 | 79 | 106 | 350 | 0 | 456 | 23888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 4 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.7407 | 18.6937 | 5.6081 | 52.1369 | 28.0405 | 0 | 0 | 0 | 7.4775 | 6.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3217 | 9.38 | 1.2144 | 24.6253 | 11.6303 | 0 | 0 | 0 | 2.5103 | 2010-05-31 | 928531.9978
7 | Demo | A | Development |  | LOC |  | 0 | 0 | 0 | 252 | 0 | 252 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 25 | 7.5 | 85 | 37.5 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.6622 | 39.1225 | 1.2231 | 4.5178 | 0 | 0 | 0 | 0 | 0.13194 | 2010-06-07 | 1573208.6417
8 | Demo | A | Development |  | Req Pages |  | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4583 | 0 | 0 | 0 | 13.25 | 6.625 | 0 | 32.975 | 0 | 0 | 0 | 0 | 6.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8419 | 0 | 0 | 0 | 21.5772 | 2.6356 | 0 | 29.2506 | 0 | 0 | 0 | 0 | 2.1442 | 2010-06-07 | 1573208.6417
9 | Demo | A | Development |  | Text Pages |  | 0 | 0 | 0 | 105 | 0 | 105 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2083 | 0 | 0 | 0 | 8.75 | 4.375 | 0 | 13.125 | 0 | 0 | 0 | 0 | 1.4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9725 | 0 | 0 | 0 | 5.7711 | 3.5894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 1573208.6417
10 | Demo | A | Development |  | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0833 | 0 | 0 | 0 | 9.5 | 4.75 | 0 | 25.75 | 0 | 0 | 0 | 0 | 1.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5725 | 0 | 0 | 0 | 9.805 | 3.9392 | 0 | 1.5989 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 1573208.6417
11 | Maint - Latent Defects | A | Maintenance |  | LOC |  | 0 | 0 | 0 | 2918 | 0 | 2918 | 2918 | 0 | 23617 | 79 | 106 | 350 | 0 | 456 | 23888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 4 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.7407 | 18.6937 | 5.6081 | 52.1369 | 28.0405 | 0 | 0 | 0 | 7.4775 | 6.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3217 | 9.38 | 1.2144 | 24.6253 | 11.6303 | 0 | 0 | 0 | 2.5103 | 2010-05-31 | 414561.7705
12 | Maint - Documentation | A | Maintenance |  | Text Pages |  | 14 | 4 | 10 | 60 | 0 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.0795 | 11.5568 | 0 | 7.6705 | 0 | 0 | 0 | 0 | 0.85227 | 23.6369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 164012.2273
13 | Maint - Doc - SVD | A | Maint - Documentation | F | Text Pages |  | 0 | 0 | 0 | 30 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0795 | 2.5568 | 0 | 7.6705 | 0 | 0 | 0 | 0 | 0.85227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 55435.2273
14 | Maint - Doc - SRS INSP | A | Maint - Documentation | F | Text Pages |  | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.3203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 80220
15 | Maint - Doc - REQM | A | Maint - Documentation | F | Text Pages |  | 14 | 4 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-03-22 | 7917
16 | Maint - Doc - Test Docs | A | Maint - Documentation | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-19 | 20440
17 | Maint - Config Mgmt | A | Maintenance |  | Text Pages |  | 0 | 0 | 0 | 56 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 114464
18 | Maint - CM - Archive V2 w/ F | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 16352
19 | Maint - CM - Archive V2 w/o F | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 16352
20 | Maint - CM - Final Builds | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 16352
21 | Maint - CM - Delivery Letters | A | Maint - Config Mgmt | G | Text Pages |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-02-08 | 8176
22 | Maint - CM - Final CM Package | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 40880
23 | Maint - CM - Create Eng Build | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-02-22 | 16352
24 | Maint - Test Eng Build | A | Maintenance | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 6.6 | 0 | 9.9 | 0 | 0 | 11.22 | 0 | 5.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 20440
25 | Maint - Val Final Builds w/ F | A | Maintenance | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-05 | 20440
26 | Maint - Val Final Build w/o F | A | Maintenance | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-05 | 20440
27 | Maint - LD - 955 | A | Maint - Latent Defects | C | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.664 | 0.4593 | 0.13779 | 1.3795 | 0.68895 | 0 | 0 | 0 | 0.18372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9456 | 0.54722 | 0.10667 | 1.1461 | 0.70694 | 0 | 0 | 0 | 0.42556 | 2010-05-24 | 11285.4514
28 | Maint - LD - 957 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 15929 | 16 | 0 | 0 | 0 | 0 | 15913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6686 | 0.4601 | 0.13803 | 2.3803 | 0.69016 | 0 | 0 | 0 | 0.18404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5967 | 0.15917 | 0.031389 | 1.3067 | 0.29472 | 0 | 0 | 0 | 0.084722 | 2010-05-24 | 11285.4514
29 | Maint - LD - 958 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 72426.8841
30 | Maint - LD - 960 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 147 | 0 | 147 | 147 | 0 | 27 | 0 | 2 | 7 | 0 | 9 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9656 | 0.85614 | 0.25684 | 3.5684 | 1.2842 | 0 | 0 | 0 | 0.34246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5756 | 0.11111 | 0.025 | 1.4897 | 0.0725 | 0 | 0 | 0 | 0.048889 | 2010-05-24 | 20999.5108
31 | Maint - LD - 961 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 39 | 0 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22714 | 0 | 0 | 0 | 0 | 0 | 6.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 5571.2988
32 | Maint - LD - 953 | A | Maint - Latent Defects | C | LOC |  | 0 | 0 | 0 | 147 | 0 | 147 | 147 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9656 | 0.85614 | 0.25684 | 2.5684 | 1.2842 | 0 | 0 | 0 | 0.34246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4089 | 0.66056 | 0.25361 | 1.2328 | 1.2306 | 0 | 0 | 0 | 0.15778 | 2010-05-24 | 20999.5108
33 | Maint - LD - 954 | A | Maint - Latent Defects | C | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 0 | 0 | 1 | 28 | 0 | 29 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6686 | 0.4601 | 0.13803 | 1.3803 | 0.69016 | 0 | 0 | 0 | 0.18404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5053 | 0.77 | 0.098611 | 3.0922 | 1.0158 | 0 | 0 | 0 | 0.26139 | 2010-05-31 | 11285.4514
34 | Maint - LD - 959 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 236 | 8 | 17 | 204 | 0 | 221 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1264 | 2.9528 | 0.88585 | 9.8585 | 4.4292 | 0 | 0 | 0 | 1.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.9947 | 1.6381 | 0.050556 | 6.6989 | 1.7017 | 0 | 0 | 0 | 0.6025 | 2010-05-31 | 72426.8841
35 | Maint - LD - 952 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 39 | 0 | 39 | 39 | 0 | 347 | 0 | 0 | 8 | 0 | 8 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3174 | 0.22714 | 0.068142 | 1.6814 | 0.34071 | 0 | 0 | 0 | 0.090856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37722 | 0.055556 | 0.032222 | 1.7531 | 0.24611 | 0 | 0 | 0 | 0.19 | 2010-05-31 | 5571.2988
36 | Maint - LD - 956 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 39 | 0 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3174 | 0 | 0 | 0.22714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 5571.2988
37 | Maint - LD - 918 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1264 | 2.9528 | 0.88585 | 8.8585 | 4.4292 | 0 | 0 | 0 | 1.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2069 | 2.5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 72426.8841
38 | Maint - LD - 919 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1264 | 2.9528 | 0.88585 | 8.8585 | 4.4292 | 0 | 0 | 0 | 1.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 72426.8841
39 | Maint - LD - 884 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 147 | 0 | 147 | 147 | 0 | 174 | 1 | 13 | 38 | 0 | 51 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9656 | 0.85614 | 0.25684 | 2.5684 | 1.2842 | 0 | 0 | 0 | 0.34246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5472 | 0.16944 | 0.31917 | 2.3192 | 1.6106 | 0 | 0 | 0 | 0.1175 | 2010-05-31 | 20999.5108
40 | Maint - LD - 885 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 3302 | 6 | 52 | 30 | 0 | 82 | 3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6686 | 0.4601 | 0.13803 | 1.3803 | 0.69016 | 0 | 0 | 0 | 0.18404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8842 | 1.2742 | 0.069167 | 1.8872 | 1.1633 | 0 | 0 | 0 | 0.13389 | 2010-05-31 | 11285.4514
41 | Maint - LD - 967 | A | Maint - Latent Defects | G | LOC | hours | 0 | 0 | 0 | 7 | 0 | 7 | 7 | 0 | 3520 | 0 | 3 | 24 | 0 | 27 | 3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.06 | 0.7 | 0.21 | 2.7 | 1.05 | 0 | 0 | 0 | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091667 | 0.20444 | 0.085 | 1.8333 | 2.6842 | 0 | 0 | 0 | 0.13333 | 2010-05-31 | 154.5952
42 | Maint - LD - 985 | A | Maint - Latent Defects | G | LOC | hours | 0 | 0 | 0 | 9 | 0 | 9 | 9 | 0 | 82 | 48 | 15 | 9 | 0 | 24 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.22 | 0.9 | 0.27 | 0.9 | 1.35 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38972 | 0.12306 | 0.089167 | 0.75 | 0.90389 | 0 | 0 | 0 | 0.35472 | 2010-05-31 | 154.5952
43 | Support | A | SYSTEM |  | Text Pages |  | 0 | 0 | 0 | 234 | 0 | 234 | 234 | 0 | 0 | 0 | 8 | 11 | 0 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 231.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.9722 | 0 | 0 | 0 | 18.25 | 7.6667 | 0 | 39.5 | 0 | 0 | 0 | 0 | 2.5556 | 110.2386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.3725 | 0 | 0 | 0 | 16.6853 | 3.1986 | 0 | 17.2003 | 0 | 0 | 0 | 0 | 2.1014 | 2010-06-07 | 775026.14
44 | Roles | A | Support |  | Text Pages |  | 0 | 0 | 0 | 165 | 0 | 165 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.3942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 405856.64
45 | Customer Interface Manager | A | Roles | G | Text Pages |  | 0 | 0 | 0 | 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-17 | 114464
46 | Planning Manager | A | Roles | E | Text Pages |  | 0 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 45990
47 | Process Manager | A | Roles | E | Text Pages |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 30660
48 | Quality Manager | A | Roles | C | Text Pages |  | 0 | 0 | 0 | 15 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 32826.64
49 | Test Manager | A | Roles | A | Text Pages |  | 0 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 40880
50 | Implementation | A | Roles | B | Text Pages |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 30660
51 | Support Manager | A | Roles | D | Text Pages |  | 0 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 36792
52 | Design Manager | A | Roles | D | Text Pages |  | 0 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 73584
53 | Checkpoint | A | Support | E | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 15925
54 | Cycle Postmortem | A | Support | E | Text Pages |  | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 47775
55 | Postmortem Report | A | Support | E | Text Pages |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 10220
56 | CMMI Training | A | Support | E | Text Pages |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-17 | 117691
57 | Process Updates | A | Support |  | Text Pages |  | 0 | 0 | 0 | 45 | 0 | 45 | 45 | 0 | 0 | 0 | 8 | 11 | 0 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.9722 | 0 | 0 | 0 | 18.25 | 7.6667 | 0 | 39.5 | 0 | 0 | 0 | 0 | 2.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.3725 | 0 | 0 | 0 | 16.6853 | 3.1986 | 0 | 17.2003 | 0 | 0 | 0 | 0 | 2.1014 | 2010-05-24 | 177558.5
58 | Add PM to Dev Processes | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55556 | 0 | 0 | 0 | 1.25 | 0.41667 | 0 | 1.6667 | 0 | 0 | 0 | 0 | 0.13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78778 | 0 | 0 | 0 | 0.97944 | 0.42722 | 0 | 1.5044 | 0 | 0 | 0 | 0 | 0.15611 | 2010-05-10 | 8232.7778
59 | Create Peer Review Script | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1111 | 0 | 0 | 0 | 2.5 | 0.83333 | 0 | 3.3333 | 0 | 0 | 0 | 0 | 0.27778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2758 | 0 | 0 | 0 | 2.3636 | 0.55861 | 0 | 1.4214 | 0 | 0 | 0 | 0 | 0.18889 | 2010-05-10 | 16465.5556
60 | Add TCs to New Feature Process | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55556 | 0 | 0 | 0 | 1.25 | 0.41667 | 0 | 1.6667 | 0 | 0 | 0 | 0 | 0.13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57222 | 0 | 0 | 0 | 0.51556 | 0.31333 | 0 | 1.1703 | 0 | 0 | 0 | 0 | 0.14333 | 2010-05-10 | 8232.7778
61 | Add Checklist to all Review/Insp Phases | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 5 | 1 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55556 | 0 | 0 | 0 | 1.25 | 0.41667 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0.13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64611 | 0 | 0 | 0 | 1.2319 | 0.41333 | 0 | 2.6228 | 0 | 0 | 0 | 0 | 0.22722 | 2010-05-10 | 10396.9444
62 | Update Specification PM | A | Process Updates | E | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55556 | 0 | 0 | 0 | 1.25 | 0.41667 | 0 | 2.0833 | 0 | 0 | 0 | 0 | 0.13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-05 | 10929.7222
63 | Update INS Form/Script | A | Process Updates | F | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55556 | 0 | 0 | 0 | 1.25 | 0.41667 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0.13889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2169 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 11801.8056
64 | Define a Design Standard | A | Process Updates | D | Text Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0833 | 0 | 0 | 0 | 9.5 | 4.75 | 0 | 25.75 | 0 | 0 | 0 | 0 | 1.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.0906 | 0 | 0 | 0 | 11.5947 | 1.4861 | 0 | 9.2644 | 0 | 0 | 0 | 0 | 1.3858 | 2010-05-10 | 111498.9167
65 | Demo - GUI | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 728515.6667
66 | Demo - GUI | A | Demo |  | LOC |  | 0 | 0 | 0 | 120 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.6 | 12 | 3.6 | 48 | 18 | 0 | 0 | 0 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.6822 | 24.25 | 0.435 | 3.2525 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 728515.6667
67 | Demo - Docs | A | Demo |  | Req Pages |  | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4583 | 0 | 0 | 0 | 13.25 | 6.625 | 0 | 32.975 | 0 | 0 | 0 | 0 | 6.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8419 | 0 | 0 | 0 | 21.5772 | 2.6356 | 0 | 29.2506 | 0 | 0 | 0 | 0 | 2.1442 | 2010-05-10 | 324358.7083
68 | Demo - Docs | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2083 | 0 | 0 | 0 | 8.75 | 4.375 | 0 | 13.125 | 0 | 0 | 0 | 0 | 1.4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9725 | 0 | 0 | 0 | 5.7711 | 3.5894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 324358.7083
69 | Demo - Docs | A | Demo |  | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0833 | 0 | 0 | 0 | 9.5 | 4.75 | 0 | 25.75 | 0 | 0 | 0 | 0 | 1.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5725 | 0 | 0 | 0 | 9.805 | 3.9392 | 0 | 1.5989 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 324358.7083
70 | Demo - Interface | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 446750.2667
71 | Demo - Interface | A | Demo |  | LOC |  | 0 | 0 | 0 | 132 | 0 | 132 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4 | 13 | 3.9 | 37 | 19.5 | 0 | 0 | 0 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.98 | 14.8725 | 0.78806 | 1.2653 | 0 | 0 | 0 | 0 | 0.13194 | 2010-06-07 | 446750.2667
72 | Demo - CM | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 32 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 73584
73 | Demo - GUI - Closure Design | A | Demo - GUI | D | Text Pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 66430
74 | Demo - GUI - Remove Legacy Button | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
75 | Demo - GUI - Remove D Tab | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
76 | Demo - GUI - Remove Messaging Tab | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
77 | Demo - GUI - Remove F Tab | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
78 | Demo - GUI - Remove C Buttons | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
79 | Demo - GUI - Remove F Buttons | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
80 | Demo - GUI - Tailor Workspace | A | Demo - GUI | C | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
81 | Demo - GUI - Tailor Status | A | Demo - GUI | C | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
82 | Demo - GUI - Tailor Settings | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 65408
83 | Demo - GUI - AIM Interface | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.2 | 4 | 1.2 | 16 | 6 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.8864 | 8.0358 | 0.145 | 1.1439 | 0 | 0 | 0 | 0 | 0
84 | Demo - GUI - GUI Desktop | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.2 | 4 | 1.2 | 16 | 6 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.6125 | 5.9986 | 0.11972 | 1.005 | 0 | 0 | 0 | 0 | 0
85 | Demo - GUI - GUI Popups | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.2 | 4 | 1.2 | 16 | 6 | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.1833 | 10.2156 | 0.17028 | 1.1036 | 0 | 0 | 0 | 0 | 0
86 | Demo - Interface - Closure Design | A | Demo - Interface | B | Text Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 94364.6667
87 | Demo - Interface - Closure | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 5 | 1.5 | 13 | 7.5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.7928 | 4.5747 | 0.092778 | 0.96111 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 126728
88 | Demo - Interface - Process | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.6 | 2 | 0.6 | 6 | 3 | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3708 | 0 | 0 | 0.30417 | 0 | 0 | 0 | 0 | 0.13194 | 2010-06-07 | 49056
89 | Demo - Inteface - HTML | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 49056
90 | Demo - Interface - GUI | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 29433.6
91 | Demo - Interface - Msg | A | Demo - Interface | C | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.8 | 6 | 1.8 | 16 | 9 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8164 | 10.2978 | 0.69528 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 98112
92 | Demo - Docs - HLD Doc | A | Demo - Docs | D | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.0833 | 0 | 0 | 0 | 9.5 | 4.75 | 0 | 25.75 | 0 | 0 | 0 | 0 | 1.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5725 | 0 | 0 | 0 | 9.805 | 3.9392 | 0 | 1.5989 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 111498.9167
93 | Demo - Docs - Req Doc | A | Demo - Docs | F | Req Pages |  | 0 | 0 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2083 | 0 | 0 | 0 | 8.75 | 4.375 | 0 | 23.875 | 0 | 0 | 0 | 0 | 1.4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9333 | 0 | 0 | 0 | 10.2833 | 0.82722 | 0 | 23.0253 | 0 | 0 | 0 | 0 | 0.22056 | 2010-05-10 | 117850.8333
94 | Demo - Docs - Req Doc - Rework | A | Demo - Docs | F | Req Pages | hours | 0 | 0 | 0 | 15 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.25 | 0 | 0 | 0 | 4.5 | 2.25 | 0 | 9.1 | 0 | 0 | 0 | 0 | 5.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9086 | 0 | 0 | 0 | 11.2939 | 1.8083 | 0 | 6.2253 | 0 | 0 | 0 | 0 | 1.9236 | 2010-05-10 | 20959.1667
95 | Demo - Docs - Test Cases | A | Demo - Docs | A | Text Pages |  | 0 | 0 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2083 | 0 | 0 | 0 | 8.75 | 4.375 | 0 | 13.125 | 0 | 0 | 0 | 0 | 1.4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9725 | 0 | 0 | 0 | 5.7711 | 3.5894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 95008.9583
96 | Demo - CM - Eng Build | A | Demo - CM | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-26 | 16352
97 | Demo - CM - Eng Build Testing | A | Demo - CM | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-03-29 | 20440
98 | Demo - CM - Final Build | A | Demo - CM | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 16352
99 | Demo - CM - Final Build Testing | A | Demo - CM | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-03-22 | 20440
100 | Maint - Test - A | A | Maintenance | F | Text Pages |  | 0 | 0 | 0 | 30 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 79170
101 | Maint - Test - B | A | Maintenance | F | Text Pages |  | 0 | 0 | 0 | 36 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 95004
102 | Postmortem Report - Cycle1 | A | Support | E | Text Pages |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 95004
103 | Maint - Doc - SRS - Rework | A | Maint - Documentation | F | Text Pages |  | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 23436
104 | Maint - LD - 997 | A | Maint - Latent Defects | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 1.2 | 0.36 | 1.2 | 1.8 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0639 | 0.43556 | 0.021944 | 0.81889 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 15624
105 | Maint - LD - 998 | A | Maint - Latent Defects | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 1.2 | 0.36 | 1.2 | 1.8 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1233 | 0.29833 | 0.031944 | 0.24389 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 15624
106 | Maint - LD - 999 | A | Maint - Latent Defects | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.96 | 1.2 | 0.36 | 1.2 | 1.8 | 0 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6661 | 0.35222 | 0 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 15624

## S (hidden)
ID | Assembly, Sub-Assembly, or Part Name | (A)ssembly or (P)art | Parent Assembly Name | Owner | Size Measure | Estimating Assumptions | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Baseline Plan Date | Baseline Plan Hours
0 | SYSTEM | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 1519.3157

## Task
TSP Task Planning Template - Form TASK | [12 empty] | Total Plan Hours | [6 empty] | Total Actual Hours
Name | Consolidated | [11 empty] | 1286.4358 | [6 empty] | 641.7222
Team | AIM | [8 empty] | Reminder:
Date | 2026-07-29 | [8 empty] | If Size and Rate are present, estimated hours is calculated as Size / Rate
whenever the plan is updated. To prevent calculation, size or rate must be blank.
Cycle | 2 |  | Plan Hours by Role
Assembly | Phase | Task | Team Leader | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Total Resource Hours | Resources | Estimated Size | Size Measure | Rate (per Hr.) | Time in Phase % | Estimated Hours | Engrs | Plan Hours | Plan Date | Plan Week | Actual Hours | Actual Date | Actual Week | Earned Value | Cumulative EV | Cumulative Plan Hours | Cumulative Plan Value | Plan Value | Predicted Date | Plan Date + Current Slip | Committed Date | Baseline Date | Baseline Plan Hours | Notes | Start Week | PHISW | PHIEW | Process | Phase
Test Manager | MGMT | Test Manager - Task Week 2 Feb 1 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-01 | 2 | 0.91333 | 2010-02-05 | 2 | 0.077734 | 0.077734 | 1 | 0.077734 | 0.077734 | 2010-02-05 |  |  | 2010-02-01 | 1 |  | 2 | 1 | 1 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 3 Feb 8 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 0 | 0 | 2010-02-01 | 2 |  | 2010-02-17 | 4 | 0 | 0.077734 | 1 | 0.077734 | 0 | 2010-02-17 |  |  | 2010-02-08 | 1 |  | 2 | 0 | 0 | Task | Task
Quality Manager | MGMT | Quality Manager - Task (Week 3 - 2/8/10) | [6 empty] | C | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-02-08 | 3 | 0.80278 | 2010-02-16 | 4 | 0.1166 | 0.15547 | 2.5 | 0.15547 | 0.1166 | 2010-02-16 |  |  | 2010-02-15 | 1.5 |  | 3 | 1.5 | 1.5 | Task | Task
Maint - LD - 952 | CODE | Maint - LD - 952 - Find and Fix | [6 empty] | B | 39 | LOC | 17.17 | 58 | 1.3174 | 1 | 1.3174 | 2010-02-08 | 3 | 0.37722 | 2010-02-08 | 3 | 0.10241 | 0.31094 | 3.8174 | 0.31094 | 0.10241 | 2010-02-08 |  |  | 2010-02-08 | 1.3174 |  | 3 | 1.3174 | 1.3174 | Issue Fixes | Find and Fix
Maint - LD - 957 | CODE | Maint - LD - 957 - Find and Fix | [6 empty] | B | 79 | LOC | 17.17 | 58 | 2.6686 | 1 | 2.6686 | 2010-02-08 | 3 | 1.5967 | 2010-02-08 | 3 | 0.20744 | 0.34333 | 6.486 | 0.34333 | 0.20744 | 2010-02-08 |  |  | 2010-02-08 | 2.6686 |  | 3 | 2.6686 | 2.6686 | Issue Fixes | Find and Fix
Maint - LD - 960 | COMPILE | Maint - LD - 960 - Compile | [6 empty] | B | 147 | LOC | 17.17 | 3 | 0.25684 | 1 | 0.25684 | 2010-02-08 | 3 | 0.025 | 2010-02-08 | 3 | 0.019965 | 0.37572 | 6.7429 | 0.37572 | 0.019965 | 2010-02-08 |  |  | 2010-02-08 | 0.25684 |  | 3 | 0.25684 | 0.25684 | Issue Fixes | Compile
Maint - LD - 960 | CODE | Maint - LD - 960 - Find and Fix | [6 empty] | B | 147 | LOC | 17.17 | 58 | 4.9656 | 1 | 4.9656 | 2010-02-08 | 3 | 1.5756 | 2010-02-09 | 3 | 0.386 | 1.1693 | 11.7085 | 1.1693 | 0.386 | 2010-02-09 |  |  | 2010-02-08 | 4.9656 |  | 3 | 4.9656 | 4.9656 | Issue Fixes | Find and Fix
Maint - LD - 952 | CR | Maint - LD - 952 - Code Review | [6 empty] | B | 39 | LOC | 17.17 | 10 | 0.22714 | 1 | 0.22714 | 2010-02-08 | 3 | 0.055556 | 2010-02-10 | 3 | 0.017657 | 1.247 | 11.9356 | 1.247 | 0.017657 | 2010-02-10 |  |  | 2010-02-08 | 0.22714 |  | 3 | 0.22714 | 0.22714 | Issue Fixes | Code Review
Maint - LD - 952 | COMPILE | Maint - LD - 952 - Compile | [6 empty] | B | 39 | LOC | 17.17 | 3 | 0.068142 | 1 | 0.068142 | 2010-02-08 | 3 | 0.032222 | 2010-02-10 | 3 | 0.005297 | 1.76 | 12.0038 | 1.76 | 0.005297 | 2010-02-10 |  |  | 2010-02-08 | 0.068142 |  | 3 | 0.068142 | 0.068142 | Issue Fixes | Compile
Maint - LD - 957 | CR | Maint - LD - 957 - Code Review | [6 empty] | B | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-08 | 3 | 0.15917 | 2010-02-10 | 3 | 0.035766 | 1.8378 | 12.4639 | 1.8378 | 0.035766 | 2010-02-10 |  |  | 2010-02-08 | 0.4601 |  | 3 | 0.4601 | 0.4601 | Issue Fixes | Code Review
Maint - LD - 957 | COMPILE | Maint - LD - 957 - Compile | [6 empty] | B | 79 | LOC | 17.17 | 3 | 0.13803 | 1 | 0.13803 | 2010-02-08 | 3 | 0.031389 | 2010-02-10 | 3 | 0.01073 | 2.3042 | 12.6019 | 2.3042 | 0.01073 | 2010-02-10 |  |  | 2010-02-08 | 0.13803 |  | 3 | 0.13803 | 0.13803 | Issue Fixes | Compile
Maint - LD - 960 | CR | Maint - LD - 960 - Code Review | [6 empty] | B | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-08 | 3 | 0.11111 | 2010-02-10 | 3 | 0.066552 | 2.3819 | 13.4581 | 2.3819 | 0.066552 | 2010-02-10 |  |  | 2010-02-08 | 0.85614 |  | 3 | 0.85614 | 0.85614 | Issue Fixes | Code Review
Implementation | MGMT | Implementation - Task 1 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-08 | 3 | 0.32528 | 2010-02-10 | 3 | 0.077734 | 2.5374 | 14.4581 | 2.5374 | 0.077734 | 2010-02-10 |  |  | 2010-02-08 | 1 |  | 3 | 1 | 1 | Task | Task
Implementation | MGMT | Implementation - Task 2 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-08 | 3 | 0.52694 | 2010-02-12 | 3 | 0.077734 | 2.6151 | 15.4581 | 2.6151 | 0.077734 | 2010-02-12 |  |  | 2010-03-08 | 1 |  | 3 | 1 | 1 | Task | Task
Maint - LD - 956 | CODE | Maint - LD - 956 - Find and Fix | [6 empty] | B | 39 | LOC | 17.17 | 58 | 1.3174 | 1 | 1.3174 | 2010-02-08 | 3 | 5.9447 | 2010-02-16 | 4 | 0.10241 | 3.2953 | 16.7755 | 3.2953 | 0.10241 | 2010-02-16 |  |  | 2010-02-08 | 1.3174 |  | 3 | 1.3174 | 1.3174 | Issue Fixes | Find and Fix
Maint - LD - 956 | CR | Maint - LD - 956 - Code Review | [6 empty] | B | 39 | LOC | 17.17 | 10 | 0.22714 | 0 | 0 | 2010-02-08 | 3 |  | 2010-02-16 | 4 | 0 | 3.373 | 16.7755 | 3.373 | 0 | 2010-02-16 |  |  | 2010-02-08 | 0.22714 |  | 3 | 0 | 0 | Issue Fixes | Code Review
Maint - LD - 956 | CODEINSP | Maint - LD - 956 - Code Peer Review | [6 empty] | B | 39 | LOC | 17.17 | 10 | 0.22714 | 0 | 0 | 2010-02-08 | 3 |  | 2010-02-16 | 4 | 0 | 3.7131 | 16.7755 | 3.7131 | 0 | 2010-02-16 |  |  | 2010-02-08 | 0.22714 |  | 3 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 956 | COMPILE | Maint - LD - 956 - Compile | [6 empty] | B | 39 | LOC | 17.17 | 3 | 0.068142 | 0 | 0 | 2010-02-08 | 3 |  | 2010-02-16 | 4 | 0 | 3.8919 | 16.7755 | 3.8919 | 0 | 2010-02-16 |  |  | 2010-02-08 | 0.068142 |  | 3 | 0 | 0 | Issue Fixes | Compile
Maint - LD - 956 | UT | Maint - LD - 956 - Unit Test | [6 empty] | B | 39 | LOC | 17.17 | 15 | 0.34071 | 0 | 0 | 2010-02-08 | 3 |  | 2010-02-16 | 4 | 0 | 4.2028 | 16.7755 | 4.2028 | 0 | 2010-02-16 |  |  | 2010-02-08 | 0.34071 |  | 3 | 0 | 0 | Issue Fixes | Unit Test
Maint - LD - 956 | PM | Maint - LD - 956 - PM | [6 empty] | B | 39 | LOC | 17.17 | 4 | 0.090856 | 0 | 0 | 2010-02-08 | 3 |  | 2010-02-16 | 4 | 0 | 4.2806 | 16.7755 | 4.2806 | 0 | 2010-02-16 |  |  | 2010-02-08 | 0.090856 |  | 3 | 0 | 0 | Issue Fixes | Postmortem
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | [6 empty] | B | 39 | LOC | 17.17 | 10 | 0.22714 | 1 | 0.22714 | 2010-02-08 | 3 | 0.92639 | 2010-02-16 | 4 | 0.017657 | 4.2806 | 17.0026 | 4.9024 | 0.017657 | 2010-02-16 |  |  | 2010-02-08 | 0.22714 |  | 3 | 0.22714 | 0.22714 | Issue Fixes | Code Peer Review
Maint - LD - 957 | CODEINSP | Maint - LD - 957 - Code Peer Review | [6 empty] | B | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-08 | 3 | 0.16944 | 2010-02-16 | 4 | 0.035766 | 4.2806 | 17.4627 | 4.9802 | 0.035766 | 2010-02-16 |  |  | 2010-02-08 | 0.4601 |  | 3 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 960 | CODEINSP | Maint - LD - 960 - Code Peer Review | [6 empty] | B | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-08 | 3 | 0.22472 | 2010-02-16 | 4 | 0.066552 | 4.2806 | 18.3189 | 5.0579 | 0.066552 | 2010-02-16 |  |  | 2010-02-08 | 0.85614 |  | 3 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Maint - LD - 952 | UT | Maint - LD - 952 - Unit Test | [6 empty] | B | 39 | LOC | 17.17 | 15 | 0.34071 | 1 | 0.34071 | 2010-02-08 | 3 | 0.24611 | 2010-02-17 | 4 | 0.026485 | 4.2806 | 18.6596 | 5.3688 | 0.026485 | 2010-02-17 |  |  | 2010-02-08 | 0.34071 |  | 3 | 0.34071 | 0.34071 | Issue Fixes | Unit Test
Maint - LD - 957 | UT | Maint - LD - 957 - Unit Test | [6 empty] | B | 79 | LOC | 17.17 | 15 | 0.69016 | 1 | 0.69016 | 2010-02-08 | 3 | 0.29472 | 2010-02-17 | 4 | 0.053649 | 4.2806 | 19.3497 | 5.7089 | 0.053649 | 2010-02-17 |  |  | 2010-02-08 | 0.69016 |  | 3 | 0.69016 | 0.69016 | Issue Fixes | Unit Test
Maint - LD - 960 | UT | Maint - LD - 960 - Unit Test | [6 empty] | B | 147 | LOC | 17.17 | 15 | 1.2842 | 1 | 1.2842 | 2010-02-08 | 3 | 0.0725 | 2010-02-17 | 4 | 0.099827 | 4.2806 | 20.634 | 5.8223 | 0.099827 | 2010-02-17 |  |  | 2010-02-08 | 1.2842 |  | 3 | 1.2842 | 1.2842 | Issue Fixes | Unit Test
Maint - LD - 952 | PM | Maint - LD - 952 - PM | [6 empty] | B | 39 | LOC | 17.17 | 4 | 0.090856 | 1 | 0.090856 | 2010-02-08 | 3 | 0.19 | 2010-02-17 | 4 | 0.0070626 | 4.2806 | 20.7248 | 5.9778 | 0.0070626 | 2010-02-17 |  |  | 2010-02-08 | 0.090856 |  | 3 | 0.090856 | 0.090856 | Issue Fixes | Postmortem
Maint - LD - 957 | PM | Maint - LD - 957 - PM | [6 empty] | B | 79 | LOC | 17.17 | 4 | 0.18404 | 1 | 0.18404 | 2010-02-08 | 3 | 0.084722 | 2010-02-17 | 4 | 0.014306 | 4.2806 | 20.9089 | 5.9778 | 0.014306 | 2010-02-17 |  |  | 2010-02-08 | 0.18404 |  | 3 | 0.18404 | 0.18404 | Issue Fixes | Postmortem
Maint - LD - 960 | PM | Maint - LD - 960 - PM | [6 empty] | B | 147 | LOC | 17.17 | 4 | 0.34246 | 1 | 0.34246 | 2010-02-08 | 3 | 0.048889 | 2010-02-17 | 4 | 0.026621 | 4.2806 | 21.2513 | 6.5996 | 0.026621 | 2010-02-17 |  |  | 2010-02-08 | 0.34246 |  | 3 | 0.34246 | 0.34246 | Issue Fixes | Postmortem
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | B | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-08 | 3 | 0.57444 | 2010-02-18 | 4 | 0.032389 | 4.2806 | 21.668 | 6.6774 | 0.032389 | 2010-02-18 |  |  | 2010-05-10 | 0.41667 |  | 3 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Define a Design Standard | DLD | Define a Design Standard - Research-NT | [6 empty] | D | 38 | Text Pages | 1.2 | 35 | 11.0833 | 1 | 11.0833 | 2010-02-08 | 3 | 17.0906 | 2010-02-10 | 3 | 0.86155 | 4.2806 | 32.7513 | 7.2992 | 0.86155 | 2010-02-10 |  |  | 2010-02-08 | 11.0833 |  | 3 | 11.0833 | 11.0833 | Document-New Technical | Research-NT
Maint - LD - 957 | CODEINSP | Maint - LD - 957 - Code Peer Review | [6 empty] | D | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-08 | 3 | 0.65722 | 2010-02-11 | 3 | 0.035766 | 4.2806 | 33.2114 | 7.9211 | 0.035766 | 2010-02-11 |  |  | 2010-05-24 | 0.4601 |  | 3 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 960 | CODEINSP | Maint - LD - 960 - Code Peer Review | [6 empty] | D | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-08 | 3 | 0.45333 | 2010-02-11 | 3 | 0.066552 | 4.2806 | 34.0676 | 7.9988 | 0.066552 | 2010-02-11 |  |  | 2010-05-24 | 0.85614 |  | 3 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | [6 empty] | D | 39 | LOC | 17.17 | 10 | 0.22714 | 1 | 0.22714 | 2010-02-08 | 3 | 0.40389 | 2010-02-11 | 3 | 0.017657 | 4.2806 | 34.2947 | 8.0377 | 0.017657 | 2010-02-11 |  |  | 2010-05-31 | 0.22714 |  | 3 | 0.22714 | 0.22714 | Issue Fixes | Code Peer Review
Design Manager | MGMT | Design Manager - Week 3 (02/08/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-02-08 | 3 | 2.6392 | 2010-02-12 | 3 | 0.15547 | 4.2806 | 36.2947 | 8.0766 | 0.15547 | 2010-02-12 |  |  | 2010-02-08 | 2 |  | 3 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 3 (02/08/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-08 | 3 | 0.43472 | 2010-02-12 | 3 | 0.077734 | 4.2806 | 37.2947 | 8.1543 | 0.077734 | 2010-02-12 |  |  | 2010-02-08 | 1 |  | 3 | 1 | 1 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 3 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-02-08 | 3 | 0.91222 | 2010-02-12 | 3 | 0.1166 | 4.2806 | 38.7947 | 8.1932 | 0.1166 | 2010-02-12 |  |  | 2010-02-08 | 1.5 |  | 3 | 1.5 | 1.5 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 4 Feb 15 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.60139 | 2010-02-19 | 4 | 0.077734 | 4.2806 | 39.7947 | 8.4264 | 0.077734 | 2010-02-19 |  |  | 2010-02-15 | 1 |  | 2 | 0 | 1 | Task | Task
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | A | 38 | Text Pages |  |  | 2 | 1 | 2 | 2010-02-15 | 4 | 1.2636 | 2010-02-25 | 5 | 0.15547 | 4.3972 | 41.7947 | 8.543 | 0.15547 | 2010-02-25 |  |  | 2010-02-15 | 2 |  | 4 | 2 | 2 | Document-New Technical | Doc Inspection-NT
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | A | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.46111 | 2010-02-26 | 5 | 0.032389 | 4.4148 | 42.2114 | 8.5606 | 0.032389 | 2010-02-26 |  |  | 2010-02-15 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | A | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.59 | 2010-02-26 | 5 | 0.032389 | 4.4506 | 42.628 | 8.5964 | 0.032389 | 2010-02-26 |  |  | 2010-02-15 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | [6 empty] | C | 39 | LOC | 17.17 | 10 | 0.22714 | 1 | 0.22714 | 2010-02-15 | 4 | 0.25028 | 2010-02-16 | 4 | 0.017657 | 4.5171 | 42.8552 | 8.663 | 0.017657 | 2010-02-16 |  |  | 2010-03-08 | 0.22714 |  | 3 | 2.7756e-17 | 0.22714 | Issue Fixes | Code Peer Review
Maint - LD - 957 | CODEINSP | Maint - LD - 957 - Code Peer Review | [6 empty] | C | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-15 | 4 | 0.26444 | 2010-02-16 | 4 | 0.035766 | 4.5603 | 43.3153 | 8.7061 | 0.035766 | 2010-02-16 |  |  | 2010-03-08 | 0.4601 |  | 4 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 960 | CODEINSP | Maint - LD - 960 - Code Peer Review | [6 empty] | C | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-15 | 4 | 0.71 | 2010-02-16 | 4 | 0.066552 | 4.6575 | 44.1714 | 8.8033 | 0.066552 | 2010-02-16 |  |  | 2010-03-08 | 0.85614 |  | 4 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Add Checklist to all Review/Insp Phases | DLD | Add Checklist to all Review/Insp Phases - Research-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 20 | 0.55556 | 1 | 0.55556 | 2010-02-15 | 4 | 0.64611 | 2010-02-17 | 4 | 0.043186 | 4.6899 | 44.727 | 8.8357 | 0.043186 | 2010-02-17 |  |  | 2010-02-15 | 0.55556 |  | 4 | 0.55556 | 0.55556 | Document-New Process | Research-NP
Add Checklist to all Review/Insp Phases | CODE | Add Checklist to all Review/Insp Phases - Draft-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 45 | 1.25 | 1 | 1.25 | 2010-02-15 | 4 | 1.2319 | 2010-02-17 | 4 | 0.097168 | 4.7331 | 45.977 | 8.8789 | 0.097168 | 2010-02-17 |  |  | 2010-02-15 | 1.25 |  | 4 | 1.25 | 1.25 | Document-New Process | Draft-NP
Add Checklist to all Review/Insp Phases | CR | Add Checklist to all Review/Insp Phases - Doc Review-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.41333 | 2010-02-18 | 4 | 0.032389 | 4.8302 | 46.3936 | 8.9761 | 0.032389 | 2010-02-18 |  |  | 2010-02-15 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Review-NP
Add TCs to New Feature Process | DLD | Add TCs to New Feature Process - Research-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 20 | 0.55556 | 1 | 0.55556 | 2010-02-15 | 4 | 0.57222 | 2010-02-18 | 4 | 0.043186 | 4.8626 | 46.9492 | 9.0084 | 0.043186 | 2010-02-18 |  |  | 2010-02-22 | 0.55556 |  | 4 | 0.55556 | 0.55556 | Document-New Process | Research-NP
Add TCs to New Feature Process | CODE | Add TCs to New Feature Process - Draft-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 45 | 1.25 | 1 | 1.25 | 2010-02-15 | 4 | 0.51556 | 2010-02-18 | 4 | 0.097168 | 4.9792 | 48.1992 | 9.125 | 0.097168 | 2010-02-18 |  |  | 2010-02-22 | 1.25 |  | 4 | 1.25 | 1.25 | Document-New Process | Draft-NP
Add TCs to New Feature Process | CR | Add TCs to New Feature Process - Doc Review-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.31333 | 2010-02-18 | 4 | 0.032389 | 5.0224 | 48.6159 | 9.1682 | 0.032389 | 2010-02-18 |  |  | 2010-02-22 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Review-NP
Quality Manager | MGMT | Quality Manager - Task (Week 4 - 2/15/10) | [6 empty] | C | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-02-15 | 4 | 2.0817 | 2010-02-19 | 4 | 0.1166 | 5.1196 | 50.1159 | 9.2654 | 0.1166 | 2010-02-19 |  |  | 2010-02-15 | 1.5 |  | 4 | 1.5 | 1.5 | Task | Task
Add PM to Dev Processes | DLD | Add PM to Dev Processes - Research-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 20 | 0.55556 | 1 | 0.55556 | 2010-02-15 | 4 | 0.78778 | 2010-02-23 | 5 | 0.043186 | 5.152 | 50.6714 | 9.2978 | 0.043186 | 2010-02-23 |  |  | 2010-03-08 | 0.55556 |  | 4 | 0.55556 | 0.55556 | Document-New Process | Research-NP
Add PM to Dev Processes | CODE | Add PM to Dev Processes - Draft-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 45 | 1.25 | 1 | 1.25 | 2010-02-15 | 4 | 0.97944 | 2010-02-24 | 5 | 0.097168 | 5.5212 | 51.9214 | 9.667 | 0.097168 | 2010-02-24 |  |  | 2010-03-08 | 1.25 |  | 4 | 1.25 | 1.25 | Document-New Process | Draft-NP
Add PM to Dev Processes | CR | Add PM to Dev Processes - Doc Review-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.42722 | 2010-02-24 | 5 | 0.032389 | 5.5878 | 52.3381 | 9.7336 | 0.032389 | 2010-02-24 |  |  | 2010-03-08 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Review-NP
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | [6 empty] | B | 507 | LOC | 17.17 | 58 | 17.1264 | 1 | 17.1264 | 2010-02-15 | 4 | 13.9947 | 2010-02-18 | 4 | 1.3313 | 5.8173 | 69.4645 | 9.9631 | 1.3313 | 2010-02-18 |  |  | 2010-02-15 | 17.1264 |  | 3 | 2.832 | 14.2944 | Issue Fixes | Find and Fix
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | [6 empty] | B | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.018611 | 2010-02-19 | 4 | 0.032389 | 5.9037 | 69.8811 | 10.0495 | 0.032389 | 2010-02-19 |  |  | 2010-05-10 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Implementation | MGMT | Implementation - Task 3 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 1.6825 | 2010-02-19 | 4 | 0.077734 | 5.9037 | 70.8811 | 10.0495 | 0.077734 | 2010-02-19 |  |  | 2010-02-15 | 1 |  | 4 | 1 | 1 | Task | Task
Define a Design Standard | CODE | Define a Design Standard - Draft-NT | [6 empty] | D | 38 | Text Pages | 1.2 | 30 | 9.5 | 1 | 9.5 | 2010-02-15 | 4 | 11.5947 | 2010-02-17 | 4 | 0.73847 | 5.9037 | 80.3811 | 10.0495 | 0.73847 | 2010-02-17 |  |  | 2010-02-08 | 9.5 |  | 3 | 7.5733 | 1.9267 | Document-New Technical | Draft-NT
Define a Design Standard | CR | Define a Design Standard - Doc Review-NT | [6 empty] | D | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-02-15 | 4 | 1.4861 | 2010-02-17 | 4 | 0.36924 | 5.9814 | 85.1311 | 10.1272 | 0.36924 | 2010-02-17 |  |  | 2010-02-15 | 4.75 |  | 4 | 4.75 | 4.75 | Document-New Technical | Doc Review-NT
Design Manager | MGMT | Design Manager - Week 4 (02/15/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-02-15 | 4 | 1.645 | 2010-02-18 | 4 | 0.15547 | 6.1757 | 87.1311 | 10.3216 | 0.15547 | 2010-02-18 |  |  | 2010-02-15 | 2 |  | 4 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 4 (02/15/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.26583 | 2010-02-18 | 4 | 0.077734 | 6.1757 | 88.1311 | 10.3216 | 0.077734 | 2010-02-18 |  |  | 2010-02-15 | 1 |  | 4 | 1 | 1 | Task | Task
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | [6 empty] | D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.56972 | 2010-02-19 | 4 | 0.032389 | 6.2405 | 88.5478 | 10.3863 | 0.032389 | 2010-02-19 |  |  | 2010-04-05 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.49694 | 2010-02-19 | 4 | 0.032389 | 6.2729 | 88.9645 | 10.4187 | 0.032389 | 2010-02-19 |  |  | 2010-04-19 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Design Manager | MGMT | Design Manager - Week 5 (02/22/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-02-15 | 4 | 1.3636 | 2010-02-22 | 5 | 0.15547 | 6.3053 | 90.9645 | 10.4511 | 0.15547 | 2010-02-22 |  |  | 2010-02-15 | 2 |  | 4 | 2 | 2 | Task | Task
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | [6 empty] | D | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-02-15 | 4 | 1.6175 | 2010-02-23 | 5 | 0.22954 | 6.3377 | 93.9173 | 10.4835 | 0.22954 | 2010-02-23 |  |  | 2010-05-31 | 2.9528 |  | 4 | 2.9528 | 2.9528 | Issue Fixes | Code Peer Review
Support Manager | MGMT | Support Manager - Week 5 (02/22/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.086389 | 2010-02-24 | 5 | 0.077734 | 6.3485 | 94.9173 | 10.4943 | 0.077734 | 2010-02-24 |  |  | 2010-02-15 | 1 |  | 4 | 1 | 1 | Task | Task
Maint - LD - 884 | CODE | Maint - LD - 884 - Find and Fix | [6 empty] | G | 147 | LOC | 17.17 | 58 | 4.9656 | 1 | 4.9656 | 2010-02-15 | 4 | 1.5472 | 2010-02-15 | 4 | 0.386 | 6.3593 | 99.8829 | 10.5051 | 0.386 | 2010-02-15 |  |  | 2010-03-29 | 4.9656 |  | 4 | 4.9656 | 4.9656 | Issue Fixes | Find and Fix
Maint - LD - 884 | CR | Maint - LD - 884 - Code Review | [6 empty] | G | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-15 | 4 | 0.16944 | 2010-02-15 | 4 | 0.066552 | 6.3701 | 100.7391 | 10.5159 | 0.066552 | 2010-02-15 |  |  | 2010-03-29 | 0.85614 |  | 4 | 0.85614 | 0.85614 | Issue Fixes | Code Review
Maint - LD - 884 | COMPILE | Maint - LD - 884 - Compile | [6 empty] | G | 147 | LOC | 17.17 | 3 | 0.25684 | 1 | 0.25684 | 2010-02-15 | 4 | 0.31917 | 2010-02-15 | 4 | 0.019965 | 6.4058 | 100.9959 | 10.5517 | 0.019965 | 2010-02-15 |  |  | 2010-03-29 | 0.25684 |  | 4 | 0.25684 | 0.25684 | Issue Fixes | Compile
Maint - LD - 952 | CODEINSP | Maint - LD - 952 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.1725 | 2010-02-16 | 4 | 0.077734 | 6.6829 | 101.9959 | 10.8287 | 0.077734 | 2010-02-16 |  |  |  | 0 |  | 4 | 1 | 1
Maint - LD - 957 | CODEINSP | Maint - LD - 957 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.21556 | 2010-02-16 | 4 | 0.077734 | 6.9599 | 102.9959 | 11.1057 | 0.077734 | 2010-02-16 |  |  |  | 0 |  | 4 | 1 | 1
Maint - LD - 960 | CODEINSP | Maint - LD - 960 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.10167 | 2010-02-16 | 4 | 0.077734 | 7.2454 | 103.9959 | 11.3912 | 0.077734 | 2010-02-16 |  |  |  | 0 |  | 4 | 1 | 1
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | G | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.75583 | 2010-02-18 | 4 | 0.032389 | 7.6314 | 104.4126 | 11.7772 | 0.032389 | 2010-02-18 |  |  | 2010-04-05 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | G | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.12861 | 2010-02-18 | 4 | 0.032389 | 7.6979 | 104.8293 | 11.8437 | 0.032389 | 2010-02-18 |  |  | 2010-04-05 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Customer Interface Manager | MGMT | Customer Interface Manager - 2/15 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.58333 | 2010-02-18 | 4 | 0.077734 | 7.7179 | 105.8293 | 11.8637 | 0.077734 | 2010-02-18 |  |  | 2010-02-08 | 4 |  | 4 | 1 | 1 | Task | Task
Maint - LD - 959 | CODEINSP | Maint - LD - 959 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.91667 | 2010-02-23 | 5 | 0.077734 | 7.7956 | 106.8293 | 11.9414 | 0.077734 | 2010-02-23 |  |  |  | 0 |  | 4 | 1 | 1
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | [6 empty] | G | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-15 | 4 | 1.1917 | 2010-02-23 | 5 | 0.066552 | 8.0031 | 107.6854 | 12.1489 | 0.066552 | 2010-02-23 |  |  | 2010-03-29 | 0.85614 |  | 4 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Process Manager | MGMT | Process Manager - Week 3 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.11861 | 2010-02-12 | 3 | 0.077734 | 8.0388 | 108.6854 | 12.1846 | 0.077734 | 2010-02-12 |  |  | 2010-02-08 | 1 |  | 3 | 0.5 | 0.5 | Task | Task
Process Manager | MGMT | Process Manager - Week 4 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.094722 | 2010-02-20 | 4 | 0.077734 | 8.0495 | 109.6854 | 12.1954 | 0.077734 | 2010-02-20 |  |  | 2010-02-22 | 1 |  | 4 | 1 | 1 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 4 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-02-15 | 4 | 1.0861 | 2010-02-20 | 4 | 0.1166 | 8.1161 | 111.1854 | 12.2619 | 0.1166 | 2010-02-20 |  |  | 2010-03-01 | 1.5 |  | 4 | 1.5 | 1.5 | Task | Task
Demo - Docs - Test Cases | DLD | Demo - Docs - Test Cases - Research-NT | [6 empty] | A | 35 | Text Pages | 1.2 | 35 | 10.2083 | 1 | 10.2083 | 2010-02-22 | 5 | 4.9725 | 2010-02-26 | 5 | 0.79354 | 8.2159 | 121.3937 | 12.3617 | 0.79354 | 2010-02-26 |  |  | 2010-02-22 | 10.2083 |  | 4 | 5.1667 | 5.0417 | Document-New Technical | Research-NT
Test Manager | MGMT | Test Manager - Task Week 5 Feb 22 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 1.0889 | 2010-02-26 | 5 | 0.077734 | 8.2425 | 122.3937 | 12.3884 | 0.077734 | 2010-02-26 |  |  | 2010-04-26 | 1 |  | 5 | 1 | 1 | Task | Task
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | C | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-02-22 | 5 | 3.1881 | 2010-02-25 | 5 | 0.36924 | 8.6312 | 127.1437 | 12.777 | 0.36924 | 2010-02-25 |  |  | 2010-02-22 | 4.75 |  | 4 | 0.28994 | 4.4601 | Document-New Technical | Doc Inspection-NT
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | [6 empty] | C | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-22 | 5 | 0.45806 | 2010-02-25 | 5 | 0.066552 | 8.8936 | 127.9999 | 13.0394 | 0.066552 | 2010-02-25 |  |  | 2010-02-22 | 0.85614 |  | 5 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | [6 empty] | C | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-02-22 | 5 | 2.9158 | 2010-02-26 | 5 | 0.22954 | 8.9713 | 130.9527 | 13.1171 | 0.22954 | 2010-02-26 |  |  | 2010-03-08 | 2.9528 |  | 5 | 2.9528 | 2.9528 | Issue Fixes | Code Peer Review
Create Peer Review Script | DLD | Create Peer Review Script - Research-NP | [6 empty] | C | 2 | Text Pages | 0.36 | 20 | 1.1111 | 1 | 1.1111 | 2010-02-22 | 5 | 1.2758 | 2010-02-26 | 5 | 0.086371 | 9.049 | 132.0638 | 13.1949 | 0.086371 | 2010-02-26 |  |  | 2010-03-01 | 1.1111 |  | 5 | 1.1111 | 1.1111 | Document-New Process | Research-NP
Maint - LD - 956 | CODEINSP | Maint - LD - 956 - Code Peer Review | [6 empty] | C | 39 | LOC | 17.17 | 10 | 0.22714 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 9.1138 | 132.0638 | 13.2596 | 0 | 2010-03-01 |  |  | 2010-03-08 | 0.22714 |  | 5 | 0 | 0 | Issue Fixes | Code Peer Review
Demo - Interface - Closure Design | CODEINSP | Demo - Interface - Closure Design - Doc Inspection-NT | [6 empty] | C | 38 | Text Pages | 1.2 | 15 | 4.75 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 9.1354 | 132.0638 | 13.2812 | 0 | 2010-03-01 |  |  | 2010-05-10 | 4.75 |  | 5 | 0 | 0 | Document-New Technical | Doc Inspection-NT
Quality Manager | MGMT | Quality Manager - Task (Week 5 - 2/22/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 1.0658 | 2010-03-01 | 6 | 0.077734 | 9.1712 | 133.0638 | 13.317 | 0.077734 | 2010-03-01 |  |  | 2010-02-22 | 1 |  | 5 | 1 | 1 | Task | Task
Create Peer Review Script | CODE | Create Peer Review Script - Draft-NP | [6 empty] | C | 2 | Text Pages | 0.36 | 45 | 2.5 | 1 | 2.5 | 2010-02-22 | 5 | 2.3636 | 2010-03-01 | 6 | 0.19434 | 9.2248 | 135.5638 | 13.3706 | 0.19434 | 2010-03-01 |  |  | 2010-03-01 | 2.5 |  | 5 | 2.5 | 2.5 | Document-New Process | Draft-NP
Maint - LD - 961 | CODEINSP | Maint - LD - 961 - Code Peer Review | [6 empty] | C | 39 | LOC | 17.17 | 10 | 0.22714 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 9.2391 | 135.5638 | 13.385 | 0 | 2010-03-01 |  |  | 2010-03-08 | 0.22714 |  | 5 | 0 | 0 | Issue Fixes | Code Peer Review
Create Peer Review Script | CR | Create Peer Review Script - Doc Review-NP | [6 empty] | C | 2 | Text Pages | 0.36 | 15 | 0.83333 | 1 | 0.83333 | 2010-02-22 | 5 | 0.55861 | 2010-03-02 | 6 | 0.064778 | 9.4462 | 136.3971 | 13.592 | 0.064778 | 2010-03-02 |  |  | 2010-03-01 | 0.83333 |  | 5 | 0.83333 | 0.83333 | Document-New Process | Doc Review-NP
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.55722 | 2010-03-02 | 6 | 0.032389 | 9.4819 | 136.8138 | 13.6277 | 0.032389 | 2010-03-02 |  |  | 2010-02-15 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.22028 | 2010-03-02 | 6 | 0.032389 | 9.4926 | 137.2305 | 13.6384 | 0.032389 | 2010-03-02 |  |  | 2010-02-22 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.40333 | 2010-03-02 | 6 | 0.032389 | 9.5704 | 137.6471 | 13.7162 | 0.032389 | 2010-03-02 |  |  | 2010-03-08 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add Checklist to all Review/Insp Phases | PM | Add Checklist to all Review/Insp Phases - Doc PM-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 5 | 0.13889 | 1 | 0.13889 | 2010-02-22 | 5 | 0.22722 | 2010-03-02 | 6 | 0.010796 | 9.5704 | 137.786 | 13.7162 | 0.010796 | 2010-03-02 |  |  | 2010-02-15 | 0.13889 |  | 5 | 0.13889 | 0.13889 | Document-New Process | Doc PM-NP
Add TCs to New Feature Process | PM | Add TCs to New Feature Process - Doc PM-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 5 | 0.13889 | 1 | 0.13889 | 2010-02-22 | 5 | 0.14333 | 2010-03-02 | 6 | 0.010796 | 9.6481 | 137.9249 | 13.7939 | 0.010796 | 2010-03-02 |  |  | 2010-02-22 | 0.13889 |  | 5 | 0.13889 | 0.13889 | Document-New Process | Doc PM-NP
Add PM to Dev Processes | PM | Add PM to Dev Processes - Doc PM-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 5 | 0.13889 | 1 | 0.13889 | 2010-02-22 | 5 | 0.15611 | 2010-03-02 | 6 | 0.010796 | 9.6838 | 138.0638 | 13.8296 | 0.010796 | 2010-03-02 |  |  | 2010-03-08 | 0.13889 |  | 5 | 0.13889 | 0.13889 | Document-New Process | Doc PM-NP
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | [6 empty] | C | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-22 | 5 | 0.51528 | 2010-03-02 | 6 | 0.035766 | 9.7374 | 138.5239 | 13.8832 | 0.035766 | 2010-03-02 |  |  | 2010-02-22 | 0.4601 |  | 5 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 959 | CR | Maint - LD - 959 - Code Review | [6 empty] | B | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-02-22 | 5 | 1.6381 | 2010-02-22 | 5 | 0.22954 | 9.7516 | 141.4767 | 13.8975 | 0.22954 | 2010-02-22 |  |  | 2010-02-22 | 2.9528 |  | 4 | 1.289 | 1.6639 | Issue Fixes | Code Review
Maint - LD - 959 | COMPILE | Maint - LD - 959 - Compile | [6 empty] | B | 507 | LOC | 17.17 | 3 | 0.88585 | 1 | 0.88585 | 2010-02-22 | 5 | 0.050556 | 2010-02-22 | 5 | 0.068861 | 10.6534 | 142.3626 | 14.7992 | 0.068861 | 2010-02-22 |  |  | 2010-02-22 | 0.88585 |  | 5 | 0.88585 | 0.88585 | Issue Fixes | Compile
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | [6 empty] | B | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.515 | 2010-02-24 | 5 | 0.032389 | 10.7311 | 142.7793 | 14.8769 | 0.032389 | 2010-02-24 |  |  | 2010-05-10 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | B | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-02-22 | 5 | 1.8656 | 2010-02-24 | 5 | 0.36924 | 10.9099 | 147.5293 | 15.0557 | 0.36924 | 2010-02-24 |  |  | 2010-05-10 | 4.75 |  | 5 | 4.75 | 4.75 | Document-New Technical | Doc Inspection-NT
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | [6 empty] | B | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-02-22 | 5 | 1.2489 | 2010-02-26 | 5 | 0.22954 | 11.8116 | 150.4821 | 15.9574 | 0.22954 | 2010-02-26 |  |  | 2010-02-22 | 2.9528 |  | 5 | 2.9528 | 2.9528 | Issue Fixes | Code Peer Review
Maint - LD - 959 | UT | Maint - LD - 959 - Unit Test | [6 empty] | B | 507 | LOC | 17.17 | 15 | 4.4292 | 1 | 4.4292 | 2010-02-22 | 5 | 1.7017 | 2010-02-26 | 5 | 0.3443 | 11.8116 | 154.9113 | 15.9574 | 0.3443 | 2010-02-26 |  |  | 2010-02-22 | 4.4292 |  | 5 | 4.4292 | 4.4292 | Issue Fixes | Unit Test
Maint - LD - 959 | PM | Maint - LD - 959 - PM | [6 empty] | B | 507 | LOC | 17.17 | 4 | 1.1811 | 1 | 1.1811 | 2010-02-22 | 5 | 0.6025 | 2010-02-26 | 5 | 0.091814 | 12.1225 | 156.0924 | 16.2683 | 0.091814 | 2010-02-26 |  |  | 2010-02-22 | 1.1811 |  | 5 | 1.1811 | 1.1811 | Issue Fixes | Postmortem
Implementation | MGMT | Implementation - Task 4 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 0.57083 | 2010-02-26 | 5 | 0.077734 | 12.1225 | 157.0924 | 16.2683 | 0.077734 | 2010-02-26 |  |  | 2010-02-22 | 1 |  | 5 | 1 | 1 | Task | Task
Demo - Interface - Closure Design | DLD | Demo - Interface - Closure Design - Research-NT | [6 empty] | B | 44 | Text Pages | 1.2 | 35 | 12.8333 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 157.0924 | 16.3616 | 0 | 2010-03-01 |  |  | 2010-03-08 | 12.8333 |  | 5 | 0 | 0 | Document-New Technical | Research-NT
Demo - Interface - Closure Design | CODE | Demo - Interface - Closure Design - Draft-NT | [6 empty] | B | 44 | Text Pages | 1.2 | 30 | 11 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 157.0924 | 16.6726 | 0 | 2010-03-01 |  |  | 2010-03-08 | 11 |  | 5 | 0 | 0 | Document-New Technical | Draft-NT
Demo - Interface - Closure Design | CR | Demo - Interface - Closure Design - Doc Review-NT | [6 empty] | B | 44 | Text Pages | 1.2 | 15 | 5.5 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 157.0924 | 16.7503 | 0 | 2010-03-01 |  |  | 2010-03-15 | 5.5 |  | 5 | 0 | 0 | Document-New Technical | Doc Review-NT
Demo - Interface - Closure Design | PM | Demo - Interface - Closure Design - Doc PM-NT | [6 empty] | B | 44 | Text Pages | 1.2 | 5 | 1.8333 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 157.0924 | 16.7503 | 0 | 2010-03-01 |  | 2010-05-21 | 2010-03-15 | 1.8333 |  | 5 | 0 | 0 | Document-New Technical | Doc PM-NT
Demo - Interface - Closure Design | CODEINSP | Demo - Interface - Closure Design - Doc Inspection-NT | [6 empty] | B | 44 | Text Pages | 1.2 | 15 | 5.5 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 157.0924 | 16.828 | 0 | 2010-03-01 |  |  | 2010-03-15 | 5.5 |  | 5 | 0 | 0 | Document-New Technical | Doc Inspection-NT
Implementation | MGMT | Implementation - Task 5 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 0 | 0 | 2010-02-22 | 5 | 0.78306 | 2010-03-05 | 6 | 0 | 12.1225 | 157.0924 | 16.9835 | 0 | 2010-03-05 |  |  | 2010-03-01 | 1 |  | 5 | 0 | 0 | Task | Task
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | [6 empty] | F | 35 | Req Pages | 1.2 | 35 | 10.2083 | 1 | 10.2083 | 2010-02-22 | 5 | 7.9333 | 2010-02-18 | 4 | 0.79354 | 12.1225 | 167.3008 | 17.0612 | 0.79354 | 2010-02-18 |  |  | 2010-02-22 | 10.2083 |  | 4 | 10 | 0.20833 | Document-New Technical | Research-NT
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | [6 empty] | F | 35 | Req Pages | 1.2 | 30 | 8.75 | 1 | 8.75 | 2010-02-22 | 5 | 10.2833 | 2010-03-05 | 6 | 0.68017 | 12.1225 | 176.0508 | 17.0612 | 0.68017 | 2010-03-05 |  |  | 2010-02-22 | 8.75 |  | 5 | 8.75 | 8.75 | Document-New Technical | Draft-NT
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | [6 empty] | D | 40 | LOC | 1 | 58 | 23.2 | 1 | 23.2 | 2010-02-22 | 5 | 20.6125 | 2010-02-24 | 5 | 1.8034 | 12.1225 | 199.2508 | 17.3722 | 1.8034 | 2010-02-24 |  |  |  | 0 |  | 4 | 3.5371 | 19.6629 | Issue Fixes | Find and Fix
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | G | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-02-22 | 5 | 1.6114 | 2010-02-25 | 5 | 0.36924 | 12.1225 | 204.0008 | 17.8386 | 0.36924 | 2010-02-25 |  |  | 2010-04-05 | 4.75 |  | 4 | 3.2319 | 1.5181 | Document-New Technical | Doc Inspection-NT
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 1.9033 | 2010-02-26 | 5 | 0.077734 | 12.1225 | 205.0008 | 17.963 | 0.077734 | 2010-02-26 |  |  | 2010-04-26 | 4 |  | 5 | 1 | 1 | Task | Task
Maint - LD - 958 | CODE | Maint - LD - 958 - Find and Fix | [6 empty] | G | 507 | LOC | 17.17 | 58 | 17.1264 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 205.0008 | 18.3322 | 0 | 2010-03-01 |  |  | 2010-02-22 | 17.1264 |  | 5 | 0 | 0 | Issue Fixes | Find and Fix
Maint - LD - 958 | CR | Maint - LD - 958 - Code Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 205.0008 | 18.4099 | 0 | 2010-03-01 |  |  | 2010-02-22 | 2.9528 |  | 5 | 0 | 0 | Issue Fixes | Code Review
Maint - LD - 958 | COMPILE | Maint - LD - 958 - Compile | [6 empty] | G | 507 | LOC | 17.17 | 3 | 0.88585 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 205.0008 | 18.4099 | 0 | 2010-03-01 |  |  | 2010-02-22 | 0.88585 |  | 5 | 0 | 0 | Issue Fixes | Compile
Maint - LD - 958 | CODEINSP | Maint - LD - 958 - Code Peer Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 205.0008 | 18.6395 | 0 | 2010-03-01 |  |  | 2010-02-22 | 2.9528 |  | 5 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 958 | UT | Maint - LD - 958 - Unit Test | [6 empty] | G | 507 | LOC | 17.17 | 15 | 4.4292 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 205.0008 | 18.869 | 0 | 2010-03-01 |  |  | 2010-03-01 | 4.4292 |  | 5 | 0 | 0 | Issue Fixes | Unit Test
Maint - LD - 958 | PM | Maint - LD - 958 - PM | [6 empty] | G | 507 | LOC | 17.17 | 4 | 1.1811 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 | 12.1225 | 205.0008 | 19.1799 | 0 | 2010-03-01 |  |  | 2010-03-01 | 1.1811 |  | 5 | 0 | 0 | Issue Fixes | Postmortem
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | [6 empty] | G | 147 | LOC | 17.17 | 15 | 1.2842 | 1 | 1.2842 | 2010-02-22 | 5 | 1.6106 | 2010-03-01 | 6 | 0.099827 | 12.1225 | 206.285 | 19.4909 | 0.099827 | 2010-03-01 |  |  | 2010-03-29 | 1.2842 |  | 5 | 1.2842 | 1.2842 | Issue Fixes | Unit Test
Maint - LD - 884 | PM | Maint - LD - 884 - PM | [6 empty] | G | 147 | LOC | 17.17 | 4 | 0.34246 | 1 | 0.34246 | 2010-02-22 | 5 | 0.1175 | 2010-03-01 | 6 | 0.026621 | 12.1225 | 206.6275 | 19.5686 | 0.026621 | 2010-03-01 |  | 2010-03-29 | 2010-03-29 | 0.34246 |  | 5 | 0.34246 | 0.34246 | Issue Fixes | Postmortem
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | [6 empty] | G | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.084167 | 2010-03-01 | 6 | 0.032389 | 12.1225 | 207.0441 | 19.5686 | 0.032389 | 2010-03-01 |  |  | 2010-04-05 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Demo - Interface - Closure Design | CODEINSP | Demo - Interface - Closure Design - Doc Inspection-NT | [6 empty] | G | 38 | Text Pages | 1.2 | 15 | 4.75 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-02 | 6 | 0 | 12.1225 | 207.0441 | 19.8795 | 0 | 2010-03-02 |  |  | 2010-04-12 | 4.75 |  | 5 | 0 | 0 | Document-New Technical | Doc Inspection-NT
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review | [6 empty] | G | 40 | LOC | 1 | 10 | 4 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-02 | 6 | 0 | 12.1225 | 207.0441 | 20.035 | 0 | 2010-03-02 |  |  | 2010-04-26 | 4 |  | 5 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 885 | CODE | Maint - LD - 885 - Find and Fix | [6 empty] | G | 79 | LOC | 17.17 | 58 | 2.6686 | 1 | 2.6686 | 2010-02-22 | 5 | 1.8842 | 2010-03-04 | 6 | 0.20744 | 12.1225 | 209.7127 | 20.0674 | 0.20744 | 2010-03-04 |  |  | 2010-03-29 | 2.6686 |  | 5 | 2.6686 | 2.6686 | Issue Fixes | Find and Fix
Maint - LD - 885 | CR | Maint - LD - 885 - Code Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-22 | 5 | 1.2742 | 2010-03-04 | 6 | 0.035766 | 12.1225 | 210.1728 | 20.0998 | 0.035766 | 2010-03-04 |  |  | 2010-03-29 | 0.4601 |  | 5 | 0.4601 | 0.4601 | Issue Fixes | Code Review
Maint - LD - 885 | COMPILE | Maint - LD - 885 - Compile | [6 empty] | G | 79 | LOC | 17.17 | 3 | 0.13803 | 1 | 0.13803 | 2010-02-22 | 5 | 0.069167 | 2010-03-04 | 6 | 0.01073 | 12.1225 | 210.3109 | 20.2985 | 0.01073 | 2010-03-04 |  |  | 2010-03-29 | 0.13803 |  | 5 | 0.13803 | 0.13803 | Issue Fixes | Compile
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-22 | 5 | 0.75028 | 2010-03-04 | 6 | 0.035766 | 12.1225 | 210.771 | 20.3763 | 0.035766 | 2010-03-04 |  |  | 2010-03-29 | 0.4601 |  | 5 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 885 | UT | Maint - LD - 885 - Unit Test | [6 empty] | G | 79 | LOC | 17.17 | 15 | 0.69016 | 1 | 0.69016 | 2010-02-22 | 5 | 1.1633 | 2010-03-04 | 6 | 0.053649 | 12.1225 | 211.4611 | 20.454 | 0.053649 | 2010-03-04 |  |  | 2010-04-05 | 0.69016 |  | 5 | 0.69016 | 0.69016 | Issue Fixes | Unit Test
Maint - LD - 885 | PM | Maint - LD - 885 - PM | [6 empty] | G | 79 | LOC | 17.17 | 4 | 0.18404 | 1 | 0.18404 | 2010-02-22 | 5 | 0.13389 | 2010-03-04 | 6 | 0.014306 | 12.1225 | 211.6452 | 20.5325 | 0.014306 | 2010-03-04 |  | 2010-03-29 | 2010-04-05 | 0.18404 |  | 5 | 0.18404 | 0.18404 | Issue Fixes | Postmortem
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | [6 empty] | G | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.36167 | 2010-03-04 | 6 | 0.032389 | 12.1225 | 212.0618 | 20.6118 | 0.032389 | 2010-03-04 |  |  | 2010-04-05 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | [6 empty] | G | 2 | Text Pages | 0.36 | 15 | 0.83333 | 1 | 0.83333 | 2010-02-22 | 5 | 0.08 | 2010-03-04 | 6 | 0.064778 | 12.1225 | 212.8952 | 20.6919 | 0.064778 | 2010-03-04 |  |  | 2010-04-05 | 0.83333 |  | 5 | 0.83333 | 0.83333 | Document-New Process | Doc Inspection-NP
Customer Interface Manager | MGMT | Customer Interface Manager - 3/1 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 0.72667 | 2010-03-05 | 6 | 0.077734 | 12.1225 | 213.8952 | 20.9251 | 0.077734 | 2010-03-05 |  |  | 2010-05-03 | 4 |  | 5 | 1 | 1 | Task | Task
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | G | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-02-22 | 5 | 0.66667 | 2010-03-05 | 6 | 0.2332 | 12.2249 | 216.8952 | 21.0275 | 0.2332 | 2010-03-05 |  |  | 2010-05-24 | 3 |  | 5 | 3 | 3
Process Manager | MGMT | Process Manager - Week 5 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 |  | 2010-02-26 | 5 | 0.077734 | 12.4324 | 217.8952 | 21.2349 | 0.077734 | 2010-02-26 |  |  | 2010-03-01 | 1 |  | 4 | 0 | 1 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 5 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-02-22 | 5 | 0.865 | 2010-02-26 | 5 | 0.1166 | 12.4523 | 219.3952 | 21.2549 | 0.1166 | 2010-02-26 |  |  | 2010-03-08 | 1.5 |  | 5 | 1.5 | 1.5 | Task | Task
CMMI Training | MGMT | CMMI Training - Task March 1 | [6 empty] | A | 6.6 | Text Pages | 1 | 100 | 6.6 | 1 | 6.6 | 2010-03-01 | 6 | 6.6 | 2010-03-05 | 6 | 0.51305 | 12.8383 | 225.9952 | 21.6409 | 0.51305 | 2010-03-05 |  |  | 2010-03-01 | 6.6 |  | 5 | 3.9583 | 2.6417
Test Manager | MGMT | Test Manager - Task Week 6 Mar 1 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-01 | 6 | 0.19056 | 2010-03-05 | 6 | 0.077734 | 12.856 | 226.9952 | 21.6585 | 0.077734 | 2010-03-05 |  |  | 2010-04-26 | 1 |  | 6 | 1 | 1 | Task | Task
CMMI Training | MGMT | CMMI Training - Day 1 | [6 empty] | C | 10.8 | Text Pages | 1 | 33 | 3.564 | 1 | 3.564 | 2010-03-01 | 6 | 3.6 | 2010-03-03 | 6 | 0.27704 | 12.8613 | 230.5592 | 21.6638 | 0.27704 | 2010-03-03 |  |  | 2010-03-01 | 10.8 |  | 5 | 2.1598 | 1.4042
CMMI Training | MGMT | CMMI Training - Day 2 | [6 empty] | C | 10.8 | Text Pages | 1 | 33 | 3.564 | 1 | 3.564 | 2010-03-01 | 6 | 3.6 | 2010-03-04 | 6 | 0.27704 | 12.8971 | 234.1232 | 21.6996 | 0.27704 | 2010-03-04 |  |  | 2010-03-01 | 10.8 |  | 6 | 3.564 | 3.564
CMMI Training | MGMT | CMMI Training - Day 3 | [6 empty] | C | 10.8 | Text Pages | 1 | 34 | 3.672 | 1 | 3.672 | 2010-03-01 | 6 | 3.6 | 2010-03-05 | 6 | 0.28544 | 12.9078 | 237.7952 | 21.7103 | 0.28544 | 2010-03-05 |  |  | 2010-03-01 | 10.8 |  | 6 | 3.672 | 3.672
Maint - LD - 953 | CODE | Maint - LD - 953 - Find and Fix | [6 empty] | C | 147 | LOC | 17.17 | 58 | 4.9656 | 1 | 4.9656 | 2010-03-01 | 6 | 2.4089 | 2010-03-08 | 7 | 0.386 | 12.9743 | 242.7608 | 21.7769 | 0.386 | 2010-03-08 |  |  | 2010-03-08 | 4.9656 |  | 6 | 4.9656 | 4.9656 | Issue Fixes | Find and Fix
Maint - LD - 953 | CR | Maint - LD - 953 - Code Review | [6 empty] | C | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-03-01 | 6 | 0.66056 | 2010-03-08 | 7 | 0.066552 | 13.0521 | 243.617 | 21.8546 | 0.066552 | 2010-03-08 |  |  | 2010-03-15 | 0.85614 |  | 6 | 0.85614 | 0.85614 | Issue Fixes | Code Review
Maint - LD - 953 | COMPILE | Maint - LD - 953 - Compile | [6 empty] | C | 147 | LOC | 17.17 | 3 | 0.25684 | 1 | 0.25684 | 2010-03-01 | 6 | 0.25361 | 2010-03-08 | 7 | 0.019965 | 13.1298 | 243.8738 | 21.9324 | 0.019965 | 2010-03-08 |  |  | 2010-03-15 | 0.25684 |  | 6 | 0.25684 | 0.25684 | Issue Fixes | Compile
Quality Manager | MGMT | Quality Manager - Task (Week 6 - 3/1/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-01 | 6 | 0.54417 | 2010-03-08 | 7 | 0.077734 | 13.2322 | 244.8738 | 22.0348 | 0.077734 | 2010-03-08 |  |  | 2010-03-01 | 1 |  | 6 | 1 | 1 | Task | Task
CMMI Training | MGMT | CMMI Training - Task | [6 empty] | B | 13.2 | Text Pages | 1 | 100 | 13.2 | 1 | 13.2 | 2010-03-01 | 6 | 13.2 | 2010-03-05 | 6 | 1.0261 | 13.2322 | 258.0738 | 22.0348 | 1.0261 | 2010-03-05 |  |  | 2010-03-01 | 13.2 |  | 5 | 2.7204 | 10.4796
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | [6 empty] | B | 2 | Text Pages | 0.36 | 15 | 0.83333 | 1 | 0.83333 | 2010-03-01 | 6 | 0.23944 | 2010-03-08 | 7 | 0.064778 | 13.2322 | 258.9071 | 22.0348 | 0.064778 | 2010-03-08 |  |  | 2010-05-10 | 0.83333 |  | 6 | 0.83333 | 0.83333 | Document-New Process | Doc Inspection-NP
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | [6 empty] | B | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-01 | 6 | 4.5833 | 2010-03-09 | 7 | 0.4664 | 13.2322 | 264.9071 | 22.0348 | 0.4664 | 2010-03-09 |  |  | 2010-05-17 | 6 |  | 6 | 6 | 6 | Task | Task
CMMI Training | MGMT | CMMI Training - Task | [6 empty] | F | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-03-01 | 6 | 8 | 2010-03-05 | 6 | 0.62187 | 13.2322 | 272.9071 | 22.0348 | 0.62187 | 2010-03-05 |  |  | 2010-05-17 | 8 |  | 5 | 3.0417 | 4.9583
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | [6 empty] | F | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-03-01 | 6 | 4.3167 | 2010-03-08 | 7 | 0.2332 | 13.2322 | 275.9071 | 22.0348 | 0.2332 | 2010-03-08 |  |  | 2010-03-22 | 3 |  | 6 | 3 | 3 | Task | Task
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | D | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-03-01 | 6 | 1.3358 | 2010-02-25 | 5 | 0.36924 | 13.2499 | 280.6571 | 22.0524 | 0.36924 | 2010-02-25 |  |  | 2010-02-15 | 4.75 |  | 5 | 4.3371 | 0.41288 | Document-New Technical | Doc Inspection-NT
Define a Design Standard | PM | Define a Design Standard - Doc PM-NT | [6 empty] | D | 38 | Text Pages | 1.2 | 5 | 1.5833 | 1 | 1.5833 | 2010-03-01 | 6 | 1.3858 | 2010-02-26 | 5 | 0.12308 | 13.2856 | 282.2405 | 22.0882 | 0.12308 | 2010-02-26 |  |  | 2010-02-15 | 1.5833 |  | 6 | 1.5833 | 1.5833 | Document-New Technical | Doc PM-NT
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | [6 empty] | D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-03-01 | 6 | 0.50194 | 2010-02-26 | 5 | 0.032389 | 13.3522 | 282.6571 | 22.1547 | 0.032389 | 2010-02-26 |  |  | 2010-03-22 | 0.41667 |  | 6 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | [6 empty] | G | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-01 | 6 | 0.28417 | 2010-03-09 | 7 | 0.4664 | 13.3787 | 288.6571 | 22.1812 | 0.4664 | 2010-03-09 |  |  | 2010-02-08 | 6 |  | 5 | 1.5875 | 4.4125 | Task | Task
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | [6 empty] | G | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-03-01 | 6 | 0.076944 | 2010-03-11 | 7 | 0.066552 | 13.4323 | 289.5133 | 22.2349 | 0.066552 | 2010-03-11 |  |  | 2010-03-01 | 0.85614 |  | 6 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Customer Interface Manager | MGMT | Customer Interface Manager - 3/8 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-01 | 6 | 0.5 | 2010-03-12 | 7 | 0.077734 | 13.5322 | 290.5133 | 22.3347 | 0.077734 | 2010-03-12 |  |  | 2010-05-03 | 4 |  | 6 | 1 | 1 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | [6 empty] | G | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-01 | 6 | 2 | 2010-03-15 | 8 | 0.34009 | 13.5392 | 294.8883 | 22.3418 | 0.34009 | 2010-03-15 |  |  | 2010-04-12 | 4.375 |  | 6 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-01 | 6 | 1.5992 | 2010-03-16 | 8 | 0.035766 | 13.5535 | 295.3484 | 22.3561 | 0.035766 | 2010-03-16 |  |  | 2010-03-01 | 0.4601 |  | 6 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 955 | CODE | Maint - LD - 955 - Find and Fix | [6 empty] | G | 79 | LOC | 17.17 | 58 | 2.6686 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 | 13.5801 | 295.3484 | 22.3827 | 0 | 2010-03-17 |  |  | 2010-02-15 | 2.6686 |  | 6 | 0 | 0 | Issue Fixes | Find and Fix
Maint - LD - 955 | CR | Maint - LD - 955 - Code Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 | 13.6125 | 295.3484 | 22.4151 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.4601 |  | 6 | 0 | 0 | Issue Fixes | Code Review
Maint - LD - 955 | COMPILE | Maint - LD - 955 - Compile | [6 empty] | G | 79 | LOC | 17.17 | 3 | 0.13803 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 | 14.9438 | 295.3484 | 23.7464 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.13803 |  | 6 | 0 | 0 | Issue Fixes | Compile
Maint - LD - 955 | UT | Maint - LD - 955 - Unit Test | [6 empty] | G | 79 | LOC | 17.17 | 15 | 0.69016 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 | 14.9762 | 295.3484 | 23.7788 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.69016 |  | 6 | 0 | 0 | Issue Fixes | Unit Test
Maint - LD - 955 | PM | Maint - LD - 955 - PM | [6 empty] | G | 79 | LOC | 17.17 | 4 | 0.18404 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 | 15.054 | 295.3484 | 23.8565 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.18404 |  | 6 | 0 | 0 | Issue Fixes | Postmortem
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | [6 empty] | A | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-08 | 7 | 4.9153 | 2010-03-09 | 7 | 0.4664 | 15.2835 | 301.3484 | 24.086 | 0.4664 | 2010-03-09 |  |  | 2010-04-26 | 6 |  | 6 | 5.3583 | 0.64167 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 7 Mar 8 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.96028 | 2010-03-12 | 7 | 0.077734 | 15.3524 | 302.3484 | 24.1549 | 0.077734 | 2010-03-12 |  |  | 2010-04-26 | 1 |  | 7 | 1 | 1 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | [6 empty] | A | 35 | Req Pages |  |  | 2 | 1 | 2 | 2010-03-08 | 7 | 6.8292 | 2010-03-12 | 7 | 0.15547 | 15.3847 | 304.3484 | 24.1873 | 0.15547 | 2010-03-12 |  |  | 2010-03-15 | 2 |  | 7 | 2 | 2 | Document-New Technical | Doc Inspection-NT
Test Manager | MGMT | Test Manager - Task Week 8 Mar 15 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.39417 | 2010-03-18 | 8 | 0.077734 | 15.754 | 305.3484 | 24.5565 | 0.077734 | 2010-03-18 |  |  | 2010-04-26 | 1 |  | 7 | 1 | 1 | Task | Task
Maint - LD - 954 | CODE | Maint - LD - 954 - Find and Fix | [6 empty] | C | 79 | LOC | 17.17 | 58 | 2.6686 | 1 | 2.6686 | 2010-03-08 | 7 | 1.5053 | 2010-03-10 | 7 | 0.20744 | 15.9835 | 308.017 | 24.7861 | 0.20744 | 2010-03-10 |  |  | 2010-03-15 | 2.6686 |  | 6 | 2.2811 | 0.38747 | Issue Fixes | Find and Fix
Maint - LD - 954 | CR | Maint - LD - 954 - Code Review | [6 empty] | C | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-08 | 7 | 0.77 | 2010-03-10 | 7 | 0.035766 | 16.3278 | 308.4771 | 25.1304 | 0.035766 | 2010-03-10 |  |  | 2010-03-15 | 0.4601 |  | 7 | 0.4601 | 0.4601 | Issue Fixes | Code Review
Maint - LD - 954 | COMPILE | Maint - LD - 954 - Compile | [6 empty] | C | 79 | LOC | 17.17 | 3 | 0.13803 | 1 | 0.13803 | 2010-03-08 | 7 | 0.098611 | 2010-03-10 | 7 | 0.01073 | 16.4196 | 308.6151 | 25.2222 | 0.01073 | 2010-03-10 |  |  | 2010-03-22 | 0.13803 |  | 7 | 0.13803 | 0.13803 | Issue Fixes | Compile
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | [6 empty] | C | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-03-08 | 7 | 0.57 | 2010-03-11 | 7 | 0.066552 | 16.4974 | 309.4713 | 25.2999 | 0.066552 | 2010-03-11 |  |  | 2010-03-15 | 0.85614 |  | 7 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Maint - LD - 953 | UT | Maint - LD - 953 - Unit Test | [6 empty] | C | 147 | LOC | 17.17 | 15 | 1.2842 | 1 | 1.2842 | 2010-03-08 | 7 | 1.2306 | 2010-03-11 | 7 | 0.099827 | 16.4974 | 310.7555 | 25.2999 | 0.099827 | 2010-03-11 |  |  | 2010-03-15 | 1.2842 |  | 7 | 1.2842 | 1.2842 | Issue Fixes | Unit Test
Maint - LD - 953 | PM | Maint - LD - 953 - PM | [6 empty] | C | 147 | LOC | 17.17 | 4 | 0.34246 | 1 | 0.34246 | 2010-03-08 | 7 | 0.15778 | 2010-03-11 | 7 | 0.026621 | 16.4974 | 311.0979 | 25.2999 | 0.026621 | 2010-03-11 |  | 2010-03-29 | 2010-03-15 | 0.34246 |  | 7 | 0.34246 | 0.34246 | Issue Fixes | Postmortem
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Inspect the Document | [6 empty] | C | 5 | Text Pages | 1 | 100 | 5 | 1 | 5 | 2010-03-08 | 7 | 4.9522 | 2010-03-11 | 7 | 0.38867 | 16.4974 | 316.0979 | 25.2999 | 0.38867 | 2010-03-11 |  |  | 2010-05-10 | 6 |  | 7 | 5 | 5 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Inspect the Document | [6 empty] | C | 27 | Req Pages | 1.2 | 15 | 3.375 | 1 | 3.375 | 2010-03-08 | 7 | 3.2683 | 2010-03-12 | 7 | 0.26235 | 16.4974 | 319.4729 | 25.2999 | 0.26235 | 2010-03-12 |  |  | 2010-03-15 | 4.375 |  | 7 | 3.375 | 3.375 | Document-New Technical | Doc Inspection-NT
Quality Manager | MGMT | Quality Manager - Task (Week 7 - 3/8/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.21556 | 2010-03-12 | 7 | 0.077734 | 16.4974 | 320.4729 | 25.2999 | 0.077734 | 2010-03-12 |  |  | 2010-03-08 | 1 |  | 7 | 1 | 1 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Attend Inspection Meeting | [6 empty] | C | 8 | Req Pages | 1.2 | 15 | 1 | 1 | 1 | 2010-03-08 | 7 | 2.8633 | 2010-03-15 | 8 | 0.077734 | 16.4974 | 321.4729 | 25.2999 | 0.077734 | 2010-03-15 |  |  |  | 0 |  | 7 | 1 | 1
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | [6 empty] | C | 2 | Text Pages | 0.36 | 15 | 0.83333 | 1 | 0.83333 | 2010-03-08 | 7 | 0.31528 | 2010-03-16 | 8 | 0.064778 | 17.5235 | 322.3063 | 26.326 | 0.064778 | 2010-03-16 |  |  | 2010-03-01 | 0.83333 |  | 7 | 0.83333 | 0.83333 | Document-New Process | Doc Inspection-NP
Create Peer Review Script | PM | Create Peer Review Script - Doc PM-NP | [6 empty] | C | 2 | Text Pages | 0.36 | 5 | 0.27778 | 1 | 0.27778 | 2010-03-08 | 7 | 0.18889 | 2010-03-16 | 8 | 0.021593 | 17.5882 | 322.5841 | 26.3908 | 0.021593 | 2010-03-16 |  |  | 2010-03-08 | 0.27778 |  | 7 | 0.27778 | 0.27778 | Document-New Process | Doc PM-NP
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | [6 empty] | C | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-08 | 7 | 0.82694 | 2010-03-16 | 8 | 0.035766 | 18.0546 | 323.0442 | 26.8572 | 0.035766 | 2010-03-16 |  |  | 2010-03-22 | 0.4601 |  | 7 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 954 | UT | Maint - LD - 954 - Unit Test | [6 empty] | C | 79 | LOC | 17.17 | 15 | 0.69016 | 1 | 0.69016 | 2010-03-08 | 7 | 1.0158 | 2010-03-16 | 8 | 0.053649 | 18.6408 | 323.7343 | 27.4433 | 0.053649 | 2010-03-16 |  |  | 2010-03-22 | 0.69016 |  | 7 | 0.69016 | 0.69016 | Issue Fixes | Unit Test
Maint - LD - 954 | PM | Maint - LD - 954 - PM | [6 empty] | C | 79 | LOC | 17.17 | 4 | 0.18404 | 1 | 0.18404 | 2010-03-08 | 7 | 0.26139 | 2010-03-16 | 8 | 0.014306 | 18.9808 | 323.9184 | 27.7834 | 0.014306 | 2010-03-16 |  | 2010-03-29 | 2010-03-22 | 0.18404 |  | 7 | 0.18404 | 0.18404 | Issue Fixes | Postmortem
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | [6 empty] | B | 13 | LOC | 1 | 58 | 7.54 | 1 | 7.54 | 2010-03-08 | 7 | 6.6828 | 2010-03-10 | 7 | 0.58612 | 18.9808 | 331.4584 | 27.7834 | 0.58612 | 2010-03-10 |  |  | 2010-03-29 | 29 |  | 6 | 0.28711 | 7.2529 | Issue Fixes | Find and Fix
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | [6 empty] | B | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-08 | 7 | 2.6703 | 2010-03-15 | 8 | 0.34009 | 19.4473 | 335.8334 | 28.2498 | 0.34009 | 2010-03-15 |  |  | 2010-05-10 | 4.375 |  | 7 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Implementation | MGMT | Implementation - Task 6 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 0 | 0 | 2010-03-08 | 7 |  | 2010-03-15 | 8 | 0 | 21.1154 | 335.8334 | 29.918 | 0 | 2010-03-15 |  |  | 2010-03-15 | 1 |  | 7 | 0 | 0 | Task | Task
Maint - CM - Create Eng Build | MGMT | Maint - CM - Create Eng Build - Task - Build System | [6 empty] | B | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-08 | 7 | 5.6253 | 2010-03-23 | 9 | 0.4664 | 21.1932 | 341.8334 | 29.9957 | 0.4664 | 2010-03-23 |  |  | 2010-02-22 | 8 |  | 7 | 6 | 6 | Task | Task
Demo - Docs - Req Doc | CR | Demo - Docs - Req Doc - Doc Review-NT | [6 empty] | F | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-08 | 7 | 0.82722 | 2010-03-08 | 7 | 0.34009 | 21.5818 | 346.2084 | 30.3844 | 0.34009 | 2010-03-08 |  |  | 2010-03-01 | 4.375 |  | 6 | 4.0417 | 0.33333 | Document-New Technical | Doc Review-NT
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | F | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-03-08 | 7 | 0.27556 | 2010-03-08 | 7 | 0.032389 | 21.6984 | 346.625 | 30.501 | 0.032389 | 2010-03-08 |  |  | 2010-03-15 | 0.41667 |  | 7 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Demo - GUI - GUI Popups | CODE | Demo - GUI - GUI Popups - Find and Fix | [6 empty] | D | 40 | LOC | 1 | 58 | 23.2 | 1 | 23.2 | 2010-03-08 | 7 | 19.1833 | 2010-03-02 | 6 | 1.8034 | 21.6984 | 369.825 | 30.501 | 1.8034 | 2010-03-02 |  |  |  | 0 |  | 6 | 21.5871 | 1.6129 | Issue Fixes | Find and Fix
Design Manager | MGMT | Design Manager - Week 6 (03/01/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-03-08 | 7 | 0.00083333 | 2010-03-05 | 6 | 0.15547 | 21.6984 | 371.825 | 30.501 | 0.15547 | 2010-03-05 |  |  | 2010-02-22 | 2 |  | 7 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 6 (03/01/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.0016667 | 2010-03-05 | 6 | 0.077734 | 21.6984 | 372.825 | 30.501 | 0.077734 | 2010-03-05 |  |  | 2010-03-01 | 1 |  | 7 | 1 | 1 | Task | Task
CMMI Training | MGMT | CMMI Training (03/01/2010) | [6 empty] | D | 15 |  |  |  | 15 | 1 | 15 | 2010-03-08 | 7 | 15 | 2010-03-05 | 6 | 1.166 | 21.6984 | 387.825 | 30.501 | 1.166 | 2010-03-05 |  |  | 2010-03-01 | 15 |  | 7 | 15 | 15
Customer Interface Manager | MGMT | Customer Interface Manager - 3/15 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.11917 | 2010-03-17 | 8 | 0.077734 | 21.6984 | 388.825 | 30.501 | 0.077734 | 2010-03-17 |  |  | 2010-05-03 | 4 |  | 6 | 0.89626 | 0.10374 | Task | Task
Maint - LD - 985 | CODE | Maint - LD - 985 - Find and Fix | [6 empty] | G | 9 | LOC | 1 | 58 | 5.22 | 1 | 5.22 | 2010-03-08 | 7 | 0.38972 | 2010-03-22 | 9 | 0.40577 | 21.6984 | 394.045 | 30.501 | 0.40577 | 2010-03-22 |  |  |  | 0 |  | 7 | 5.22 | 5.22 | Issue Fixes | Find and Fix
Maint - LD - 985 | CR | Maint - LD - 985 - Code Review | [6 empty] | G | 9 | LOC | 1 | 10 | 0.9 | 1 | 0.9 | 2010-03-08 | 7 | 0.12306 | 2010-03-22 | 9 | 0.069961 | 21.7762 | 394.945 | 30.5787 | 0.069961 | 2010-03-22 |  |  |  | 0 |  | 7 | 0.9 | 0.9 | Issue Fixes | Code Review
Maint - LD - 985 | COMPILE | Maint - LD - 985 - Compile | [6 empty] | G | 9 | LOC | 1 | 3 | 0.27 | 1 | 0.27 | 2010-03-08 | 7 | 0.089167 | 2010-03-22 | 9 | 0.020988 | 21.9511 | 395.215 | 30.7536 | 0.020988 | 2010-03-22 |  |  |  | 0 |  | 7 | 0.27 | 0.27 | Issue Fixes | Compile
Maint - LD - 985 | CODEINSP | Maint - LD - 985 - Code Peer Review | [6 empty] | G | 9 | LOC | 1 | 10 | 0.9 | 1 | 0.9 | 2010-03-08 | 7 | 0.75 | 2010-03-22 | 9 | 0.069961 | 22.8528 | 396.115 | 31.6553 | 0.069961 | 2010-03-22 |  |  |  | 0 |  | 7 | 0.9 | 0.9 | Issue Fixes | Code Peer Review
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-08 | 7 | 0.14833 | 2010-03-22 | 9 | 0.035766 | 23.0083 | 396.5751 | 31.8108 | 0.035766 | 2010-03-22 |  |  | 2010-02-15 | 0.4601 |  | 7 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | [6 empty] | E | 4 | Text Pages | 1 | 100 | 4 | 1 | 4 | 2010-03-08 | 7 | 7.5778 | 2010-03-01 | 6 | 0.31094 | 23.0549 | 400.5751 | 31.8574 | 0.31094 | 2010-03-01 |  |  |  | 0 |  | 5 | 0.5 | 0.5 | Task | Task
Process Manager | MGMT | Process Manager - Week 6 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.41278 | 2010-03-05 | 6 | 0.077734 | 23.9566 | 401.5751 | 32.7592 | 0.077734 | 2010-03-05 |  |  | 2010-03-08 | 1 |  | 7 | 1 | 1 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 6 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-03-08 | 7 | 1.4208 | 2010-03-05 | 6 | 0.1166 | 23.9566 | 403.0751 | 32.7592 | 0.1166 | 2010-03-05 |  |  | 2010-03-15 | 1.5 |  | 7 | 1.5 | 1.5 | Task | Task
Demo - Docs - Test Cases | CODE | Demo - Docs - Test Cases - Draft-NT | [6 empty] | A | 35 | Text Pages | 1.2 | 30 | 8.75 | 1 | 8.75 | 2010-03-15 | 8 | 5.7711 | 2010-03-19 | 8 | 0.68017 | 23.9566 | 411.8251 | 32.9146 | 0.68017 | 2010-03-19 |  |  | 2010-03-08 | 8.75 |  | 7 | 5.3583 | 3.3917 | Document-New Technical | Draft-NT
Test Manager | MGMT | Test Manager - Task Week 9 Mar 22 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-15 | 8 | 4.0064 | 2010-03-26 | 9 | 0.077734 | 23.9566 | 412.8251 | 33.0701 | 0.077734 | 2010-03-26 |  |  | 2010-04-26 | 1 |  | 8 | 1 | 1 | Task | Task
Maint - LD - 955 | CODE | Maint - LD - 955 - Find and Fix | [6 empty] | C | 79 | LOC | 17.2 | 58 | 2.664 | 1 | 2.664 | 2010-03-15 | 8 | 2.9456 | 2010-03-16 | 8 | 0.20708 | 23.9566 | 415.4891 | 33.1167 | 0.20708 | 2010-03-16 |  |  |  | 0 |  | 7 | 1.7112 | 0.9528 | Issue Fixes | Find and Fix
Maint - LD - 955 | CR | Maint - LD - 955 - Code Review | [6 empty] | C | 79 | LOC | 17.2 | 10 | 0.4593 | 1 | 0.4593 | 2010-03-15 | 8 | 0.54722 | 2010-03-16 | 8 | 0.035703 | 23.9566 | 415.9484 | 33.2722 | 0.035703 | 2010-03-16 |  |  |  | 0 |  | 8 | 0.4593 | 0.4593 | Issue Fixes | Code Review
Maint - LD - 955 | COMPILE | Maint - LD - 955 - Compile | [6 empty] | C | 79 | LOC | 17.2 | 3 | 0.13779 | 1 | 0.13779 | 2010-03-15 | 8 | 0.10667 | 2010-03-16 | 8 | 0.010711 | 23.9566 | 416.0862 | 33.5054 | 0.010711 | 2010-03-16 |  |  |  | 0 |  | 8 | 0.13779 | 0.13779 | Issue Fixes | Compile
Quality Manager | MGMT | Quality Manager - Task (Week 8 - 3/15/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-15 | 8 | 3.4844 | 2010-03-22 | 9 | 0.077734 | 23.9566 | 417.0862 | 33.5676 | 0.077734 | 2010-03-22 |  |  | 2010-03-15 | 1 |  | 8 | 1 | 1 | Task | Task
Maint - LD - 958 | CODEINSP | Maint - LD - 958 - Code Peer Review | [6 empty] | C | 507 | LOC | 17.17 | 10 | 2.9528 | 0 | 0 | 2010-03-15 | 8 |  | 2010-03-22 | 9 | 0 | 23.9566 | 417.0862 | 33.8785 | 0 | 2010-03-22 |  |  | 2010-03-08 | 2.9528 |  | 8 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 967 | CODEINSP | Maint - LD - 967 - Code Peer Review | [6 empty] | C |  |  |  |  | 1 | 1 | 1 | 2010-03-15 | 8 | 0.8225 | 2010-03-23 | 9 | 0.077734 | 23.9566 | 418.0862 | 34.4615 | 0.077734 | 2010-03-23 |  |  |  | 0 |  | 8 | 1 | 1
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | [6 empty] | C | 79 | LOC | 17.2 | 10 | 0.4593 | 1 | 0.4593 | 2010-03-15 | 8 | 0.49806 | 2010-03-25 | 9 | 0.035703 | 23.9566 | 418.5455 | 34.617 | 0.035703 | 2010-03-25 |  |  |  | 0 |  | 8 | 0.4593 | 0.4593 | Issue Fixes | Code Peer Review
Maint - LD - 955 | UT | Maint - LD - 955 - Unit Test | [6 empty] | C | 79 | LOC | 17.2 | 15 | 0.68895 | 1 | 0.68895 | 2010-03-15 | 8 | 0.70694 | 2010-03-25 | 9 | 0.053555 | 23.9566 | 419.2344 | 34.6947 | 0.053555 | 2010-03-25 |  |  |  | 0 |  | 8 | 0.68895 | 0.68895 | Issue Fixes | Unit Test
Maint - LD - 955 | PM | Maint - LD - 955 - PM | [6 empty] | C | 79 | LOC | 17.2 | 4 | 0.18372 | 1 | 0.18372 | 2010-03-15 | 8 | 0.42556 | 2010-03-25 | 9 | 0.014281 | 23.9566 | 419.4182 | 34.7725 | 0.014281 | 2010-03-25 |  |  |  | 0 |  | 8 | 0.18372 | 0.18372 | Issue Fixes | Postmortem
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | [6 empty] | B | 37 | LOC | 1 | 58 | 21.46 | 1 | 21.46 | 2010-03-15 | 8 | 55.11 | 2010-03-25 | 9 | 1.6682 | 23.9566 | 440.8782 | 34.9279 | 1.6682 | 2010-03-25 |  |  | 2010-03-29 | 29 |  | 7 | 4.3721 | 17.0879 | Issue Fixes | Find and Fix
Implementation | MGMT | Implementation - Task 7 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-15 | 8 |  | 2010-03-26 | 9 | 0.077734 | 23.9566 | 441.8782 | 35.1611 | 0.077734 | 2010-03-26 |  |  | 2010-03-29 | 1 |  | 8 | 1 | 1 | Task | Task
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | [6 empty] | F | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-15 | 8 | 2.1819 | 2010-03-08 | 7 | 0.4664 | 23.9566 | 447.8782 | 35.2233 | 0.4664 | 2010-03-08 |  |  | 2010-03-22 | 6 |  | 7 | 2.25 | 3.75 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | [6 empty] | F | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-15 | 8 | 2.4717 | 2010-03-15 | 8 | 0.34009 | 23.9566 | 452.2532 | 35.8452 | 0.34009 | 2010-03-15 |  |  | 2010-03-01 | 4.375 |  | 8 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Demo - Docs - Req Doc | PM | Demo - Docs - Req Doc - Doc PM-NT | [6 empty] | F | 35 | Req Pages | 1.2 | 5 | 1.4583 | 1 | 1.4583 | 2010-03-15 | 8 | 0.22056 | 2010-03-16 | 8 | 0.11336 | 23.9566 | 453.7115 | 35.9229 | 0.11336 | 2010-03-16 |  |  | 2010-03-01 | 1.4583 |  | 8 | 1.4583 | 1.4583 | Document-New Technical | Doc PM-NT
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | [6 empty] | D | 2 | Text Pages | 0.36 | 15 | 0.83333 | 1 | 0.83333 | 2010-03-15 | 8 | 0.78667 | 2010-03-08 | 7 | 0.064778 | 23.9566 | 454.5448 | 37.4776 | 0.064778 | 2010-03-08 |  |  | 2010-03-15 | 0.83333 |  | 7 | 0.38712 | 0.44621 | Document-New Process | Doc Inspection-NP
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | [6 empty] | D | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-03-15 | 8 | 0.66944 | 2010-03-08 | 7 | 0.066552 | 23.9566 | 455.401 | 37.5554 | 0.066552 | 2010-03-08 |  |  | 2010-05-31 | 0.85614 |  | 8 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | [6 empty] | D | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-15 | 8 | 0.62167 | 2010-03-08 | 7 | 0.035766 | 23.9566 | 455.8611 | 38.1772 | 0.035766 | 2010-03-08 |  |  | 2010-05-31 | 0.4601 |  | 8 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | [6 empty] | D | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-15 | 8 | 2.4033 | 2010-03-09 | 7 | 0.4664 | 23.9566 | 461.8611 | 38.7991 | 0.4664 | 2010-03-09 |  |  | 2010-05-24 | 6 |  | 8 | 6 | 6 | Task | Task
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | [6 empty] | D | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-03-15 | 8 | 0.58583 | 2010-03-10 | 7 | 0.066552 | 23.9566 | 462.7172 | 38.8768 | 0.066552 | 2010-03-10 |  |  | 2010-05-24 | 0.85614 |  | 8 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Maint - LD - 967 | CODE | Maint - LD - 967 - Find and Fix | [6 empty] | G | 7 | LOC | 1 | 58 | 4.06 | 1 | 4.06 | 2010-03-15 | 8 | 0.091667 | 2010-03-22 | 9 | 0.3156 | 23.9566 | 466.7772 | 38.9092 | 0.3156 | 2010-03-22 |  |  |  | 0 |  | 7 | 1.1462 | 2.9138 | Issue Fixes | Find and Fix
Maint - LD - 967 | CR | Maint - LD - 967 - Code Review | [6 empty] | G | 7 | LOC | 1 | 10 | 0.7 | 1 | 0.7 | 2010-03-15 | 8 | 0.20444 | 2010-03-22 | 9 | 0.054414 | 23.9566 | 467.4772 | 39.2785 | 0.054414 | 2010-03-22 |  |  |  | 0 |  | 8 | 0.7 | 0.7 | Issue Fixes | Code Review
Maint - LD - 967 | COMPILE | Maint - LD - 967 - Compile | [6 empty] | G | 7 | LOC | 1 | 3 | 0.21 | 1 | 0.21 | 2010-03-15 | 8 | 0.085 | 2010-03-22 | 9 | 0.016324 | 23.9566 | 467.6872 | 39.3562 | 0.016324 | 2010-03-22 |  |  |  | 0 |  | 8 | 0.21 | 0.21 | Issue Fixes | Compile
Maint - LD - 967 | CODEINSP | Maint - LD - 967 - Code Peer Review | [6 empty] | G | 7 | LOC | 1 | 10 | 0.7 | 1 | 0.7 | 2010-03-15 | 8 | 0.28333 | 2010-03-22 | 9 | 0.054414 | 23.9566 | 468.3872 | 39.6671 | 0.054414 | 2010-03-22 |  |  |  | 0 |  | 8 | 0.7 | 0.7 | Issue Fixes | Code Peer Review
Maint - LD - 985 | UT | Maint - LD - 985 - Unit Test | [6 empty] | G | 9 | LOC | 1 | 15 | 1.35 | 1 | 1.35 | 2010-03-15 | 8 | 0.90389 | 2010-03-23 | 9 | 0.10494 | 23.9566 | 469.7372 | 40.289 | 0.10494 | 2010-03-23 |  |  |  | 0 |  | 8 | 1.35 | 1.35 | Issue Fixes | Unit Test
Process Manager | MGMT | Process Manager - Week 7 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-15 | 8 | 0.33389 | 2010-03-12 | 7 | 0.077734 | 23.9566 | 470.7372 | 40.9109 | 0.077734 | 2010-03-12 |  |  | 2010-03-15 | 1 |  | 7 | 0 | 1 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 7 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-03-15 | 8 | 1.6664 | 2010-03-12 | 7 | 0.1166 | 23.9566 | 472.2372 | 41.1441 | 0.1166 | 2010-03-12 |  |  | 2010-03-22 | 1.5 |  | 8 | 1.5 | 1.5 | Task | Task
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | [6 empty] | A | 35 | Text Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-22 | 9 | 3.5894 | 2010-04-02 | 10 | 0.34009 | 23.9566 | 476.6122 | 41.2218 | 0.34009 | 2010-04-02 |  |  | 2010-03-08 | 4.375 |  | 8 | 1.6083 | 2.7667 | Document-New Technical | Doc Review-NT
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework CODEINSP | [6 empty] | A |  |  |  |  | 2.3 | 1 | 2.3 | 2010-03-22 | 9 | 2.1714 | 2010-04-02 | 10 | 0.17879 | 23.9566 | 478.9122 | 41.5328 | 0.17879 | 2010-04-02 |  |  |  | 0 |  | 9 | 2.3 | 2.3
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | [6 empty] | C | 20 | LOC | 1 | 58 | 11.6 | 1 | 11.6 | 2010-03-22 | 9 | 9.3156 | 2010-03-26 | 9 | 0.90172 | 23.9566 | 490.5122 | 41.8437 | 0.90172 | 2010-03-26 |  |  | 2010-04-26 | 23.2 |  | 8 | 4.7181 | 6.8819 | Issue Fixes | Find and Fix
Quality Manager | MGMT | Quality Manager - Task (Week 9 - 3/22/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-22 | 9 | 0.71222 | 2010-03-29 | 10 | 0.077734 | 23.9566 | 491.5122 | 42.7765 | 0.077734 | 2010-03-29 |  |  | 2010-03-15 | 1 |  | 9 | 1 | 1 | Task | Task
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Peer Review | [6 empty] | C |  |  |  |  | 2.3 | 1 | 2.3 | 2010-03-22 | 9 | 2.0517 | 2010-03-31 | 10 | 0.17879 | 23.9566 | 493.8122 | 42.8542 | 0.17879 | 2010-03-31 |  |  |  | 0 |  | 9 | 2.3 | 2.3
Demo - Interface - Closure | CR | Demo - Interface - Closure - Code Review | [6 empty] | B | 50 | LOC | 1 | 10 | 5 | 1 | 5 | 2010-03-22 | 9 | 4.5747 | 2010-03-26 | 9 | 0.38867 | 23.9566 | 498.8122 | 43.1652 | 0.38867 | 2010-03-26 |  |  | 2010-03-29 | 5 |  | 8 | 3.9121 | 1.0879 | Issue Fixes | Code Review
Demo - Interface - Closure | COMPILE | Demo - Interface - Closure - Compile | [6 empty] | B | 50 | LOC | 1 | 3 | 1.5 | 1 | 1.5 | 2010-03-22 | 9 | 0.092778 | 2010-03-26 | 9 | 0.1166 | 24.7501 | 500.3122 | 43.9587 | 0.1166 | 2010-03-26 |  |  | 2010-03-29 | 1.5 |  | 9 | 1.5 | 1.5 | Issue Fixes | Compile
Demo - Inteface - HTML | CODE | Demo - Interface - HTML - Find and Fix | [6 empty] | B | 12 | LOC | 1 | 58 | 6.96 | 0 | 0 | 2010-03-22 | 9 |  | 2010-03-29 | 10 | 0 | 25.4303 | 500.3122 | 44.6389 | 0 | 2010-03-29 |  |  | 2010-04-19 | 6.96 |  | 9 | 0 | 0 | Issue Fixes | Find and Fix
Demo - Inteface - HTML | CR | Demo - Interface - HTML - Code Review | [6 empty] | B | 12 | LOC | 1 | 10 | 1.2 | 0 | 0 | 2010-03-22 | 9 |  | 2010-03-29 | 10 | 0 | 26.0522 | 500.3122 | 45.2608 | 0 | 2010-03-29 |  |  | 2010-04-19 | 1.2 |  | 9 | 0 | 0 | Issue Fixes | Code Review
Demo - Inteface - HTML | COMPILE | Demo - Interface - HTML - Compile | [6 empty] | B | 12 | LOC | 1 | 3 | 0.36 | 0 | 0 | 2010-03-22 | 9 |  | 2010-03-29 | 10 | 0 | 26.2854 | 500.3122 | 45.494 | 0 | 2010-03-29 |  |  | 2010-04-19 | 0.36 |  | 9 | 0 | 0 | Issue Fixes | Compile
Demo - Inteface - HTML | CODEINSP | Demo - Interface - HTML - Code Peer Review | [6 empty] | B | 12 | LOC | 1 | 10 | 1.2 | 0 | 0 | 2010-03-22 | 9 |  | 2010-03-29 | 10 | 0 | 26.6255 | 500.3122 | 45.834 | 0 | 2010-03-29 |  |  | 2010-04-19 | 1.2 |  | 9 | 0 | 0 | Issue Fixes | Code Peer Review
Demo - Inteface - HTML | UT | Demo - Interface - HTML - Unit Test | [6 empty] | B | 12 | LOC | 1 | 15 | 1.8 | 0 | 0 | 2010-03-22 | 9 |  | 2010-03-29 | 10 | 0 | 26.6579 | 500.3122 | 45.8664 | 0 | 2010-03-29 |  |  | 2010-04-19 | 1.8 |  | 9 | 0 | 0 | Issue Fixes | Unit Test
Demo - Inteface - HTML | PM | Demo - Interface - HTML - PM | [6 empty] | B | 12 | LOC | 1 | 4 | 0.48 | 0 | 0 | 2010-03-22 | 9 |  | 2010-03-29 | 10 | 0 | 27.1243 | 500.3122 | 46.3328 | 0 | 2010-03-29 |  | 2010-05-21 | 2010-04-19 | 0.48 |  | 9 | 0 | 0 | Issue Fixes | Postmortem
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review - Prepare Material | [6 empty] | B | 10 | LOC | 1 | 10 | 1 | 1 | 1 | 2010-03-22 | 9 | 0.96111 | 2010-03-29 | 10 | 0.077734 | 27.4644 | 501.3122 | 46.6729 | 0.077734 | 2010-03-29 |  |  | 2010-03-29 | 5 |  | 9 | 1 | 1 | Issue Fixes | Code Peer Review
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | [6 empty] | B | 15 | Req Pages | 1 | 15 | 2.25 | 1 | 2.25 | 2010-03-22 | 9 | 0.34722 | 2010-03-31 | 10 | 0.1749 | 27.5777 | 503.5622 | 46.7863 | 0.1749 | 2010-03-31 |  |  |  | 0 |  | 9 | 2.25 | 2.25 | Document-New Technical | Doc Inspection-NT
Demo - Interface - Process | CODE | Demo - Interface - Process - Find and Fix | [6 empty] | B | 20 | LOC | 1 | 58 | 11.6 | 1 | 11.6 | 2010-03-22 | 9 | 3.3708 | 2010-03-31 | 10 | 0.90172 | 27.9858 | 515.1622 | 47.1944 | 0.90172 | 2010-03-31 |  |  | 2010-04-12 | 11.6 |  | 9 | 11.6 | 11.6 | Issue Fixes | Find and Fix
Demo - Interface - Process | CR | Demo - Interface - Process - Code Review | [6 empty] | B | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-03-22 | 9 |  | 2010-03-31 | 10 | 0.15547 | 28.3356 | 517.1622 | 47.5442 | 0.15547 | 2010-03-31 |  |  | 2010-04-12 | 2 |  | 9 | 2 | 2 | Issue Fixes | Code Review
Demo - Interface - Process | COMPILE | Demo - Interface - Process - Compile | [6 empty] | B | 20 | LOC | 1 | 3 | 0.6 | 1 | 0.6 | 2010-03-22 | 9 |  | 2010-03-31 | 10 | 0.04664 | 28.5105 | 517.7622 | 47.7191 | 0.04664 | 2010-03-31 |  |  | 2010-04-12 | 0.6 |  | 9 | 0.6 | 0.6 | Issue Fixes | Compile
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | [6 empty] | F | 15 | Req Pages | 1 | 35 | 5.25 | 1 | 5.25 | 2010-03-22 | 9 | 4.9086 | 2010-03-22 | 9 | 0.4081 | 28.6854 | 523.0122 | 47.894 | 0.4081 | 2010-03-22 |  |  |  | 0 |  | 8 | 2.4167 | 2.8333 | Document-New Technical | Research-NT
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | [6 empty] | F | 15 | Req Pages | 1 | 30 | 4.5 | 1 | 4.5 | 2010-03-22 | 9 | 11.2939 | 2010-03-24 | 9 | 0.3498 | 28.6854 | 527.5122 | 47.9523 | 0.3498 | 2010-03-24 |  |  |  | 0 |  | 9 | 4.5 | 4.5 | Document-New Technical | Draft-NT
Demo - Docs - Req Doc - Rework | CR | Demo - Docs - Req Doc - Rework - Doc Review-NT | [6 empty] | F | 15 | Req Pages | 1 | 15 | 2.25 | 1 | 2.25 | 2010-03-22 | 9 | 1.8083 | 2010-03-25 | 9 | 0.1749 | 28.6854 | 529.7622 | 49.1183 | 0.1749 | 2010-03-25 |  |  |  | 0 |  | 9 | 2.25 | 2.25 | Document-New Technical | Doc Review-NT
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | [6 empty] | F | 15 | Req Pages | 1 | 15 | 2.25 | 1 | 2.25 | 2010-03-22 | 9 | 1.655 | 2010-03-31 | 10 | 0.1749 | 28.6854 | 532.0122 | 50.2843 | 0.1749 | 2010-03-31 |  |  |  | 0 |  | 9 | 2.25 | 2.25 | Document-New Technical | Doc Inspection-NT
Demo - GUI - AIM Interface | CODE | Demo - GUI - AIM Interface - Find and Fix | [6 empty] | D | 40 | LOC | 1 | 58 | 23.2 | 1 | 23.2 | 2010-03-22 | 9 | 19.8864 | 2010-03-11 | 7 | 1.8034 | 28.6854 | 555.2122 | 50.6536 | 1.8034 | 2010-03-11 |  |  |  | 0 |  | 8 | 15.3814 | 7.8186 | Issue Fixes | Find and Fix
Design Manager | MGMT | Design Manager - Week 7 (03/08/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-03-22 | 9 |  | 2010-03-12 | 7 | 0.15547 | 28.6854 | 557.2122 | 50.6967 | 0.15547 | 2010-03-12 |  |  | 2010-03-01 | 2 |  | 9 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 7 (03/08/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-22 | 9 |  | 2010-03-12 | 7 | 0.077734 | 28.6854 | 558.2122 | 50.7939 | 0.077734 | 2010-03-12 |  |  | 2010-03-01 | 1 |  | 9 | 1 | 1 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | [6 empty] | D | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-22 | 9 | 2.9225 | 2010-03-15 | 8 | 0.34009 | 28.6854 | 562.5872 | 50.8263 | 0.34009 | 2010-03-15 |  |  | 2010-03-08 | 4.375 |  | 9 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | [6 empty] | D | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-22 | 9 | 0.66611 | 2010-03-15 | 8 | 0.035766 | 28.6854 | 563.0473 | 50.8587 | 0.035766 | 2010-03-15 |  |  | 2010-05-31 | 0.4601 |  | 9 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Desktop | CR | Demo - GUI - GUI Desktop - Code Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-03-22 | 9 | 5.9986 | 2010-03-16 | 8 | 0.31094 | 28.6854 | 567.0473 | 50.8695 | 0.31094 | 2010-03-16 |  |  |  | 0 |  | 9 | 4 | 4 | Issue Fixes | Code Review
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | [6 empty] | D | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-22 | 9 | 0.49972 | 2010-03-17 | 8 | 0.035766 | 28.6854 | 567.5074 | 51.2387 | 0.035766 | 2010-03-17 |  |  | 2010-05-24 | 0.4601 |  | 9 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Design Manager | MGMT | Design Manager - Week 8 (03/15/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-03-22 | 9 | 1.8319 | 2010-03-19 | 8 | 0.15547 | 28.6854 | 569.5074 | 51.5788 | 0.15547 | 2010-03-19 |  |  | 2010-03-08 | 2 |  | 9 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 8 (03/15/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-22 | 9 | 0.33194 | 2010-03-19 | 8 | 0.077734 | 28.6854 | 570.5074 | 52.978 | 0.077734 | 2010-03-19 |  |  | 2010-03-08 | 1 |  | 9 | 1 | 1 | Task | Task
Maint - LD - 985 | PM | Maint - LD - 985 - PM | [6 empty] | G | 9 | LOC | 1 | 4 | 0.36 | 1 | 0.36 | 2010-03-22 | 9 | 0.35472 | 2010-03-23 | 9 | 0.027984 | 28.6854 | 570.8674 | 53.2579 | 0.027984 | 2010-03-23 |  |  |  | 0 |  | 8 | 0.12615 | 0.23385 | Issue Fixes | Postmortem
Process Manager | MGMT | Process Manager - Week 8 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-22 | 9 | 0.37972 | 2010-03-19 | 8 | 0.077734 | 28.6854 | 571.8674 | 53.6776 | 0.077734 | 2010-03-19 |  |  | 2010-04-05 | 1 |  | 8 | 0.5 | 0.5 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 8 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-03-22 | 9 | 1.3628 | 2010-03-19 | 8 | 0.1166 | 28.6854 | 573.3674 | 54.1534 | 0.1166 | 2010-03-19 |  |  | 2010-04-05 | 1.5 |  | 9 | 1.5 | 1.5 | Task | Task
Process Manager | MGMT | Process Manager - Week 9 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-22 | 9 | 0.23556 | 2010-03-26 | 9 | 0.077734 | 28.6854 | 574.3674 | 54.3772 | 0.077734 | 2010-03-26 |  |  | 2010-03-22 | 1 |  | 9 | 1 | 1 | Task | Task
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | [6 empty] | A | 8 | Text Pages |  |  | 4 | 1 | 4 | 2010-03-29 | 10 | 9.5353 | 2010-04-02 | 10 | 0.31094 | 28.6854 | 578.3674 | 54.455 | 0.31094 | 2010-04-02 |  |  | 2010-04-05 | 8 |  | 9 | 0.93333 | 3.0667 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 10 Mar 29 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-29 | 10 | 0.96722 | 2010-04-02 | 10 | 0.077734 | 28.6854 | 579.3674 | 54.6882 | 0.077734 | 2010-04-02 |  |  | 2010-04-26 | 1 |  | 10 | 1 | 1 | Task | Task
Demo - Interface - Msg | CODE | Demo - Interface - Convert It- Msg Env Database | [6 empty] | C | 20 | LOC | 1 | 58 | 11.6 | 1 | 11.6 | 2010-03-29 | 10 | 7.4069 | 2010-04-01 | 10 | 0.90172 | 28.6854 | 590.9674 | 55.038 | 0.90172 | 2010-04-01 |  |  |  | 0 |  | 9 | 5.8181 | 5.7819
Demo - Inteface - HTML | CODEINSP | Demo - Interface - Convert It - Code Peer Review | [6 empty] | C | 12 | LOC | 1 | 10 | 1.2 | 0 | 0 | 2010-03-29 | 10 |  | 2010-04-01 | 10 | 0 | 28.6854 | 590.9674 | 55.4344 | 0 | 2010-04-01 |  |  | 2010-02-22 | 1.2 |  | 10 | 0 | 0 | Issue Fixes | Code Peer Review
Demo - Interface - Msg | CR | Demo - Interface - Convert It - Code Review | [6 empty] | C | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-03-29 | 10 | 5.8081 | 2010-04-02 | 10 | 0.31094 | 28.6854 | 594.9674 | 55.621 | 0.31094 | 2010-04-02 |  |  | 2010-05-03 | 4 |  | 10 | 4 | 4 | Issue Fixes | Code Review
Demo - Interface - Msg | [8 empty] | C | [6 empty] | 0 | 2010-03-29 | 10 |  |  |  | 0 | 28.6854 | 594.9674 | 56.4822 | 0 | 2010-03-29 | 2010-03-29 |  |  | 0 |  | 10 | 0 | 0
Demo - Interface - Msg | COMPILE | Demo - Interface - Convert It - Compile | [6 empty] | C | 40 | LOC | 1 | 3 | 1.2 | 1 | 1.2 | 2010-03-29 | 10 | 0.69528 |  |  | 0 | 28.6854 | 596.1674 | 56.681 | 0.093281 | 2010-09-20 | 2010-03-29 |  | 2010-05-03 | 1.2 |  | 10 | 1.2 | 1.2 | Issue Fixes | Compile
Demo - Interface - Closure | CODEINSP | Demo - Interface - Interface Closure - Code Peer Review | [6 empty] | C | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-03-29 | 10 |  |  |  | 0 | 28.6854 | 600.1674 | 56.8798 | 0.31094 | 2010-09-27 | 2010-03-29 |  | 2010-02-15 | 4 |  | 10 | 4 | 4 | Issue Fixes | Code Peer Review
Quality Manager | MGMT | Quality Manager - Task (Week 10 - 3/29/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-29 | 10 |  |  |  | 0 | 28.6854 | 601.1674 | 56.946 | 0.077734 | 2010-10-04 | 2010-03-29 |  | 2010-03-29 | 1 |  | 10 | 1 | 1 | Task | Task
Quality Manager | [8 empty] | C | [6 empty] | 0 | 2010-03-29 | 10 |  |  |  | 0 | 28.6854 | 601.1674 | 57.1792 | 0 | 2010-10-04 | 2010-03-29 |  |  | 0 |  | 10 | 0 | 0
Demo - Interface - Msg | CODE | Demo - Interface - Msg - Find and Fix | [6 empty] | B | 20 | LOC | 1 | 58 | 11.6 | 1 | 11.6 | 2010-03-29 | 10 | 12.0939 | 2010-03-31 | 10 | 0.90172 | 28.6854 | 612.7674 | 57.8788 | 0.90172 | 2010-03-31 |  |  | 2010-04-05 | 11.6 |  | 9 | 1.9621 | 9.6379 | Issue Fixes | Find and Fix
Implementation | MGMT | Implementation - Task 8 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 0 | 0 | 2010-03-29 | 10 |  | 2010-04-01 | 10 | 0 | 29.547 | 612.7674 | 58.7404 | 0 | 2010-04-01 |  |  | 2010-04-05 | 1 |  | 10 | 0 | 0 | Task | Task
Maint - CM - Create Eng Build | MGMT | Maint - CM - Create Eng Build - Task - Finalize Build | [6 empty] | B | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-03-29 | 10 |  |  |  | 0 | 29.5828 | 614.7674 | 58.7761 | 0.15547 | 2010-09-20 | 2010-03-29 |  | 2010-02-22 | 8 |  | 10 | 2 | 2 | Task | Task
Demo - Interface - Msg | CR | Demo - Interface - Msg - Code Review | [6 empty] | B | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-03-29 | 10 | 4.4897 |  |  | 0 | 29.6493 | 616.7674 | 58.8427 | 0.15547 | 2010-09-20 | 2010-03-29 |  | 2010-04-05 | 2 |  | 10 | 2 | 2 | Issue Fixes | Code Review
Demo - Interface - Msg | COMPILE | Demo - Interface - Msg - Compile | [6 empty] | B | 20 | LOC | 1 | 3 | 0.6 | 1 | 0.6 | 2010-03-29 | 10 |  |  |  | 0 | 29.667 | 617.3674 | 58.8603 | 0.04664 | 2010-09-27 | 2010-03-29 |  | 2010-04-05 | 0.6 |  | 10 | 0.6 | 0.6 | Issue Fixes | Compile
Demo - Interface - Msg | CODEINSP | Demo - Interface - Msg - Code Peer Review | [6 empty] | B | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-03-29 | 10 |  |  |  | 0 | 29.8224 | 619.3674 | 59.0158 | 0.15547 | 2010-09-27 | 2010-03-29 |  | 2010-04-12 | 2 |  | 10 | 2 | 2 | Issue Fixes | Code Peer Review
Demo - Interface - Msg | UT | Demo - Interface - Msg - Unit Test | [6 empty] | B | 20 | LOC | 1 | 15 | 3 | 1 | 3 | 2010-03-29 | 10 |  |  |  | 0 | 29.9002 | 622.3674 | 59.0935 | 0.2332 | 2010-10-04 | 2010-03-29 |  | 2010-04-12 | 3 |  | 10 | 3 | 3 | Issue Fixes | Unit Test
Demo - Interface - Msg | PM | Demo - Interface - Msg - PM | [6 empty] | B | 20 | LOC | 1 | 4 | 0.8 | 1 | 0.8 | 2010-03-29 | 10 |  |  |  | 0 | 30.6386 | 623.1674 | 59.832 | 0.062187 | 2010-10-04 | 2010-03-29 | 2010-05-21 | 2010-04-12 | 0.8 |  | 10 | 0.8 | 0.8 | Issue Fixes | Postmortem
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | [6 empty] | F | 15 | Req Pages | 1 | 5 | 0.75 | 1 | 0.75 | 2010-03-29 | 10 | 1.9236 |  |  | 0 | 31.0079 | 623.9174 | 60.2013 | 0.058301 | 2010-09-20 | 2010-04-05 |  |  | 0 |  | 9 | 0.16667 | 0.58333 | Document-New Technical | Doc PM-NT
Demo - GUI - GUI Popups | CR | Demo - GUI - GUI Popups - Code Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-03-29 | 10 | 10.2156 | 2010-03-19 | 8 | 0.31094 | 31.1633 | 627.9174 | 60.3567 | 0.31094 | 2010-03-19 |  |  |  | 0 |  | 9 | 0.88618 | 3.1138 | Issue Fixes | Code Review
Maint - LD - 958 | CODEINSP | Maint - LD - 958 - Code Peer Review | [6 empty] | D | 507 | LOC | 17.17 | 10 | 2.9528 | 0 | 0 | 2010-03-29 | 10 |  | 2010-03-22 | 9 | 0 | 31.2411 | 627.9174 | 60.4345 | 0 | 2010-03-22 |  |  | 2010-05-24 | 2.9528 |  | 10 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 967 | CODEINSP | Maint - LD - 967 CODEINSP | [6 empty] | D |  | LOC |  |  | 1 | 1 | 1 | 2010-03-29 | 10 | 0.7275 | 2010-03-23 | 9 | 0.077734 | 31.2735 | 628.9174 | 60.4668 | 0.077734 | 2010-03-23 |  |  |  | 0 |  | 10 | 1 | 1
Demo - GUI - AIM Interface | CR | Demo - GUI - AIM Interface - Code Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-03-29 | 10 | 8.0358 | 2010-03-24 | 9 | 0.31094 | 31.3059 | 632.9174 | 60.4992 | 0.31094 | 2010-03-24 |  |  |  | 0 |  | 10 | 4 | 4 | Issue Fixes | Code Review
Demo - Docs - HLD Doc | DLD | Demo - Docs - HLD Doc - Research-NT | [6 empty] | D | 38 | HLD Pages | 1.2 | 35 | 11.0833 | 1 | 11.0833 | 2010-03-29 | 10 | 14.5725 | 2010-03-24 | 9 | 0.86155 | 31.4613 | 644.0008 | 60.6547 | 0.86155 | 2010-03-24 |  |  | 2010-02-22 | 11.0833 |  | 10 | 11.0833 | 11.0833 | Document-New Technical | Research-NT
Planning Manager | MGMT | Planning Manager - Week 9 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-03-29 | 10 | 0.97361 | 2010-03-26 | 9 | 0.1166 | 31.6909 | 645.5008 | 60.8842 | 0.1166 | 2010-03-26 |  |  | 2010-03-29 | 1.5 |  | 9 | 0 | 1.5 | Task | Task
Process Manager | MGMT | Process Manager - Week 10 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-29 | 10 | 0.093889 | 2010-04-02 | 10 | 0.077734 | 31.7686 | 646.5008 | 60.962 | 0.077734 | 2010-04-02 |  |  | 2010-04-12 | 1 |  | 10 | 1 | 1 | Task | Task
Maint - Test Eng Build | MGMT | Maint - Test Eng Build - Task | [6 empty] | A | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-04-05 | 11 |  |  |  | 0 | 33.572 | 654.5008 | 62.7654 | 0.62187 | 2010-11-01 | 2010-04-05 | 2010-03-29 | 2010-04-12 | 8 |  | 10 | 1.9333 | 6.0667 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 11 Apr 5 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 33.9413 | 655.5008 | 63.1346 | 0.077734 | 2010-11-01 | 2010-04-05 |  | 2010-04-26 | 1 |  | 11 | 1 | 1 | Task | Task
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 34.0643 | 656.5008 | 63.2577 | 0.077734 | 2010-11-08 | 2010-04-05 |  | 2010-04-12 | 1 |  | 11 | 1 | 1
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 34.0967 | 657.5008 | 63.2901 | 0.077734 | 2010-10-04 | 2010-04-05 |  | 2010-04-05 | 1 |  | 10 | 0.018132 | 0.98187
Demo - Interface - Process | CODEINSP | Demo - Interface - Taclink Process - Code Peer Review | [6 empty] | C | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-04-05 | 11 |  |  |  | 0 | 35.9002 | 659.5008 | 65.0935 | 0.15547 | 2010-10-11 | 2010-04-05 |  | 2010-02-15 | 2 |  | 11 | 2 | 2 | Issue Fixes | Code Peer Review
Quality Manager | MGMT | Quality Manager - Task (Week 11 - 4/5/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 36.0556 | 660.5008 | 65.249 | 0.077734 | 2010-10-11 | 2010-04-05 |  | 2010-04-05 | 1 |  | 11 | 1 | 1 | Task | Task
Quality Manager | [8 empty] | C | [6 empty] | 0 | 2010-04-05 | 11 |  |  |  | 0 | 36.1334 | 660.5008 | 65.3267 | 0 | 2010-10-11 | 2010-04-05 |  |  | 0 |  | 11 | 0 | 0
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review | [6 empty] | B | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-05 | 11 |  |  |  | 0 | 37.2994 | 664.5008 | 66.4928 | 0.31094 | 2010-10-11 | 2010-04-05 |  | 2010-03-29 | 5 |  | 10 | 1.9621 | 2.0379 | Issue Fixes | Code Peer Review
Demo - Interface - Closure | UT | Demo - Interface - Closure - Unit Test | [6 empty] | B | 50 | LOC | 1 | 15 | 7.5 | 1 | 7.5 | 2010-04-05 | 11 |  |  |  | 0 | 37.3642 | 672.0008 | 66.5575 | 0.58301 | 2010-10-18 | 2010-04-05 |  | 2010-04-05 | 7.5 |  | 11 | 7.5 | 7.5 | Issue Fixes | Unit Test
Demo - Interface - Closure | PM | Demo - Interface - Closure - PM | [6 empty] | B | 50 | LOC | 1 | 4 | 2 | 1 | 2 | 2010-04-05 | 11 |  |  |  | 0 | 37.4307 | 674.0008 | 66.6241 | 0.15547 | 2010-10-25 | 2010-04-05 | 2010-05-21 | 2010-04-05 | 2 |  | 11 | 2 | 2 | Issue Fixes | Postmortem
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 37.4665 | 675.0008 | 66.6599 | 0.077734 | 2010-10-25 | 2010-04-05 |  | 2010-04-05 | 1 |  | 11 | 1 | 1
Implementation | MGMT | Implementation - Task 9 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 37.9329 | 676.0008 | 67.1263 | 0.077734 | 2010-10-25 | 2010-04-05 |  | 2010-04-05 | 1 |  | 11 | 1 | 1 | Task | Task
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | [6 empty] | B | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-04-05 | 11 | 0.30417 |  |  | 0 | 37.9994 | 678.0008 | 67.1928 | 0.15547 | 2010-11-01 | 2010-04-05 |  | 2010-04-19 | 2 |  | 11 | 2 | 2 | Issue Fixes | Code Peer Review
Demo - Interface - Process | UT | Demo - Interface - Process - Unit Test | [6 empty] | B | 20 | LOC | 1 | 15 | 3 | 1 | 3 | 2010-04-05 | 11 |  |  |  | 0 | 39.8029 | 681.0008 | 68.9962 | 0.2332 | 2010-11-01 | 2010-04-05 |  | 2010-04-19 | 3 |  | 11 | 3 | 3 | Issue Fixes | Unit Test
Demo - Interface - Process | PM | Demo - Interface - Process - PM | [6 empty] | B | 20 | LOC | 1 | 4 | 0.8 | 1 | 0.8 | 2010-04-05 | 11 | 0.13194 |  |  | 0 | 39.9583 | 681.8008 | 69.1517 | 0.062187 | 2010-11-08 | 2010-04-05 | 2010-05-21 | 2010-04-19 | 0.8 |  | 11 | 0.8 | 0.8 | Issue Fixes | Postmortem
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | [6 empty] | F |  | Text Pages | 1 |  | 15 | 1 | 15 | 2010-04-05 | 11 | 7.5172 |  |  | 0 | 40.0361 | 696.8008 | 69.2294 | 1.166 | 2010-11-15 | 2010-04-12 |  |  | 0 |  | 10 | 11.4167 | 3.5833
Demo - Docs - HLD Doc | CODE | Demo - Docs - HLD Doc - Draft-NT | [6 empty] | D | 38 | HLD Pages | 1.2 | 30 | 9.5 | 1 | 9.5 | 2010-04-05 | 11 | 9.805 | 2010-03-26 | 9 | 0.73847 | 40.3762 | 706.3008 | 69.5695 | 0.73847 | 2010-03-26 |  |  | 2010-02-22 | 9.5 |  | 10 | 4.8028 | 4.6972 | Document-New Technical | Draft-NT
Design Manager | MGMT | Design Manager - Week 9 (03/22/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-05 | 11 | 1.9561 | 2010-03-26 | 9 | 0.15547 | 40.4119 | 708.3008 | 69.6053 | 0.15547 | 2010-03-26 |  |  | 2010-03-15 | 2 |  | 11 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 9 (03/22/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 | 0.66833 | 2010-03-26 | 9 | 0.077734 | 40.7229 | 709.3008 | 69.9162 | 0.077734 | 2010-03-26 |  |  | 2010-03-15 | 1 |  | 11 | 1 | 1 | Task | Task
Demo - GUI - AIM Interface | COMPILE | Demo - GUI - AIM Interface - Compile | [6 empty] | D | 40 | LOC | 1 | 3 | 1.2 | 1 | 1.2 | 2010-04-05 | 11 | 0.145 | 2010-03-26 | 9 | 0.093281 | 40.7586 | 710.5008 | 69.952 | 0.093281 | 2010-03-26 |  |  |  | 0 |  | 11 | 1.2 | 1.2 | Issue Fixes | Compile
Demo - GUI - GUI Desktop | COMPILE | Demo - GUI - GUI Desktop - Compile | [6 empty] | D | 40 | LOC | 1 | 3 | 1.2 | 1 | 1.2 | 2010-04-05 | 11 | 0.11972 | 2010-03-26 | 9 | 0.093281 | 40.9141 | 711.7008 | 70.1075 | 0.093281 | 2010-03-26 |  |  |  | 0 |  | 11 | 1.2 | 1.2 | Issue Fixes | Compile
Demo - GUI - GUI Popups | COMPILE | Demo - GUI - GUI Popups - Compile | [6 empty] | D | 40 | LOC | 1 | 3 | 1.2 | 1 | 1.2 | 2010-04-05 | 11 | 0.17028 | 2010-03-26 | 9 | 0.093281 | 40.9918 | 712.9008 | 70.1852 | 0.093281 | 2010-03-26 |  |  |  | 0 |  | 11 | 1.2 | 1.2 | Issue Fixes | Compile
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 0 | 0 | 2010-04-05 | 11 |  | 2010-03-29 | 10 | 0 | 41.3028 | 712.9008 | 70.4961 | 0 | 2010-03-29 |  |  | 2010-06-07 | 1.2 |  | 11 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 998 | CODE | Maint - LD - 998 Find and Fix | [6 empty] | D | 12 | LOC | 1 | 58 | 6.96 | 1 | 6.96 | 2010-04-05 | 11 | 2.1233 | 2010-03-30 | 10 | 0.54103 | 41.3028 | 719.8608 | 70.4961 | 0.54103 | 2010-03-30 |  |  |  | 0 |  | 11 | 6.96 | 6.96
Maint - LD - 998 | CR | Maint - LD - 998 Code Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 1 | 1.2 | 2010-04-05 | 11 | 0.29833 | 2010-03-30 | 10 | 0.093281 | 41.3805 | 721.0608 | 70.5739 | 0.093281 | 2010-03-30 |  |  |  | 0 |  | 11 | 1.2 | 1.2
Maint - LD - 998 | COMPILE | Maint - LD - 998 Compile | [6 empty] | D | 12 | LOC | 1 | 3 | 0.36 | 1 | 0.36 | 2010-04-05 | 11 | 0.031944 | 2010-03-30 | 10 | 0.027984 | 41.6914 | 721.4208 | 70.8848 | 0.027984 | 2010-03-30 |  |  |  | 0 |  | 11 | 0.36 | 0.36
Maint - LD - 998 | CODEINSP | Maint - LD - 998 Code Peer Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 1 | 1.2 | 2010-04-05 | 11 | 0.24389 | 2010-03-30 | 10 | 0.093281 | 42.553 | 722.6208 | 71.7464 | 0.093281 | 2010-03-30 |  |  |  | 0 |  | 11 | 1.2 | 1.2
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | [6 empty] | G | 507 | LOC | 17.17 | 58 | 17.1264 | 1 | 17.1264 | 2010-04-05 | 11 | 10.2069 | 2010-03-23 | 9 | 1.3313 | 43.2915 | 739.7471 | 72.4848 | 1.3313 | 2010-03-23 |  |  | 2010-03-08 | 17.1264 |  | 9 | 7.7662 | 1.3602 | Issue Fixes | Find and Fix
Maint - LD - 967 | UT | Maint - LD - 967 - Unit Test | [6 empty] | G | 7 | LOC | 1 | 15 | 1.05 | 1 | 1.05 | 2010-04-05 | 11 | 2.6842 | 2010-03-23 | 9 | 0.081621 | 43.4469 | 740.7971 | 72.6403 | 0.081621 | 2010-03-23 |  |  |  | 0 |  | 11 | 1.05 | 1.05 | Issue Fixes | Unit Test
Maint - LD - 967 | PM | Maint - LD - 967 - PM | [6 empty] | G | 7 | LOC | 1 | 4 | 0.28 | 1 | 0.28 | 2010-04-05 | 11 | 0.13333 | 2010-03-23 | 9 | 0.021766 | 43.5247 | 741.0771 | 72.718 | 0.021766 | 2010-03-23 |  |  |  | 0 |  | 11 | 0.28 | 0.28 | Issue Fixes | Postmortem
Customer Interface Manager | MGMT | Customer Interface Manager - 3/22 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  | 2010-03-25 | 9 | 0.077734 | 43.6179 | 742.0771 | 72.8113 | 0.077734 | 2010-03-25 |  |  | 2010-05-03 | 4 |  | 11 | 1 | 1 | Task | Task
Maint - CM - Delivery Letters | MGMT | Maint - CM - Delivery Letters - Task | [6 empty] | G | 4 | Text Pages | 1 | 100 | 4 | 1 | 4 | 2010-04-05 | 11 |  |  |  | 0 | 43.7112 | 746.0771 | 72.9046 | 0.31094 | 2010-09-27 | 2010-04-05 |  | 2010-02-08 | 4 |  | 11 | 4 | 4 | Task | Task
Planning Manager | MGMT | Planning Manager - Week 10 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-04-05 | 11 | 0.80306 | 2010-04-02 | 10 | 0.1166 | 43.8045 | 747.5771 | 72.9979 | 0.1166 | 2010-04-02 |  |  | 2010-04-12 | 1.5 |  | 10 | 0.5 | 1 | Task | Task
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  |  |  | 0 | 43.8045 | 748.5771 | 72.9979 | 0.077734 | 2010-10-04 | 2010-04-05 |  | 2010-03-29 | 1 |  | 11 | 1 | 1 | Task | Task
Process Manager | MGMT | Process Manager - Week 11 | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 | 0.23694 |  |  | 0 | 44.3455 | 749.5771 | 73.5389 | 0.077734 | 2010-10-11 | 2010-04-05 |  | 2010-04-19 | 1 |  | 11 | 1 | 1 | Task | Task
Maint - Val Final Builds w/ F | MGMT | Maint - Val Final Builds w/ F - Task | [6 empty] | A | 8 | Text Pages |  |  | 4 | 1 | 4 | 2010-04-12 | 12 |  |  |  | 0 | 44.4388 | 753.5771 | 73.6322 | 0.31094 | 2010-11-22 | 2010-04-12 |  | 2010-04-05 | 8 |  | 11 | 1.9333 | 2.0667 | Task | Task
Demo - Docs - Test Cases | CODEINSP | Demo - Docs - Test Cases - Doc Inspection-NT | [6 empty] | A | 35 | Text Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-04-12 | 12 |  |  |  | 0 | 44.4668 | 757.9521 | 73.6602 | 0.34009 | 2010-12-13 | 2010-04-12 |  | 2010-03-15 | 4.375 |  | 12 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Demo - Docs - Test Cases | PM | Demo - Docs - Test Cases - Doc PM-NT | [6 empty] | A | 35 | Text Pages | 1.2 | 5 | 1.4583 | 1 | 1.4583 | 2010-04-12 | 12 |  |  |  | 0 | 44.5601 | 759.4105 | 73.7535 | 0.11336 | 2010-12-20 | 2010-04-12 | 2010-05-21 | 2010-03-15 | 1.4583 |  | 12 | 1.4583 | 1.4583 | Document-New Technical | Doc PM-NT
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | A | 38 | HLD Pages |  |  | 2 | 1 | 2 | 2010-04-12 | 12 |  |  |  | 0 | 45.1011 | 761.4105 | 74.2945 | 0.15547 | 2010-12-27 | 2010-04-12 |  | 2010-03-15 | 2 |  | 12 | 2 | 2 | Document-New Technical | Doc Inspection-NT
Demo - GUI - Closure Design | CODEINSP | Demo - GUI - Closure Design - Doc Inspection-NT | [6 empty] | A | 38 | Text Pages |  |  | 2 | 0 | 0 | 2010-04-12 | 12 |  |  |  | 0 | 45.1944 | 761.4105 | 74.3878 | 0 | 2010-12-27 | 2010-04-12 |  | 2010-03-29 | 2 |  | 12 | 0 | 0 | Document-New Technical | Doc Inspection-NT
Demo - Interface - Msg | CODEINSP | Demo - Interface - Convert It - Code Peer Review | [6 empty] | C | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-12 | 12 |  |  |  | 0 | 45.2224 | 765.4105 | 74.4158 | 0.31094 | 2010-10-18 | 2010-04-12 |  | 2010-05-03 | 4 |  | 11 | 2.4181 | 1.5819 | Issue Fixes | Code Peer Review
Demo - Interface - Msg | UT | Demo - Interface - Convert It - Unit Test | [6 empty] | C | 40 | LOC | 1 | 15 | 6 | 1 | 6 | 2010-04-12 | 12 |  |  |  | 0 | 45.3157 | 771.4105 | 74.509 | 0.4664 | 2010-11-01 | 2010-04-12 |  | 2010-05-03 | 6 |  | 12 | 6 | 6 | Issue Fixes | Unit Test
Demo - Interface - Msg | PM | Demo - Interface - Convert It - PM | [6 empty] | C | 40 | LOC | 1 | 4 | 1.6 | 1 | 1.6 | 2010-04-12 | 12 |  |  |  | 0 | 45.6849 | 773.0105 | 74.8783 | 0.12437 | 2010-11-08 | 2010-04-12 | 2010-05-21 | 2010-05-03 | 1.6 |  | 12 | 1.6 | 1.6 | Issue Fixes | Postmortem
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | C | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-04-12 | 12 |  |  |  | 0 | 46.2259 | 777.7605 | 75.4193 | 0.36924 | 2010-11-15 | 2010-04-12 |  | 2010-03-15 | 4.75 |  | 12 | 4.75 | 4.75 | Document-New Technical | Doc Inspection-NT
Quality Manager | MGMT | Quality Manager - Task (Week 12 - 4/12/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-12 | 12 |  |  |  | 0 | 46.3192 | 778.7605 | 75.5126 | 0.077734 | 2010-11-22 | 2010-04-12 |  | 2010-04-12 | 1 |  | 12 | 1 | 1 | Task | Task
Quality Manager | [8 empty] | C | [6 empty] | 0 | 2010-04-12 | 12 |  |  |  | 0 | 46.3472 | 778.7605 | 75.5406 | 0 | 2010-11-22 | 2010-04-12 |  |  | 0 |  | 12 | 0 | 0
Demo - CM - Eng Build | MGMT | Demo - CM - Eng Build - Task | [6 empty] | B | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-04-12 | 12 |  |  |  | 0 | 46.4405 | 786.7605 | 75.6339 | 0.62187 | 2010-11-15 | 2010-04-12 |  | 2010-04-26 | 8 |  | 11 | 2.6621 | 5.3379 | Task | Task
Implementation | MGMT | Implementation - Task 10 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-12 | 12 |  |  |  | 0 | 46.4405 | 787.7605 | 75.6339 | 0.077734 | 2010-11-22 | 2010-04-12 |  | 2010-04-05 | 1 |  | 12 | 1 | 1 | Task | Task
Maint - Test Eng Build | CODE | Maint - Test - Eng Build - Write Test Cases | [6 empty] | F | 30 | Text Pages | 1 | 50 | 15 | 1 | 15 | 2010-04-12 | 12 |  |  |  | 0 | 46.4405 | 802.7605 | 75.6339 | 1.166 | 2011-01-17 | 2010-04-19 |  | 2010-04-26 | 15 |  | 11 | 8.4167 | 6.5833 | Test | Write Test Cases
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | F | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-04-12 | 12 | 1.5989 |  |  | 0 | 46.4405 | 807.5105 | 76.0031 | 0.36924 | 2011-01-31 | 2010-04-19 |  | 2010-03-15 | 4.75 |  | 12 | 4.75 | 4.75 | Document-New Technical | Doc Inspection-NT
Update INS Form/Script | DLD | Update INS Form/Script - Research-NP | [6 empty] | F | 1 | Text Pages | 0.36 | 20 | 0.55556 | 1 | 0.55556 | 2010-04-12 | 12 |  |  |  | 0 | 46.4405 | 808.066 | 76.1262 | 0.043186 | 2011-02-07 | 2010-04-19 |  | 2010-03-01 | 0.55556 |  | 12 | 0.55556 | 0.55556 | Document-New Process | Research-NP
Maint - LD - 999 | CODE | Maint - LD - 999 Find and Fix | [6 empty] | D | 12 | LOC | 1 | 58 | 6.96 | 1 | 6.96 | 2010-04-12 | 12 | 2.6661 | 2010-03-31 | 10 | 0.54103 | 46.4405 | 815.026 | 76.2816 | 0.54103 | 2010-03-31 |  |  |  | 0 |  | 11 | 2.9828 | 3.9772
Maint - LD - 999 | CR | Maint - LD - 999 Code Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 1 | 1.2 | 2010-04-12 | 12 | 0.35222 | 2010-03-31 | 10 | 0.093281 | 46.4405 | 816.226 | 76.3594 | 0.093281 | 2010-03-31 |  |  |  | 0 |  | 12 | 1.2 | 1.2
Maint - LD - 999 | COMPILE | Maint - LD - 999 Compile | [6 empty] | D | 12 | LOC | 1 | 3 | 0.36 | 1 | 0.36 | 2010-04-12 | 12 |  | 2010-03-31 | 10 | 0.027984 | 46.4405 | 816.586 | 76.5148 | 0.027984 | 2010-03-31 |  |  |  | 0 |  | 12 | 0.36 | 0.36
Maint - LD - 999 | CODEINSP | Maint - LD - 999 Code Peer Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 1 | 1.2 | 2010-04-12 | 12 | 0.053333 | 2010-03-31 | 10 | 0.093281 | 46.4405 | 817.786 | 76.5926 | 0.093281 | 2010-03-31 |  |  |  | 0 |  | 12 | 1.2 | 1.2
Demo - Docs - HLD Doc | CR | Demo - Docs - HLD Doc - Doc Review-NT | [6 empty] | D | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-04-12 | 12 | 3.9392 | 2010-03-31 | 10 | 0.36924 | 46.4405 | 822.536 | 76.748 | 0.36924 | 2010-03-31 |  |  | 2010-02-22 | 4.75 |  | 12 | 4.75 | 4.75 | Document-New Technical | Doc Review-NT
Maint - LD - 997 | CODE | Maint - LD - 997 Find and Fix | [6 empty] | D | 12 | LOC | 1 | 58 | 6.96 | 1 | 6.96 | 2010-04-12 | 12 | 9.0639 | 2010-04-01 | 10 | 0.54103 | 46.4405 | 829.496 | 76.8258 | 0.54103 | 2010-04-01 |  |  |  | 0 |  | 12 | 6.96 | 6.96
Maint - LD - 997 | CR | Maint - LD - 997 Code Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 1 | 1.2 | 2010-04-12 | 12 | 0.43556 | 2010-04-01 | 10 | 0.093281 | 46.4405 | 830.696 | 76.9035 | 0.093281 | 2010-04-01 |  |  |  | 0 |  | 12 | 1.2 | 1.2
Maint - LD - 997 | COMPILE | Maint - LD - 997 Compile | [6 empty] | D | 12 | LOC | 1 | 3 | 0.36 | 1 | 0.36 | 2010-04-12 | 12 | 0.021944 | 2010-04-01 | 10 | 0.027984 | 46.4405 | 831.056 | 77.059 | 0.027984 | 2010-04-01 |  |  |  | 0 |  | 12 | 0.36 | 0.36
Maint - LD - 997 | CODEINSP | Maint - LD - 997 Code Peer Review | [6 empty] | D | 12 | LOC | 1 | 10 | 1.2 | 1 | 1.2 | 2010-04-12 | 12 | 0.81889 | 2010-04-01 | 10 | 0.093281 | 46.4405 | 832.256 | 77.1367 | 0.093281 | 2010-04-01 |  |  |  | 0 |  | 12 | 1.2 | 1.2
Design Manager | MGMT | Design Manager - Week 10 (03/29/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 0 | 0 | 2010-04-12 | 12 |  | 2010-04-02 | 10 | 0 | 46.4405 | 832.256 | 77.2922 | 0 | 2010-04-02 |  |  | 2010-03-15 | 2 |  | 12 | 0 | 0 | Task | Task
Support Manager | MGMT | Support Manager - Week 10 (03/29/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 0 | 0 | 2010-04-12 | 12 |  | 2010-04-02 | 10 | 0 | 46.4405 | 832.256 | 77.3699 | 0 | 2010-04-02 |  |  | 2010-03-15 | 1 |  | 12 | 0 | 0 | Task | Task
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | [6 empty] | G | 30 | Text Pages | 1.76 | 15 | 2.5568 | 1 | 2.5568 | 2010-04-12 | 12 |  |  |  | 0 | 46.4405 | 834.8128 | 77.5254 | 0.19875 | 2010-10-04 | 2010-04-12 |  | 2010-02-15 | 2.5568 |  | 11 | 0.30977 | 2.247 | Document-Maintenance | Doc Inspection-M
Maint - LD - 918 | CR | Maint - LD - 918 - Code Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-12 | 12 | 2.5811 |  |  | 0 | 46.4405 | 837.7657 | 77.6031 | 0.22954 | 2010-10-18 | 2010-04-12 |  | 2010-03-08 | 2.9528 |  | 12 | 2.9528 | 2.9528 | Issue Fixes | Code Review
Maint - LD - 918 | COMPILE | Maint - LD - 918 - Compile | [6 empty] | G | 507 | LOC | 17.17 | 3 | 0.88585 | 1 | 0.88585 | 2010-04-12 | 12 |  |  |  | 0 | 46.4405 | 838.6515 | 77.6355 | 0.068861 | 2010-10-18 | 2010-04-12 |  | 2010-03-08 | 0.88585 |  | 12 | 0.88585 | 0.88585 | Issue Fixes | Compile
Planning Manager | MGMT | Planning Manager - Week 11 | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-04-12 | 12 | 0.4225 |  |  | 0 | 46.4405 | 840.1515 | 77.791 | 0.1166 | 2010-11-01 | 2010-04-12 |  | 2010-04-19 | 1.5 |  | 11 | 0 | 1.5 | Task | Task
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | [6 empty] | C | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 843.1043 | 77.8687 | 0.22954 | 2010-11-29 | 2010-04-19 |  | 2010-03-01 | 2.9528 |  | 12 | 1.0681 | 1.8847 | Issue Fixes | Code Peer Review
Maint - LD - 919 | CODEINSP | Maint - LD - 919 - Code Peer Review | [6 empty] | C | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 846.0572 | 78.0242 | 0.22954 | 2010-12-06 | 2010-04-19 |  | 2010-03-01 | 2.9528 |  | 13 | 2.9528 | 2.9528 | Issue Fixes | Code Peer Review
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - Ada Interface - Code Peer Review | [6 empty] | C | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 850.0572 | 78.1019 | 0.31094 | 2010-12-13 | 2010-04-19 |  |  | 0 |  | 13 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | [6 empty] | C | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 854.0572 | 78.1196 | 0.31094 | 2010-12-20 | 2010-04-19 |  |  | 0 |  | 13 | 4 | 4 | Issue Fixes | Code Peer Review
Quality Manager | MGMT | Quality Manager - Task (Week 13 - 4/19/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 855.0572 | 78.275 | 0.077734 | 2010-12-27 | 2010-04-19 |  | 2010-04-19 | 1 |  | 13 | 1 | 1 | Task | Task
Quality Manager | [8 empty] | C | [6 empty] | 0 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 855.0572 | 78.3528 | 0 | 2010-12-27 | 2010-04-19 |  |  | 0 |  | 13 | 0 | 0
Maint - CM - Final CM Package | MGMT | Maint - CM - Final CM Package - Task | [6 empty] | B | 20 | Text Pages | 1 | 100 | 20 | 1 | 20 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 875.0572 | 78.3704 | 1.5547 | 2010-12-20 | 2010-04-19 |  | 2010-05-03 | 20 |  | 12 | 15.6621 | 4.3379 | Task | Task
Implementation | MGMT | Implementation - Task 11 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 876.0572 | 78.6 | 0.077734 | 2010-12-20 | 2010-04-19 |  | 2010-04-12 | 1 |  | 13 | 1 | 1 | Task | Task
Maint - CM - Archive V2 w/o F | MGMT | Maint - CM - Archive V2 w/o F - Task | [6 empty] | B | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 884.0572 | 78.8295 | 0.62187 | 2011-01-03 | 2010-04-19 |  | 2010-05-03 | 8 |  | 13 | 8 | 8 | Task | Task
Maint - CM - Archive V2 w/ F | MGMT | Maint - CM - Archive V2 w/ F - Task | [6 empty] | B | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 892.0572 | 78.985 | 0.62187 | 2011-01-17 | 2010-04-19 |  | 2010-05-03 | 8 |  | 13 | 8 | 8 | Task | Task
Update INS Form/Script | CODE | Update INS Form/Script - Draft-NP | [6 empty] | F | 1 | Text Pages | 0.36 | 45 | 1.25 | 1 | 1.25 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 893.3072 | 79.0627 | 0.097168 | 2011-02-07 | 2010-04-26 |  | 2010-03-01 | 1.25 |  | 12 | 0.11111 | 1.1389 | Document-New Process | Draft-NP
Update INS Form/Script | CR | Update INS Form/Script - Doc Review-NP | [6 empty] | F | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 893.7238 | 79.3736 | 0.032389 | 2011-02-14 | 2010-04-26 |  | 2010-03-01 | 0.41667 |  | 13 | 0.41667 | 0.41667 | Document-New Process | Doc Review-NP
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | F | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 894.1405 | 79.5291 | 0.032389 | 2011-02-14 | 2010-04-26 |  | 2010-03-01 | 0.41667 |  | 13 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Update INS Form/Script | PM | Update INS Form/Script - Doc PM-NP | [6 empty] | F | 1 | Text Pages | 0.36 | 5 | 0.13889 | 1 | 0.13889 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 894.2794 | 79.6846 | 0.010796 | 2011-02-14 | 2010-04-26 |  | 2010-03-01 | 0.13889 |  | 13 | 0.13889 | 0.13889 | Document-New Process | Doc PM-NP
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | F | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 899.0294 | 79.9955 | 0.36924 | 2011-03-07 | 2010-04-26 |  | 2010-03-15 | 4.75 |  | 13 | 4.75 | 4.75 | Document-New Technical | Doc Inspection-NT
Demo - Docs - Test Cases | CODEINSP | Demo - Docs - Test Cases - Doc Inspection-NT | [6 empty] | F | 35 | Text Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 903.4044 | 80.2287 | 0.34009 | 2011-03-21 | 2010-04-26 |  | 2010-03-22 | 4.375 |  | 13 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | D | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 908.1544 | 80.5396 | 0.36924 | 2010-09-20 | 2010-04-19 |  | 2010-03-01 | 4.75 |  | 12 | 2.7928 | 1.9572 | Document-New Technical | Doc Inspection-NT
Demo - Docs - HLD Doc | PM | Demo - Docs - HLD Doc - Doc PM-NT | [6 empty] | D | 38 | HLD Pages | 1.2 | 5 | 1.5833 | 1 | 1.5833 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 909.7377 | 81.0061 | 0.12308 | 2010-09-20 | 2010-04-19 |  | 2010-03-08 | 1.5833 |  | 13 | 1.5833 | 1.5833 | Document-New Technical | Doc PM-NT
Design Manager | MGMT | Design Manager - Week 11 (04/05/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 911.7377 | 81.1304 | 0.15547 | 2010-09-27 | 2010-04-19 |  | 2010-03-22 | 2 |  | 13 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 11 (04/05/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 912.7377 | 81.4414 | 0.077734 | 2010-09-27 | 2010-04-19 |  | 2010-03-22 | 1 |  | 13 | 1 | 1 | Task | Task
Design Manager | MGMT | Design Manager - Week 12 (04/12/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 914.7377 | 81.9078 | 0.15547 | 2010-09-27 | 2010-04-19 |  | 2010-04-05 | 2 |  | 13 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 12 (04/12/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 915.7377 | 82.0321 | 0.077734 | 2010-09-27 | 2010-04-19 |  | 2010-04-05 | 1 |  | 13 | 1 | 1 | Task | Task
Design Manager | MGMT | Design Manager - Week 13 (04/19/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 917.7377 | 82.3431 | 0.15547 | 2010-10-04 | 2010-04-19 |  | 2010-04-12 | 2 |  | 13 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 13 (04/19/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 918.7377 | 82.8095 | 0.077734 | 2010-10-04 | 2010-04-19 |  | 2010-04-12 | 1 |  | 13 | 1 | 1 | Task | Task
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 919.7377 | 82.9339 | 0.077734 | 2010-10-04 | 2010-04-19 |  | 2010-04-12 | 1 |  | 13 | 1 | 1
Design Manager | MGMT | Design Manager - Week 14 (04/26/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 921.7377 | 83.2739 | 0.15547 | 2010-10-04 | 2010-04-19 |  | 2010-04-19 | 2 |  | 13 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 14 (04/26/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 922.7377 | 83.4139 | 0.077734 | 2010-10-04 | 2010-04-19 |  | 2010-04-19 | 1 |  | 13 | 1 | 1 | Task | Task
Design Manager | MGMT | Design Manager - Week 15 (05/03/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 924.7377 | 83.4512 | 0.15547 | 2010-10-11 | 2010-04-19 |  | 2010-04-26 | 2 |  | 13 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 15 (05/03/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 925.7377 | 83.5911 | 0.077734 | 2010-10-11 | 2010-04-19 |  | 2010-04-26 | 1 |  | 13 | 1 | 1 | Task | Task
Design Manager | MGMT | Design Manager - Week 16 (05/10/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 927.7377 | 83.6284 | 0.15547 | 2010-10-11 | 2010-04-19 |  | 2010-05-10 | 2 |  | 13 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 16 (05/10/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 928.7377 | 83.7683 | 0.077734 | 2010-10-11 | 2010-04-19 |  | 2010-05-10 | 1 |  | 13 | 1 | 1 | Task | Task
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-19 | 13 |  |  |  | 0 | 46.4405 | 929.1544 | 83.8056 | 0.032389 | 2010-10-11 | 2010-04-19 |  | 2010-05-24 | 0.41667 |  | 13 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-19 | 13 |  |  |  | 0 | 46.8265 | 932.1072 | 84.1916 | 0.22954 | 2010-10-25 | 2010-04-19 |  | 2010-03-08 | 2.9528 |  | 12 | 1.9143 | 1.0385 | Issue Fixes | Code Peer Review
Maint - LD - 918 | UT | Maint - LD - 918 - Unit Test | [6 empty] | G | 507 | LOC | 17.17 | 15 | 4.4292 | 1 | 4.4292 | 2010-04-19 | 13 |  |  |  | 0 | 46.893 | 936.5365 | 84.2582 | 0.3443 | 2010-11-08 | 2010-04-19 |  | 2010-03-15 | 4.4292 |  | 13 | 4.4292 | 4.4292 | Issue Fixes | Unit Test
Maint - LD - 918 | PM | Maint - LD - 918 - PM | [6 empty] | G | 507 | LOC | 17.17 | 4 | 1.1811 | 1 | 1.1811 | 2010-04-19 | 13 |  |  |  | 0 | 46.913 | 937.7176 | 84.2782 | 0.091814 | 2010-11-15 | 2010-04-19 |  | 2010-03-15 | 1.1811 |  | 13 | 1.1811 | 1.1811 | Issue Fixes | Postmortem
Customer Interface Manager | MGMT | Customer Interface Manager - 3/29 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 |  |  |  | 0 | 46.9907 | 938.7176 | 84.3559 | 0.077734 | 2010-11-15 | 2010-04-19 |  | 2010-05-10 | 4 |  | 13 | 1 | 1 | Task | Task
Update Specification PM | DLD | Update Specification PM - Research-NP | [6 empty] | E | 1 | Text Pages | 0.36 | 20 | 0.55556 | 1 | 0.55556 | 2010-04-19 | 13 |  |  |  | 0 | 47.0685 | 939.2731 | 84.4336 | 0.043186 | 2010-11-01 | 2010-04-19 |  | 2010-02-15 | 0.55556 |  | 12 | 0.5 | 0.055556 | Document-New Process | Research-NP
Update Specification PM | CODE | Update Specification PM - Draft-NP | [6 empty] | E | 1 | Text Pages | 0.36 | 45 | 1.25 | 1 | 1.25 | 2010-04-19 | 13 |  |  |  | 0 | 47.1462 | 940.5231 | 84.5114 | 0.097168 | 2010-11-15 | 2010-04-19 |  | 2010-02-15 | 1.25 |  | 13 | 1.25 | 1.25 | Document-New Process | Draft-NP
Update Specification PM | CR | Update Specification PM - Doc Review-NP | [6 empty] | E | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-19 | 13 |  |  |  | 0 | 47.1786 | 940.9398 | 84.5438 | 0.032389 | 2010-11-22 | 2010-04-19 |  | 2010-02-15 | 0.41667 |  | 13 | 0.41667 | 0.41667 | Document-New Process | Doc Review-NP
Update Specification PM | CODEINSP | Update Specification PM - Doc Inspection-NP | [6 empty] | E | 1 | Text Pages | 0.36 | 15 | 0.41667 | 3 | 1.25 | 2010-04-19 | 13 |  |  |  | 0 | 47.211 | 942.1898 | 84.5761 | 0.097168 | 2010-12-06 | 2010-04-19 |  | 2010-02-22 | 1.25 |  | 13 | 1.25 | 1.25 | Document-New Process | Doc Inspection-NP
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | [6 empty] | C | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-26 | 14 |  |  |  | 0 | 47.2887 | 946.1898 | 84.6539 | 0.31094 | 2011-01-03 | 2010-04-26 |  |  | 0 |  | 13 | 2.1625 | 1.8375 | Issue Fixes | Code Peer Review
Demo - Interface - Msg | CODEINSP | Demo - Interface - XML to Lchr - Code Peer Review | [6 empty] | C | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-04-26 | 14 |  |  |  | 0 | 47.3664 | 948.1898 | 84.7316 | 0.15547 | 2011-01-10 | 2010-04-26 |  | 2010-02-22 | 2 |  | 14 | 2 | 2 | Issue Fixes | Code Peer Review
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-26 | 14 |  |  |  | 0 | 47.433 | 948.6065 | 84.7982 | 0.032389 | 2011-01-10 | 2010-04-26 |  | 2010-03-15 | 0.41667 |  | 14 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Update Specification PM | CODEINSP | Update Specification PM - Doc Inspection-NP | [6 empty] | C | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-26 | 14 |  |  |  | 0 | 47.8022 | 949.0231 | 85.1674 | 0.032389 | 2011-01-10 | 2010-04-26 |  | 2010-03-15 | 0.41667 |  | 14 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | [6 empty] | C | 30 | Text Pages | 1.76 | 15 | 2.5568 | 1 | 2.5568 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 951.58 | 85.2451 | 0.19875 | 2011-01-17 | 2010-04-26 |  | 2010-04-05 | 2.5568 |  | 14 | 2.5568 | 2.5568 | Document-Maintenance | Doc Inspection-M
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Attend Inspection Meeting | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 952.58 | 85.2451 | 0.077734 | 2011-01-17 | 2010-04-26 |  |  | 0 |  | 14 | 1 | 1
Quality Manager | MGMT | Quality Manager - Task (Week 14 - 4/26/10) | [6 empty] | C | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 953.58 | 85.2451 | 0.077734 | 2011-01-24 | 2010-04-26 |  | 2010-04-19 | 1 |  | 14 | 1 | 1 | Task | Task
Quality Manager | MGMT | Quality Manager - Task (Week 15 - 5/3/10) | [6 empty] | C | 2 | Text Pages | 2 | 101 | 1.01 | 1 | 1.01 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 954.59 | 85.2451 | 0.078511 | 2011-01-24 | 2010-04-26 |  | 2010-05-03 | 1.01 |  | 14 | 1.01 | 1.01 | Task | Task
Quality Manager | MGMT | Quality Manager - Task (Week 16 - 5/10/10) | [6 empty] | C | 3 | Text Pages | 3 | 102 | 1.02 | 1 | 1.02 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 955.61 | 85.2451 | 0.079289 | 2011-01-24 | 2010-04-26 |  | 2010-05-10 | 1.02 |  | 14 | 1.02 | 1.02 | Task | Task
Quality Manager | MGMT | Quality Manager - Task (Week 17 - 5/17/10) | [6 empty] | C | 4 | Text Pages | 4 | 103 | 1.03 | 1 | 1.03 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 956.64 | 85.2451 | 0.080066 | 2011-01-31 | 2010-04-26 |  | 2010-05-10 | 1.03 |  | 14 | 1.03 | 1.03 | Task | Task
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | C | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-04-26 | 14 |  |  |  | 0 | 47.88 | 959.64 | 85.2451 | 0.2332 | 2011-01-31 | 2010-04-26 |  | 2010-05-10 | 3 |  | 14 | 3 | 3
Implementation | MGMT | Implementation - Task 12 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 47.9798 | 960.64 | 85.345 | 0.077734 | 2011-01-17 | 2010-04-26 |  | 2010-05-03 | 1 |  | 13 | 0.66211 | 0.33789 | Task | Task
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | B | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-04-26 | 14 |  |  |  | 0 | 48.0064 | 961.0566 | 85.3716 | 0.032389 | 2011-01-17 | 2010-04-26 |  | 2010-05-10 | 0.41667 |  | 14 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | B | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-04-26 | 14 |  |  |  | 0 | 48.0388 | 965.8066 | 85.404 | 0.36924 | 2011-01-24 | 2010-04-26 |  | 2010-05-10 | 4.75 |  | 14 | 4.75 | 4.75 | Document-New Technical | Doc Inspection-NT
Implementation | MGMT | Implementation - Task 13 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 48.0388 | 966.8066 | 85.404 | 0.077734 | 2011-01-24 | 2010-04-26 |  | 2010-04-12 | 1 |  | 14 | 1 | 1 | Task | Task
Demo - Interface - Msg | CODEINSP | Demo - Interface - Msg - Code Peer Review | [6 empty] | B | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-26 | 14 |  |  |  | 0 | 48.0388 | 970.8066 | 85.404 | 0.31094 | 2011-01-31 | 2010-04-26 |  | 2010-05-24 | 4 |  | 14 | 4 | 4 | Issue Fixes | Code Peer Review
Maint - CM - Final Builds | MGMT | Maint - CM - Final Builds - Task | [6 empty] | B | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-04-26 | 14 |  |  |  | 0 | 48.2462 | 978.8066 | 85.6114 | 0.62187 | 2011-02-14 | 2010-04-26 |  | 2010-05-24 | 8 |  | 14 | 8 | 8 | Task | Task
Design Manager | MGMT | Design Manager - Week 17 (05/17/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-26 | 14 |  |  |  | 0 | 48.282 | 980.8066 | 85.6472 | 0.15547 | 2010-10-18 | 2010-04-26 |  | 2010-05-24 | 2 |  | 13 | 1.0428 | 0.95715 | Task | Task
Support Manager | MGMT | Support Manager - Week 17 (05/17/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 48.2927 | 981.8066 | 85.6579 | 0.077734 | 2010-10-18 | 2010-04-26 |  | 2010-05-24 | 1 |  | 14 | 1 | 1 | Task | Task
Design Manager | MGMT | Design Manager - Week 18 (05/24/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-26 | 14 |  |  |  | 0 | 48.3285 | 983.8066 | 85.6937 | 0.15547 | 2010-10-18 | 2010-04-26 |  | 2010-05-24 | 2 |  | 14 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 18 (05/24/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 48.3822 | 984.8066 | 85.7473 | 0.077734 | 2010-10-18 | 2010-04-26 |  | 2010-05-24 | 1 |  | 14 | 1 | 1 | Task | Task
Maint - LD - 961 | CODEINSP | Maint - LD - 961 - Code Peer Review | [6 empty] | D | 39 | LOC | 17.17 | 10 | 0.22714 | 1 | 0.22714 | 2010-04-26 | 14 |  |  |  | 0 | 48.3965 | 985.0338 | 85.7616 | 0.017657 | 2010-10-18 | 2010-04-26 |  | 2010-05-24 | 0.22714 |  | 14 | 0.22714 | 0.22714 | Issue Fixes | Code Peer Review
Design Manager | MGMT | Design Manager - Week 19 (05/31/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-26 | 14 |  |  |  | 0 | 48.4289 | 987.0338 | 85.794 | 0.15547 | 2010-10-25 | 2010-04-26 |  | 2010-05-31 | 2 |  | 14 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 19 (05/31/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 48.4936 | 988.0338 | 85.8588 | 0.077734 | 2010-10-25 | 2010-04-26 |  | 2010-05-31 | 1 |  | 14 | 1 | 1 | Task | Task
Maint - LD - 956 | CODEINSP | Maint - LD - 956 - Code Peer Review | [6 empty] | D | 39 | LOC | 17.17 | 10 | 0.22714 | 1 | 0.22714 | 2010-04-26 | 14 |  |  |  | 0 | 48.5714 | 988.2609 | 85.9365 | 0.017657 | 2010-10-25 | 2010-04-26 |  | 2010-05-31 | 0.22714 |  | 14 | 0.22714 | 0.22714 | Issue Fixes | Code Peer Review
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | [6 empty] | D | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-26 | 14 |  |  |  | 0 | 48.8046 | 991.2137 | 86.1697 | 0.22954 | 2010-10-25 | 2010-04-26 |  | 2010-05-31 | 2.9528 |  | 14 | 2.9528 | 2.9528 | Issue Fixes | Code Peer Review
Maint - LD - 919 | CODEINSP | Maint - LD - 919 - Code Peer Review | [6 empty] | D | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-26 | 14 |  |  |  | 0 | 49.271 | 994.1666 | 86.6361 | 0.22954 | 2010-11-01 | 2010-04-26 |  | 2010-05-31 | 2.9528 |  | 14 | 2.9528 | 2.9528 | Issue Fixes | Code Peer Review
Design Manager | MGMT | Design Manager - Week 20 (06/07/2010) | [6 empty] | D | 2 | Text Pages | 1 | 100 | 2 | 1 | 2 | 2010-04-26 | 14 |  |  |  | 0 | 49.3375 | 996.1666 | 86.7027 | 0.15547 | 2010-11-01 | 2010-04-26 |  | 2010-05-31 | 2 |  | 14 | 2 | 2 | Task | Task
Support Manager | MGMT | Support Manager - Week 20 (06/07/2010) | [6 empty] | D | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 49.4153 | 997.1666 | 86.7804 | 0.077734 | 2010-11-01 | 2010-04-26 |  | 2010-05-31 | 1 |  | 14 | 1 | 1 | Task | Task
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-04-26 | 14 |  |  |  | 0 | 49.7553 | 1001.1666 | 87.1205 | 0.31094 | 2010-11-08 | 2010-04-26 |  | 2010-06-07 | 4 |  | 14 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | [6 empty] | D | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-04-26 | 14 |  |  |  | 0 | 49.7911 | 1003.1666 | 87.1563 | 0.15547 | 2010-11-08 | 2010-04-26 |  | 2010-06-07 | 2 |  | 14 | 2 | 2 | Issue Fixes | Code Peer Review
Customer Interface Manager | MGMT | Customer Interface Manager - 4/5 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 49.7911 | 1004.1666 | 87.1563 | 0.077734 | 2010-11-22 | 2010-04-26 |  | 2010-05-10 | 4 |  | 13 | 0.35109 | 0.64891 | Task | Task
Update Specification PM | PM | Update Specification PM - Doc PM-NP | [6 empty] | E | 1 | Text Pages | 0.36 | 5 | 0.13889 | 1 | 0.13889 | 2010-04-26 | 14 |  |  |  | 0 | 49.7911 | 1004.3054 | 87.1563 | 0.010796 | 2010-12-06 | 2010-04-26 |  | 2010-02-22 | 0.13889 |  | 13 | 0.027778 | 0.11111 | Document-New Process | Doc PM-NP
Process Manager | MGMT | Process Manager - Task | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 |  |  |  | 0 | 49.7911 | 1005.3054 | 87.1563 | 0.077734 | 2010-12-13 | 2010-04-26 |  | 2010-04-26 | 1 |  | 14 | 1 | 1 | Task | Task
Demo - CM - Eng Build Testing | MGMT | Demo - CM - Eng Build Testing - Task | [6 empty] | A | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-05-03 | 15 |  |  |  | 0 | 49.7911 | 1013.3054 | 87.1563 | 0.62187 | 2011-01-31 | 2010-05-03 | 2010-05-21 | 2010-03-29 | 8 |  | 12 | 0.1 | 0.9 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 12 Apr 12 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-03 | 15 |  |  |  | 0 | 49.7911 | 1014.3054 | 87.1563 | 0.077734 | 2011-02-07 | 2010-05-03 |  | 2010-05-10 | 1 |  | 15 | 1 | 1 | Task | Task
Demo - CM - Final Build | MGMT | Demo - CM - Final Build - Task | [6 empty] | B | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-05-03 | 15 |  |  |  | 0 | 49.8688 | 1022.3054 | 87.234 | 0.62187 | 2011-02-28 | 2010-05-03 |  | 2010-05-24 | 8 |  | 14 | 3.4954 | 4.5046 | Task | Task
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | B | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-05-03 | 15 |  |  |  | 0 | 50.2746 | 1025.3054 | 87.6398 | 0.2332 | 2011-03-07 | 2010-05-03 |  | 2010-05-31 | 3 |  | 15 | 3 | 3
Implementation | MGMT | Implementation - Task 14 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-03 | 15 |  |  |  | 0 | 50.3446 | 1026.3054 | 87.7097 | 0.077734 | 2011-03-07 | 2010-05-03 |  | 2010-04-26 | 1 |  | 15 | 1 | 1 | Task | Task
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | [6 empty] | B | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-03 | 15 |  |  |  | 0 | 50.3656 | 1030.3054 | 87.7307 | 0.31094 | 2011-03-14 | 2010-05-03 |  |  | 0 |  | 15 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | [6 empty] | B | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-03 | 15 |  |  |  | 0 | 50.4355 | 1034.3054 | 87.8007 | 0.31094 | 2011-03-21 | 2010-05-03 |  |  | 0 |  | 15 | 4 | 4 | Issue Fixes | Code Peer Review
Maint - Test Eng Build | CODE | Maint - Test - Eng Build - Write Test Cases | [6 empty] | F | 36 | Text Pages | 1 | 50 | 18 | 1 | 18 | 2010-05-03 | 15 | 0.39333 |  |  | 0 | 50.4713 | 1052.3054 | 87.8365 | 1.3992 | 2011-05-30 | 2010-05-10 |  | 2010-04-05 | 18 |  | 13 | 0.76389 | 5.2361 | Test | Write Test Cases
Maint - Test Eng Build | CR | Maint - Test - Eng Build - Review TC | [6 empty] | F | 36 | Text Pages | 1 | 10 | 3.6 | 1 | 3.6 | 2010-05-03 | 15 |  |  |  | 0 | 50.7869 | 1055.9054 | 88.1521 | 0.27984 | 2011-06-13 | 2010-05-10 |  | 2010-04-05 | 3.6 |  | 15 | 3.6 | 3.6 | Test | Review TC
Demo - Inteface - HTML | CODEINSP | Demo - Interface - HTML - Code Peer Review | [6 empty] | D | 20 | LOC | 1 | 10 | 2 | 1 | 2 | 2010-05-03 | 15 |  |  |  | 0 | 50.8413 | 1057.9054 | 88.2065 | 0.15547 | 2010-11-08 | 2010-05-03 |  | 2010-06-07 | 2 |  | 14 | 0.68292 | 1.3171 | Issue Fixes | Code Peer Review
Demo - Interface - Msg | CODEINSP | Demo - Interface - Msg - Code Peer Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-03 | 15 |  |  |  | 0 | 50.8576 | 1061.9054 | 88.2228 | 0.31094 | 2010-11-15 | 2010-05-03 |  | 2010-06-07 | 4 |  | 15 | 4 | 4 | Issue Fixes | Code Peer Review
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | D | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-05-03 | 15 |  |  |  | 0 | 50.912 | 1064.9054 | 88.2772 | 0.2332 | 2010-11-15 | 2010-05-03 |  | 2010-06-07 | 3 |  | 15 | 3 | 3
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - AIM Interface - Code Peer Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-03 | 15 | 1.1439 |  |  | 0 | 51.017 | 1068.9054 | 88.3822 | 0.31094 | 2010-11-22 | 2010-05-03 |  |  | 0 |  | 15 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - GUI - AIM Interface | UT | Demo - GUI - AIM Interface - Unit Test | [6 empty] | D | 40 | LOC | 1 | 15 | 6 | 1 | 6 | 2010-05-03 | 15 |  |  |  | 0 | 51.045 | 1074.9054 | 88.4101 | 0.4664 | 2010-11-29 | 2010-05-03 |  |  | 0 |  | 15 | 6 | 6 | Issue Fixes | Unit Test
Demo - GUI - AIM Interface | PM | Demo - GUI - AIM Interface - PM | [6 empty] | D | 40 | LOC | 1 | 4 | 1.6 | 1 | 1.6 | 2010-05-03 | 15 |  |  |  | 0 | 52.3763 | 1076.5054 | 89.7414 | 0.12437 | 2010-11-29 | 2010-05-03 |  |  | 0 |  | 15 | 1.6 | 1.6 | Issue Fixes | Postmortem
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-03 | 15 | 1.005 |  |  | 0 | 52.4579 | 1080.5054 | 89.8231 | 0.31094 | 2010-12-06 | 2010-05-03 |  |  | 0 |  | 15 | 4 | 4 | Issue Fixes | Code Peer Review
Planning Manager | MGMT | Planning Manager - Task | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-05-03 | 15 |  |  |  | 0 | 52.4797 | 1082.0054 | 89.8448 | 0.1166 | 2011-01-03 | 2010-05-03 |  | 2010-04-26 | 1.5 |  | 14 | 0.88889 | 0.61111 | Task | Task
Process Manager | MGMT | Process Manager - Task | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-03 | 15 |  |  |  | 0 | 52.5574 | 1083.0054 | 89.9226 | 0.077734 | 2011-01-10 | 2010-05-03 |  | 2010-05-03 | 1 |  | 15 | 1 | 1 | Task | Task
Maint - Doc - Test Docs | MGMT | Maint - Doc - Test Docs - Task | [6 empty] | A | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1091.0054 | 90.2335 | 0.62187 | 2011-03-14 | 2010-05-10 |  | 2010-04-19 | 8 |  | 15 | 3.1 | 4.9 | Task | Task
Maint - LD - 961 | MGMT | Maint - LD - 961 - Task | [6 empty] | B | 12 | LOC | 1 | 100 | 12 | 1 | 12 | 2010-05-10 | 16 | 6.18 |  |  | 0 | 52.5574 | 1103.0054 | 90.4323 | 0.93281 | 2011-04-04 | 2010-05-10 |  |  | 0 |  | 15 | 5.4954 | 6.5046 | Task | Task
Implementation | MGMT | Implementation - Task 15 | [6 empty] | B | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1104.0054 | 90.6618 | 0.077734 | 2011-04-11 | 2010-05-10 |  | 2010-05-03 | 1 |  | 16 | 1 | 1 | Task | Task
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - AIM Interface - Code Peer Review | [6 empty] | B | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1108.0054 | 90.7307 | 0.31094 | 2011-04-11 | 2010-05-10 |  |  | 0 |  | 16 | 4 | 4 | Issue Fixes | Code Peer Review
Maint - Test Eng Build | CODEINSP | Maint - Test - Eng Build - Peer Review TC | [6 empty] | F | 36 | Text Pages | 1 | 15 | 5.4 | 1 | 5.4 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1113.4054 | 90.9602 | 0.41976 | 2011-07-04 | 2010-05-17 |  | 2010-04-12 | 5.4 |  | 15 | 3.1639 | 2.2361 | Test | Peer Review TC
Maint - Test Eng Build | ST | Maint - Test - Eng Build - Validate TC and Test SW | [6 empty] | F | 36 | Text Pages | 1 | 17 | 6.12 | 1 | 6.12 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1119.5254 | 91.3045 | 0.47573 | 2011-08-01 | 2010-05-17 |  | 2010-04-12 | 6.12 |  | 16 | 6.12 | 6.12 | Test | Validate TC and Test Software
Maint - Test Eng Build | PM | Maint - Test - Eng Build - Analyze and Record Results | [6 empty] | F | 36 | Text Pages | 1 | 8 | 2.88 | 1 | 2.88 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1122.4054 | 91.3963 | 0.22387 | 2011-08-08 | 2010-05-17 | 2010-03-29 | 2010-04-12 | 2.88 |  | 16 | 2.88 | 2.88 | Test | Analyze and Record Results
Demo - GUI - GUI Desktop | UT | Demo - GUI - GUI Desktop - Unit Test | [6 empty] | D | 40 | LOC | 1 | 15 | 6 | 1 | 6 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1128.4054 | 91.474 | 0.4664 | 2010-12-13 | 2010-05-10 |  |  | 0 |  | 15 | 0.082919 | 5.9171 | Issue Fixes | Unit Test
Demo - GUI - GUI Desktop | PM | Demo - GUI - GUI Desktop - PM | [6 empty] | D | 40 | LOC | 1 | 4 | 1.6 | 1 | 1.6 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1130.0054 | 91.5518 | 0.12437 | 2010-12-13 | 2010-05-10 |  |  | 0 |  | 16 | 1.6 | 1.6 | Issue Fixes | Postmortem
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | [6 empty] | D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-05-10 | 16 | 1.1036 |  |  | 0 | 52.5574 | 1134.0054 | 92.8831 | 0.31094 | 2010-12-13 | 2010-05-10 |  |  | 0 |  | 16 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Popups | UT | Demo - GUI - GUI Popups - Unit Test | [6 empty] | D | 40 | LOC | 1 | 15 | 6 | 1 | 6 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1140.0054 | 93.1126 | 0.4664 | 2010-12-20 | 2010-05-10 |  |  | 0 |  | 16 | 6 | 6 | Issue Fixes | Unit Test
Demo - GUI - GUI Popups | PM | Demo - GUI - GUI Popups - PM | [6 empty] | D | 40 | LOC | 1 | 4 | 1.6 | 1 | 1.6 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1141.6054 | 93.1815 | 0.12437 | 2010-12-20 | 2010-05-10 |  |  | 0 |  | 16 | 1.6 | 1.6 | Issue Fixes | Postmortem
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework PM | [6 empty] | D | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1145.9804 | 93.411 | 0.34009 | 2010-12-27 | 2010-05-10 |  |  | 0 |  | 16 | 4.375 | 4.375
Maint - LD - 919 | CODE | Maint - LD - 919 - Find and Fix | [6 empty] | G | 507 | LOC | 17.17 | 58 | 17.1264 | 1 | 17.1264 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1163.1068 | 93.7553 | 1.3313 | 2011-01-10 | 2010-05-10 |  | 2010-03-22 | 17.1264 |  | 14 | 7.3511 | 1.7753 | Issue Fixes | Find and Fix
Maint - LD - 919 | CR | Maint - LD - 919 - Code Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1166.0596 | 93.833 | 0.22954 | 2011-01-17 | 2010-05-10 |  | 2010-03-22 | 2.9528 |  | 16 | 2.9528 | 2.9528 | Issue Fixes | Code Review
Maint - LD - 919 | COMPILE | Maint - LD - 919 - Compile | [6 empty] | G | 507 | LOC | 17.17 | 3 | 0.88585 | 1 | 0.88585 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1166.9455 | 93.9249 | 0.068861 | 2011-01-24 | 2010-05-10 |  | 2010-03-22 | 0.88585 |  | 16 | 0.88585 | 0.88585 | Issue Fixes | Compile
Planning Manager | MGMT | Planning Manager - Task | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1168.4455 | 93.9572 | 0.1166 | 2011-01-24 | 2010-05-10 |  | 2010-05-03 | 1.5 |  | 15 | 1.3889 | 0.11111 | Task | Task
Process Manager | MGMT | Process Manager - Task | [6 empty] | E | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-10 | 16 |  |  |  | 0 | 52.5574 | 1169.4455 | 94.3265 | 0.077734 | 2011-02-07 | 2010-05-10 |  | 2010-05-10 | 1 |  | 16 | 1 | 1 | Task | Task
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | F | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1170.4455 | 94.4042 | 0.077734 | 2011-08-15 | 2010-05-24 |  | 2010-04-12 | 1 |  | 16 | 0.76389 | 0.23611
Maint - Test Eng Build | CR | Maint - Test - Eng Build - Review TC | [6 empty] | F | 30 | Text Pages | 1 | 10 | 3 | 1 | 3 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1173.4455 | 94.7443 | 0.2332 | 2011-08-22 | 2010-05-24 |  | 2010-04-26 | 3 |  | 17 | 3 | 3 | Test | Review TC
Maint - Test Eng Build | CODEINSP | Maint - Test - Eng Build - Peer Review TC | [6 empty] | F | 30 | Text Pages | 1 | 15 | 4.5 | 1 | 4.5 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1177.9455 | 94.822 | 0.3498 | 2011-09-12 | 2010-05-24 |  | 2010-04-26 | 4.5 |  | 17 | 4.5 | 4.5 | Test | Peer Review TC
Maint - LD - 997 | UT | Maint - LD - 997 Unit Test | [6 empty] | D | 12 | LOC | 1 | 15 | 1.8 | 1 | 1.8 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1179.7455 | 94.8998 | 0.13992 | 2010-12-27 | 2010-05-17 |  |  | 0 |  | 16 | 0.50792 | 1.2921
Maint - LD - 997 | PM | Maint - LD - 997 PM | [6 empty] | D | 12 | LOC | 1 | 4 | 0.48 | 1 | 0.48 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1180.2255 | 94.9775 | 0.037312 | 2010-12-27 | 2010-05-17 |  |  | 0 |  | 17 | 0.48 | 0.48
Maint - LD - 998 | UT | Maint - LD - 998 Unit Test | [6 empty] | D | 12 | LOC | 1 | 15 | 1.8 | 1 | 1.8 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1182.0255 | 95.0552 | 0.13992 | 2011-01-03 | 2010-05-17 |  |  | 0 |  | 17 | 1.8 | 1.8
Maint - LD - 998 | PM | Maint - LD - 998 PM | [6 empty] | D | 12 | LOC | 1 | 4 | 0.48 | 1 | 0.48 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1182.5055 | 95.133 | 0.037312 | 2011-01-03 | 2010-05-17 |  |  | 0 |  | 17 | 0.48 | 0.48
Maint - LD - 999 | UT | Maint - LD - 999 Unit Test | [6 empty] | D | 12 | LOC | 1 | 15 | 1.8 | 1 | 1.8 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1184.3055 | 95.4439 | 0.13992 | 2011-01-03 | 2010-05-17 |  |  | 0 |  | 17 | 1.8 | 1.8
Maint - LD - 999 | PM | Maint - LD - 999 PM | [6 empty] | D | 12 | LOC | 1 | 4 | 0.48 | 1 | 0.48 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1184.7855 | 95.4439 | 0.037312 | 2011-01-03 | 2010-05-17 |  |  | 0 |  | 17 | 0.48 | 0.48
Maint - LD - 919 | CODEINSP | Maint - LD - 919 - Code Peer Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1187.7383 | 95.7549 | 0.22954 | 2011-01-31 | 2010-05-17 |  | 2010-03-22 | 2.9528 |  | 16 | 2.386 | 0.56679 | Issue Fixes | Code Peer Review
Maint - LD - 919 | UT | Maint - LD - 919 - Unit Test | [6 empty] | G | 507 | LOC | 17.17 | 15 | 4.4292 | 1 | 4.4292 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1192.1676 | 96.0658 | 0.3443 | 2011-02-14 | 2010-05-17 |  | 2010-03-29 | 4.4292 |  | 17 | 4.4292 | 4.4292 | Issue Fixes | Unit Test
Customer Interface Manager | MGMT | Customer Interface Manager - 4/12 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1193.1676 | 96.3767 | 0.077734 | 2011-02-14 | 2010-05-17 |  | 2010-05-10 | 4 |  | 17 | 1 | 1 | Task | Task
Maint - LD - 919 | PM | Maint - LD - 919 - PM | [6 empty] | G | 507 | LOC | 17.17 | 4 | 1.1811 | 1 | 1.1811 | 2010-05-17 | 17 |  |  |  | 0 | 52.5574 | 1194.3487 | 96.4545 | 0.091814 | 2011-02-21 | 2010-05-17 |  | 2010-03-29 | 1.1811 |  | 17 | 1.1811 | 1.1811 | Issue Fixes | Postmortem
Update Specification PM | CODEINSP | Update Specification PM - Doc Inspection-NP | [6 empty] | G | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-05-17 | 17 |  |  |  | 0 | 52.674 | 1194.7654 | 96.5711 | 0.032389 | 2011-02-21 | 2010-05-17 |  | 2010-04-05 | 0.41667 |  | 17 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Planning Manager | MGMT | Planning Manager - Task | [6 empty] | E | 1.5 | Text Pages | 1 | 100 | 1.5 | 1 | 1.5 | 2010-05-17 | 17 |  |  |  | 0 | 52.7517 | 1196.2654 | 96.6488 | 0.1166 | 2011-02-21 | 2010-05-17 |  | 2010-05-10 | 1.5 |  | 16 | 0.88889 | 0.61111 | Task | Task
Demo - CM - Final Build Testing | MGMT | Demo - CM - Final Build Testing - Task | [6 empty] | A | 8 | Text Pages | 1 | 100 | 8 | 1 | 8 | 2010-05-24 | 18 |  |  |  | 0 | 52.8295 | 1204.2654 | 96.7265 | 0.62187 | 2011-04-18 | 2010-05-24 | 2010-05-21 | 2010-03-22 | 8 |  | 16 | 5.1 | 2.9 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 13 Apr 19 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-24 | 18 |  |  |  | 0 | 52.9461 | 1205.2654 | 96.8431 | 0.077734 | 2011-04-25 | 2010-05-24 |  | 2010-05-10 | 1 |  | 18 | 1 | 1 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 14 Apr 26 | [6 empty] | A | 1 | Text Pages |  |  | 1 | 0.5 | 0.5 | 2010-05-24 | 18 |  |  |  | 0 | 53.0238 | 1205.7654 | 96.9209 | 0.038867 | 2011-04-25 | 2010-05-24 |  | 2010-05-10 | 1 |  | 18 | 0.5 | 0.5 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 15 May 3 | [6 empty] | A | 1 | Text Pages |  |  | 1 | 0.5 | 0.5 | 2010-05-24 | 18 |  |  |  | 0 | 53.1404 | 1206.2654 | 97.0375 | 0.038867 | 2011-05-02 | 2010-05-24 |  | 2010-05-10 | 1 |  | 18 | 0.5 | 0.5 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 16 May 10 | [6 empty] | A | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-24 | 18 |  |  |  | 0 | 53.4513 | 1207.2654 | 97.3484 | 0.077734 | 2011-05-02 | 2010-05-24 |  | 2010-05-10 | 1 |  | 18 | 1 | 1 | Task | Task
Test Manager | MGMT | Test Manager - Task Week 17 May 17 | [6 empty] | A | 1 | Text Pages |  |  | 1 | 0.5 | 0.5 | 2010-05-24 | 18 |  |  |  | 0 | 53.5291 | 1207.7654 | 97.4261 | 0.038867 | 2011-05-02 | 2010-05-24 |  | 2010-05-10 | 1 |  | 18 | 0.5 | 0.5 | Task | Task
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | A | 3 | Test | 1 | 100 | 3 | 1 | 3 | 2010-05-24 | 18 |  |  |  | 0 | 53.6457 | 1210.7654 | 97.5427 | 0.2332 | 2011-05-16 | 2010-05-24 |  | 2010-05-10 | 3 |  | 18 | 3 | 3
Maint - Test Eng Build | ST | Maint - Test - Eng Build - Validate TC and Test SW | [6 empty] | F | 30 | Text Pages | 1 | 17 | 5.1 | 1 | 5.1 | 2010-05-24 | 18 |  |  |  | 0 | 53.7234 | 1215.8654 | 97.6205 | 0.39644 | 2011-10-03 | 2010-05-31 |  | 2010-05-03 | 5.1 |  | 17 | 4.2639 | 0.83611 | Test | Validate TC and Test Software
Maint - Test Eng Build | PM | Maint - Test - Eng Build - Analyze and Record Results | [6 empty] | F | 30 | Text Pages | 1 | 8 | 2.4 | 1 | 2.4 | 2010-05-24 | 18 |  |  |  | 0 | 53.84 | 1218.2654 | 97.7371 | 0.18656 | 2011-10-10 | 2010-05-31 | 2010-03-29 | 2010-05-03 | 2.4 |  | 18 | 2.4 | 2.4 | Test | Analyze and Record Results
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | G | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-05-24 | 18 |  |  |  | 0 | 53.9177 | 1223.0154 | 97.8148 | 0.36924 | 2011-03-07 | 2010-05-24 |  | 2010-04-05 | 4.75 |  | 17 | 0.40617 | 4.3438 | Document-New Technical | Doc Inspection-NT
Customer Interface Manager | MGMT | Customer Interface Manager - 4/19 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-24 | 18 |  |  |  | 0 | 54.0343 | 1224.0154 | 97.9314 | 0.077734 | 2011-03-07 | 2010-05-24 |  | 2010-05-10 | 4 |  | 18 | 1 | 1 | Task | Task
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | E | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-05-24 | 18 |  |  |  | 0 | 54.1121 | 1227.0154 | 98.0091 | 0.2332 | 2011-03-21 | 2010-05-24 |  | 2010-05-17 | 3 |  | 17 | 2.3889 | 0.61111 | Task | Task
Maint - Doc - SVD | CODE | Maint - Doc - SVD - Draft-M | [6 empty] | F | 30 | Text Pages | 1.76 | 65 | 11.0795 | 1 | 11.0795 | 2010-05-31 | 19 |  |  |  | 0 | 54.2287 | 1238.0949 | 98.1257 | 0.86126 | 2011-11-21 | 2010-06-07 |  | 2010-05-10 | 11.0795 |  | 18 | 8.7639 | 2.3157 | Document-Maintenance | Draft-M
Maint - Doc - SVD | CR | Maint - Doc - SVD - Doc Review-M | [6 empty] | F | 30 | Text Pages | 1.76 | 15 | 2.5568 | 1 | 2.5568 | 2010-05-31 | 19 |  |  |  | 0 | 54.3064 | 1240.6517 | 98.2035 | 0.19875 | 2011-12-05 | 2010-06-07 |  | 2010-05-10 | 2.5568 |  | 19 | 2.5568 | 2.5568 | Document-Maintenance | Doc Review-M
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | [6 empty] | F | 30 | Text Pages | 1.76 | 15 | 2.5568 | 1 | 2.5568 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1243.2085 | 98.3201 | 0.19875 | 2011-12-12 | 2010-06-07 |  | 2010-05-10 | 2.5568 |  | 19 | 2.5568 | 2.5568 | Document-Maintenance | Doc Inspection-M
Maint - Doc - SVD | PM | Maint - Doc - SVD - Doc PM-M | [6 empty] | F | 30 | Text Pages | 1.76 | 5 | 0.85227 | 1 | 0.85227 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1244.0608 | 98.3978 | 0.066251 | 2011-12-19 | 2010-06-07 |  | 2010-05-10 | 0.85227 |  | 19 | 0.85227 | 0.85227 | Document-Maintenance | Doc PM-M
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | F | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1247.0608 | 98.4755 | 0.2332 | 2011-12-26 | 2010-06-07 |  | 2010-05-17 | 3 |  | 19 | 3 | 3
Demo - Docs - Test Cases | CODEINSP | Demo - Docs - Test Cases - Doc Inspection-NT | [6 empty] | G | 35 | Text Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1251.4358 | 98.5921 | 0.34009 | 2011-03-21 | 2010-05-31 |  | 2010-04-12 | 4.375 |  | 18 | 2.6562 | 1.7188 | Document-New Technical | Doc Inspection-NT
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1252.4358 | 98.6353 | 0.077734 | 2011-03-28 | 2010-05-31 |  | 2010-04-12 | 1 |  | 19 | 1 | 1
Customer Interface Manager | MGMT | Customer Interface Manager - 4/26 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1253.4358 | 98.7325 | 0.077734 | 2011-03-28 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/3 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1254.4358 | 98.7649 | 0.077734 | 2011-04-04 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/10 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1255.4358 | 98.8621 | 0.077734 | 2011-04-04 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/17 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1256.4358 | 98.8729 | 0.077734 | 2011-04-04 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Postmortem Report | MGMT | Postmortem Report - Task | [6 empty] | E | 4 | Text Pages | 1 | 100 | 4 | 1 | 4 | 2010-05-31 | 19 |  |  |  | 0 | 54.423 | 1260.4358 | 98.9506 | 0.31094 | 2011-05-02 | 2010-05-31 |  | 2010-05-31 | 4 |  | 18 | 1.3889 | 2.6111 | Task | Task
Maint - Doc - SRS - Rework | CR | Maint - Doc - SRS - Rework Doc Review | [6 empty] | F |  | Text Pages | 1 |  | 9 | 1 | 9 | 2010-06-07 | 20 |  |  |  | 0 | 54.423 | 1269.4358 | 99.0672 | 0.69961 | 2012-01-30 | 2010-06-14 |  |  | 0 |  | 19 | 0.71843 | 8.2816
Customer Interface Manager | MGMT | Customer Interface Manager - 5/24 | [6 empty] | G | 1 |  |  | 100 | 4 | 1 | 4 | 2010-06-07 | 20 |  |  |  | 0 | 54.423 | 1273.4358 | 99.1449 | 0.31094 | 2011-04-18 | 2010-06-07 |  |  | 0 |  | 19 | 1.2812 | 2.7188
Customer Interface Manager | MGMT | Customer Interface Manager - 5/31 | [6 empty] | G | 1 | [5 empty] | 0 | 2010-06-07 | 20 |  |  |  | 0 | 54.423 | 1273.4358 | 99.2615 | 0 | 2011-04-18 | 2010-06-07 |  |  | 0 |  | 20 | 0 | 0
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - AIM Interface - Code Peer Review | [6 empty] | G | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-06-07 | 20 |  |  |  | 0 | 54.423 | 1277.4358 | 99.3393 | 0.31094 | 2011-05-02 | 2010-06-07 |  |  | 0 |  | 20 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | [6 empty] | G | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-06-14 | 21 |  |  |  | 0 | 54.423 | 1281.4358 | 99.4559 | 0.31094 | 2011-05-16 | 2010-06-14 |  |  | 0 |  | 20 | 1.2812 | 2.7188 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | [6 empty] | G | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-06-14 | 21 |  |  |  | 0 | 54.423 | 1285.4358 | 99.6891 | 0.31094 | 2011-05-23 | 2010-06-14 |  |  | 0 |  | 21 | 4 | 4 | Issue Fixes | Code Peer Review
Customer Interface Manager | MGMT | Customer Interface Manager - 6/7 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-06-14 | 21 |  |  |  | 0 | 54.423 | 1286.4358 | 100 | 0.077734 | 2011-05-23 | 2010-06-14 |  |  | 0 |  | 21 | 1 | 1
Generate Task List
Update Plan

## Schedule
TSP Schedule Planning Template - Form SCHEDULE
| Name | Consolidated
| Team | AIM |  |  |  |  | Total Task Plan Hours | 1286.4358
| Date | 2026-07-29 |  |  |  |  | Total Schedule Plan Hours | 1502.3
[7 empty] | Difference | -215.8642
| Cycle | 2
Date | Week | Plan Hours | Cumulative Plan Hours | Actual Hours | Cumulative Actual Hours | Planned Value | Cumulative PV | Earned Value | Cumulative EV | Predicted Hours | Cumulative Predicted Hours | Predicted Earned Value | Cumulative Predicted EV | Baseline Plan Hours | Baseline Cumulative Plan Hours | Baseline PV | Baseline Cumulative PV | Notes | Earned Value Trend
2010-01-25 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2010-02-01 | 2 | 1 | 1 | 2.28 | 2.28 | 0.077734 | 0.077734 | 0.077734 | 0.077734 |  |  | 0.077734 | 0.077734 | 1 | 1 | 0.081548 | 0.081548 |  | 0
2010-02-08 | 3 | 48.7 | 49.7 | 37.3439 | 39.6239 | 2.9379 | 3.0157 | 2.4163 | 2.4941 |  |  | 2.4163 | 2.4941 | 66 | 67 | 3.7134 | 3.7949 |  | 0.17296
2010-02-15 | 4 | 85 | 134.7 | 64.5606 | 104.1844 | 5.6272 | 8.6429 | 5.9423 | 8.4364 |  |  | 5.9423 | 8.4364 | 86 | 153 | 3.9187 | 7.7136 |  | 0.02389
2010-02-22 | 5 | 103 | 237.7 | 83.8464 | 188.0308 | 8.4116 | 17.0545 | 7.0358 | 15.4723 |  |  | 7.0358 | 15.4723 | 105 | 258 | 8.1163 | 15.8299 |  | 0.092775
2010-03-01 | 6 | 95.6 | 333.3 | 91.3806 | 279.4114 | 5.9042 | 22.9587 | 8.8931 | 24.3654 |  |  | 8.8931 | 24.3654 | 99 | 357 | 5.8388 | 21.6687 |  | -0.057735
2010-03-08 | 7 | 85 | 418.3 | 97.7117 | 377.1231 | 8.374 | 31.3327 | 8.1566 | 32.522 |  |  | 8.1566 | 32.522 | 93 | 450 | 6.9413 | 28.61 |  | -0.03657
2010-03-15 | 8 | 82.6 | 500.9 | 88.4331 | 465.5561 | 5.3763 | 36.709 | 3.9874 | 36.5094 |  |  | 3.9874 | 36.5094 | 94 | 544 | 5.576 | 34.186 |  | 0.0054356
2010-03-22 | 9 | 91 | 591.9 | 91.1819 | 556.7381 | 7.939 | 44.648 | 10.2735 | 46.7829 |  |  | 10.2735 | 46.7829 | 94 | 638 | 4.7137 | 38.8997 |  | -0.045635
2010-03-29 | 10 | 91 | 682.9 | 84.3247 | 641.0628 | 5.6072 | 50.2552 | 7.6401 | 54.423 |  |  | 7.6401 | 54.423 | 104 | 742 | 7.9942 | 46.8939 |  | -0.076582
2010-04-05 | 11 | 85.4 | 768.3 | 0.65944 | 641.7222 | 8.0126 | 58.2677 | 0 | 54.423 |  |  | 0 | 54.423 | 105 | 847 | 8.5274 | 55.4214 |  | 0.065984
2010-04-12 | 12 | 94 | 862.3 | 0 | 641.7222 | 7.0407 | 65.3085 | 0 | 54.423 |  |  | 0 | 54.423 | 104 | 951 | 7.3731 | 62.7945 |  | 0.16668
2010-04-19 | 13 | 87 | 949.3 | 0 | 641.7222 | 7.9319 | 73.2403 | 0 | 54.423 |  |  | 0 | 54.423 | 105 | 1056 | 5.0212 | 67.8157 |  | 0.25693
2010-04-26 | 14 | 89 | 1038.3 | 0 | 641.7222 | 4.9062 | 78.1466 | 0 | 54.423 |  |  | 0 | 54.423 | 104 | 1160 | 7.3323 | 75.148 |  | 0.30358
2010-05-03 | 15 | 90 | 1128.3 | 0 | 641.7222 | 6.0399 | 84.1865 | 0 | 54.423 |  |  | 0 | 54.423 | 95 | 1255 | 7.3579 | 82.5059 |  | 0.35354
2010-05-10 | 16 | 78 | 1206.3 | 0 | 641.7222 | 6.7193 | 90.9059 | 0 | 54.423 |  |  | 0 | 54.423 | 104 | 1359 | 7.1254 | 89.6313 |  | 0.40133
2010-05-17 | 17 | 69 | 1275.3 | 0 | 641.7222 | 2.0848 | 92.9907 | 0 | 54.423 |  |  | 0 | 54.423 | 95 | 1454 | 5.3043 | 94.9356 |  | 0.41475
2010-05-24 | 18 | 78 | 1353.3 | 0 | 641.7222 | 2.3903 | 95.381 | 0 | 54.423 |  |  | 0 | 54.423 | 64 | 1518 | 3.2393 | 98.1749 |  | 0.42941
2010-05-31 | 19 | 75 | 1428.3 | 0 | 641.7222 | 2.5979 | 97.9789 | 0 | 54.423 |  |  | 0 | 54.423 | 61 | 1579 | 1.2543 | 99.4292 |  | 0.44454
2010-06-07 | 20 | 66 | 1494.3 | 0 | 641.7222 | 1.3215 | 99.3004 | 0 | 54.423 |  |  | 0 | 54.423 | 46 | 1625 | 0.57083 | 100 |  | 0.45194
2010-06-14 | 21 | 8 | 1502.3 | 0 | 641.7222 | 0.69961 | 100 | 0 | 54.423 |  |  | 0 | 54.423 | [5 empty] | 0.45577
2010-06-21 | 22 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-06-28 | 23 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-07-05 | 24 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-07-12 | 25 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-07-19 | 26 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-07-26 | 27 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-08-02 | 28 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-08-09 | 29 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-08-16 | 30 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-08-23 | 31 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-08-30 | 32 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-09-06 | 33 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-09-13 | 34 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 0 | 54.423
2010-09-20 | 35 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 1.4199 | 55.8429
2010-09-27 | 36 |  |  | 0 | 641.7222 |  |  | 0 | 54.423 |  |  | 1.5955 | 57.4384
2010-10-04 | 37 | [10 empty] | 1.5955 | 59.0339
2010-10-11 | 38 | [10 empty] | 1.5955 | 60.6295
2010-10-18 | 39 | [10 empty] | 1.5955 | 62.225
2010-10-25 | 40 | [10 empty] | 1.5955 | 63.8205
2010-11-01 | 41 | [10 empty] | 1.5955 | 65.416
2010-11-08 | 42 | [10 empty] | 1.5955 | 67.0115
2010-11-15 | 43 | [10 empty] | 1.5955 | 68.607
2010-11-22 | 44 | [10 empty] | 1.5955 | 70.2025
2010-11-29 | 45 | [10 empty] | 1.5955 | 71.798
2010-12-06 | 46 | [10 empty] | 1.5955 | 73.3936
2010-12-13 | 47 | [10 empty] | 1.5955 | 74.9891
2010-12-20 | 48 | [10 empty] | 1.5955 | 76.5846
2010-12-27 | 49 | [10 empty] | 1.5955 | 78.1801
2011-01-03 | 50 | [10 empty] | 1.412 | 79.5921
2011-01-10 | 51 | [10 empty] | 1.0733 | 80.6654
2011-01-17 | 52 | [10 empty] | 1.0733 | 81.7387
2011-01-24 | 53 | [10 empty] | 1.0733 | 82.812
2011-01-31 | 54 | [10 empty] | 1.0733 | 83.8853
2011-02-07 | 55 | [10 empty] | 0.88646 | 84.7718
2011-02-14 | 56 | [10 empty] | 0.84266 | 85.6144
2011-02-21 | 57 | [10 empty] | 0.84266 | 86.4571
2011-02-28 | 58 | [10 empty] | 0.84266 | 87.2997
2011-03-07 | 59 | [10 empty] | 0.84266 | 88.1424
2011-03-14 | 60 | [10 empty] | 0.84266 | 88.9851
2011-03-21 | 61 | [10 empty] | 0.84266 | 89.8277
2011-03-28 | 62 | [10 empty] | 0.84266 | 90.6704
2011-04-04 | 63 | [10 empty] | 0.84266 | 91.513
2011-04-11 | 64 | [10 empty] | 0.80683 | 92.3199
2011-04-18 | 65 | [10 empty] | 0.4946 | 92.8145
2011-04-25 | 66 | [10 empty] | 0.4946 | 93.3091
2011-05-02 | 67 | [10 empty] | 0.46881 | 93.7779
2011-05-09 | 68 | [10 empty] | 0.44129 | 94.2192
2011-05-16 | 69 | [10 empty] | 0.42886 | 94.648
2011-05-23 | 70 | [10 empty] | 0.31899 | 94.967
2011-05-30 | 71 | [10 empty] | 0.19424 | 95.1613
2011-06-06 | 72 | [10 empty] | 0.13908 | 95.3003
2011-06-13 | 73 | [10 empty] | 0.13908 | 95.4394
2011-06-20 | 74 | [10 empty] | 0.13908 | 95.5785
2011-06-27 | 75 | [10 empty] | 0.13908 | 95.7176
2011-07-04 | 76 | [10 empty] | 0.13908 | 95.8567
2011-07-11 | 77 | [10 empty] | 0.13908 | 95.9958
2011-07-18 | 78 | [10 empty] | 0.13908 | 96.1348
2011-07-25 | 79 | [10 empty] | 0.13908 | 96.2739
2011-08-01 | 80 | [10 empty] | 0.13908 | 96.413
2011-08-08 | 81 | [10 empty] | 0.13908 | 96.5521
2011-08-15 | 82 | [10 empty] | 0.13908 | 96.6912
2011-08-22 | 83 | [10 empty] | 0.13908 | 96.8303
2011-08-29 | 84 | [10 empty] | 0.13908 | 96.9693
2011-09-05 | 85 | [10 empty] | 0.13908 | 97.1084
2011-09-12 | 86 | [10 empty] | 0.13908 | 97.2475
2011-09-19 | 87 | [10 empty] | 0.13908 | 97.3866
2011-09-26 | 88 | [10 empty] | 0.13908 | 97.5257
2011-10-03 | 89 | [10 empty] | 0.13908 | 97.6648
2011-10-10 | 90 | [10 empty] | 0.13908 | 97.8038
2011-10-17 | 91 | [10 empty] | 0.13908 | 97.9429
2011-10-24 | 92 | [10 empty] | 0.13908 | 98.082
2011-10-31 | 93 | [10 empty] | 0.13908 | 98.2211
2011-11-07 | 94 | [10 empty] | 0.13908 | 98.3602
2011-11-14 | 95 | [10 empty] | 0.13908 | 98.4993
2011-11-21 | 96 | [10 empty] | 0.13908 | 98.6383
2011-11-28 | 97 | [10 empty] | 0.13908 | 98.7774
2011-12-05 | 98 | [10 empty] | 0.13908 | 98.9165
2011-12-12 | 99 | [10 empty] | 0.13908 | 99.0556
2011-12-19 | 100 | [10 empty] | 0.13908 | 99.1947
2011-12-26 | 101 | [10 empty] | 0.13908 | 99.3338
2012-01-02 | 102 | [10 empty] | 0.13908 | 99.4728
2012-01-09 | 103 | [10 empty] | 0.13908 | 99.6119
2012-01-16 | 104 | [10 empty] | 0.13908 | 99.751
2012-01-23 | 105 | [10 empty] | 0.13908 | 99.8901
2012-01-30 | 106 | [10 empty] | 0.10991 | 100

## Risk (hidden)
Risk | Impact | Likelihood | Priority | Assigned | Date

## LOGT (hidden)
TSP Time Recording Log - Form LOGT
Name | Consolidated |  |  | Date | 2026-07-29
Team | AIM
|  |  |  | Cycle | 2
|  |  |  | Hours Logged | 641.7222
Assembly | Phase | Task | Date | Start | Int. | Stop | Delta | Comments
Test Manager | MGMT | Test Manager - Task Week 2 Feb 1 | 2010-02-04 |  |  |  | 20.3167
Test Manager | MGMT | Test Manager - Task Week 2 Feb 1 | 2010-02-05 |  |  |  | 34.4833
Test Manager | MGMT | Test Manager - Task Week 4 Feb 15 | 2010-02-19 |  |  |  | 14.8
Test Manager | MGMT | Test Manager - Task Week 4 Feb 15 | 2010-02-19 |  |  |  | 21.2833
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-22 |  |  |  | 14.5
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-22 |  |  |  | 11.5833
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-22 |  |  |  | 27.6667
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-22 |  |  |  | 14.2667
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-22 |  |  |  | 9.55
Demo - Docs - Test Cases | DLD | Demo - Docs - Test Cases - Research-NT | 2010-02-24 |  |  |  | 86.0667
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-25 |  |  |  | 61.3167
Demo - Docs - Test Cases | DLD | Demo - Docs - Test Cases - Research-NT | 2010-02-25 |  |  |  | 89.4
Demo - Docs - Test Cases | DLD | Demo - Docs - Test Cases - Research-NT | 2010-02-25 |  |  |  | 65.1
Demo - Docs - Test Cases | DLD | Demo - Docs - Test Cases - Research-NT | 2010-02-26 |  |  |  | 57.7833
Test Manager | MGMT | Test Manager - Task Week 5 Feb 22 | 2010-02-26 |  |  |  | 61.3833
Test Manager | MGMT | Test Manager - Task Week 5 Feb 22 | 2010-02-26 |  |  |  | 3.95
Demo - Docs - Test Cases | CODE | Demo - Docs - Test Cases - Draft-NT | 2010-03-01 |  |  |  | 39.75
Demo - Docs - Test Cases | CODE | Demo - Docs - Test Cases - Draft-NT | 2010-03-02 |  |  |  | 51.6833
Demo - Docs - Test Cases | CODE | Demo - Docs - Test Cases - Draft-NT | 2010-03-02 |  |  |  | 25.4333
CMMI Training | MGMT | CMMI Training - Task March 1 | 2010-03-03 |  |  |  | 132
CMMI Training | MGMT | CMMI Training - Task March 1 | 2010-03-04 |  |  |  | 132
CMMI Training | MGMT | CMMI Training - Task March 1 | 2010-03-05 |  |  |  | 132
Test Manager | MGMT | Test Manager - Task Week 6 Mar 1 | 2010-03-05 |  |  |  | 11.4333
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-08 |  |  |  | 22.5833
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-08 |  |  |  | 52.1833
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-08 |  |  |  | 39.7833
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-08 |  |  |  | 98.8667
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 81.5
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-09 |  |  |  | 33.8833
Test Manager | MGMT | Test Manager - Task Week 7 Mar 8 | 2010-03-09 |  |  |  | 47.7667
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-11 |  |  |  | 30.7167
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-11 |  |  |  | 69.2
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-11 |  |  |  | 42.9667
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-12 |  |  |  | 97.9833
Test Manager | MGMT | Test Manager - Task Week 7 Mar 8 | 2010-03-12 |  |  |  | 9.85
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 |  |  |  | 135
Demo - Docs - Test Cases | CODE | Demo - Docs - Test Cases - Draft-NT | 2010-03-19 |  |  |  | 229.4
2010-03-16
2010-03-17
2010-03-18
Test Manager | MGMT | Test Manager - Task Week 8 Mar 15 | 2010-03-19 |  |  |  | 23.65
Test Manager | MGMT | Test Manager - Task Week 9 Mar 22 | 2010-03-22 |  |  |  | 216.1167
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | 2010-03-22 |  |  |  | 20.2167
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | 2010-03-22 |  |  |  | 114.4667
2010-03-23
2010-03-24
2010-03-25
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-03-26 |  |  |  | 49.4667
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-03-26 |  |  |  | 90
Test Manager | MGMT | Test Manager - Task Week 9 Mar 22 | 2010-03-26 |  |  |  | 24.2667
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-03-29 |  |  |  | 115.65
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-03-29 |  |  |  | 18.6667
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework CODEINSP | 2010-03-30 |  |  |  | 67.35
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework CODEINSP | 2010-03-31 |  |  |  | 62.9333
2010-03-30
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | 2010-03-31 |  |  |  | 31.2833
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-04-01 |  |  |  | 108.1667
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-04-01 |  |  |  | 116.7333
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | 2010-04-02 |  |  |  | 73.4333
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | 2010-04-02 |  |  |  | 33.6333
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | 2010-04-02 |  |  |  | 15.7667
Test Manager | MGMT | Test Manager - Task Week 10 Mar 29 | 2010-04-02 |  |  |  | 28.8333
Test Manager | MGMT | Test Manager - Task Week 10 Mar 29 | 2010-04-02 |  |  |  | 29.2
Quality Manager | MGMT | Quality Manager - Task (Week 3 - 2/8/10) | 2010-02-16 |  |  |  | 48.1667
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | 2010-02-16 |  |  |  | 15.0167
Maint - LD - 957 | CODEINSP | Maint - LD - 957 - Code Peer Review | 2010-02-16 |  |  |  | 15.8667
Maint - LD - 960 | CODEINSP | Maint - LD - 960 - Code Peer Review | 2010-02-16 |  |  |  | 42.6
Add Checklist to all Review/Insp Phases | DLD | Add Checklist to all Review/Insp Phases - Research-NP | 2010-02-17 |  |  |  | 38.7667
Add Checklist to all Review/Insp Phases | CODE | Add Checklist to all Review/Insp Phases - Draft-NP | 2010-02-17 |  |  |  | 73.9167
Add Checklist to all Review/Insp Phases | CR | Add Checklist to all Review/Insp Phases - Doc Review-NP | 2010-02-18 |  |  |  | 24.8
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-18 |  |  |  | 6.6333
Add TCs to New Feature Process | DLD | Add TCs to New Feature Process - Research-NP | 2010-02-18 |  |  |  | 34.3333
Add TCs to New Feature Process | CODE | Add TCs to New Feature Process - Draft-NP | 2010-02-18 |  |  |  | 30.9333
Add TCs to New Feature Process | CR | Add TCs to New Feature Process - Doc Review-NP | 2010-02-18 |  |  |  | 18.8
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-02-18 |  |  |  | 5.6833
Quality Manager | MGMT | Quality Manager - Task (Week 4 - 2/15/10) | 2010-02-19 |  |  |  | 102.8333
Quality Manager | MGMT | Quality Manager - Task (Week 4 - 2/15/10) | 2010-02-19 |  |  |  | 22.0667
Quality Manager | MGMT | Quality Manager - Task (Week 5 - 2/22/10) | 2010-02-22 |  |  |  | 26.9
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-23 |  |  |  | 138.7833
Add PM to Dev Processes | DLD | Add PM to Dev Processes - Research-NP | 2010-02-23 |  |  |  | 47.2667
Add PM to Dev Processes | CODE | Add PM to Dev Processes - Draft-NP | 2010-02-24 |  |  |  | 58.7667
Add PM to Dev Processes | CR | Add PM to Dev Processes - Doc Review-NP | 2010-02-24 |  |  |  | 25.6333
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | 2010-02-24 |  |  |  | 10.3333
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | 2010-02-24 |  |  |  | 95.3167
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-25 |  |  |  | 52.5
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | 2010-02-25 |  |  |  | 27.4833
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | 2010-02-26 |  |  |  | 79.6333
Create Peer Review Script | DLD | Create Peer Review Script - Research-NP | 2010-02-26 |  |  |  | 76.55
Create Peer Review Script | CODE | Create Peer Review Script - Draft-NP | 2010-02-26 |  |  |  | 59.3
Quality Manager | MGMT | Quality Manager - Task (Week 5 - 2/22/10) | 2010-03-01 |  |  |  | 37.05
Create Peer Review Script | CODE | Create Peer Review Script - Draft-NP | 2010-03-01 |  |  |  | 82.5167
Create Peer Review Script | CR | Create Peer Review Script - Doc Review-NP | 2010-03-02 |  |  |  | 33.5167
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | 2010-03-02 |  |  |  | 9.05
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-03-02 |  |  |  | 26.8
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-03-02 |  |  |  | 3.75
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | 2010-03-02 |  |  |  | 13.8667
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-03-02 |  |  |  | 3.7833
Add Checklist to all Review/Insp Phases | PM | Add Checklist to all Review/Insp Phases - Doc PM-NP | 2010-03-02 |  |  |  | 13.6333
Add TCs to New Feature Process | PM | Add TCs to New Feature Process - Doc PM-NP | 2010-03-02 |  |  |  | 8.6
Add PM to Dev Processes | PM | Add PM to Dev Processes - Doc PM-NP | 2010-03-02 |  |  |  | 9.3667
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | 2010-03-02 |  |  |  | 30.9167
CMMI Training | MGMT | CMMI Training - Day 1 | 2010-03-03 |  |  |  | 216
CMMI Training | MGMT | CMMI Training - Day 2 | 2010-03-04 |  |  |  | 216
CMMI Training | MGMT | CMMI Training - Day 3 | 2010-03-05 |  |  |  | 216
Maint - LD - 953 | CODE | Maint - LD - 953 - Find and Fix | 2010-03-05 |  |  |  | 62.7833
Quality Manager | MGMT | Quality Manager - Task (Week 6 - 3/1/10) | 2010-03-08 |  |  |  | 32.65
Maint - LD - 953 | CODE | Maint - LD - 953 - Find and Fix | 2010-03-08 |  |  |  | 81.75
Maint - LD - 953 | CR | Maint - LD - 953 - Code Review | 2010-03-08 |  |  |  | 39.6333
Maint - LD - 953 | COMPILE | Maint - LD - 953 - Compile | 2010-03-08 |  |  |  | 15.2167
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | 2010-03-08 |  |  |  | 17.95
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Inspect the Document | 2010-03-08 |  |  |  | 44.3667
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Inspect the Document | 2010-03-09 |  |  |  | 139.0167
Maint - LD - 954 | CODE | Maint - LD - 954 - Find and Fix | 2010-03-09 |  |  |  | 63.7
Maint - LD - 954 | CODE | Maint - LD - 954 - Find and Fix | 2010-03-10 |  |  |  | 26.6167
Maint - LD - 954 | CR | Maint - LD - 954 - Code Review | 2010-03-10 |  |  |  | 18.8
Maint - LD - 954 | CR | Maint - LD - 954 - Code Review | 2010-03-10 |  |  |  | 27.4
Maint - LD - 954 | COMPILE | Maint - LD - 954 - Compile | 2010-03-10 |  |  |  | 5.9167
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | 2010-03-10 |  |  |  | 40.0333
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | 2010-03-11 |  |  |  | 16.25
Maint - LD - 953 | UT | Maint - LD - 953 - Unit Test | 2010-03-11 |  |  |  | 73.8333
Maint - LD - 953 | PM | Maint - LD - 953 - PM | 2010-03-11 |  |  |  | 9.4667
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Inspect the Document | 2010-03-11 |  |  |  | 113.75
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Inspect the Document | 2010-03-12 |  |  |  | 42.0833
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Inspect the Document | 2010-03-12 |  |  |  | 71.3667
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Inspect the Document | 2010-03-12 |  |  |  | 82.65
Quality Manager | MGMT | Quality Manager - Task (Week 7 - 3/8/10) | 2010-03-12 |  |  |  | 12.9333
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Attend Inspection Meeting | 2010-03-15 |  |  |  | 171.8
Maint - LD - 955 | CODE | Maint - LD - 955 - Find and Fix | 2010-03-15 |  |  |  | 49.8667
Maint - LD - 955 | CODE | Maint - LD - 955 - Find and Fix | 2010-03-16 |  |  |  | 126.8667
Maint - LD - 955 | CR | Maint - LD - 955 - Code Review | 2010-03-16 |  |  |  | 32.8333
Maint - LD - 955 | COMPILE | Maint - LD - 955 - Compile | 2010-03-16 |  |  |  | 6.4
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | 2010-03-16 |  |  |  | 12.2333
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | 2010-03-16 |  |  |  | 9.5833
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | 2010-03-16 |  |  |  | 9.8667
Create Peer Review Script | PM | Create Peer Review Script - Doc PM-NP | 2010-03-16 |  |  |  | 11.3333
Maint - LD - 954 | UT | Maint - LD - 954 - Unit Test | 2010-03-16 |  |  |  | 60.95
Maint - LD - 954 | PM | Maint - LD - 954 - PM | 2010-03-16 |  |  |  | 15.6833
Quality Manager | MGMT | Quality Manager - Task (Week 8 - 3/15/10) | 2010-03-17 |  |  |  | 86.3167
Quality Manager | MGMT | Quality Manager - Task (Week 8 - 3/15/10) | 2010-03-22 |  |  |  | 122.75
Maint - LD - 967 | CODEINSP | Maint - LD - 967 - Code Peer Review | 2010-03-23 |  |  |  | 49.35
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | 2010-03-23 |  |  |  | 165.5667
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | 2010-03-24 |  |  |  | 62.8
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | 2010-03-24 |  |  |  | 96.4333
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | 2010-03-24 |  |  |  | 83.2
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | 2010-03-25 |  |  |  | 107.9333
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | 2010-03-25 |  |  |  | 17.65
Maint - LD - 955 | UT | Maint - LD - 955 - Unit Test | 2010-03-25 |  |  |  | 42.4167
Maint - LD - 955 | PM | Maint - LD - 955 - PM | 2010-03-25 |  |  |  | 25.5333
Demo - Interface - Msg | CODE | Demo - Interface - Convert It - Flowchart and Code Logic | 2010-03-26 |  |  |  | 43
Demo - Interface - Msg | CODE | Demo - Interface - Convert It- Msg Env Database | 2010-03-26 |  |  |  | 62.1833
Quality Manager | MGMT | Quality Manager - Task (Week 9 - 3/22/10) | 2010-03-29 |  |  |  | 42.7333
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Peer Review | 2010-03-31 |  |  |  | 123.1
Demo - Interface - Msg | CODE | Demo - Interface - Convert It- Msg Env Database | 2010-03-31 |  |  |  | 256.6167
Demo - Interface - Msg | CODE | Demo - Interface - Convert It- Msg Env Database | 2010-04-01 |  |  |  | 125.6167
Demo - Interface - Msg | CR | Demo - Interface - Convert It - Code Review | 2010-04-01 |  |  |  | 88.7333
Demo - Interface - Msg | CR | Demo - Interface - Convert It - Code Review | 2010-04-01 |  |  |  | 51.7333
Demo - Interface - Msg | CR | Demo - Interface - Convert It - Code Review | 2010-04-02 |  |  |  | 91.6167
Demo - Interface - Msg | CR | Demo - Interface - Convert It - Code Review | 2010-04-02 |  |  |  | 116.4
Demo - Interface - Msg | COMPILE | Demo - Interface - Convert It - Compile | 2010-04-02 |  |  |  | 41.7167
Maint - LD - 952 | CODE | Maint - LD - 952 - Find and Fix | 2010-02-08 |  |  |  | 22.6333
Maint - LD - 957 | CODE | Maint - LD - 957 - Find and Fix | 2010-02-08 |  |  |  | 95.8
Maint - LD - 960 | CODE | Maint - LD - 960 - Find and Fix | 2010-02-08 |  |  |  | 20.9333
Maint - LD - 956 | CODE | Maint - LD - 956 - Find and Fix | 2010-02-08 |  |  |  | 57.6
Maint - LD - 960 | CODE | Maint - LD - 960 - Find and Fix | 2010-02-09 |  |  |  | 73.6
Maint - LD - 956 | CODE | Maint - LD - 956 - Find and Fix | 2010-02-09 |  |  |  | 29.9
Maint - LD - 956 | CODE | Maint - LD - 956 - Find and Fix | 2010-02-09 |  |  |  | 176.5333
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-09 |  |  |  | 68.0167
Maint - LD - 956 | CODE | Maint - LD - 956 - Find and Fix | 2010-02-10 |  |  |  | 92.65
Maint - LD - 952 | CR | Maint - LD - 952 - Code Review | 2010-02-10 |  |  |  | 3.3333
Maint - LD - 952 | COMPILE | Maint - LD - 952 - Compile | 2010-02-10 |  |  |  | 1.9333
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | 2010-02-10 |  |  |  | 12
Maint - LD - 957 | CR | Maint - LD - 957 - Code Review | 2010-02-10 |  |  |  | 9.55
Maint - LD - 957 | COMPILE | Maint - LD - 957 - Compile | 2010-02-10 |  |  |  | 1.8833
Maint - LD - 957 | CODEINSP | Maint - LD - 957 - Code Peer Review | 2010-02-10 |  |  |  | 10.1667
Maint - LD - 960 | CR | Maint - LD - 960 - Code Review | 2010-02-10 |  |  |  | 6.6667
Maint - LD - 960 | COMPILE | Maint - LD - 960 - Compile | 2010-02-10 |  |  |  | 1.5
Maint - LD - 960 | CODEINSP | Maint - LD - 960 - Code Peer Review | 2010-02-10 |  |  |  | 13.4833
Implementation | MGMT | Implementation - Task 1 | 2010-02-12 |  |  |  | 19.5167
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | 2010-02-16 |  |  |  | 43.5833
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-16 |  |  |  | 170.2833
Maint - LD - 952 | UT | Maint - LD - 952 - Unit Test | 2010-02-17 |  |  |  | 14.7667
Maint - LD - 957 | UT | Maint - LD - 957 - Unit Test | 2010-02-17 |  |  |  | 17.6833
Maint - LD - 960 | UT | Maint - LD - 960 - Unit Test | 2010-02-17 |  |  |  | 4.35
Maint - LD - 952 | PM | Maint - LD - 952 - PM | 2010-02-17 |  |  |  | 11.4
Maint - LD - 957 | PM | Maint - LD - 957 - PM | 2010-02-17 |  |  |  | 5.0833
Maint - LD - 960 | PM | Maint - LD - 960 - PM | 2010-02-17 |  |  |  | 2.9333
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-17 |  |  |  | 13.45
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-17 |  |  |  | 34.5
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-17 |  |  |  | 23.9167
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-17 |  |  |  | 167.25
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-18 |  |  |  | 286
Implementation | MGMT | Implementation - Task 2 | 2010-02-18 |  |  |  | 31.6167
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-18 |  |  |  | 34.4667
Maint - LD - 959 | CODE | Maint - LD - 959 - Find and Fix | 2010-02-18 |  |  |  | 76.2667
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-02-19 |  |  |  | 1.1167
Maint - LD - 959 | CR | Maint - LD - 959 - Code Review | 2010-02-22 |  |  |  | 83.2167
Maint - LD - 959 | CR | Maint - LD - 959 - Code Review | 2010-02-22 |  |  |  | 15.0667
Maint - LD - 959 | COMPILE | Maint - LD - 959 - Compile | 2010-02-22 |  |  |  | 3.0333
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | 2010-02-23 |  |  |  | 63.1833
Maint - LD - 961 | MGMT | Maint - LD - 961 - Task | 2010-02-23 |  |  |  | 239.5833
Maint - LD - 961 | MGMT | Maint - LD - 961 - Task | 2010-02-24 |  |  |  | 131.2167
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | 2010-02-24 |  |  |  | 30.9
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-24 |  |  |  | 58.9333
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-25 |  |  |  | 53
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | 2010-02-26 |  |  |  | 8.4333
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | 2010-02-26 |  |  |  | 3.3167
Maint - LD - 959 | UT | Maint - LD - 959 - Unit Test | 2010-02-26 |  |  |  | 22.9667
Maint - LD - 959 | UT | Maint - LD - 959 - Unit Test | 2010-02-26 |  |  |  | 38.3167
Maint - LD - 959 | UT | Maint - LD - 959 - Unit Test | 2010-02-26 |  |  |  | 40.8167
Maint - LD - 959 | PM | Maint - LD - 959 - PM | 2010-02-26 |  |  |  | 36.15
Implementation | MGMT | Implementation - Task 3 | 2010-02-26 |  |  |  | 100.95
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | 2010-03-01 |  |  |  | 88.9
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | 2010-03-02 |  |  |  | 40.1
CMMI Training | MGMT | CMMI Training - Task | 2010-03-03 |  |  |  | 264
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | 2010-03-03 |  |  |  | 62.3667
CMMI Training | MGMT | CMMI Training - Task | 2010-03-04 |  |  |  | 264
CMMI Training | MGMT | CMMI Training - Task | 2010-03-05 |  |  |  | 264
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | 2010-03-08 |  |  |  | 14.3667
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-08 |  |  |  | 96.1
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | 2010-03-08 |  |  |  | 14.75
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-08 |  |  |  | 25.2167
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | 2010-03-08 |  |  |  | 102.9667
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 105.9
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 73
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix - Create Baseline | 2010-03-09 |  |  |  | 91.8833
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-10 |  |  |  | 218
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-10 |  |  |  | 191.2667
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-10 |  |  |  | 78.9
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-11 |  |  |  | 282.55
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-11 |  |  |  | 33.3333
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-11 |  |  |  | 225
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-12 |  |  |  | 177.4833
Implementation | MGMT | Implementation - Task 4 | 2010-03-12 |  |  |  | 34.25
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-13 |  |  |  | 390
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 |  |  |  | 135
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-15 |  |  |  | 18.35
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-16 |  |  |  | 323.1833
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-17 |  |  |  | 441.3167
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-18 |  |  |  | 378.4167
Maint - CM - Create Eng Build | MGMT | Maint - CM - Create Eng Build - Task - Build System | 2010-03-23 |  |  |  | 283.4333
Maint - CM - Create Eng Build | MGMT | Maint - CM - Create Eng Build - Task - Build System | 2010-03-24 |  |  |  | 54.0833
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-24 |  |  |  | 396.8
Demo - Interface - Closure | CODE | Demo - Interface - Closure - Find and Fix | 2010-03-25 |  |  |  | 152
Demo - Interface - Closure | CR | Demo - Interface - Closure - Code Review | 2010-03-25 |  |  |  | 99.7
Demo - Interface - Closure | CR | Demo - Interface - Closure - Code Review | 2010-03-26 |  |  |  | 125.3167
Demo - Interface - Closure | CR | Demo - Interface - Closure - Code Review | 2010-03-26 |  |  |  | 49.4667
Implementation | MGMT | Implementation - Task 5 | 2010-03-26 |  |  |  | 46.9833
Demo - Interface - Closure | COMPILE | Demo - Interface - Closure - Compile | 2010-03-26 |  |  |  | 5.5667
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review - Prepare Material | 2010-03-29 |  |  |  | 57.6667
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | 2010-03-29 |  |  |  | 9.2833
Demo - Interface - Msg | CODE | Demo - Interface - Msg - Find and Fix | 2010-03-29 |  |  |  | 179.9667
Demo - Interface - Msg | CODE | Demo - Interface - Msg - Find and Fix | 2010-03-30 |  |  |  | 64.9167
Demo - Interface - Msg | CODE | Demo - Interface - Msg - Find and Fix | 2010-03-30 |  |  |  | 344.0167
Demo - Interface - Msg | CODE | Demo - Interface - Msg - Find and Fix | 2010-03-31 |  |  |  | 136.7333
Demo - Interface - Process | CODE | Demo - Interface - Process - Find and Fix | 2010-03-31 |  |  |  | 202.25
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | 2010-03-31 |  |  |  | 18.25
Demo - Interface - Process | PM | Demo - Interface - Process - PM | 2010-03-31 |  |  |  | 7.9167
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | 2010-03-31 |  |  |  | 11.55
Demo - Interface - Msg | CR | Demo - Interface - Msg - Code Review | 2010-03-31 |  |  |  | 195.3167
Demo - Interface - Msg | CR | Demo - Interface - Msg - Code Review | 2010-04-01 |  |  |  | 17.0167
Demo - Interface - Msg | CR | Demo - Interface - Msg - Code Review | 2010-04-01 |  |  |  | 57.05
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-05 |  |  |  | 39
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-05 |  |  |  | 24
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-05 |  |  |  | 19
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-16 |  |  |  | 62
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-17 |  |  |  | 122
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-18 |  |  |  | 82
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-18 |  |  |  | 86
Demo - Docs - Req Doc | DLD | Demo - Docs - Req Doc - Research-NT | 2010-02-18 |  |  |  | 42
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-18 |  |  |  | 72
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-19 |  |  |  | 77
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-19 |  |  |  | 98
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-22 |  |  |  | 54
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-23 |  |  |  | 52
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-23 |  |  |  | 67
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-24 |  |  |  | 48
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-24 |  |  |  | 43
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-25 |  |  |  | 64
Demo - Docs - Req Doc | CODE | Demo - Docs - Req Doc - Draft-NT | 2010-02-25 |  |  |  | 42
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | 2010-02-26 |  |  |  | 74
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | 2010-02-26 |  |  |  | 24
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | 2010-02-26 |  |  |  | 31
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | 2010-02-26 |  |  |  | 50
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | 2010-02-26 |  |  |  | 51
Maint - Doc - REQM | MGMT | Maint - Doc - REQM - Task | 2010-03-01 |  |  |  | 29
CMMI Training | MGMT | CMMI Training - Task | 2010-03-03 |  |  |  | 180
CMMI Training | MGMT | CMMI Training - Task | 2010-03-04 |  |  |  | 180
CMMI Training | MGMT | CMMI Training - Task | 2010-03-05 |  |  |  | 120
Demo - Docs - Req Doc | CR | Demo - Docs - Req Doc - Doc Review-NT | 2010-03-08 |  |  |  | 49.6333
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-03-08 |  |  |  | 16.5333
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 28.8333
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 50.9167
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 20.1833
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 30.9833
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 |  |  |  | 148.3
Demo - Docs - Req Doc | PM | Demo - Docs - Req Doc - Doc PM-NT | 2010-03-16 |  |  |  | 13.2333
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 9.3
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 7.3667
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 12.5667
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 1.5667
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 20.25
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 7.8833
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 26.1333
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-17 |  |  |  | 20.1667
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 10.2667
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 26.05
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 15.1
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 22.8667
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 28.7167
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 25.6833
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 6.65
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 33.0833
Demo - Docs - Req Doc - Rework | DLD | Demo - Docs - Req Doc - Rework - Research-NT | 2010-03-18 |  |  |  | 20.8667
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-18 |  |  |  | 18.95
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 20.2833
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 30.5667
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 15.85
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 14.7667
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 20.1167
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 24.0667
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 23.25
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 16.9833
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-19 |  |  |  | 41.3
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-20 |  |  |  | 70.7333
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-23 |  |  |  | 40.8667
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-23 |  |  |  | 18.9167
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-23 |  |  |  | 44.2333
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 47.3167
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 12.6333
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 102.9167
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 35.5833
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 41.3333
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 19.1833
Demo - Docs - Req Doc - Rework | CODE | Demo - Docs - Req Doc - Rework - Draft-NT | 2010-03-24 |  |  |  | 17.7833
Demo - Docs - Req Doc - Rework | CR | Demo - Docs - Req Doc - Rework - Doc Review-NT | 2010-03-24 |  |  |  | 6.1167
Demo - Docs - Req Doc - Rework | CR | Demo - Docs - Req Doc - Rework - Doc Review-NT | 2010-03-24 |  |  |  | 18.6167
Demo - Docs - Req Doc - Rework | CR | Demo - Docs - Req Doc - Rework - Doc Review-NT | 2010-03-25 |  |  |  | 65.8667
Demo - Docs - Req Doc - Rework | CR | Demo - Docs - Req Doc - Rework - Doc Review-NT | 2010-03-25 |  |  |  | 17.9
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | 2010-03-25 |  |  |  | 15.3
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | 2010-03-25 |  |  |  | 15.3833
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | 2010-03-26 |  |  |  | 48.95
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | 2010-03-26 |  |  |  | 16.3
Maint - Test Eng Build | CODE | Maint - Test - Eng Build - Write Test Cases | 2010-03-26 |  |  |  | 23.6
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-30 |  |  |  | 42.5833
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-30 |  |  |  | 53.6167
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-30 |  |  |  | 50.2667
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-30 |  |  |  | 64.3333
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-30 |  |  |  | 30.3667
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 25.0333
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 4.4
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 18.3167
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 12.4167
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 10.85
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 16.6167
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 6.65
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 4.1667
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 30.95
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-03-31 |  |  |  | 10.6833
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | 2010-03-31 |  |  |  | 22.8667
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | 2010-03-31 |  |  |  | 19.0833
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | 2010-04-01 |  |  |  | 57.35
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-04-01 |  |  |  | 25.15
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-04-01 |  |  |  | 35
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | 2010-04-01 |  |  |  | 9.6333
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | 2010-04-02 |  |  |  | 31.0833
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | 2010-04-02 |  |  |  | 24.8167
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | 2010-04-02 |  |  |  | 37.3167
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | 2010-04-02 |  |  |  | 11.7
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | 2010-04-02 |  |  |  | 10.5
Define a Design Standard | DLD | Define a Design Standard - Research-NT | 2010-02-08 |  |  |  | 254.25
Define a Design Standard | DLD | Define a Design Standard - Research-NT | 2010-02-09 |  |  |  | 337.1833
Define a Design Standard | DLD | Define a Design Standard - Research-NT | 2010-02-10 |  |  |  | 253.0333
Define a Design Standard | CODE | Define a Design Standard - Draft-NT | 2010-02-11 |  |  |  | 78.1167
Maint - LD - 960 | CODEINSP | Maint - LD - 960 - Code Peer Review | 2010-02-11 |  |  |  | 27.2
Maint - LD - 952 | CODEINSP | Maint - LD - 952 - Code Peer Review | 2010-02-11 |  |  |  | 24.2333
Maint - LD - 957 | CODEINSP | Maint - LD - 957 - Code Peer Review | 2010-02-11 |  |  |  | 39.4333
Design Manager | MGMT | Design Manager - Week 3 (02/08/2010) | 2010-02-11 |  |  |  | 158.35
Define a Design Standard | CODE | Define a Design Standard - Draft-NT | 2010-02-12 |  |  |  | 263.2
Support Manager | MGMT | Support Manager - Week 3 (02/08/2010) | 2010-02-12 |  |  |  | 26.0833
Support Manager
Define a Design Standard | CODE | Define a Design Standard - Draft-NT | 2010-02-16 |  |  |  | 271.45
Define a Design Standard | CODE | Define a Design Standard - Draft-NT | 2010-02-17 |  |  |  | 82.9167
Design Manager | MGMT | Design Manager - Week 4 (02/15/2010) | 2010-02-17 |  |  |  | 98.7
Define a Design Standard | CR | Define a Design Standard - Doc Review-NT | 2010-02-17 |  |  |  | 89.1667
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | 2010-02-17 |  |  |  | 93.2333
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | 2010-02-18 |  |  |  | 336.1167
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | 2010-02-19 |  |  |  | 272.1667
Support Manager | MGMT | Support Manager - Week 4 (02/15/2010) | 2010-02-19 |  |  |  | 15.95
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-19 |  |  |  | 29.8167
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-02-19 |  |  |  | 34.1833
Add TCs to New Feature Process
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | 2010-02-22 |  |  |  | 200.1833
Design Manager | MGMT | Design Manager - Week 5 (02/22/2010) | 2010-02-22 |  |  |  | 81.8167
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | 2010-02-22 |  |  |  | 60.6
Maint - LD - 959 | CODEINSP | Maint - LD - 959 - Code Peer Review | 2010-02-23 |  |  |  | 97.05
Demo - GUI - GUI Desktop | CODE | Demo - GUI - GUI Desktop - Find and Fix | 2010-02-23 |  |  |  | 274.45
Support Manager | MGMT | Support Manager - Week 5 (02/22/2010) | 2010-02-24 |  |  |  | 5.1833
Demo - GUI - GUI Popups | CODE | Demo - GUI - GUI Popups - Find and Fix | 2010-02-24 |  |  |  | 327.5333
Define a Design Standard | DLD | Define a Design Standard - Research-NT | 2010-02-25 |  |  |  | 180.9667
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-25 |  |  |  | 80.15
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | 2010-02-26 |  |  |  | 30.1167
Define a Design Standard | PM | Define a Design Standard - Doc PM-NT | 2010-02-26 |  |  |  | 83.15
Demo - Docs - HLD Doc | DLD | Demo - Docs - HLD Doc - Research-NT | 2010-02-26 |  |  |  | 195.25
Demo - GUI - GUI Popups | CODE | Demo - GUI - GUI Popups - Find and Fix | 2010-03-01 |  |  |  | 265.2333
Demo - GUI - GUI Popups | CODE | Demo - GUI - GUI Popups - Find and Fix | 2010-03-02 |  |  |  | 558.2333
CMMI Training | MGMT | CMMI Training (03/01/2010) | 2010-03-03 |  |  |  | 300
CMMI Training | MGMT | CMMI Training (03/01/2010) | 2010-03-04 |  |  |  | 300
CMMI Training | MGMT | CMMI Training (03/01/2010) | 2010-03-05 |  |  |  | 300
Design Manager | MGMT | Design Manager - Week 6 (03/01/2010) | 2010-03-05 |  |  |  | 0.05
Support Manager | MGMT | Support Manager - Week 6 (03/01/2010) | 2010-03-05 |  |  |  | 0.1
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | 2010-03-08 |  |  |  | 40.1667
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | 2010-03-08 |  |  |  | 37.3
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | 2010-03-08 |  |  |  | 47.2
Demo - GUI - AIM Interface | CODE | Demo - GUI - AIM Interface - Find and Fix | 2010-03-08 |  |  |  | 143.1667
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 144.2
Demo - GUI - AIM Interface | CODE | Demo - GUI - AIM Interface - Find and Fix | 2010-03-09 |  |  |  | 197.1333
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | 2010-03-10 |  |  |  | 14.3
Demo - GUI - AIM Interface | CODE | Demo - GUI - AIM Interface - Find and Fix | 2010-03-10 |  |  |  | 215.2333
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | 2010-03-10 |  |  |  | 20.85
Demo - GUI - AIM Interface | CODE | Demo - GUI - AIM Interface - Find and Fix | 2010-03-10 |  |  |  | 172.2
Demo - GUI - AIM Interface | CODE | Demo - GUI - AIM Interface - Find and Fix | 2010-03-11 |  |  |  | 465.45
Demo - GUI - AIM Interface | CR | Demo - GUI - AIM Interface - Code Review | 2010-03-15 |  |  |  | 242.1
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 |  |  |  | 40.1667
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 |  |  |  | 135.1833
Demo - GUI - GUI Desktop | CR | Demo - GUI - GUI Desktop - Code Review | 2010-03-16 |  |  |  | 359.9167
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | 2010-03-16 |  |  |  | 39.9667
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | 2010-03-17 |  |  |  | 29.9833
Demo - GUI - GUI Popups | CR | Demo - GUI - GUI Popups - Code Review | 2010-03-17 |  |  |  | 419.95
Demo - GUI - GUI Popups | CR | Demo - GUI - GUI Popups - Code Review | 2010-03-18 |  |  |  | 192.9833
Design Manager | MGMT | Design Manager - Week 8 (03/15/2010) | 2010-03-19 |  |  |  | 109.9167
Support Manager | MGMT | Support Manager - Week 8 (03/15/2010) | 2010-03-19 |  |  |  | 19.9167
Demo - Docs - HLD Doc | DLD | Demo - Docs - HLD Doc - Research-NT | 2010-03-22 |  |  |  | 139.8667
Maint - LD - 967 | CODEINSP | Maint - LD - 967 CODEINSP | 2010-03-23 |  |  |  | 43.65
Demo - Docs - HLD Doc | DLD | Demo - Docs - HLD Doc - Research-NT | 2010-03-23 |  |  |  | 374.9333
Demo - Docs - HLD Doc | DLD | Demo - Docs - HLD Doc - Research-NT | 2010-03-24 |  |  |  | 164.3
Demo - GUI - AIM Interface | CR | Demo - GUI - AIM Interface - Code Review | 2010-03-24 |  |  |  | 240.05
Demo - Docs - HLD Doc | CODE | Demo - Docs - HLD Doc - Draft-NT | 2010-03-25 |  |  |  | 420.05
Demo - GUI - AIM Interface | COMPILE | Demo - GUI - AIM Interface - Compile | 2010-03-26 |  |  |  | 8.7
Demo - GUI - GUI Desktop | COMPILE | Demo - GUI - GUI Desktop - Compile | 2010-03-26 |  |  |  | 7.1833
Demo - GUI - GUI Popups | COMPILE | Demo - GUI - GUI Popups - Compile | 2010-03-26 |  |  |  | 10.2167
Demo - Docs - HLD Doc | CODE | Demo - Docs - HLD Doc - Draft-NT | 2010-03-26 |  |  |  | 168.25
Design Manager | MGMT | Design Manager - Week 9 (03/22/2010) | 2010-03-26 |  |  |  | 117.3667
Support Manager | MGMT | Support Manager - Week 9 (03/22/2010) | 2010-03-26 |  |  |  | 40.1
Demo - Docs - HLD Doc | CR | Demo - Docs - HLD Doc - Doc Review-NT | 2010-03-29 |  |  |  | 157.15
Demo - Docs - HLD Doc | CR | Demo - Docs - HLD Doc - Doc Review-NT | 2010-03-29 |  |  |  | 79.2
Maint - LD - 998 | CODE | Maint - LD - 998 Find and Fix | 2010-03-30 |  |  |  | 127.4
Maint - LD - 998 | CR | Maint - LD - 998 Code Review | 2010-03-30 |  |  |  | 17.9
Maint - LD - 998 | COMPILE | Maint - LD - 998 Compile | 2010-03-30 |  |  |  | 1.9167
Maint - LD - 998 | CODEINSP | Maint - LD - 998 Code Peer Review | 2010-03-30 |  |  |  | 14.6333
Maint - LD - 997 | CODE | Maint - LD - 997 Find and Fix | 2010-03-30 |  |  |  | 203.6
Maint - LD - 999 | CODE | Maint - LD - 999 Find and Fix | 2010-03-31 |  |  |  | 159.9667
Maint - LD - 999 | CR | Maint - LD - 999 Code Review | 2010-03-31 |  |  |  | 21.1333
Maint - LD - 999 | CODEINSP | Maint - LD - 999 Code Peer Review | 2010-03-31 |  |  |  | 3.2
Maint - LD - 997 | CODE | Maint - LD - 997 Find and Fix | 2010-03-31 |  |  |  | 200.1333
Maint - LD - 997 | CODE | Maint - LD - 997 Find and Fix | 2010-04-01 |  |  |  | 140.1
Maint - LD - 997 | CR | Maint - LD - 997 Code Review | 2010-04-01 |  |  |  | 26.1333
Maint - LD - 997 | COMPILE | Maint - LD - 997 Compile | 2010-04-01 |  |  |  | 1.3167
Maint - LD - 997 | CODEINSP | Maint - LD - 997 Code Peer Review | 2010-04-01 |  |  |  | 49.1333
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - AIM Interface - Code Peer Review | 2010-04-02 |  |  |  | 68.6333
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | 2010-04-02 |  |  |  | 60.3
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | 2010-04-02 |  |  |  | 66.2167
Maint - LD - 952 | CODEINSP | Maint - LD - 952 CODEINSP | 2010-02-16 |  |  |  | 10.35
Maint - LD - 957 | CODEINSP | Maint - LD - 957 CODEINSP | 2010-02-16 |  |  |  | 12.9333
Maint - LD - 960 | CODEINSP | Maint - LD - 960 CODEINSP | 2010-02-16 |  |  |  | 6.1
Maint - LD - 884 | CODE | Maint - LD - 884 - Find and Fix | 2010-02-17 |  |  |  | 54.6333
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 |  |  |  | 23.3667
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-18 |  |  |  | 7.7167
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 |  |  |  | 11.05
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 |  |  |  | 4.9667
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 |  |  |  | 5.9667
Maint - LD - 884 | CODE | Maint - LD - 884 - Find and Fix | 2010-02-18 |  |  |  | 38.2
Maint - LD - 884 | CR | Maint - LD - 884 - Code Review | 2010-02-18 |  |  |  | 10.1667
Maint - LD - 884 | COMPILE | Maint - LD - 884 - Compile | 2010-02-18 |  |  |  | 4.3
Customer Interface Manager | MGMT | Customer Interface Manager - 2/15 | 2010-02-18 |  |  |  | 35
Maint - LD - 959 | CODEINSP | Maint - LD - 959 CODEINSP | 2010-02-23 |  |  |  | 55
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | 2010-02-23 |  |  |  | 20.15
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | 2010-02-23 |  |  |  | 24.2
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-24 |  |  |  | 42.6833
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-25 |  |  |  | 54
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | 2010-02-25 |  |  |  | 50
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | 2010-02-26 |  |  |  | 40
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | 2010-02-26 |  |  |  | 52.1833
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | 2010-03-01 |  |  |  | 25.1667
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | 2010-03-01 |  |  |  | 5.05
Maint - LD - 884 | PM | Maint - LD - 884 - PM | 2010-03-01 |  |  |  | 7.05
Maint - LD - 885 | CODE | Maint - LD - 885 - Find and Fix | 2010-03-01 |  |  |  | 47.0833
Maint - LD - 885 | CR | Maint - LD - 885 - Code Review | 2010-03-02 |  |  |  | 9.0833
Maint - LD - 884 | COMPILE | Maint - LD - 884 - Compile | 2010-03-02 |  |  |  | 14.85
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | 2010-03-02 |  |  |  | 51.35
Maint - LD - 885 | UT | Maint - LD - 885 - Unit Test | 2010-03-02 |  |  |  | 39.6833
Customer Interface Manager | MGMT | Customer Interface Manager - 3/1 | 2010-03-03 |  |  |  | 37.4
Maint - LD - 885 | CODE | Maint - LD - 885 - Find and Fix | 2010-03-03 |  |  |  | 65.9667
Maint - LD - 885 | CR | Maint - LD - 885 - Code Review | 2010-03-03 |  |  |  | 67.3667
Maint - LD - 885 | COMPILE | Maint - LD - 885 - Compile | 2010-03-03 |  |  |  | 4.15
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | 2010-03-04 |  |  |  | 45.0167
Maint - LD - 885 | UT | Maint - LD - 885 - Unit Test | 2010-03-04 |  |  |  | 30.1167
Maint - LD - 885 | PM | Maint - LD - 885 - PM | 2010-03-04 |  |  |  | 8.0333
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | 2010-03-03 |  |  |  | 19.2833
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | 2010-03-04 |  |  |  | 4.8
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-03-04 |  |  |  | 21.7
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-04 |  |  |  | 97.15
Customer Interface Manager | MGMT | Customer Interface Manager - 3/1 | 2010-03-04 |  |  |  | 6.2
Cycle Postmortem | MGMT | Cycle Postmortem - Task | 2010-03-01 |  |  |  | 40
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-08 |  |  |  | 11.6333
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 |  |  |  | 17.05
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-09 |  |  |  | 97.1667
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | 2010-03-11 |  |  |  | 4.6167
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-11 |  |  |  | 130.3
Customer Interface Manager | MGMT | Customer Interface Manager - 3/8 | 2010-03-09 |  |  |  | 30
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 |  |  |  | 120
Maint - LD - 985 | CODE | Maint - LD - 985 - Find and Fix | 2010-03-15 |  |  |  | 23.3833
Maint - LD - 985 | CR | Maint - LD - 985 - Code Review | 2010-03-15 |  |  |  | 7.3833
Maint - LD - 985 | COMPILE | Maint - LD - 985 - Compile | 2010-03-15 |  |  |  | 5.35
Maint - LD - 985 | CODEINSP | Maint - LD - 985 - Code Peer Review | 2010-03-16 |  |  |  | 45
Customer Interface Manager | MGMT | Customer Interface Manager - 3/15 | 2010-03-16 |  |  |  | 7.15
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | 2010-03-16 |  |  |  | 95.95
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-16 |  |  |  | 170.2333
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-17 |  |  |  | 105.9333
Maint - LD - 967 | CODE | Maint - LD - 967 - Find and Fix | 2010-03-22 |  |  |  | 5.5
Maint - LD - 967 | CR | Maint - LD - 967 - Code Review | 2010-03-22 |  |  |  | 12.2667
Maint - LD - 967 | COMPILE | Maint - LD - 967 - Compile | 2010-03-22 |  |  |  | 5.1
Maint - LD - 967 | CODEINSP | Maint - LD - 967 - Code Peer Review | 2010-03-22 |  |  |  | 17
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | 2010-03-22 |  |  |  | 8.9
Maint - LD - 985 | UT | Maint - LD - 985 - Unit Test | 2010-03-23 |  |  |  | 54.2333
Maint - LD - 985 | PM | Maint - LD - 985 - PM | 2010-03-23 |  |  |  | 21.2833
Maint - LD - 967 | UT | Maint - LD - 967 - Unit Test | 2010-03-23 |  |  |  | 161.05
Maint - LD - 918 | CR | Maint - LD - 918 - Code Review | 2010-03-25 |  |  |  | 154.8667
Maint - LD - 967 | PM | Maint - LD - 967 - PM | 2010-03-23 |  |  |  | 8
Planning Manager | MGMT | Planning Manager - Week 3 | 2010-02-08 |  |  |  | 22.7
Planning Manager | MGMT | Planning Manager - Week 3 | 2010-02-12 |  |  |  | 32.0333
Process Manager | MGMT | Process Manager - Week 3 | 2010-02-12 |  |  |  | 7.1167
Planning Manager | MGMT | Planning Manager - Week 4 | 2010-02-16 |  |  |  | 8.4667
Planning Manager | MGMT | Planning Manager - Week 4 | 2010-02-16 |  |  |  | 9.6833
Process Manager | MGMT | Process Manager - Week 4 | 2010-02-16 |  |  |  | 5.6833
Planning Manager | MGMT | Planning Manager - Week 4 | 2010-02-18 |  |  |  | 21.0833
Planning Manager | MGMT | Planning Manager - Week 4 | 2010-02-18 |  |  |  | 14.9667
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-19 |  |  |  | 28.1333
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-19 |  |  |  | 20.35
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-20 |  |  |  | 109.6833
Planning Manager | MGMT | Planning Manager - Week 4 | 2010-02-20 |  |  |  | 10.9667
Planning Manager | MGMT | Planning Manager - Week 5 | 2010-02-22 |  |  |  | 46.2667
MGMT
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-23 |  |  |  | 31.5167
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-23 |  |  |  | 2.7667
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-23 |  |  |  | 80.9167
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-24 |  |  |  | 52.7667
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-24 |  |  |  | 24.6833
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-25 |  |  |  | 22.2667
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-25 |  |  |  | 7.35
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-25 |  |  |  | 29.6833
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-25 |  |  |  | 10.4333
Planning Manager | MGMT | Planning Manager - Week 5 | 2010-02-26 |  |  |  | 5.6333
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-02-26 |  |  |  | 31.7167
Planning Manager | MGMT | Planning Manager - Week 6 | 2010-03-01 |  |  |  | 5.6667
Process Manager | MGMT | Process Manager - Week 6 | 2010-03-01 |  |  |  | 24.7667
Planning Manager | MGMT | Planning Manager - Week 6 | 2010-03-01 |  |  |  | 7.8167
Postmortem Report - Cycle1 | MGMT | Postmortem Report - Cycle1 - Task | 2010-03-01 |  |  |  | 2.4
Planning Manager | MGMT | Planning Manager - Week 6 | 2010-03-01 |  |  |  | 64.3667
Planning Manager | MGMT | Planning Manager - Week 6 | 2010-03-05 |  |  |  | 7.4
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-08 |  |  |  | 11.1
Process Manager | MGMT | Process Manager - Week 7 | 2010-03-08 |  |  |  | 17.7667
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-08 |  |  |  | 11.0667
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-08 |  |  |  | 2.7833
Process Manager | MGMT | Process Manager - Week 7 | 2010-03-08 |  |  |  | 2.2667
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-08 |  |  |  | 5.7167
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-08 |  |  |  | 6.1833
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-11 |  |  |  | 14.65
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-12 |  |  |  | 9.4833
Planning Manager | MGMT | Planning Manager - Week 7 | 2010-03-12 |  |  |  | 39
Planning Manager | MGMT | Planning Manager - Week 8 | 2010-03-15 |  |  |  | 37.8667
Process Manager | MGMT | Process Manager - Week 8 | 2010-03-15 |  |  |  | 22.7833
Planning Manager | MGMT | Planning Manager - Week 8 | 2010-03-15 |  |  |  | 17.1667
Planning Manager | MGMT | Planning Manager - Week 8 | 2010-03-16 |  |  |  | 6.0667
Planning Manager | MGMT | Planning Manager - Week 8 | 2010-03-16 |  |  |  | 20.6667
Planning Manager | MGMT | Planning Manager - Week 9 | 2010-03-22 |  |  |  | 30.7
Process Manager | MGMT | Process Manager - Week 9 | 2010-03-22 |  |  |  | 14.1333
Planning Manager | MGMT | Planning Manager - Week 9 | 2010-03-22 |  |  |  | 22.4
Planning Manager | MGMT | Planning Manager - Week 9 | 2010-03-26 |  |  |  | 5.3167
Planning Manager | MGMT | Planning Manager - Week 10 | 2010-03-29 |  |  |  | 32.3167
Process Manager | MGMT | Process Manager - Week 10 | 2010-03-29 |  |  |  | 5.6333
Planning Manager | MGMT | Planning Manager - Week 10 | 2010-03-31 |  |  |  | 10.5167
Planning Manager | MGMT | Planning Manager - Week 10 | 2010-04-01 |  |  |  | 5.35
Planning Manager | MGMT | Planning Manager - Week 11 | 2010-04-05 |  |  |  | 25.35
Process Manager | MGMT | Process Manager - Week 11 | 2010-04-05 |  |  |  | 14.2167

## LOGD (hidden)
TSP Defect Recording Log - Form LOGD
Name | Consolidated |  |  | Date | 2026-07-29
Team | AIM
|  |  |  | Cycle | 2
Date | Num | Type | Assembly | Injected | Removed | Fix Time | Fix Ref. | Description
2010-03-22 |  | 270 | Demo - Docs - Test Cases | CODE | CR | 20 |  | Okay Comment
2010-03-22 |  | 240 | Demo - Docs - Test Cases | CODE | CR | 5 |  | Okay Comment
2010-03-22 |  | 270 | Demo - Docs - Test Cases | CODE | CR | 2 |  | Okay Comment
2010-03-22 |  | 240 | Demo - Docs - Test Cases | CODE | CR | 1 |  | Okay Comment
2010-03-22 |  | 240 | Demo - Docs - Test Cases | CODE | CR | 5 |  | Okay Comment
2010-03-22 |  | 240 | Demo - Docs - Test Cases | CODE | CR | 2 |  | Okay Comment
2010-03-31 |  | 240 | Demo - Docs - Test Cases | CODE | CR | 3 |  | Okay Comment
2010-03-31 |  | 260 | Demo - Docs - Test Cases | CODE | CR | 0.5 |  | Okay Comment
2010-03-31 |  | 200 | Demo - Docs - Test Cases | CODE | CR | 2 |  | Okay Comment
2010-03-31 |  | 200 | Demo - Docs - Test Cases | CODE | CR | 2 |  | Okay Comment
2010-03-31 |  | 280 | Demo - Docs - Test Cases | CODE | CR | 5 |  | Okay Comment
2010-03-31 |  | 270 | Demo - Docs - Test Cases | CODE | CR | 0.5 |  | Okay Comment
2010-04-02 |  | 200 | Demo - Docs - Test Cases | CODE | CR | 1 |  | Okay Comment
2010-04-02 |  | 270 | Demo - Docs - Test Cases | CODE | CR | 1 |  | Okay Comment
2010-02-18 |  | 250 | Add Checklist to all Review/Insp Phases | CODE | CR | 1 |  | Good Descriptions
2010-02-24 |  | 250 | Add PM to Dev Processes | CODE | CR | 1 |  | Good Descriptions
2010-02-24 |  | 230 | Add PM to Dev Processes | CODE | CR | 2 |  | Good Descriptions
2010-03-02 |  | 200 | Add Checklist to all Review/Insp Phases | CODE | CODEINSP | 2 |  | Good Descriptions
2010-03-02 |  | 260 | Add Checklist to all Review/Insp Phases | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-02 |  | 200 | Add Checklist to all Review/Insp Phases | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-02 |  | 240 | Add PM to Dev Processes | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-02 |  | 240 | Add PM to Dev Processes | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-02 |  | 240 | Add PM to Dev Processes | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-02 |  | 230 | Add TCs to New Feature Process | CODE | CODEINSP | 2 |  | Good Descriptions
2010-03-16 |  | 10 | Maint - LD - 955 | CODE | CR | 1 |  | Good Descriptions
2010-03-16 |  | 20 | Maint - LD - 955 | CODE | COMPILE | 1 |  | Good Descriptions
2010-03-16 |  | 260 | Create Peer Review Script | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-16 |  | 200 | Create Peer Review Script | CODE | CODEINSP | 1 |  | Good Descriptions
2010-03-16 |  | 240 | Create Peer Review Script | CODE | CODEINSP | 1 |  | Good Descriptions
2010-04-02 |  | 20 | Demo - Interface - Msg | CODE | CR | 1 |  | Good Descriptions
2010-02-16 |  | 20 | Maint - LD - 952 | CODE | CODEINSP | 1 |  | Okay comments
2010-02-22 |  | 90 | Maint - LD - 959 | CODE | CR | 1 |  | Okay comments
2010-02-26 |  | 80 | Maint - LD - 959 | CODE | CODEINSP | 1 |  | Okay comments
2010-02-26 |  | 80 | Maint - LD - 959 | CODE | CODEINSP | 1 |  | Okay comments
2010-02-26 |  | 80 | Maint - LD - 959 | CODE | CODEINSP | 1 |  | Okay comments
2010-03-08 |  | 260 | Demo - Docs - Req Doc | CODE | CR | 0.5 |  | Good Description
2010-03-08 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 8 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.2 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.2 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.2 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.3 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.5 |  | Good Description
2010-03-25 |  | 200 | Demo - Docs - Req Doc | CODE | CR | 0.5 |  | Good Description
2010-02-17 |  | 240 | Define a Design Standard | CODE | CODEINSP | 7 |  | Good Description
2010-02-17 |  | 260 | Define a Design Standard | CODE | CODEINSP | 1 |  | Good Description
2010-02-17 |  | 260 | Define a Design Standard | CODE | CODEINSP | 1 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 5 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 5 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 3 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 3 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 7 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 9 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 1 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 3 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 4 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-02-25 |  | 260 | Define a Design Standard | CODE | CODEINSP | 2 |  | Good Description
2010-03-25 |  | 70 | Demo - GUI - GUI Popups | CODE | CR | 5 |  | Good Description
2010-03-25 |  | 20 | Demo - GUI - AIM Interface | CODE | COMPILE | 25 |  | Good Description
2010-03-25 |  | 30 | Demo - GUI - AIM Interface | CODE | CR | 45 |  | Good Description
2010-03-25 |  | 80 | Demo - GUI - GUI Desktop | CODE | CR | 5 |  | Good Description
2010-03-25 |  | 80 | Demo - GUI - AIM Interface | CODE | CR | 5 |  | Good Description
2010-04-01 |  | 20 | Maint - LD - 997 | CODE | COMPILE | 3 |  | Good Description
2010-03-02 |  | 40 | Maint - LD - 885 | CODE | CR | 5 |  | okay comments
2010-03-03 |  | 60 | Maint - LD - 885 | CODE | CR | 66 |  | okay comments
2010-03-23 |  | 80 | Maint - LD - 967 | CODE | UT | 161.1 |  | okay comments

## Week
TSP Week Summary - Form WEEK
Name | Consolidated |  |  |  |  | Date | 2026-07-29
Team | AIM
Status for Week | 10 | Selected Assembly |  |  |  | Cycle | 2
Week Date | 2010-03-29 | SYSTEM
Task Hours %Change |  | Weekly Data | Plan | Actual | Plan / Actual | Plan - Actual | Project End Dates
Baseline | 1519.3157 | Schedule hours for this week | 91 | 84.3247 | 1.0792 | 6.6753 | Baseline | 2010-06-07
Current | 1286.4358 | Schedule hours this cycle to date | 682.9 | 641.0628 | 1.0653 | 41.8372 | Plan | 2010-06-14
%Change | -15.33% | Earned value for this week | 5.6072 | 7.6401 | 0.73392 | -2.0329 | Predicted | 2012-01-30
|  | Earned value this cycle to date | 50.2552 | 54.423 | 0.92342 | -4.1678
|  | To-date hours for tasks completed | 700.1171 | 611.995 | 1.144
|  | To-date average hours per week | 68.29 | 64.1063 | 1.0653
|  | EV per completed task hour to date | 0.077734 | 0.088927
|  | Consolidated Team Member Schedule Data |  | Plan Hours | Actual Hours | Plan Value | Earned Value
Team Leader
Customer Interface Manager
Design Manager
Implementation Manager
Planning Manager
|  | Totals |  | 0 | 0 | 0 | 0
Assembly | Phase | Task | Re-source | Plan Hrs. | Actual Hrs. | EV or PV | CPI | Baseline or Committed Date and Week |  | Plan Date and Week |  | Slip Date and Week |  | Predicted Date and Week |  | Actual Date and Week
COMPLETED MILESTONES
Demo - Inteface - HTML | PM | Demo - Interface - HTML - PM | B | 0 |  | 0 |  | 2010-05-21 | 17 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
OPEN MILESTONES
Maint - Test Eng Build | PM | Maint - Test - Eng Build - Analyze and Record Results | F | 2.88 |  | 0 |  | 2010-03-29 | 10 | 2010-05-10 | 16 | 2010-05-17 | 17 | 2011-08-08 | 81
Maint - Test Eng Build | PM | Maint - Test - Eng Build - Analyze and Record Results | F | 2.4 |  | 0 |  | 2010-03-29 | 10 | 2010-05-24 | 18 | 2010-05-31 | 19 | 2011-10-10 | 90
Maint - Test Eng Build | MGMT | Maint - Test Eng Build - Task | A | 8 |  | 0 |  | 2010-03-29 | 10 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-01 | 41
Demo - CM - Eng Build Testing | MGMT | Demo - CM - Eng Build Testing - Task | A | 8 |  | 0 |  | 2010-05-21 | 17 | 2010-05-03 | 15 | 2010-05-03 | 15 | 2011-01-31 | 54
Demo - CM - Final Build Testing | MGMT | Demo - CM - Final Build Testing - Task | A | 8 |  | 0 |  | 2010-05-21 | 17 | 2010-05-24 | 18 | 2010-05-24 | 18 | 2011-04-18 | 65
Demo - Docs - Test Cases | PM | Demo - Docs - Test Cases - Doc PM-NT | A | 1.4583 |  | 0 |  | 2010-05-21 | 17 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-12-20 | 48
Demo - Interface - Process | PM | Demo - Interface - Process - PM | B | 0.8 | 0.13194 | 0 | 6.0632 | 2010-05-21 | 17 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-08 | 42
Demo - Interface - Closure | PM | Demo - Interface - Closure - PM | B | 2 |  | 0 |  | 2010-05-21 | 17 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-25 | 40
Demo - Interface - Msg | PM | Demo - Interface - Convert It - PM | C | 1.6 |  | 0 |  | 2010-05-21 | 17 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-08 | 42
Demo - Interface - Msg | PM | Demo - Interface - Msg - PM | B | 0.8 |  | 0 |  | 2010-05-21 | 17 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-10-04 | 37
TASKS COMPLETED IN WEEK 10
Demo - Docs - Test Cases | CR | Demo - Docs - Test Cases - Doc Review-NT | A | 4.375 | 3.5894 | 0.34009 | 1.2189 | 2010-03-08 | 7 | 2010-03-22 | 9 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework CODEINSP | A | 2.3 | 2.1714 | 0.17879 | 1.0592 |  |  | 2010-03-22 | 9 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Quality Manager | MGMT | Quality Manager - Task (Week 9 - 3/22/10) | C | 1 | 0.71222 | 0.077734 | 1.4041 | 2010-03-15 | 8 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Peer Review | C | 2.3 | 2.0517 | 0.17879 | 1.121 |  |  | 2010-03-22 | 9 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Demo - Inteface - HTML | CODE | Demo - Interface - HTML - Find and Fix | B | 0 |  | 0 |  | 2010-04-19 | 13 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Inteface - HTML | CR | Demo - Interface - HTML - Code Review | B | 0 |  | 0 |  | 2010-04-19 | 13 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Inteface - HTML | COMPILE | Demo - Interface - HTML - Compile | B | 0 |  | 0 |  | 2010-04-19 | 13 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Inteface - HTML | CODEINSP | Demo - Interface - HTML - Code Peer Review | B | 0 |  | 0 |  | 2010-04-19 | 13 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Inteface - HTML | UT | Demo - Interface - HTML - Unit Test | B | 0 |  | 0 |  | 2010-04-19 | 13 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Inteface - HTML | PM | Demo - Interface - HTML - PM | B | 0 |  | 0 |  | 2010-04-19 | 13 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review - Prepare Material | B | 1 | 0.96111 | 0.077734 | 1.0405 | 2010-03-29 | 10 | 2010-03-22 | 9 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | B | 2.25 | 0.34722 | 0.1749 | 6.48 |  |  | 2010-03-22 | 9 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Demo - Interface - Process | CODE | Demo - Interface - Process - Find and Fix | B | 11.6 | 3.3708 | 0.90172 | 3.4413 | 2010-04-12 | 12 | 2010-03-22 | 9 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Demo - Interface - Process | CR | Demo - Interface - Process - Code Review | B | 2 |  | 0.15547 |  | 2010-04-12 | 12 | 2010-03-22 | 9 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Demo - Interface - Process | COMPILE | Demo - Interface - Process - Compile | B | 0.6 |  | 0.04664 |  | 2010-04-12 | 12 | 2010-03-22 | 9 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Demo - Docs - Req Doc - Rework | CODEINSP | Demo - Docs - Req Doc - Rework - Doc Inspection-NT | F | 2.25 | 1.655 | 0.1749 | 1.3595 |  |  | 2010-03-22 | 9 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Maint - Val Final Build w/o F | MGMT | Maint - Val Final Build w/o F - Task | A | 4 | 9.5353 | 0.31094 | 0.41949 | 2010-04-05 | 11 | 2010-03-29 | 10 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Test Manager | MGMT | Test Manager - Task Week 10 Mar 29 | A | 1 | 0.96722 | 0.077734 | 1.0339 | 2010-04-26 | 14 | 2010-03-29 | 10 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Demo - Interface - Msg | CODE | Demo - Interface - Convert It- Msg Env Database | C | 11.6 | 7.4069 | 0.90172 | 1.5661 |  |  | 2010-03-29 | 10 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Demo - Inteface - HTML | CODEINSP | Demo - Interface - Convert It - Code Peer Review | C | 0 |  | 0 |  | 2010-02-22 | 5 | 2010-03-29 | 10 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Demo - Interface - Msg | CR | Demo - Interface - Convert It - Code Review | C | 4 | 5.8081 | 0.31094 | 0.6887 | 2010-05-03 | 15 | 2010-03-29 | 10 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Demo - Interface - Msg | CODE | Demo - Interface - Msg - Find and Fix | B | 11.6 | 12.0939 | 0.90172 | 0.95916 | 2010-04-05 | 11 | 2010-03-29 | 10 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Implementation | MGMT | Implementation - Task 8 | B | 0 |  | 0 |  | 2010-04-05 | 11 | 2010-03-29 | 10 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Process Manager | MGMT | Process Manager - Week 10 | E | 1 | 0.093889 | 0.077734 | 10.6509 | 2010-04-12 | 12 | 2010-03-29 | 10 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | D | 0 |  | 0 |  | 2010-06-07 | 20 | 2010-04-05 | 11 |  |  | 2010-03-29 | 10 | 2010-03-29 | 10
Maint - LD - 998 | CODE | Maint - LD - 998 Find and Fix | D | 6.96 | 2.1233 | 0.54103 | 3.2779 |  |  | 2010-04-05 | 11 |  |  | 2010-03-30 | 10 | 2010-03-30 | 10
Maint - LD - 998 | CR | Maint - LD - 998 Code Review | D | 1.2 | 0.29833 | 0.093281 | 4.0223 |  |  | 2010-04-05 | 11 |  |  | 2010-03-30 | 10 | 2010-03-30 | 10
Maint - LD - 998 | COMPILE | Maint - LD - 998 Compile | D | 0.36 | 0.031944 | 0.027984 | 11.2696 |  |  | 2010-04-05 | 11 |  |  | 2010-03-30 | 10 | 2010-03-30 | 10
Maint - LD - 998 | CODEINSP | Maint - LD - 998 Code Peer Review | D | 1.2 | 0.24389 | 0.093281 | 4.9203 |  |  | 2010-04-05 | 11 |  |  | 2010-03-30 | 10 | 2010-03-30 | 10
Planning Manager | MGMT | Planning Manager - Week 10 | E | 1.5 | 0.80306 | 0.1166 | 1.8679 | 2010-04-12 | 12 | 2010-04-05 | 11 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Maint - LD - 999 | CODE | Maint - LD - 999 Find and Fix | D | 6.96 | 2.6661 | 0.54103 | 2.6105 |  |  | 2010-04-12 | 12 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Maint - LD - 999 | CR | Maint - LD - 999 Code Review | D | 1.2 | 0.35222 | 0.093281 | 3.4069 |  |  | 2010-04-12 | 12 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Maint - LD - 999 | COMPILE | Maint - LD - 999 Compile | D | 0.36 |  | 0.027984 |  |  |  | 2010-04-12 | 12 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Maint - LD - 999 | CODEINSP | Maint - LD - 999 Code Peer Review | D | 1.2 | 0.053333 | 0.093281 | 22.5 |  |  | 2010-04-12 | 12 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Demo - Docs - HLD Doc | CR | Demo - Docs - HLD Doc - Doc Review-NT | D | 4.75 | 3.9392 | 0.36924 | 1.2058 | 2010-02-22 | 5 | 2010-04-12 | 12 |  |  | 2010-03-31 | 10 | 2010-03-31 | 10
Maint - LD - 997 | CODE | Maint - LD - 997 Find and Fix | D | 6.96 | 9.0639 | 0.54103 | 0.76788 |  |  | 2010-04-12 | 12 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Maint - LD - 997 | CR | Maint - LD - 997 Code Review | D | 1.2 | 0.43556 | 0.093281 | 2.7551 |  |  | 2010-04-12 | 12 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Maint - LD - 997 | COMPILE | Maint - LD - 997 Compile | D | 0.36 | 0.021944 | 0.027984 | 16.4051 |  |  | 2010-04-12 | 12 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Maint - LD - 997 | CODEINSP | Maint - LD - 997 Code Peer Review | D | 1.2 | 0.81889 | 0.093281 | 1.4654 |  |  | 2010-04-12 | 12 |  |  | 2010-04-01 | 10 | 2010-04-01 | 10
Design Manager | MGMT | Design Manager - Week 10 (03/29/2010) | D | 0 |  | 0 |  | 2010-03-15 | 8 | 2010-04-12 | 12 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
Support Manager | MGMT | Support Manager - Week 10 (03/29/2010) | D | 0 |  | 0 |  | 2010-03-15 | 8 | 2010-04-12 | 12 |  |  | 2010-04-02 | 10 | 2010-04-02 | 10
TASKS DUE THROUGH WEEK 12
Demo - Interface - Msg | COMPILE | Demo - Interface - Convert It - Compile | C | 1.2 | 0.69528 | 0.093281 | 1.7259 | 2010-05-03 | 15 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-09-20 | 35
Demo - Interface - Closure | CODEINSP | Demo - Interface - Interface Closure - Code Peer Review | C | 4 |  | 0.31094 |  | 2010-02-15 | 4 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-09-27 | 36
Quality Manager | MGMT | Quality Manager - Task (Week 10 - 3/29/10) | C | 1 |  | 0.077734 |  | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-10-04 | 37
Maint - CM - Create Eng Build | MGMT | Maint - CM - Create Eng Build - Task - Finalize Build | B | 2 |  | 0.15547 |  | 2010-02-22 | 5 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-09-20 | 35
Demo - Interface - Msg | CR | Demo - Interface - Msg - Code Review | B | 2 | 4.4897 | 0.15547 | 0.44546 | 2010-04-05 | 11 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-09-20 | 35
Demo - Interface - Msg | COMPILE | Demo - Interface - Msg - Compile | B | 0.6 |  | 0.04664 |  | 2010-04-05 | 11 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-09-27 | 36
Demo - Interface - Msg | CODEINSP | Demo - Interface - Msg - Code Peer Review | B | 2 |  | 0.15547 |  | 2010-04-12 | 12 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-09-27 | 36
Demo - Interface - Msg | UT | Demo - Interface - Msg - Unit Test | B | 3 |  | 0.2332 |  | 2010-04-12 | 12 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-10-04 | 37
Demo - Interface - Msg | PM | Demo - Interface - Msg - PM | B | 0.8 |  | 0.062187 |  | 2010-04-12 | 12 | 2010-03-29 | 10 | 2010-03-29 | 10 | 2010-10-04 | 37
Demo - Docs - Req Doc - Rework | PM | Demo - Docs - Req Doc - Rework - Doc PM-NT | F | 0.75 | 1.9236 | 0.058301 | 0.38989 |  |  | 2010-03-29 | 10 | 2010-04-05 | 11 | 2010-09-20 | 35
Maint - Test Eng Build | MGMT | Maint - Test Eng Build - Task | A | 8 |  | 0.62187 |  | 2010-04-12 | 12 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-01 | 41
Test Manager | MGMT | Test Manager - Task Week 11 Apr 5 | A | 1 |  | 0.077734 |  | 2010-04-26 | 14 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-01 | 41
Checkpoint | MGMT | Checkpoint - Task | A | 1 |  | 0.077734 |  | 2010-04-12 | 12 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-08 | 42
Checkpoint | MGMT | Checkpoint - Task | C | 1 |  | 0.077734 |  | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-04 | 37
Demo - Interface - Process | CODEINSP | Demo - Interface - Taclink Process - Code Peer Review | C | 2 |  | 0.15547 |  | 2010-02-15 | 4 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-11 | 38
Quality Manager | MGMT | Quality Manager - Task (Week 11 - 4/5/10) | C | 1 |  | 0.077734 |  | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-11 | 38
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review | B | 4 |  | 0.31094 |  | 2010-03-29 | 10 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-11 | 38
Demo - Interface - Closure | UT | Demo - Interface - Closure - Unit Test | B | 7.5 |  | 0.58301 |  | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-18 | 39
Demo - Interface - Closure | PM | Demo - Interface - Closure - PM | B | 2 |  | 0.15547 |  | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-25 | 40
Checkpoint | MGMT | Checkpoint - Task | B | 1 |  | 0.077734 |  | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-25 | 40
Implementation | MGMT | Implementation - Task 9 | B | 1 |  | 0.077734 |  | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-25 | 40
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | B | 2 | 0.30417 | 0.15547 | 6.5753 | 2010-04-19 | 13 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-01 | 41
Demo - Interface - Process | UT | Demo - Interface - Process - Unit Test | B | 3 |  | 0.2332 |  | 2010-04-19 | 13 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-01 | 41
Demo - Interface - Process | PM | Demo - Interface - Process - PM | B | 0.8 | 0.13194 | 0.062187 | 6.0632 | 2010-04-19 | 13 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-11-08 | 42
Maint - Doc - SRS - Rework | CODE | Maint - Doc - SRS - Rework Draft | F | 15 | 7.5172 | 1.166 | 1.9954 |  |  | 2010-04-05 | 11 | 2010-04-12 | 12 | 2010-11-15 | 43
Maint - CM - Delivery Letters | MGMT | Maint - CM - Delivery Letters - Task | G | 4 |  | 0.31094 |  | 2010-02-08 | 3 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-09-27 | 36
Checkpoint | MGMT | Checkpoint - Task | E | 1 |  | 0.077734 |  | 2010-03-29 | 10 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-04 | 37
Process Manager | MGMT | Process Manager - Week 11 | E | 1 | 0.23694 | 0.077734 | 4.2204 | 2010-04-19 | 13 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-10-11 | 38
Maint - Val Final Builds w/ F | MGMT | Maint - Val Final Builds w/ F - Task | A | 4 |  | 0.31094 |  | 2010-04-05 | 11 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-22 | 44
Demo - Docs - Test Cases | CODEINSP | Demo - Docs - Test Cases - Doc Inspection-NT | A | 4.375 |  | 0.34009 |  | 2010-03-15 | 8 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-12-13 | 47
Demo - Docs - Test Cases | PM | Demo - Docs - Test Cases - Doc PM-NT | A | 1.4583 |  | 0.11336 |  | 2010-03-15 | 8 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-12-20 | 48
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | A | 2 |  | 0.15547 |  | 2010-03-15 | 8 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-12-27 | 49
Demo - GUI - Closure Design | CODEINSP | Demo - GUI - Closure Design - Doc Inspection-NT | A | 0 |  | 0 |  | 2010-03-29 | 10 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-12-27 | 49
Demo - Interface - Msg | CODEINSP | Demo - Interface - Convert It - Code Peer Review | C | 4 |  | 0.31094 |  | 2010-05-03 | 15 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-18 | 39
Demo - Interface - Msg | UT | Demo - Interface - Convert It - Unit Test | C | 6 |  | 0.4664 |  | 2010-05-03 | 15 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-01 | 41
Demo - Interface - Msg | PM | Demo - Interface - Convert It - PM | C | 1.6 |  | 0.12437 |  | 2010-05-03 | 15 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-08 | 42
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | C | 4.75 |  | 0.36924 |  | 2010-03-15 | 8 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-15 | 43
Quality Manager | MGMT | Quality Manager - Task (Week 12 - 4/12/10) | C | 1 |  | 0.077734 |  | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-22 | 44
Demo - CM - Eng Build | MGMT | Demo - CM - Eng Build - Task | B | 8 |  | 0.62187 |  | 2010-04-26 | 14 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-15 | 43
Implementation | MGMT | Implementation - Task 10 | B | 1 |  | 0.077734 |  | 2010-04-05 | 11 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-22 | 44
Maint - Test Eng Build | CODE | Maint - Test - Eng Build - Write Test Cases | F | 15 |  | 1.166 |  | 2010-04-26 | 14 | 2010-04-12 | 12 | 2010-04-19 | 13 | 2011-01-17 | 52
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | F | 4.75 | 1.5989 | 0.36924 | 2.9708 | 2010-03-15 | 8 | 2010-04-12 | 12 | 2010-04-19 | 13 | 2011-01-31 | 54
Update INS Form/Script | DLD | Update INS Form/Script - Research-NP | F | 0.55556 |  | 0.043186 |  | 2010-03-01 | 6 | 2010-04-12 | 12 | 2010-04-19 | 13 | 2011-02-07 | 55
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | G | 2.5568 |  | 0.19875 |  | 2010-02-15 | 4 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-04 | 37
Maint - LD - 918 | CR | Maint - LD - 918 - Code Review | G | 2.9528 | 2.5811 | 0.22954 | 1.144 | 2010-03-08 | 7 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-18 | 39
Maint - LD - 918 | COMPILE | Maint - LD - 918 - Compile | G | 0.88585 |  | 0.068861 |  | 2010-03-08 | 7 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-18 | 39
Planning Manager | MGMT | Planning Manager - Week 11 | E | 1.5 | 0.4225 | 0.1166 | 3.5503 | 2010-04-19 | 13 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-11-01 | 41
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | C | 2.9528 |  | 0.22954 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-29 | 45
Maint - LD - 919 | CODEINSP | Maint - LD - 919 - Code Peer Review | C | 2.9528 |  | 0.22954 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-06 | 46
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - Ada Interface - Code Peer Review | C | 4 |  | 0.31094 |  |  |  | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-13 | 47
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | C | 4 |  | 0.31094 |  |  |  | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-20 | 48
Quality Manager | MGMT | Quality Manager - Task (Week 13 - 4/19/10) | C | 1 |  | 0.077734 |  | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-27 | 49
Maint - CM - Final CM Package | MGMT | Maint - CM - Final CM Package - Task | B | 20 |  | 1.5547 |  | 2010-05-03 | 15 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-20 | 48
Implementation | MGMT | Implementation - Task 11 | B | 1 |  | 0.077734 |  | 2010-04-12 | 12 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-20 | 48
Maint - CM - Archive V2 w/o F | MGMT | Maint - CM - Archive V2 w/o F - Task | B | 8 |  | 0.62187 |  | 2010-05-03 | 15 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2011-01-03 | 50
Maint - CM - Archive V2 w/ F | MGMT | Maint - CM - Archive V2 w/ F - Task | B | 8 |  | 0.62187 |  | 2010-05-03 | 15 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2011-01-17 | 52
Update INS Form/Script | CODE | Update INS Form/Script - Draft-NP | F | 1.25 |  | 0.097168 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-26 | 14 | 2011-02-07 | 55
Update INS Form/Script | CR | Update INS Form/Script - Doc Review-NP | F | 0.41667 |  | 0.032389 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-26 | 14 | 2011-02-14 | 56
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | F | 0.41667 |  | 0.032389 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-26 | 14 | 2011-02-14 | 56
Update INS Form/Script | PM | Update INS Form/Script - Doc PM-NP | F | 0.13889 |  | 0.010796 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-26 | 14 | 2011-02-14 | 56
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | F | 4.75 |  | 0.36924 |  | 2010-03-15 | 8 | 2010-04-19 | 13 | 2010-04-26 | 14 | 2011-03-07 | 59
Demo - Docs - Test Cases | CODEINSP | Demo - Docs - Test Cases - Doc Inspection-NT | F | 4.375 |  | 0.34009 |  | 2010-03-22 | 9 | 2010-04-19 | 13 | 2010-04-26 | 14 | 2011-03-21 | 61
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | D | 4.75 |  | 0.36924 |  | 2010-03-01 | 6 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-09-20 | 35
Demo - Docs - HLD Doc | PM | Demo - Docs - HLD Doc - Doc PM-NT | D | 1.5833 |  | 0.12308 |  | 2010-03-08 | 7 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-09-20 | 35
Design Manager | MGMT | Design Manager - Week 11 (04/05/2010) | D | 2 |  | 0.15547 |  | 2010-03-22 | 9 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-09-27 | 36
Support Manager | MGMT | Support Manager - Week 11 (04/05/2010) | D | 1 |  | 0.077734 |  | 2010-03-22 | 9 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-09-27 | 36
Design Manager | MGMT | Design Manager - Week 12 (04/12/2010) | D | 2 |  | 0.15547 |  | 2010-04-05 | 11 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-09-27 | 36
Support Manager | MGMT | Support Manager - Week 12 (04/12/2010) | D | 1 |  | 0.077734 |  | 2010-04-05 | 11 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-09-27 | 36
Design Manager | MGMT | Design Manager - Week 13 (04/19/2010) | D | 2 |  | 0.15547 |  | 2010-04-12 | 12 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-04 | 37
Support Manager | MGMT | Support Manager - Week 13 (04/19/2010) | D | 1 |  | 0.077734 |  | 2010-04-12 | 12 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-04 | 37
Checkpoint | MGMT | Checkpoint - Task | D | 1 |  | 0.077734 |  | 2010-04-12 | 12 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-04 | 37
Design Manager | MGMT | Design Manager - Week 14 (04/26/2010) | D | 2 |  | 0.15547 |  | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-04 | 37
Support Manager | MGMT | Support Manager - Week 14 (04/26/2010) | D | 1 |  | 0.077734 |  | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-04 | 37
Design Manager | MGMT | Design Manager - Week 15 (05/03/2010) | D | 2 |  | 0.15547 |  | 2010-04-26 | 14 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-11 | 38
Support Manager | MGMT | Support Manager - Week 15 (05/03/2010) | D | 1 |  | 0.077734 |  | 2010-04-26 | 14 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-11 | 38
Design Manager | MGMT | Design Manager - Week 16 (05/10/2010) | D | 2 |  | 0.15547 |  | 2010-05-10 | 16 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-11 | 38
Support Manager | MGMT | Support Manager - Week 16 (05/10/2010) | D | 1 |  | 0.077734 |  | 2010-05-10 | 16 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-11 | 38
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | D | 0.41667 |  | 0.032389 |  | 2010-05-24 | 18 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-11 | 38
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | G | 2.9528 |  | 0.22954 |  | 2010-03-08 | 7 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-10-25 | 40
Maint - LD - 918 | UT | Maint - LD - 918 - Unit Test | G | 4.4292 |  | 0.3443 |  | 2010-03-15 | 8 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-08 | 42
Maint - LD - 918 | PM | Maint - LD - 918 - PM | G | 1.1811 |  | 0.091814 |  | 2010-03-15 | 8 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-15 | 43
Customer Interface Manager | MGMT | Customer Interface Manager - 3/29 | G | 1 |  | 0.077734 |  | 2010-05-10 | 16 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-15 | 43
Update Specification PM | DLD | Update Specification PM - Research-NP | E | 0.55556 |  | 0.043186 |  | 2010-02-15 | 4 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-01 | 41
Update Specification PM | CODE | Update Specification PM - Draft-NP | E | 1.25 |  | 0.097168 |  | 2010-02-15 | 4 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-15 | 43
Update Specification PM | CR | Update Specification PM - Doc Review-NP | E | 0.41667 |  | 0.032389 |  | 2010-02-15 | 4 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-11-22 | 44
Update Specification PM | CODEINSP | Update Specification PM - Doc Inspection-NP | E | 1.25 |  | 0.097168 |  | 2010-02-22 | 5 | 2010-04-19 | 13 | 2010-04-19 | 13 | 2010-12-06 | 46
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | C | 4 |  | 0.31094 |  |  |  | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-03 | 50
Demo - Interface - Msg | CODEINSP | Demo - Interface - XML to Lchr - Code Peer Review | C | 2 |  | 0.15547 |  | 2010-02-22 | 5 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-10 | 51
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | C | 0.41667 |  | 0.032389 |  | 2010-03-15 | 8 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-10 | 51
Update Specification PM | CODEINSP | Update Specification PM - Doc Inspection-NP | C | 0.41667 |  | 0.032389 |  | 2010-03-15 | 8 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-10 | 51
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | C | 2.5568 |  | 0.19875 |  | 2010-04-05 | 11 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-17 | 52
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Attend Inspection Meeting | C | 1 |  | 0.077734 |  |  |  | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-17 | 52
Quality Manager | MGMT | Quality Manager - Task (Week 14 - 4/26/10) | C | 1 |  | 0.077734 |  | 2010-04-19 | 13 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-24 | 53
Quality Manager | MGMT | Quality Manager - Task (Week 15 - 5/3/10) | C | 1.01 |  | 0.078511 |  | 2010-05-03 | 15 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-24 | 53
Quality Manager | MGMT | Quality Manager - Task (Week 16 - 5/10/10) | C | 1.02 |  | 0.079289 |  | 2010-05-10 | 16 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-24 | 53
Quality Manager | MGMT | Quality Manager - Task (Week 17 - 5/17/10) | C | 1.03 |  | 0.080066 |  | 2010-05-10 | 16 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-31 | 54
Cycle Postmortem | MGMT | Cycle Postmortem - Task | C | 3 |  | 0.2332 |  | 2010-05-10 | 16 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-31 | 54
Implementation | MGMT | Implementation - Task 12 | B | 1 |  | 0.077734 |  | 2010-05-03 | 15 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-17 | 52
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | B | 0.41667 |  | 0.032389 |  | 2010-05-10 | 16 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-17 | 52
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | B | 4.75 |  | 0.36924 |  | 2010-05-10 | 16 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-24 | 53
Implementation | MGMT | Implementation - Task 13 | B | 1 |  | 0.077734 |  | 2010-04-12 | 12 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-24 | 53
Demo - Interface - Msg | CODEINSP | Demo - Interface - Msg - Code Peer Review | B | 4 |  | 0.31094 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-01-31 | 54
Maint - CM - Final Builds | MGMT | Maint - CM - Final Builds - Task | B | 8 |  | 0.62187 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2011-02-14 | 56
Design Manager | MGMT | Design Manager - Week 17 (05/17/2010) | D | 2 |  | 0.15547 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-18 | 39
Support Manager | MGMT | Support Manager - Week 17 (05/17/2010) | D | 1 |  | 0.077734 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-18 | 39
Design Manager | MGMT | Design Manager - Week 18 (05/24/2010) | D | 2 |  | 0.15547 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-18 | 39
Support Manager | MGMT | Support Manager - Week 18 (05/24/2010) | D | 1 |  | 0.077734 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-18 | 39
Maint - LD - 961 | CODEINSP | Maint - LD - 961 - Code Peer Review | D | 0.22714 |  | 0.017657 |  | 2010-05-24 | 18 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-18 | 39
Design Manager | MGMT | Design Manager - Week 19 (05/31/2010) | D | 2 |  | 0.15547 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-25 | 40
Support Manager | MGMT | Support Manager - Week 19 (05/31/2010) | D | 1 |  | 0.077734 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-25 | 40
Maint - LD - 956 | CODEINSP | Maint - LD - 956 - Code Peer Review | D | 0.22714 |  | 0.017657 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-25 | 40
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | D | 2.9528 |  | 0.22954 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-10-25 | 40
Maint - LD - 919 | CODEINSP | Maint - LD - 919 - Code Peer Review | D | 2.9528 |  | 0.22954 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-11-01 | 41
Design Manager | MGMT | Design Manager - Week 20 (06/07/2010) | D | 2 |  | 0.15547 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-11-01 | 41
Support Manager | MGMT | Support Manager - Week 20 (06/07/2010) | D | 1 |  | 0.077734 |  | 2010-05-31 | 19 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-11-01 | 41
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review | D | 4 |  | 0.31094 |  | 2010-06-07 | 20 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-11-08 | 42
Demo - Interface - Process | CODEINSP | Demo - Interface - Process - Code Peer Review | D | 2 |  | 0.15547 |  | 2010-06-07 | 20 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-11-08 | 42
Customer Interface Manager | MGMT | Customer Interface Manager - 4/5 | G | 1 |  | 0.077734 |  | 2010-05-10 | 16 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-11-22 | 44
Update Specification PM | PM | Update Specification PM - Doc PM-NP | E | 0.13889 |  | 0.010796 |  | 2010-02-22 | 5 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-12-06 | 46
Process Manager | MGMT | Process Manager - Task | E | 1 |  | 0.077734 |  | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-04-26 | 14 | 2010-12-13 | 47

## IRTL (hidden)
TSP Issue/Risk Tracking Log - Form IRTL
Name | Consolidated |  |  |  |  | Date | 2026-07-29
Team | AIM
[6 empty] | Cycle | 1900-01-01
Issue or Risk Number | R=Risk I=Issue | Date Created | P=Personal T=Team | Likelihood (H,M,L) | Impact (H,M,L) | Owner | Follow-up Date | Description | Current Status | Date Status Changed

## IRWeek (hidden)
TSP Issue Risk Week Summary - Form IRWEEK
Name | Consolidated |  |  | Date | 2026-07-29
Team | AIM |  |  | Team
Week | 1 |  |  | Cycle | 2
Issue/Risk Number | P=Personal T=Team | R=Risk I=Issue | Description |  | Status

## PIP (hidden)
TSP Process Improvement Proposal - Form PIP
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2
PIP Number | Date Created | P=Personal T=Team | Priority (H,M, L) | Owner | Problem Description | Improvement Suggestion | Process Elements Affected | How Closed? D=Deferred I=Implemented | Date Closed

## DefectTypes
Type | Description | Detailed Description
10 | Documentation
20 | Syntax
30 | Build, Package
40 | Assignment
50 | Interface
60 | Checking
70 | Data
80 | Function
90 | System
100 | Environment
200 | Doc Omission
210 | Doc Ambiguous Statement/Data
220 | Doc Duplicate Statement
230 | Doc Unclear Statement/Data
240 | Doc Incorrect Statement/Data
250 | Doc Grammer
260 | Doc Spelling
270 | Doc Format
280 | Doc Abbreviation
300 | Req Omission
310 | Req Ambiguous
320 | Req Duplicate
330 | Req Unclear
340 | Req Incorrect
350 | Req Inconsistent
360 | Req Extraneous Info
Restore Defect Type Defaults

## Phases (hidden)
Phase | Description | Task Generator S-System P-Part N-None | LOGT Track Time | LOGD Track Defects Injected | LOGD Track Defects Removed | PDF | DefDen | DefRatios | DevTimeRatio | RvwRate | PhaseYld | ProcYld | DI Rate | DR Rate
MGMT | Management and Miscellaneous | S | Y | N | N | N | N |  |  | N | N | N | N | N
STRAT | Launch and Strategy | S | Y | N | N | N | N |  |  | N | N | N | N | N
PLAN | Planning | S | Y | Y | Y | N | N |  |  | N | Y | Y | Y | Y
REQ | Requirements | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
STP | System Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
REQINSP | REQ Inspection | S | Y | Y | Y | N | Y |  | Requirements | Y | Y | N | Y | Y
HLD | High-Level Design | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
ITP | Integration Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
HLDINSP | HLD Inspection | S | Y | Y | Y | N | Y |  | High-Level Design | Y | Y | N | Y | Y
DLD | Detailed Design | P | Y | Y | Y | N | N |  | Code | N | Y | N | Y | Y
DLDR | DLD Review | P | Y | Y | Y | N | Y | Unit Test | Detailed Design | Y | Y | N | Y | Y
TD | Test Development | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
DLDINSP | DLD Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
CODE | Code | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
CR | Code Review | P | Y | Y | Y | N | Y | Compile | Code | Y | Y | N | Y | Y
COMPILE | Compile | P | Y | Y | Y | y | Y |  |  | N | Y | Y | Y | Y
CODEINSP | Code Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
UT | Unit Test | P | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
IT | Build and Integration Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
ST | System Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
DOC | Documentation | S | Y | N | N | N | N |  |  | N | N | N | N | N
PM | Postmortem | S | Y | N | N | N | N |  |  | N | N | N | N | N
AT | Acceptance Test | N | N | Y | Y | Y | Y |  |  | N | N | Y | N | N
PL | Product Life | N | N | Y | Y | Y | Y |  |  | N | N | N | N | N
Copyright 1998 James W. Over

## QProfParam (hidden)
Parameter | Value | Description
Design/Code Time | 100% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time
Restore Qprofile Parameter Defaults

## Custom Processes
TSP Custom Processes Form
Name | Consolidated
Team | AIM
Date | 2026-07-29
Cycle | 2
Process | Phase | Default Task Name | Process Step Description | Map-to Phase | Time in Phase% | Defects Injected per Hour | Phase Yield | # of Resources
Team Software Process | PLAN | - Planning |  | PLAN | 2 | 0 | 0
Team Software Process | REQ | - Requirements |  | REQ | 2 | 0.25 | 0
Team Software Process | STP | - System Test Plan |  | STP | 2.5 | 0 | 0
Team Software Process | REQINSP | - REQ Inspection |  | REQINSP | 5 | 0 | 0.7
Team Software Process | HLD | - High-Level Design |  | HLD | 7 | 0.25 | 0
Team Software Process | ITP | - Integration Test Plan |  | ITP | 5 | 0 | 0
Team Software Process | HLDINSP | - HLD Inspection |  | HLDINSP | 3 | 0 | 0.7
Team Software Process | DLD | - Detailed Design |  | DLD | 11.5 | 0.75 | 0
Team Software Process | DLDR | - DLD Review |  | DLDR | 5 | 0 | 0.7
Team Software Process | TD | - Test Development |  | TD | 5 | 0 | 0
Team Software Process | DLDINSP | - DLD Inspection |  | DLDINSP | 10 | 0 | 0.7
Team Software Process | CODE | - Code |  | CODE | 15 | 2 | 0
Team Software Process | CR | - Code Review |  | CR | 5 | 0 | 0.7
Team Software Process | COMPILE | - Compile |  | COMPILE | 1 | 0.3 | 0.5
Team Software Process | CODEINSP | - Code Inspection |  | CODEINSP | 9 | 0 | 0.7
Team Software Process | UT | - Unit Test |  | UT | 3 | 0.067 | 0.9
Team Software Process | IT | - Build and Integration Test |  | IT | 3 | 0 | 0.8
Team Software Process | ST | - System Test |  | ST | 5 | 0 | 0.8
Team Software Process | PM | - Postmortem |  | PM | 1 |  | 0.65
Issue Fixes | Find and Fix | - Find and Fix |  | CODE | 58 | 0.038
Issue Fixes | Code Review | - Code Review |  | CR | 10 |  | 0.23077
Issue Fixes | Compile | - Compile |  | COMPILE | 3 |  | 0.3
Issue Fixes | Code Peer Review | - Code Peer Review |  | CODEINSP | 10 |  | 0.42857
Issue Fixes | Unit Test | - Unit Test |  | UT | 15 |  | 1
Issue Fixes | Postmortem | - PM |  | PM | 4
New Features | Detail Design | - Detailed Design |  | DLD | 25 | 1.12
New Features | UT Descriptions | - UT Description |  | TD | 5
New Features | Design Review | - Design Review |  | DLDR | 3 |  | 0.4375
New Features | Design Inspection | - Design Inspection |  | DLDINSP | 11 |  | 1
New Features | Code | - Code |  | CODE | 20 | 0.81
New Features | Code Review | - Code Review |  | CR | 3 |  | 0.375
New Features | Compile | - Compile |  | COMPILE | 1 |  | 0.4
New Features | Code Peer Review | - Code Peer Review |  | CODEINSP | 15 |  | 0.44444
New Features | Unit Test | - Unit Test |  | UT | 15 |  | 1
New Features | Postmortem | - PM |  | PM | 2
Test | Write Test Cases | - Write Test Cases |  | CODE | 50 | 0.64
Test | Review TC | - Review TC |  | CR | 10 |  | 0.76786
Test | Peer Review TC | - Peer Review TC |  | CODEINSP | 15 |  | 0.15385
Test | Validate TC and Test Software | - Validate TC and Test SW |  | ST | 17 |  | 1
Test | Analyze and Record Results | - Analyze and Record Results |  | PM | 8
New Prototype | Define Use Cases | - Define Use Cases |  | DLD | 30 | 1.12
New Prototype | Build Prototype | - Build Prototype |  | CODE | 40 | 0.81
New Prototype | Validate Prototype | - Validate Prototype |  | UT | 20 |  | 1
New Prototype | Demo Prototype | - Demo Prototype |  | PM | 10
DAR Prototype | Build Prototype | - Build Prototype |  | CODE | 55 | 0.81
DAR Prototype | Validate Prototype | - Validate Prototype |  | UT | 35 |  | 1
DAR Prototype | Demo Prototype | - Demo Prototype |  | PM | 10
DAR Process | DAR | - DAR |  | PLAN | 100
Document-Maintenance | Draft-M | - Draft-M |  | CODE | 65 | 0.4
Document-Maintenance | Doc Review-M | - Doc Review-M |  | CR | 15 |  | 0.32308
Document-Maintenance | Doc Inspection-M | - Doc Inspection-M |  | CODEINSP | 15 |  | 1
Document-Maintenance | Doc PM-M | - Doc PM-M |  | PM | 5
Document-New Process | Research-NP | - Research-NP |  | DLD | 20
Document-New Process | Draft-NP | - Draft-NP |  | CODE | 45 | 0.4
Document-New Process | Doc Review-NP | - Doc Review-NP |  | CR | 15 |  | 0.18605
Document-New Process | Doc Inspection-NP | - Doc Inspection-NP |  | CODEINSP | 15 |  | 1
Document-New Process | Doc PM-NP | - Doc PM-NP |  | PM | 5
Document-New Technical | Research-NT | - Research-NT |  | DLD | 35
Document-New Technical | Draft-NT | - Draft-NT |  | CODE | 30 | 1.2
Document-New Technical | Doc Review-NT | - Doc Review-NT |  | CR | 15 |  | 0.94118
Document-New Technical | Doc Inspection-NT | - Doc Inspection-NT |  | CODEINSP | 15 |  | 1
Document-New Technical | Doc PM-NT | - Doc PM-NT |  | PM | 5
Task | Task | - Task |  | MGMT | 100
Document-Test | Research-T | - Research-T |  | DLD | 35
Document-Test | Draft-T | - Draft-T |  | CODE | 30 | 0.4
Document-Test | Doc Review-T | - Doc Review-T |  | CR | 15 |  | 0.32
Document-Test | Doc Inspection-T | - Doc Inspection-T |  | CODEINSP | 15 |  | 0.32
Document-Test | Doc PM-T | - Doc PM-T |  | PM | 5 |  | 1

## PlanGuide
General | - If your team does not have historical data, use these guidelines as standard planning factors. - In all cases, use your judgement. If some guideline does not fit your case, use your best estimate instead.
TSP Plans | Overall plan - produced first by the total team and later adjusted to conform to the balanced plan. Bottom-up plan - produced by each engineer for the next phase Balanced plan - the next phase plan after load balancing
Requirements | - The Requirements process depends heavily on The nature of The project, so no General guidelines are given. - In General, expect that all input materials will have be to inspected and substantially reworked.
Requirements Inspections | - The QUAL guideline provides a General factor to use In determining The time needed for The Requirements inspection. - Again, If this number is unrealistic for your project and situation, use your best estimate.
High-Level Design | - The High-Level Design process is highly variable and The time depends principally on The size, complexity, and General nature of The system, so no General guideline is given. - Without prior data, most teams substantially underestimate The time High-Level Design will require.
Implementation Phase | Implementation covers detailed design through unit test. - Calculate total implementation time from LOC/hour rates. - New or large modifications: about 10 LOC per hour. - Small changes to large systems: about 5 LOC per hour. - Pick a number that seems appropriate for your project. - Maintenance fixes, use an average rate: 5 and 20 hours per fix, depending on complexity and degree of testing.
Implementation Allocation | In estimating the implementation phases, - Make an overall estimate based on LOC/hour rates. - Then use these percentages to Calculate The phase times.
Detailed design - 22.1%
Detailed design review - 11.1%
Detailed design inspection - 8.8%
Coding - 20.0%
Code review - 10.0%
Compiling - 3.4%
Code inspection - 8.8%
Unit test - 15.8%
Integration and System Test | For these phases, estimate the defect-free test time and add 5 hours per defect in integration and 10 hours in system test

## QualGuide
Measure | Goal | Comments
Percent Defect Free (PDF)
Compile | > 10%
Unit Test | > 50%
Integration Test | > 70%
System Test | > 90%
Defects/KLOC:
Total defects injected | 75 - 150 | If not PSP trained, use 100 to 200.
Compile | < 10 | All defects
Unit Test | < 5 | All major defects (in source LOC)
Integration Test | < 0.5 | All major defects (in source LOC)
System Test | < 0.2 | All major defects (in source LOC)
Defect Ratios
Detailed design review defects /unit test defects | > 2.0 | All major defects (in source LOC)
Code review defects/compile defects | > 2.0 | All major defects (in source LOC)
Development Time Ratios
Requirements inspection/requirements time | > 0.25 | Elicitation in requirements time
High-level design inspection/high-level design time | > 0.5 | Design work only, not studies
Detailed design/coding time | > 1.00
Detailed design review/detailed design time | > 0.5
Code review/code time | > 0.5
Review and Inspection Rates
Requirements pages/hour | < 2 | Single-spaced text pages
High-level design pages/hour | < 5 | Formatted design logic
Detailed design text lines/hour | < 100 | Pseudocode ~ equal to 3 LOC
Code LOC/hour | < 200 | Logical LOC
Defect Injection and Removal Rates
Requirements defects injected/hour | 0.25 | Only major defects
Requirements inspection defects removed/hour | 0.5 | Only major defects
High-level design defects injected/hour | 0.25 | Only major defects
High-level design inspection defects removed/hour | 0.5 | Only major defects
Detailed design defects injected/hour | 0.75 | Only design defects
Detailed design review defects removed/hour | 1.5 | Only design defects
Detailed design inspection defects removed/hour | 0.5 | Only design defects
Code defects injected/hour | 2 | All defects
Code review defects removed/hour | 4 | All defects in source LOC
Compile defects injected/hour | 0.3 | Any defects
Code inspection defects removed/hour | 1 | All defects in source LOC
Unit test defects injected/hour | 0.067 | Any defects
Phase Yields
Team requirements inspections | ~ 70% | Not counting editorial comments
Design reviews and inspections | ~ 70% | Using state analysis, trace tables
Code reviews and inspections | ~ 70% | Using personal checklists
Compiling | ~ 50% | 90+ % of syntax defects
Unit test - at 5 or less defects/KLOC | ~ 90% | For high defects/KLOC - 50-75%
Integration and system test - at < 1.0 defects/KLOC | ~ 80% | For high defects/KLOC - 30-65%
Acceptance test - at < 1.0 defects/KLOC | ~ 65% | For high defects/KLOC - 30%
Before compile | >75% | Assuming sound design methods
Before unit test | > 85% | Assuming logic checks in reviews
Before integration test | > 97.5% | For small products, 1 defect max.
Before system test | > 99% | For small products, 1 defect max.