## Index (hidden)
Index of Forms and Charts
FORMS | Description | CHARTS | Description
Launch Meeting/Planning Forms |  | Cumulative Earned Value | Cumulative Planned vs. earned vs. projected earned value
Use these forms to plan a new project |  | Earned Value per Week | Planned, earned, and projected value per week
Project | Project startup and summary form | Earned Value Trend | Cumulative Plan Value / Cumulateive Earned Value per week
Team | Team member summary | Cumulative Plan vs. Actual Hours | Cumulative planned vs. actual hours per week
Roles | TSPe role assignments | Plan vs. Actual Hours per Week | Planned vs. actual hours per week
Goals | Team goals | Percent Defect Free | Percent of components that are defect free by phase
SUMS | Size summary | Cumulative Defects Removed by Phase | Cumulative defects removed by phase for each component
Task | Task plan template | Defects Removed by Phase | Defects removed by phase for each component
Schedule | Schedule plan template | Defect Density by Phase | Defects per KLOC by phase for each component
|  | Review Rates | Inspection and review rates for each component
|  | Phase Yield | Phase yield for each component
|  | Process Yield | Process yield for each component
|  | Quality Profile | Five point quality profile for each component
|  | Time in Phase% | Percentage of time spent in each phase
|  | Defects Injected% | Percentage of defects injected in each phase
|  | Defects Removed% | Percentage of defects removed in each phase
Weekly Meeting/Tracking Forms
Use these forms for gathering data and tracking
TimeLog | Time recording Log
DefectLog | Defect recording log
Weekly meeting status report
Task | Task plan template
Schedule | Schedule plan template
Quality actuals for system and components
Resource actuals for system and components
Defects injected/removed for system and components
Standards
Phases | TSPe process phase standard
DefectTypes | Defect type standard
Copyright 1998 James W. Over

## TSPi Instructions (hidden)
TSP Support Tool Instructions
Strategy Development and Planning
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Before STRAT1 | Team Leader | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Before STRAT1 | Team Leader | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Before STRAT1 | Team Leader | Enter the role assignments on the Roles worksheet. | Roles!B2
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
STRAT1: Produce the Size Estimate | Planning Manager | Enter on the SUMS worksheet, the names and size estimates of all assemblies and parts for this cycle. | SUMS!B8
PLAN1: Produce the Task Plan | Planning Manager | Click the Generate Task List button to create a default task list. | Task!A8
PLAN1: Produce the Task Plan | Planning Manager | Revise the task list adding or deleting tasks as necessary. Then for each task, estimate the size where appropriate, the time, and the time for each engineer assigned to the task. | Task!A8
PLAN1: Produce the Schedule Plan | Planning Manager | Enter hours per week in the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
| Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate a schedule. | Task!A8
PLAN1: Quality Plan | Team | Before creating the quality plan, review the quality standard in the textbook.
PLAN1: Quality Plan | Quality/Process Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
PLAN1: Quality Plan | Quality/Process Manager | Enter estimated phase yields for each phase. | SUMQ!D55
PLAN1: Quality Plan | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
PLAN: Balance Workload | Planning Manager | Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the copies automatically. | Team!B2
PLAN: Balance Workload | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set their planned hours to zero). | Task!A8
PLAN: Balance Workload | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
PLAN: Balance Workload | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
PLAN: Balance Workload | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Weekly Tracking
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
STRAT, PLAN, REQ, DES, IMP, TEST, PM | All team members | During all TSPi phases, use the time log to record data on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
REQ, DES, IMP, TEST | All team members | During TSPi phases REQ, DES, IMP, and TEST, use the defect log to record data on each defect. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
Weekly | All team members | Click the Update Task and Schedule Plan button on the Task worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!C8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!A2
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!C8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Cycle Postmortem
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the cycle. | Project!Name

## TSP Instructions (hidden)
TSP Support Tool Instructions
Strategy Development and Planning
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Launch Meeting 2 | Launch Coach or Planning Manager | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the role assignments on the Roles worksheet. (Optional) | Roles!B2
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the team goals on the Goals worksheet. (Optional) | Goals!A3
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
Launch Meeting 3 | Launch Coach or Planning Manager | Enter all the software assemblies identified during this meeting. Enter the name, assembly/part flag, part of, and size measure. Requirements and High-Level Design documents may also be entered on SUMS. | SUMS!B8
Launch Meeting 4 | Launch Coach or Planning Manager | Enter on the SUMS worksheet, the size estimates of all software assemblies. | SUMS!B8
Launch Meeting 4 | Launch Coach or Planning Manager | Click the Generate Task List button to create an initial task list based on the assemblies on SUMS. | Task!A8
Launch Meeting 4 | Launch Coach or Planning Manager | Revise the initial task list by adding or deleting tasks as necessary. Then complete the estimate for each task by entering a size estimate, size measure, rate in units per hour, the estimated hours, and the number of engineers assigned to the task. | Task!A8
Launch Meeting 4 | Launch Coach or Planning Manager | Enter hours per week for the team on the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
Launch Meeting 4 | Launch Coach or Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate the overall plan. | Task!A8
Launch Meeting 5 | Team | Before creating the quality plan, review the quality guidelines in the TSP Launch Notebook
Launch Meeting 5 | Launch Coach, Planning Manager, or Quality Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
Launch Meeting 5 | Launch Coach, Planning Manager, or Quality Manager | Enter estimated phase yields for each phase. | SUMQ!D55
Launch Meeting 5 | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
Launch Meeting 6 | Launch Coach or Planning Manager | Enter the initials of the team member(s) assigned to each task in the resources column on worksheet Task. | Task!A8
Launch Meeting 6 | Launch Coach or Planning Manager | Enter the initials of the team member that owns each leaf assembly in the owner column on worksheet SUMS. Note that plan and actual size are copied from the owner's workbook to the team workbook during consolidation, so each leaf assembly MUST have an owner. | SUMS!B8
Launch Meeting 6 | Launch Coach or Planning Manager | Make 1 copy of the team workbook for the consolidated team plan. Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the engineer's copies automatically. | Team!B2
Launch Meeting 6 | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set the column Number of Engineers to 1). | Task!A8
Launch Meeting 6 | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
Launch Meeting 6 | Each engineer | Click the Update Task and Schedule Plan button on the Task Worksheet to generate your individual plan. Repeat the previous two steps until you are satisfied with the plan
Launch Meeting 6 | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
Launch Meeting 6 | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Launch Meeting 7 | Launch Coach or Planning Manager | Enter the team risks on the IRTL worksheet. (Optional) | IRTL!B7
Weekly Tracking
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
All | All team members | While working, use the time log to record time spent on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
All | All team members | While working, use the defect log to record each defect found. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
All | All team members | While working, use the issue/risk tracking log (IRTL) to record new issues and risks or to change status of existing issues or risks. | IRTL!B7
All | All team members | To review status against your plan select the Update item on the TSP Tools menu. | Project!B3
Weekly | All team members | Ensure that the completion data for all completed tasks has been entered, and all size, time, and defect data for the week have been entered.
Weekly | All team members | Review the task on worksheet Task and move all organize them into the following order. 1-completed tasks 2-tasks planned for the next two weeks 3-remaining tasks | Task!A8
Weekly | All team members | Click the Update Project button on the Task worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!A8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Prepare a weekly issue/risk report. The worksheet IRWeek contains the information for this reportt. | IRWeek!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!A3
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!A8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Prepare a weekly issue/risk report. The worksheet IRWeek contains the information for this reportt. | IRWeek!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Phase Postmortem
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the IRTL worksheet and print a copy of all team issues and risk | IRTL!B7
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the phase or project. | Project!Name

## Project
TSP | - Project Summary | [5 empty] | Plan | Actual | Phase | %
[6 empty] | Design/Code Time | 0 | 0 | Management and Miscellaneous | 0.056064
Name | Team Member G | Date | 2026-07-29 |  |  | Code Review Time | 0 | 0 | Code | 0.85229
Project | AIM | Start Date | 2010-01-25 |  |  | Compile Defects/KLOC | 1 | 1 | Code Inspection | 0.09165
Team | AIM |  |  | Weeks Shown | 19 | Unit Test Ddefects/KLOC | 1 | 1
Assembly |  | Cycle |  |  |  | Design Review Time | 0 | 0
Version: | TSP.20100105. ©2009 J. Over. | Today's Date Override |  |  |  | COMPILE | 3.4722
[6 empty] | CODEINSP | 2.7778
[6 empty] | UT | 2.0833
[6 empty] | IT | 0
[6 empty] | ST | 0
[6 empty] | 1 Year | 0
[6 empty] | Product Life | 0
[6 empty] | QPI | 0 | 0
Draw
Print
Use Time Log
Use Defect Log
Time and Defect Log Controls
Chart Controls
Max
Copy
Submit...
Team Folder

## Team
TSP Team Members - Form TEAM
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle
ID | Name | Initials | Phone | e-mail | Workbook Filename | Planned Tasks | Planned Task Hours | Planned Schedule Weeks | Planned End Date | Predicted End Date
1 | Team Member A | A |  |  | A.xls
2 | Team Member C | C |  |  | C.xls
3 | Team Member B | B |  |  | B.xls
4 | Team Member F | F |  |  | F.xls
5 | Team Member D | D |  |  | D.xls
6 | Team Member G | G |  |  | G.xls
7 | Team Member E | E |  |  | E.xls
8
9
10
11
12
13
14
15
16
17
18
19
20
[6 empty] | 0 | 0 | 0 | 0 | 0
[6 empty] | Total |  | Max
Formulas:
Planned End Date = MAX(J8:[Planned End Date, row above])
Predicted End Date = MAX(K8:[Predicted End Date, row above])
Make Team Member Workbooks
Consolidation Mode
Consolidate Plans

## Goals (hidden)
TSP Team Goals - Form GOAL
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle |  | Measure |  | Tracking
Stakeholder | Goal Desciption | Plan | Actual | Who | When
Customer
Al
PFRMS
Management
Sapenter
Sapenter
Team

## Roles
TSP Team Member Role Assignments - Form ROLE
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle
Team Member Roles | Requirements | Design | Implementation | Integration and Test
Team Leader | G
C
Customer Interface Manager | G
A
Design Manager | D
C
Implementation Manager | B
D
Planning Manager | E
C
Process Manager | E
F
Quality Manager | C
E
Support Manager | D
B
Test Manager | A
F

## STRAT (hidden)
TSP Strategy Recording - Form STRAT
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle
Estimated Allocation to Development Cycle
|  |  |  | Estimated |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8
Ref. | Feature, Function, or Component | Description | Size Unit | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours | Size | Hours

## INV (hidden)
TSP Process Inventory - Form INV
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle |  | Estimate
|  | Size |  |  | Effort
Ref. | Work Element | Unit | New | Mod. | Hours | Due Date | Assigned To

## SUMP
TSP Plan Summary - Form SUMP
Name | Team Member G |  |  | Date | 2026-07-29
Team | AIM
Assembly |  |  |  | Cycle
Program Size | Plan | Actual
Total Requirements Pages (SRS) | 605 | 11
Total HLD Pages (SDS) | 38 | 0
Total Detailed Design Lines
Base LOC (B) | 0 | 23617
Deleted LOC (D) | 0 | 79
Modified LOC (M) | 0 | 106
Added LOC (A) | 3170 | 350
Reused LOC (R) | 0 | 0
New and Changed LOC (N) | 3170 | 456
Total LOC (T) | 3170 | 23888
Total New Reuse LOC | 0 | 0
Estimated Object LOC (E)
Upper Prediction Interval (70%)
Lower Prediction Interval (70%)
Time in Phase (hours) | Plan | Actual | Actual%
Management and Miscellaneous | 33 | 4.7833 | 11.35%
Launch and Strategy | 0 | 0 | 0%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 0 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 0 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 0 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 51.167 | 14.1197 | 33.5%
Code Review | 8.8219 | 4.3522 | 10.33%
Compile | 2.6466 | 0.5625 | 1.335%
Code Inspection | 50.3217 | 11.2278 | 26.64%
Unit Test | 13.2328 | 6.3619 | 15.09%
Build and Integration Test | 0 | 0 | 0%
System Test | 0 | 0 | 0%
Documentation | 0 | 0 | 0%
Postmortem | 3.5288 | 0.73944 | 1.754%
Total | 162.7188 | 42.1469 | 100%
Total Time UPI (70%)
Total Time LPI (70%)
Defects Injected | Plan | Actual | Actual%
Planning | 0 | 0 | 0%
Requirements | 0 | 0 | 0%
System Test Plan | 0 | 0 | 0%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 0 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 0 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 0 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 102.334 | 3 | 100%
Code Review | 0 | 0 | 0%
Compile | 0.79397 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 0.8866 | 0 | 0%
Build and Integration Test | 0 | 0 | 0%
System Test | 0 | 0 | 0%
Total Development Defects Injected | 104.0146 | 3 | 100%
Defects Removed | Plan | Actual | Actual% |  |  | Phase | Plan | Actual
Planning | 0 | 0 | 0% |  |  | Planning | 0 | 0
Requirements | 0 | 0 | 0% |  |  | Requirements | 0 | 0
System Test Plan | 0 | 0 | 0% |  |  | System Test Plan | 0 | 0
REQ Inspection | 0 | 0 | 0% |  |  | REQ Inspection | 0 | 0
High-Level Design | 0 | 0 | 0% |  |  | High-Level Design | 0 | 0
Integration Test Plan | 0 | 0 | 0% |  |  | Integration Test Plan | 0 | 0
HLD Inspection | 0 | 0 | 0% |  |  | HLD Inspection | 0 | 0
Detailed Design | 0 | 0 | 0% |  |  | Detailed Design | 0 | 0
DLD Review | 0 | 0 | 0% |  |  | DLD Review | 0 | 0
Test Development | 0 | 0 | 0% |  |  | Test Development | 0 | 0
DLD Inspection | 0 | 0 | 0% |  |  | DLD Inspection | 0 | 0
Code | 0 | 0 | 0% |  |  | Code | 0 | 0
Code Review | 71.6338 | 2 | 66.67% |  |  | Code Review | 71.6338 | 2
Compile | 15.7471 | 0 | 0% |  |  | Compile | 87.3809 | 2
Code Inspection | 11.023 | 0 | 0% |  |  | Code Inspection | 98.4039 | 2
Unit Test | 5.0497 | 1 | 33.33% |  |  | Unit Test | 103.4535 | 3
Build and Integration Test | 0.44886 | 0 | 0% |  |  | Build and Integration Test | 103.9024 | 3
System Test | 0.089772 | 0 | 0% |  |  | System Test | 103.9922 | 3
Total Development Defects Removed | 103.9922 | 3 |  |  |  | Acceptance Test | 104.0067 | 3
Acceptance Test | 0.014588 | 0 |  |  |  | Product Life | 104.0146 | 3
Product Life | 0.007855 | 0
Summary | Plan | Actual
LOC/Hour | 19.4815 | 10.8193
CPI (Cost-Performance Index) |  | 3.8608
% Reuse | 0% | 0%
% New Reuse | 0% | 0%

## SUMQ
TSP Quality Plan - Form SUMQ
Name | Team Member G |  |  | Date | 2026-07-29
Team | AIM
Assembly |  |  |  | Cycle
SYSTEM Percent Defect Free |  |  | Actual
In Compile |  |  | 100%
In Unit Test |  |  | 97.22%
In Build and Integration Test |  |  | 100%
In System Test |  |  | 100%
In Acceptance Test |  |  | 100%
In Product Life |  |  | 100%
Defects/Page |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0 | 0
Defects/KLOC |  | Plan | Actual
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 22.5974 | 4.386
Compile |  | 4.9675 | 0
Code Inspection |  | 3.4773 | 0
Unit Test |  | 1.593 | 2.193
Build and Integration Test |  | 0.1416 | 0
System Test |  | 0.028319 | 0
Total Development |  | 32.8051 | 6.5789
Acceptance Test |  | 0.0046019 | 0
Product Life |  | 0.0024779 | 0
Total |  | 32.8122 | 6.5789
Defect Ratios |  | Plan | Actual
DLD Review/Unit Test |  | 0 | 0
Code Review/Compile |  | 4.549 | 0
Development Time Ratios |  | Plan | Actual
REQ Inspection/Requirements |  | 0 | 0
HLD Inspection/High-Level Design |  | 0 | 0
Detailed Design/Code |  | 0 | 0
DLD Review/Detailed Design |  | 0 | 0
Code Review/Code |  | 0.17241 | 0.30824
Inspection/Review Rates |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0 | 0
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 359.3331 | 104.7741
Code Inspection |  | 62.9946 | 40.6136
A/FR |  | 3.7245 | 2.25
Phase Yields |  | Plan | Actual |  |  | Phase Yield Planning Guidelines
Planning |  | 0% | 0% |  |  | Planning | 0%
Requirements |  | 0% | 0% |  |  | Requirements | 0%
System Test Plan |  | 0% | 0% |  |  | System Test Plan | 0%
REQ Inspection |  | 70% | 0% |  |  | REQ Inspection | 70% | Not counting editorial comments
High-Level Design |  | 0% | 0% |  |  | High-Level Design | 0%
Integration Test Plan |  | 0% | 0% |  |  | Integration Test Plan | 0%
HLD Inspection |  | 70% | 0% |  |  | HLD Inspection | 70% | Using state analysis, trace tables
Detailed Design |  | 0% | 0% |  |  | Detailed Design | 0%
DLD Review |  | 70% | 0% |  |  | DLD Review | 70% | Using state analysis, trace tables
Test Development |  | 0% | 0% |  |  | Test Development | 0%
DLD Inspection |  | 70% | 0% |  |  | DLD Inspection | 70% | Using state analysis, trace tables
Code |  | 0% | 0% |  |  | Code | 0%
Code Review |  | 70% | 66.67% |  |  | Code Review | 70% | Using personal checklists
Compile |  | 50% | 0% |  |  | Compile | 50% | 90+ % of syntax defects
Code Inspection |  | 70% | 0% |  |  | Code Inspection | 70%
Unit Test |  | 90% | 100% |  |  | Unit test - at < 5 defects/KLOC | 90% | For high defects/KLOC - 50-75%
Build and Integration Test |  | 80% | 0% |  |  | Integration test at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65%
System Test |  | 80% | 0% |  |  | System test - at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65%
Acceptance Test |  | 65% | 0% |  |  | Acceptance test - at < 1.0 defects/KLOC | 65% | For high defects/KLOC - 30%
Process Yields |  | Plan | Actual
% Before Compile |  | 70% | 66.67%
% Before Unit Test |  | 95.42% | 66.67%
% Before Build and Integration Test |  | 99.46% | 100%
% Before System Test |  | 99.89% | 100%
% Before Acceptance Test |  | 99.98% | 100%
Defect Injection Rates (Defects Injected Per Hour) |  | Plan | Actual |  |  | Defect Injection Rates Planning Guidelines
Planning |  | 0 | 0 |  |  | Planning | 0
Requirements |  | 0.25 | 0 |  |  | Requirements | 0.25 | Only major defects
System Test Plan |  | 0 | 0 |  |  | System Test Plan | 0
REQ Inspection |  | 0 | 0 |  |  | REQ Inspection | 0
High-Level Design |  | 0.25 | 0 |  |  | High-Level Design | 0.25 | Only major defects
Integration Test Plan |  | 0 | 0 |  |  | Integration Test Plan | 0
HLD Inspection |  | 0 | 0 |  |  | HLD Inspection | 0
Detailed Design |  | 0.75 | 0 |  |  | Detailed Design | 0.75 | Only design defects
DLD Review |  | 0 | 0 |  |  | DLD Review | 0
Test Development |  | 0 | 0 |  |  | Test Development | 0
DLD Inspection |  | 0 | 0 |  |  | DLD Inspection | 0
Code |  | 2 | 0.21247 |  |  | Code | 2 | All defects
Code Review |  | 0 | 0 |  |  | Code Review | 0
Compile |  | 0.3 | 0 |  |  | Compile | 0.3 | Any defects
Code Inspection |  | 0 | 0 |  |  | Code Inspection | 0
Unit Test |  | 0.067 | 0 |  |  | Unit Test | 0.067 | Any defects
Build and Integration Test |  | 0 | 0 |  |  | Build and Integration Test | 0
System Test |  | 0 | 0 |  |  | System Test | 0
Defect Removal Rates |  | Plan | Actual
Planning |  | 0 | 0
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0 | 0
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0 | 0
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 0 | 0
DLD Inspection |  | 0 | 0
Code |  | 0 | 0
Code Review |  | 8.12 | 0.45954
Compile |  | 5.95 | 0
Code Inspection |  | 0.21905 | 0
Unit Test |  | 0.3816 | 0.15718
Build and Integration Test |  | 0 | 0
System Test |  | 0 | 0
Transfer Defect Injection Rate Guidelines to Plan
Transfer Phase Yield Guidelines to Plan

## S (hidden)
ID | Assembly, Sub-Assembly, or Part Name | (A)ssembly or (P)art | Parent Assembly Name | Owner | Size Measure | Estimating Assumptions | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Baseline Plan Date | Baseline Plan Hours
0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 238.888

## SUMS
TSP Size Summary - Form SUMS
| Name | Team Member G
| Team | AIM
| Date | 2026-07-29
| Cycle | [5 empty] | Planned Size | [7 empty] | Actual Size | [7 empty] | Planned Defects Injected | [19 empty] | Actual Defects Injected | [19 empty] | Planned Defects Removed | [19 empty] | Actual Defects Removed | [19 empty] | Planned Time | [21 empty] | Actual Time
ID | Assembly, Sub-Assembly, or Part Name | (A)ssembly or (P)art | Parent Assembly Name | Owner | Size Measure | Estimating Assumptions | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Baseline Plan Date | Baseline Plan Hours
1 | Development | A | SYSTEM |  | LOC |  | 0 | 0 | 0 | 3170 | 0 | 3170 | 3170 | 0 | 23617 | 79 | 106 | 350 | 0 | 456 | 23888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.167 | 8.8219 | 2.6466 | 26.5983 | 13.2328 | 0 | 0 | 0 | 3.5288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.1197 | 4.3522 | 0.5625 | 6.2061 | 6.3619 | 0 | 0 | 0 | 0.73944 | 2010-06-07 | 357391.5199
2 | Development | A | SYSTEM |  | Text Pages |  | 14 | 4 | 10 | 311 | 0 | 321 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.9318 | 0 | 0 | 0 | 0 | 0 | 0.28417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 357391.5199
3 | Development | A | SYSTEM |  | Req Pages |  | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 357391.5199
4 | Development | A | SYSTEM |  | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 357391.5199
5 | Maintenance | A | Development |  | Text Pages |  | 14 | 4 | 10 | 206 | 0 | 216 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5568 | 0 | 0 | 0 | 0 | 0 | 0.28417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 132647.4283
6 | Maintenance | A | Development |  | LOC |  | 0 | 0 | 0 | 2918 | 0 | 2918 | 2918 | 0 | 23617 | 79 | 106 | 350 | 0 | 456 | 23888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.167 | 8.8219 | 2.6466 | 14.5983 | 13.2328 | 0 | 0 | 0 | 3.5288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.1197 | 4.3522 | 0.5625 | 6.2061 | 6.3619 | 0 | 0 | 0 | 0.73944 | 2010-05-31 | 132647.4283
7 | Demo | A | Development |  | LOC |  | 0 | 0 | 0 | 252 | 0 | 252 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 224744.0917
8 | Demo | A | Development |  | Req Pages |  | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 224744.0917
9 | Demo | A | Development |  | Text Pages |  | 0 | 0 | 0 | 105 | 0 | 105 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 224744.0917
10 | Demo | A | Development |  | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 224744.0917
11 | Maint - Latent Defects | A | Maintenance |  | LOC |  | 0 | 0 | 0 | 2918 | 0 | 2918 | 2918 | 0 | 23617 | 79 | 106 | 350 | 0 | 456 | 23888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.167 | 8.8219 | 2.6466 | 14.5983 | 13.2328 | 0 | 0 | 0 | 3.5288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.1197 | 4.3522 | 0.5625 | 6.2061 | 6.3619 | 0 | 0 | 0 | 0.73944 | 2010-05-31 | 59223.1101
12 | Maint - Documentation | A | Maintenance |  | Text Pages |  | 14 | 4 | 10 | 60 | 0 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5568 | 0 | 0 | 0 | 0 | 0 | 0.28417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 23430.3182
13 | Maint - Doc - SVD | A | Maint - Documentation | F | Text Pages |  | 0 | 0 | 0 | 30 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 7919.3182
14 | Maint - Doc - SRS INSP | A | Maint - Documentation | F | Text Pages |  | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 11460
15 | Maint - Doc - REQM | A | Maint - Documentation | F | Text Pages |  | 14 | 4 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-03-22 | 1131
16 | Maint - Doc - Test Docs | A | Maint - Documentation | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-19 | 2920
17 | Maint - Config Mgmt | A | Maintenance |  | Text Pages |  | 0 | 0 | 0 | 56 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 16352
18 | Maint - CM - Archive V2 w/ F | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 2336
19 | Maint - CM - Archive V2 w/o F | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 2336
20 | Maint - CM - Final Builds | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 2336
21 | Maint - CM - Delivery Letters | A | Maint - Config Mgmt | G | Text Pages |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-02-08 | 1168
22 | Maint - CM - Final CM Package | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 5840
23 | Maint - CM - Create Eng Build | A | Maint - Config Mgmt | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-02-22 | 2336
24 | Maint - Test Eng Build | A | Maintenance | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 2920
25 | Maint - Val Final Builds w/ F | A | Maintenance | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-05 | 2920
26 | Maint - Val Final Build w/o F | A | Maintenance | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-05 | 2920
27 | Maint - LD - 955 | A | Maint - Latent Defects | C | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14833 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 1612.2073
28 | Maint - LD - 957 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 15929 | 16 | 0 | 0 | 0 | 0 | 15913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21556 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 1612.2073
29 | Maint - LD - 958 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 10346.6977
30 | Maint - LD - 960 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 147 | 0 | 147 | 147 | 0 | 27 | 0 | 2 | 7 | 0 | 9 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10167 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 2999.9301
31 | Maint - LD - 961 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 39 | 0 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 795.8998
32 | Maint - LD - 953 | A | Maint - Latent Defects | C | LOC |  | 0 | 0 | 0 | 147 | 0 | 147 | 147 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.076944 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 2999.9301
33 | Maint - LD - 954 | A | Maint - Latent Defects | C | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 0 | 0 | 1 | 28 | 0 | 29 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5992 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 1612.2073
34 | Maint - LD - 959 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 236 | 8 | 17 | 204 | 0 | 221 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91667 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 10346.6977
35 | Maint - LD - 952 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 39 | 0 | 39 | 39 | 0 | 347 | 0 | 0 | 8 | 0 | 8 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1725 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 795.8998
36 | Maint - LD - 956 | A | Maint - Latent Defects | B | LOC |  | 0 | 0 | 0 | 39 | 0 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 795.8998
37 | Maint - LD - 918 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1264 | 2.9528 | 0.88585 | 2.9528 | 4.4292 | 0 | 0 | 0 | 1.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2069 | 2.5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 10346.6977
38 | Maint - LD - 919 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 507 | 0 | 507 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1264 | 2.9528 | 0.88585 | 2.9528 | 4.4292 | 0 | 0 | 0 | 1.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 10346.6977
39 | Maint - LD - 884 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 147 | 0 | 147 | 147 | 0 | 174 | 1 | 13 | 38 | 0 | 51 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9656 | 0.85614 | 0.25684 | 0.85614 | 1.2842 | 0 | 0 | 0 | 0.34246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5472 | 0.16944 | 0.31917 | 1.1917 | 1.6106 | 0 | 0 | 0 | 0.1175 | 2010-05-31 | 2999.9301
40 | Maint - LD - 885 | A | Maint - Latent Defects | G | LOC |  | 0 | 0 | 0 | 79 | 0 | 79 | 79 | 0 | 3302 | 6 | 52 | 30 | 0 | 82 | 3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6686 | 0.4601 | 0.13803 | 0.4601 | 0.69016 | 0 | 0 | 0 | 0.18404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8842 | 1.2742 | 0.069167 | 0.75028 | 1.1633 | 0 | 0 | 0 | 0.13389 | 2010-05-31 | 1612.2073
41 | Maint - LD - 967 | A | Maint - Latent Defects | G | LOC | hours | 0 | 0 | 0 | 7 | 0 | 7 | 7 | 0 | 3520 | 0 | 3 | 24 | 0 | 27 | 3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.06 | 0.7 | 0.21 | 0.7 | 1.05 | 0 | 0 | 0 | 0.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.091667 | 0.20444 | 0.085 | 0.28333 | 2.6842 | 0 | 0 | 0 | 0.13333 | 2010-05-31 | 22.085
42 | Maint - LD - 985 | A | Maint - Latent Defects | G | LOC | hours | 0 | 0 | 0 | 9 | 0 | 9 | 9 | 0 | 82 | 48 | 15 | 9 | 0 | 24 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.22 | 0.9 | 0.27 | 0.9 | 1.35 | 0 | 0 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38972 | 0.12306 | 0.089167 | 0.75 | 0.90389 | 0 | 0 | 0 | 0.35472 | 2010-05-31 | 22.085
43 | Support | A | SYSTEM |  | Text Pages |  | 0 | 0 | 0 | 234 | 0 | 234 | 234 | 0 | 0 | 0 | 8 | 11 | 0 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6667 | 0 | 0 | 0 | 0 | 0 | 4.4992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0217 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 110718.02
44 | Roles | A | Support |  | Text Pages |  | 0 | 0 | 0 | 165 | 0 | 165 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 57979.52
45 | Customer Interface Manager | A | Roles | G | Text Pages |  | 0 | 0 | 0 | 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-17 | 16352
46 | Planning Manager | A | Roles | E | Text Pages |  | 0 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 6570
47 | Process Manager | A | Roles | E | Text Pages |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 4380
48 | Quality Manager | A | Roles | C | Text Pages |  | 0 | 0 | 0 | 15 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 4689.52
49 | Test Manager | A | Roles | A | Text Pages |  | 0 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 5840
50 | Implementation | A | Roles | B | Text Pages |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 4380
51 | Support Manager | A | Roles | D | Text Pages |  | 0 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 5256
52 | Design Manager | A | Roles | D | Text Pages |  | 0 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 10512
53 | Checkpoint | A | Support | E | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 2275
54 | Cycle Postmortem | A | Support | E | Text Pages |  | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 6825
55 | Postmortem Report | A | Support | E | Text Pages |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 1460
56 | CMMI Training | A | Support | E | Text Pages |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-17 | 16813
57 | Process Updates | A | Support |  | Text Pages |  | 0 | 0 | 0 | 45 | 0 | 45 | 45 | 0 | 0 | 0 | 8 | 11 | 0 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0217 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 25365.5
58 | Add PM to Dev Processes | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.084167 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 1176.1111
59 | Create Peer Review Script | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 2352.2222
60 | Add TCs to New Feature Process | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36167 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 1176.1111
61 | Add Checklist to all Review/Insp Phases | A | Process Updates | C | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 5 | 1 | 0 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.12861 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 1485.2778
62 | Update Specification PM | A | Process Updates | E | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-05 | 1561.3889
63 | Update INS Form/Script | A | Process Updates | F | Text Pages |  | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75583 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 1685.9722
64 | Define a Design Standard | A | Process Updates | D | Text Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6114 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 15928.4167
65 | Demo - GUI | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 104073.6667
66 | Demo - GUI | A | Demo |  | LOC |  | 0 | 0 | 0 | 120 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-31 | 104073.6667
67 | Demo - Docs | A | Demo |  | Req Pages |  | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 46336.9583
68 | Demo - Docs | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 46336.9583
69 | Demo - Docs | A | Demo |  | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 46336.9583
70 | Demo - Interface | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 63821.4667
71 | Demo - Interface | A | Demo |  | LOC |  | 0 | 0 | 0 | 132 | 0 | 132 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 63821.4667
72 | Demo - CM | A | Demo |  | Text Pages |  | 0 | 0 | 0 | 32 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 10512
73 | Demo - GUI - Closure Design | A | Demo - GUI | D | Text Pages |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9490
74 | Demo - GUI - Remove Legacy Button | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
75 | Demo - GUI - Remove D Tab | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
76 | Demo - GUI - Remove Messaging Tab | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
77 | Demo - GUI - Remove F Tab | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
78 | Demo - GUI - Remove C Buttons | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
79 | Demo - GUI - Remove F Buttons | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
80 | Demo - GUI - Tailor Workspace | A | Demo - GUI | C | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
81 | Demo - GUI - Tailor Status | A | Demo - GUI | C | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
82 | Demo - GUI - Tailor Settings | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 9344
83 | Demo - GUI - AIM Interface | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | Demo - GUI - GUI Desktop | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | Demo - GUI - GUI Popups | A | Demo - GUI | D | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Demo - Interface - Closure Design | A | Demo - Interface | B | Text Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 13480.6667
87 | Demo - Interface - Closure | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 18104
88 | Demo - Interface - Process | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 7008
89 | Demo - Inteface - HTML | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 7008
90 | Demo - Interface - GUI | A | Demo - Interface | B | LOC |  | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 4204.8
91 | Demo - Interface - Msg | A | Demo - Interface | C | LOC |  | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-06-07 | 14016
92 | Demo - Docs - HLD Doc | A | Demo - Docs | D | HLD Pages |  | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 15928.4167
93 | Demo - Docs - Req Doc | A | Demo - Docs | F | Req Pages |  | 0 | 0 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 16835.8333
94 | Demo - Docs - Req Doc - Rework | A | Demo - Docs | F | Req Pages | hours | 0 | 0 | 0 | 15 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-10 | 2994.1667
95 | Demo - Docs - Test Cases | A | Demo - Docs | A | Text Pages |  | 0 | 0 | 0 | 35 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 13572.7083
96 | Demo - CM - Eng Build | A | Demo - CM | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-26 | 2336
97 | Demo - CM - Eng Build Testing | A | Demo - CM | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-03-29 | 2920
98 | Demo - CM - Final Build | A | Demo - CM | B | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-24 | 2336
99 | Demo - CM - Final Build Testing | A | Demo - CM | A | Text Pages |  | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-03-22 | 2920
100 | Maint - Test - A | A | Maintenance | F | Text Pages |  | 0 | 0 | 0 | 30 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-05-03 | 11310
101 | Maint - Test - B | A | Maintenance | F | Text Pages |  | 0 | 0 | 0 | 36 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 13572
102 | Postmortem Report - Cycle1 | A | Support | E | Text Pages |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 13572
103 | Maint - Doc - SRS - Rework | A | Maint - Documentation | F | Text Pages |  | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 3348
104 | Maint - LD - 997 | A | Maint - Latent Defects | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 2232
105 | Maint - LD - 998 | A | Maint - Latent Defects | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 2232
106 | Maint - LD - 999 | A | Maint - Latent Defects | D | LOC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010-04-12 | 2232

## Task
TSP Task Planning Template - Form TASK | [12 empty] | Total Plan Hours | [6 empty] | Total Actual Hours
Name | Team Member G | [11 empty] | 162.7188 | [6 empty] | 42.1469
Team | AIM | [8 empty] | Reminder:
Date | 2026-07-29 | [8 empty] | If Size and Rate are present, estimated hours is calculated as Size / Rate
whenever the plan is updated. To prevent calculation, size or rate must be blank.
Cycle |  |  | Plan Hours by Role
Assembly | Phase | Task | Team Leader | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Total Resource Hours | Resources | Estimated Size | Size Measure | Rate (per Hr.) | Time in Phase % | Estimated Hours | Engrs | Plan Hours | Plan Date | Plan Week | Actual Hours | Actual Date | Actual Week | Earned Value | Cumulative EV | Cumulative Plan Hours | Cumulative Plan Value | Plan Value | Predicted Date | Plan Date + Current Slip | Committed Date | Baseline Date | Baseline Plan Hours | Notes | Start Week | PHISW | PHIEW | Process | Phase
Maint - LD - 884 | CODE | Maint - LD - 884 - Find and Fix | [6 empty] | G | 147 | LOC | 17.17 | 58 | 4.9656 | 1 | 4.9656 | 2010-02-15 | 4 | 1.5472 | 2010-02-15 | 4 | 3.0517 |  | 4.9656 | 3.0517 | 3.0517 | 2010-02-15 |  |  | 2010-03-29 | 4.9656 |  | 4 | 4.9656 | 4.9656 | Issue Fixes | Find and Fix
Maint - LD - 884 | CR | Maint - LD - 884 - Code Review | [6 empty] | G | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-15 | 4 | 0.16944 | 2010-02-15 | 4 | 0.52615 |  | 5.8218 | 3.5778 | 0.52615 | 2010-02-15 |  |  | 2010-03-29 | 0.85614 |  | 4 | 0.85614 | 0.85614 | Issue Fixes | Code Review
Maint - LD - 884 | COMPILE | Maint - LD - 884 - Compile | [6 empty] | G | 147 | LOC | 17.17 | 3 | 0.25684 | 1 | 0.25684 | 2010-02-15 | 4 | 0.31917 | 2010-02-15 | 4 | 0.15784 |  | 6.0786 | 3.7357 | 0.15784 | 2010-02-15 |  |  | 2010-03-29 | 0.25684 |  | 4 | 0.25684 | 0.25684 | Issue Fixes | Compile
Maint - LD - 952 | CODEINSP | Maint - LD - 952 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.1725 | 2010-02-16 | 4 | 0.61456 |  | 7.0786 | 4.3502 | 0.61456 | 2010-02-16 |  |  |  | 0 |  | 4 | 1 | 1
Maint - LD - 957 | CODEINSP | Maint - LD - 957 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.21556 | 2010-02-16 | 4 | 0.61456 |  | 8.0786 | 4.9648 | 0.61456 | 2010-02-16 |  |  |  | 0 |  | 4 | 1 | 1
Maint - LD - 960 | CODEINSP | Maint - LD - 960 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.10167 | 2010-02-16 | 4 | 0.61456 |  | 9.0786 | 5.5793 | 0.61456 | 2010-02-16 |  |  |  | 0 |  | 4 | 1 | 1
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | [6 empty] | C, B, G, F, A, D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.75583 | 2010-02-18 | 4 | 0.25607 |  | 9.4953 | 5.8354 | 0.25607 | 2010-02-18 |  |  | 2010-04-05 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | [6 empty] | C, B, G, F, A, D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-15 | 4 | 0.12861 | 2010-02-18 | 4 | 0.25607 |  | 9.912 | 6.0915 | 0.25607 | 2010-02-18 |  |  | 2010-04-05 | 0.41667 |  | 4 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Customer Interface Manager | MGMT | Customer Interface Manager - 2/15 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.58333 | 2010-02-18 | 4 | 0.61456 |  | 10.912 | 6.706 | 0.61456 | 2010-02-18 |  |  | 2010-02-08 | 4 |  | 4 | 1 | 1 | Task | Task
Maint - LD - 959 | CODEINSP | Maint - LD - 959 CODEINSP | [6 empty] | G |  |  |  | 10 | 1 | 1 | 1 | 2010-02-15 | 4 | 0.91667 | 2010-02-23 | 5 | 0.61456 |  | 11.912 | 7.3206 | 0.61456 | 2010-02-23 |  |  |  | 0 |  | 4 | 1 | 1
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | [6 empty] | G, C, D | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-02-15 | 4 | 1.1917 | 2010-02-23 | 5 | 0.52615 |  | 12.7681 | 7.8467 | 0.52615 | 2010-02-23 |  |  | 2010-03-29 | 0.85614 |  | 4 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | [6 empty] | C, B, G, F, A, D | 38 | Text Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-02-22 | 5 | 1.6114 | 2010-02-25 | 5 | 2.9191 |  | 17.5181 | 10.7659 | 2.9191 | 2010-02-25 |  |  | 2010-04-05 | 4.75 |  | 4 | 3.2319 | 1.5181 | Document-New Technical | Doc Inspection-NT
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 1.9033 | 2010-02-26 | 5 | 0.61456 |  | 18.5181 | 11.3804 | 0.61456 | 2010-02-26 |  |  | 2010-04-26 | 4 |  | 5 | 1 | 1 | Task | Task
Maint - LD - 958 | CODE | Maint - LD - 958 - Find and Fix | [6 empty] | G | 507 | LOC | 17.17 | 58 | 17.1264 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 |  | 18.5181 | 11.3804 | 0 | 2010-03-01 |  |  | 2010-02-22 | 17.1264 |  | 5 | 0 | 0 | Issue Fixes | Find and Fix
Maint - LD - 958 | CR | Maint - LD - 958 - Code Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 |  | 18.5181 | 11.3804 | 0 | 2010-03-01 |  |  | 2010-02-22 | 2.9528 |  | 5 | 0 | 0 | Issue Fixes | Code Review
Maint - LD - 958 | COMPILE | Maint - LD - 958 - Compile | [6 empty] | G | 507 | LOC | 17.17 | 3 | 0.88585 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 |  | 18.5181 | 11.3804 | 0 | 2010-03-01 |  |  | 2010-02-22 | 0.88585 |  | 5 | 0 | 0 | Issue Fixes | Compile
Maint - LD - 958 | CODEINSP | Maint - LD - 958 - Code Peer Review | [6 empty] | G, C, D | 507 | LOC | 17.17 | 10 | 2.9528 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 |  | 18.5181 | 11.3804 | 0 | 2010-03-01 |  |  | 2010-02-22 | 2.9528 |  | 5 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 958 | UT | Maint - LD - 958 - Unit Test | [6 empty] | G | 507 | LOC | 17.17 | 15 | 4.4292 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 |  | 18.5181 | 11.3804 | 0 | 2010-03-01 |  |  | 2010-03-01 | 4.4292 |  | 5 | 0 | 0 | Issue Fixes | Unit Test
Maint - LD - 958 | PM | Maint - LD - 958 - PM | [6 empty] | G | 507 | LOC | 17.17 | 4 | 1.1811 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-01 | 6 | 0 |  | 18.5181 | 11.3804 | 0 | 2010-03-01 |  |  | 2010-03-01 | 1.1811 |  | 5 | 0 | 0 | Issue Fixes | Postmortem
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | [6 empty] | G | 147 | LOC | 17.17 | 15 | 1.2842 | 1 | 1.2842 | 2010-02-22 | 5 | 1.6106 | 2010-03-01 | 6 | 0.78922 |  | 19.8023 | 12.1697 | 0.78922 | 2010-03-01 |  |  | 2010-03-29 | 1.2842 |  | 5 | 1.2842 | 1.2842 | Issue Fixes | Unit Test
Maint - LD - 884 | PM | Maint - LD - 884 - PM | [6 empty] | G | 147 | LOC | 17.17 | 4 | 0.34246 | 1 | 0.34246 | 2010-02-22 | 5 | 0.1175 | 2010-03-01 | 6 | 0.21046 |  | 20.1448 | 12.3801 | 0.21046 | 2010-03-01 |  | 2010-03-29 | 2010-03-29 | 0.34246 |  | 5 | 0.34246 | 0.34246 | Issue Fixes | Postmortem
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | [6 empty] | C, B, G, D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.084167 | 2010-03-01 | 6 | 0.25607 |  | 20.5614 | 12.6362 | 0.25607 | 2010-03-01 |  |  | 2010-04-05 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Demo - Interface - Closure Design | CODEINSP | Demo - Interface - Closure Design - Doc Inspection-NT | [6 empty] | B, C, G, D | 38 | Text Pages | 1.2 | 15 | 4.75 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-02 | 6 | 0 |  | 20.5614 | 12.6362 | 0 | 2010-03-02 |  |  | 2010-04-12 | 4.75 |  | 5 | 0 | 0 | Document-New Technical | Doc Inspection-NT
Demo - Interface - Closure | CODEINSP | Demo - Interface - Closure - Code Peer Review | [6 empty] | C, B, G, D | 40 | LOC | 1 | 10 | 4 | 0 | 0 | 2010-02-22 | 5 |  | 2010-03-02 | 6 | 0 |  | 20.5614 | 12.6362 | 0 | 2010-03-02 |  |  | 2010-04-26 | 4 |  | 5 | 0 | 0 | Issue Fixes | Code Peer Review
Maint - LD - 885 | CODE | Maint - LD - 885 - Find and Fix | [6 empty] | G | 79 | LOC | 17.17 | 58 | 2.6686 | 1 | 2.6686 | 2010-02-22 | 5 | 1.8842 | 2010-03-04 | 6 | 1.64 |  | 23.2301 | 14.2762 | 1.64 | 2010-03-04 |  |  | 2010-03-29 | 2.6686 |  | 5 | 2.6686 | 2.6686 | Issue Fixes | Find and Fix
Maint - LD - 885 | CR | Maint - LD - 885 - Code Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-22 | 5 | 1.2742 | 2010-03-04 | 6 | 0.28276 |  | 23.6902 | 14.559 | 0.28276 | 2010-03-04 |  |  | 2010-03-29 | 0.4601 |  | 5 | 0.4601 | 0.4601 | Issue Fixes | Code Review
Maint - LD - 885 | COMPILE | Maint - LD - 885 - Compile | [6 empty] | G | 79 | LOC | 17.17 | 3 | 0.13803 | 1 | 0.13803 | 2010-02-22 | 5 | 0.069167 | 2010-03-04 | 6 | 0.084828 |  | 23.8282 | 14.6438 | 0.084828 | 2010-03-04 |  |  | 2010-03-29 | 0.13803 |  | 5 | 0.13803 | 0.13803 | Issue Fixes | Compile
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | [6 empty] | G, C, D | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-02-22 | 5 | 0.75028 | 2010-03-04 | 6 | 0.28276 |  | 24.2883 | 14.9265 | 0.28276 | 2010-03-04 |  |  | 2010-03-29 | 0.4601 |  | 5 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 885 | UT | Maint - LD - 885 - Unit Test | [6 empty] | G | 79 | LOC | 17.17 | 15 | 0.69016 | 1 | 0.69016 | 2010-02-22 | 5 | 1.1633 | 2010-03-04 | 6 | 0.42414 |  | 24.9785 | 15.3507 | 0.42414 | 2010-03-04 |  |  | 2010-04-05 | 0.69016 |  | 5 | 0.69016 | 0.69016 | Issue Fixes | Unit Test
Maint - LD - 885 | PM | Maint - LD - 885 - PM | [6 empty] | G | 79 | LOC | 17.17 | 4 | 0.18404 | 1 | 0.18404 | 2010-02-22 | 5 | 0.13389 | 2010-03-04 | 6 | 0.1131 |  | 25.1625 | 15.4638 | 0.1131 | 2010-03-04 |  | 2010-03-29 | 2010-04-05 | 0.18404 |  | 5 | 0.18404 | 0.18404 | Issue Fixes | Postmortem
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | [6 empty] | C, B, G, D | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-02-22 | 5 | 0.36167 | 2010-03-04 | 6 | 0.25607 |  | 25.5792 | 15.7199 | 0.25607 | 2010-03-04 |  |  | 2010-04-05 | 0.41667 |  | 5 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | [6 empty] | C, B, G, D | 2 | Text Pages | 0.36 | 15 | 0.83333 | 1 | 0.83333 | 2010-02-22 | 5 | 0.08 | 2010-03-04 | 6 | 0.51213 |  | 26.4125 | 16.232 | 0.51213 | 2010-03-04 |  |  | 2010-04-05 | 0.83333 |  | 5 | 0.83333 | 0.83333 | Document-New Process | Doc Inspection-NP
Customer Interface Manager | MGMT | Customer Interface Manager - 3/1 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-02-22 | 5 | 0.72667 | 2010-03-05 | 6 | 0.61456 |  | 27.4125 | 16.8465 | 0.61456 | 2010-03-05 |  |  | 2010-05-03 | 4 |  | 5 | 1 | 1 | Task | Task
Cycle Postmortem | MGMT | Cycle Postmortem - Task | [6 empty] | G | 3 | Text Pages | 1 | 100 | 3 | 1 | 3 | 2010-02-22 | 5 | 0.66667 | 2010-03-05 | 6 | 1.8437 |  | 30.4125 | 18.6902 | 1.8437 | 2010-03-05 |  |  | 2010-05-24 | 3 |  | 5 | 3 | 3
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | [6 empty] | C, B, G, F, A, D | 6 | Text Pages | 1 | 100 | 6 | 1 | 6 | 2010-03-01 | 6 | 0.28417 | 2010-03-09 | 7 | 3.6873 |  | 36.4125 | 22.3776 | 3.6873 | 2010-03-09 |  |  | 2010-02-08 | 6 |  | 5 | 1.5875 | 4.4125 | Task | Task
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | [6 empty] | C, D, G | 147 | LOC | 17.17 | 10 | 0.85614 | 1 | 0.85614 | 2010-03-01 | 6 | 0.076944 | 2010-03-11 | 7 | 0.52615 |  | 37.2686 | 22.9037 | 0.52615 | 2010-03-11 |  |  | 2010-03-01 | 0.85614 |  | 6 | 0.85614 | 0.85614 | Issue Fixes | Code Peer Review
Customer Interface Manager | MGMT | Customer Interface Manager - 3/8 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-01 | 6 | 0.5 | 2010-03-12 | 7 | 0.61456 |  | 38.2686 | 23.5183 | 0.61456 | 2010-03-12 |  |  | 2010-05-03 | 4 |  | 6 | 1 | 1 | Task | Task
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | [6 empty] | C, D, G | 35 | Req Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-03-01 | 6 | 2 | 2010-03-15 | 8 | 2.6887 |  | 42.6436 | 26.2069 | 2.6887 | 2010-03-15 |  |  | 2010-04-12 | 4.375 |  | 6 | 4.375 | 4.375 | Document-New Technical | Doc Inspection-NT
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | [6 empty] | C, D, G | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-01 | 6 | 1.5992 | 2010-03-16 | 8 | 0.28276 |  | 43.1037 | 26.4897 | 0.28276 | 2010-03-16 |  |  | 2010-03-01 | 0.4601 |  | 6 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 955 | CODE | Maint - LD - 955 - Find and Fix | [6 empty] | G | 79 | LOC | 17.17 | 58 | 2.6686 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 |  | 43.1037 | 26.4897 | 0 | 2010-03-17 |  |  | 2010-02-15 | 2.6686 |  | 6 | 0 | 0 | Issue Fixes | Find and Fix
Maint - LD - 955 | CR | Maint - LD - 955 - Code Review | [6 empty] | G | 79 | LOC | 17.17 | 10 | 0.4601 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 |  | 43.1037 | 26.4897 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.4601 |  | 6 | 0 | 0 | Issue Fixes | Code Review
Maint - LD - 955 | COMPILE | Maint - LD - 955 - Compile | [6 empty] | G | 79 | LOC | 17.17 | 3 | 0.13803 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 |  | 43.1037 | 26.4897 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.13803 |  | 6 | 0 | 0 | Issue Fixes | Compile
Maint - LD - 955 | UT | Maint - LD - 955 - Unit Test | [6 empty] | G | 79 | LOC | 17.17 | 15 | 0.69016 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 |  | 43.1037 | 26.4897 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.69016 |  | 6 | 0 | 0 | Issue Fixes | Unit Test
Maint - LD - 955 | PM | Maint - LD - 955 - PM | [6 empty] | G | 79 | LOC | 17.17 | 4 | 0.18404 | 0 | 0 | 2010-03-01 | 6 |  | 2010-03-17 | 8 | 0 |  | 43.1037 | 26.4897 | 0 | 2010-03-17 |  |  | 2010-02-15 | 0.18404 |  | 6 | 0 | 0 | Issue Fixes | Postmortem
Customer Interface Manager | MGMT | Customer Interface Manager - 3/15 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-03-08 | 7 | 0.11917 | 2010-03-17 | 8 | 0.61456 |  | 44.1037 | 27.1043 | 0.61456 | 2010-03-17 |  |  | 2010-05-03 | 4 |  | 6 | 0.89626 | 0.10374 | Task | Task
Maint - LD - 985 | CODE | Maint - LD - 985 - Find and Fix | [6 empty] | G | 9 | LOC | 1 | 58 | 5.22 | 1 | 5.22 | 2010-03-08 | 7 | 0.38972 | 2010-03-22 | 9 | 3.208 |  | 49.3237 | 30.3123 | 3.208 | 2010-03-22 |  |  |  | 0 |  | 7 | 5.22 | 5.22 | Issue Fixes | Find and Fix
Maint - LD - 985 | CR | Maint - LD - 985 - Code Review | [6 empty] | G | 9 | LOC | 1 | 10 | 0.9 | 1 | 0.9 | 2010-03-08 | 7 | 0.12306 | 2010-03-22 | 9 | 0.5531 |  | 50.2237 | 30.8654 | 0.5531 | 2010-03-22 |  |  |  | 0 |  | 7 | 0.9 | 0.9 | Issue Fixes | Code Review
Maint - LD - 985 | COMPILE | Maint - LD - 985 - Compile | [6 empty] | G | 9 | LOC | 1 | 3 | 0.27 | 1 | 0.27 | 2010-03-08 | 7 | 0.089167 | 2010-03-22 | 9 | 0.16593 |  | 50.4937 | 31.0313 | 0.16593 | 2010-03-22 |  |  |  | 0 |  | 7 | 0.27 | 0.27 | Issue Fixes | Compile
Maint - LD - 985 | CODEINSP | Maint - LD - 985 - Code Peer Review | [6 empty] | G, C | 9 | LOC | 1 | 10 | 0.9 | 1 | 0.9 | 2010-03-08 | 7 | 0.75 | 2010-03-22 | 9 | 0.5531 |  | 51.3937 | 31.5844 | 0.5531 | 2010-03-22 |  |  |  | 0 |  | 7 | 0.9 | 0.9 | Issue Fixes | Code Peer Review
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | [6 empty] | G, C, D | 79 | LOC | 17.17 | 10 | 0.4601 | 1 | 0.4601 | 2010-03-08 | 7 | 0.14833 | 2010-03-22 | 9 | 0.28276 |  | 51.8538 | 31.8671 | 0.28276 | 2010-03-22 |  |  | 2010-02-15 | 0.4601 |  | 7 | 0.4601 | 0.4601 | Issue Fixes | Code Peer Review
Maint - LD - 967 | CODE | Maint - LD - 967 - Find and Fix | [6 empty] | G | 7 | LOC | 1 | 58 | 4.06 | 1 | 4.06 | 2010-03-15 | 8 | 0.091667 | 2010-03-22 | 9 | 2.4951 |  | 55.9138 | 34.3622 | 2.4951 | 2010-03-22 |  |  |  | 0 |  | 7 | 1.1462 | 2.9138 | Issue Fixes | Find and Fix
Maint - LD - 967 | CR | Maint - LD - 967 - Code Review | [6 empty] | G | 7 | LOC | 1 | 10 | 0.7 | 1 | 0.7 | 2010-03-15 | 8 | 0.20444 | 2010-03-22 | 9 | 0.43019 |  | 56.6138 | 34.7924 | 0.43019 | 2010-03-22 |  |  |  | 0 |  | 8 | 0.7 | 0.7 | Issue Fixes | Code Review
Maint - LD - 967 | COMPILE | Maint - LD - 967 - Compile | [6 empty] | G | 7 | LOC | 1 | 3 | 0.21 | 1 | 0.21 | 2010-03-15 | 8 | 0.085 | 2010-03-22 | 9 | 0.12906 |  | 56.8238 | 34.9215 | 0.12906 | 2010-03-22 |  |  |  | 0 |  | 8 | 0.21 | 0.21 | Issue Fixes | Compile
Maint - LD - 967 | CODEINSP | Maint - LD - 967 - Code Peer Review | [6 empty] | G, C | 7 | LOC | 1 | 10 | 0.7 | 1 | 0.7 | 2010-03-15 | 8 | 0.28333 | 2010-03-22 | 9 | 0.43019 |  | 57.5238 | 35.3517 | 0.43019 | 2010-03-22 |  |  |  | 0 |  | 8 | 0.7 | 0.7 | Issue Fixes | Code Peer Review
Maint - LD - 985 | UT | Maint - LD - 985 - Unit Test | [6 empty] | G | 9 | LOC | 1 | 15 | 1.35 | 1 | 1.35 | 2010-03-15 | 8 | 0.90389 | 2010-03-23 | 9 | 0.82965 |  | 58.8738 | 36.1813 | 0.82965 | 2010-03-23 |  |  |  | 0 |  | 8 | 1.35 | 1.35 | Issue Fixes | Unit Test
Maint - LD - 985 | PM | Maint - LD - 985 - PM | [6 empty] | G | 9 | LOC | 1 | 4 | 0.36 | 1 | 0.36 | 2010-03-22 | 9 | 0.35472 | 2010-03-23 | 9 | 0.22124 |  | 59.2338 | 36.4026 | 0.22124 | 2010-03-23 |  |  |  | 0 |  | 8 | 0.12615 | 0.23385 | Issue Fixes | Postmortem
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | [6 empty] | G | 507 | LOC | 17.17 | 58 | 17.1264 | 1 | 17.1264 | 2010-04-05 | 11 | 10.2069 | 2010-03-23 | 9 | 10.5251 |  | 76.3602 | 46.9277 | 10.5251 | 2010-03-23 |  |  | 2010-03-08 | 17.1264 |  | 9 | 7.7662 | 1.3602 | Issue Fixes | Find and Fix
Maint - LD - 967 | UT | Maint - LD - 967 - Unit Test | [6 empty] | G | 7 | LOC | 1 | 15 | 1.05 | 1 | 1.05 | 2010-04-05 | 11 | 2.6842 | 2010-03-23 | 9 | 0.64528 |  | 77.4102 | 47.573 | 0.64528 | 2010-03-23 |  |  |  | 0 |  | 11 | 1.05 | 1.05 | Issue Fixes | Unit Test
Maint - LD - 967 | PM | Maint - LD - 967 - PM | [6 empty] | G | 7 | LOC | 1 | 4 | 0.28 | 1 | 0.28 | 2010-04-05 | 11 | 0.13333 | 2010-03-23 | 9 | 0.17208 |  | 77.6902 | 47.7451 | 0.17208 | 2010-03-23 |  |  |  | 0 |  | 11 | 0.28 | 0.28 | Issue Fixes | Postmortem
Customer Interface Manager | MGMT | Customer Interface Manager - 3/22 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-05 | 11 |  | 2010-03-25 | 9 | 0.61456 |  | 78.6902 | 48.3596 | 0.61456 | 2010-03-25 |  |  | 2010-05-03 | 4 |  | 11 | 1 | 1 | Task | Task
Maint - CM - Delivery Letters | MGMT | Maint - CM - Delivery Letters - Task | [6 empty] | G | 4 | Text Pages | 1 | 100 | 4 | 1 | 4 | 2010-04-05 | 11 | [5 empty] | 82.6902 | 50.8179 | 2.4582 | 2010-09-27 | 2010-04-05 |  | 2010-02-08 | 4 |  | 11 | 4 | 4 | Task | Task
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | [6 empty] | F, G, C | 30 | Text Pages | 1.76 | 15 | 2.5568 | 1 | 2.5568 | 2010-04-12 | 12 | [5 empty] | 85.247 | 52.3892 | 1.5713 | 2010-10-04 | 2010-04-12 |  | 2010-02-15 | 2.5568 |  | 11 | 0.30977 | 2.247 | Document-Maintenance | Doc Inspection-M
Maint - LD - 918 | CR | Maint - LD - 918 - Code Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-12 | 12 | 2.5811 |  |  |  |  | 88.1999 | 54.2039 | 1.8147 | 2010-10-18 | 2010-04-12 |  | 2010-03-08 | 2.9528 |  | 12 | 2.9528 | 2.9528 | Issue Fixes | Code Review
Maint - LD - 918 | COMPILE | Maint - LD - 918 - Compile | [6 empty] | G | 507 | LOC | 17.17 | 3 | 0.88585 | 1 | 0.88585 | 2010-04-12 | 12 | [5 empty] | 89.0857 | 54.7483 | 0.5444 | 2010-10-18 | 2010-04-12 |  | 2010-03-08 | 0.88585 |  | 12 | 0.88585 | 0.88585 | Issue Fixes | Compile
Maint - LD - 918 | CODEINSP | Maint - LD - 918 - Code Peer Review | [6 empty] | G, C, D | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-04-19 | 13 | [5 empty] | 92.0385 | 56.5629 | 1.8147 | 2010-10-25 | 2010-04-19 |  | 2010-03-08 | 2.9528 |  | 12 | 1.9143 | 1.0385 | Issue Fixes | Code Peer Review
Maint - LD - 918 | UT | Maint - LD - 918 - Unit Test | [6 empty] | G | 507 | LOC | 17.17 | 15 | 4.4292 | 1 | 4.4292 | 2010-04-19 | 13 | [5 empty] | 96.4678 | 59.285 | 2.722 | 2010-11-08 | 2010-04-19 |  | 2010-03-15 | 4.4292 |  | 13 | 4.4292 | 4.4292 | Issue Fixes | Unit Test
Maint - LD - 918 | PM | Maint - LD - 918 - PM | [6 empty] | G | 507 | LOC | 17.17 | 4 | 1.1811 | 1 | 1.1811 | 2010-04-19 | 13 | [5 empty] | 97.6489 | 60.0108 | 0.72587 | 2010-11-15 | 2010-04-19 |  | 2010-03-15 | 1.1811 |  | 13 | 1.1811 | 1.1811 | Issue Fixes | Postmortem
Customer Interface Manager | MGMT | Customer Interface Manager - 3/29 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-19 | 13 | [5 empty] | 98.6489 | 60.6254 | 0.61456 | 2010-11-15 | 2010-04-19 |  | 2010-05-10 | 4 |  | 13 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 4/5 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-04-26 | 14 | [5 empty] | 99.6489 | 61.2399 | 0.61456 | 2010-11-22 | 2010-04-26 |  | 2010-05-10 | 4 |  | 13 | 0.35109 | 0.64891 | Task | Task
Maint - LD - 919 | CODE | Maint - LD - 919 - Find and Fix | [6 empty] | G | 507 | LOC | 17.17 | 58 | 17.1264 | 1 | 17.1264 | 2010-05-10 | 16 | [5 empty] | 116.7753 | 71.7651 | 10.5251 | 2011-01-10 | 2010-05-10 |  | 2010-03-22 | 17.1264 |  | 14 | 7.3511 | 1.7753 | Issue Fixes | Find and Fix
Maint - LD - 919 | CR | Maint - LD - 919 - Code Review | [6 empty] | G | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-05-10 | 16 | [5 empty] | 119.7281 | 73.5798 | 1.8147 | 2011-01-17 | 2010-05-10 |  | 2010-03-22 | 2.9528 |  | 16 | 2.9528 | 2.9528 | Issue Fixes | Code Review
Maint - LD - 919 | COMPILE | Maint - LD - 919 - Compile | [6 empty] | G | 507 | LOC | 17.17 | 3 | 0.88585 | 1 | 0.88585 | 2010-05-10 | 16 | [5 empty] | 120.614 | 74.1242 | 0.5444 | 2011-01-24 | 2010-05-10 |  | 2010-03-22 | 0.88585 |  | 16 | 0.88585 | 0.88585 | Issue Fixes | Compile
Maint - LD - 919 | CODEINSP | Maint - LD - 919 - Code Peer Review | [6 empty] | G, C, D | 507 | LOC | 17.17 | 10 | 2.9528 | 1 | 2.9528 | 2010-05-17 | 17 | [5 empty] | 123.5668 | 75.9388 | 1.8147 | 2011-01-31 | 2010-05-17 |  | 2010-03-22 | 2.9528 |  | 16 | 2.386 | 0.56679 | Issue Fixes | Code Peer Review
Maint - LD - 919 | UT | Maint - LD - 919 - Unit Test | [6 empty] | G | 507 | LOC | 17.17 | 15 | 4.4292 | 1 | 4.4292 | 2010-05-17 | 17 | [5 empty] | 127.996 | 78.6609 | 2.722 | 2011-02-14 | 2010-05-17 |  | 2010-03-29 | 4.4292 |  | 17 | 4.4292 | 4.4292 | Issue Fixes | Unit Test
Customer Interface Manager | MGMT | Customer Interface Manager - 4/12 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-17 | 17 | [5 empty] | 128.996 | 79.2754 | 0.61456 | 2011-02-14 | 2010-05-17 |  | 2010-05-10 | 4 |  | 17 | 1 | 1 | Task | Task
Maint - LD - 919 | PM | Maint - LD - 919 - PM | [6 empty] | G | 507 | LOC | 17.17 | 4 | 1.1811 | 1 | 1.1811 | 2010-05-17 | 17 | [5 empty] | 130.1772 | 80.0013 | 0.72587 | 2011-02-21 | 2010-05-17 |  | 2010-03-29 | 1.1811 |  | 17 | 1.1811 | 1.1811 | Issue Fixes | Postmortem
Update Specification PM | CODEINSP | Update Specification PM - Doc Inspection-NP | [6 empty] | E, C, G | 1 | Text Pages | 0.36 | 15 | 0.41667 | 1 | 0.41667 | 2010-05-17 | 17 | [5 empty] | 130.5938 | 80.2574 | 0.25607 | 2011-02-21 | 2010-05-17 |  | 2010-04-05 | 0.41667 |  | 17 | 0.41667 | 0.41667 | Document-New Process | Doc Inspection-NP
Demo - Docs - HLD Doc | CODEINSP | Demo - Docs - HLD Doc - Doc Inspection-NT | [6 empty] | C, B, G, F, A, D | 38 | HLD Pages | 1.2 | 15 | 4.75 | 1 | 4.75 | 2010-05-24 | 18 | [5 empty] | 135.3438 | 83.1765 | 2.9191 | 2011-03-07 | 2010-05-24 |  | 2010-04-05 | 4.75 |  | 17 | 0.40617 | 4.3438 | Document-New Technical | Doc Inspection-NT
Customer Interface Manager | MGMT | Customer Interface Manager - 4/19 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-24 | 18 | [5 empty] | 136.3438 | 83.7911 | 0.61456 | 2011-03-07 | 2010-05-24 |  | 2010-05-10 | 4 |  | 18 | 1 | 1 | Task | Task
Demo - Docs - Test Cases | CODEINSP | Demo - Docs - Test Cases - Doc Inspection-NT | [6 empty] | H, F, G | 35 | Text Pages | 1.2 | 15 | 4.375 | 1 | 4.375 | 2010-05-31 | 19 | [5 empty] | 140.7188 | 86.4797 | 2.6887 | 2011-03-21 | 2010-05-31 |  | 2010-04-12 | 4.375 |  | 18 | 2.6562 | 1.7188 | Document-New Technical | Doc Inspection-NT
Checkpoint | MGMT | Checkpoint - Task | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 | [5 empty] | 141.7188 | 87.0943 | 0.61456 | 2011-03-28 | 2010-05-31 |  | 2010-04-12 | 1 |  | 19 | 1 | 1
Customer Interface Manager | MGMT | Customer Interface Manager - 4/26 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 | [5 empty] | 142.7188 | 87.7089 | 0.61456 | 2011-03-28 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/3 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 | [5 empty] | 143.7188 | 88.3234 | 0.61456 | 2011-04-04 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/10 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 | [5 empty] | 144.7188 | 88.938 | 0.61456 | 2011-04-04 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/17 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-05-31 | 19 | [5 empty] | 145.7188 | 89.5525 | 0.61456 | 2011-04-04 | 2010-05-31 |  | 2010-05-17 | 4 |  | 19 | 1 | 1 | Task | Task
Customer Interface Manager | MGMT | Customer Interface Manager - 5/24 | [6 empty] | G | 1 |  |  | 100 | 4 | 1 | 4 | 2010-06-07 | 20 | [5 empty] | 149.7188 | 92.0108 | 2.4582 | 2011-04-18 | 2010-06-07 |  |  | 0 |  | 19 | 1.2812 | 2.7188
Customer Interface Manager | MGMT | Customer Interface Manager - 5/31 | [6 empty] | G | 1 | [5 empty] | 0 | 2010-06-07 | 20 | [5 empty] | 149.7188 | 92.0108 | 0 | 2011-04-18 | 2010-06-07 |  |  | 0 |  | 20 | 0 | 0
Demo - GUI - AIM Interface | CODEINSP | Demo - GUI - AIM Interface - Code Peer Review | [6 empty] | C, B, G, D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-06-07 | 20 | [5 empty] | 153.7188 | 94.469 | 2.4582 | 2011-05-02 | 2010-06-07 |  |  | 0 |  | 20 | 4 | 4 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Desktop | CODEINSP | Demo - GUI - GUI Desktop - Code Peer Review | [6 empty] | C, B, G, D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-06-14 | 21 | [5 empty] | 157.7188 | 96.9272 | 2.4582 | 2011-05-16 | 2010-06-14 |  |  | 0 |  | 20 | 1.2812 | 2.7188 | Issue Fixes | Code Peer Review
Demo - GUI - GUI Popups | CODEINSP | Demo - GUI - GUI Popups - Code Peer Review | [6 empty] | C, B, G, D | 40 | LOC | 1 | 10 | 4 | 1 | 4 | 2010-06-14 | 21 | [5 empty] | 161.7188 | 99.3854 | 2.4582 | 2011-05-23 | 2010-06-14 |  |  | 0 |  | 21 | 4 | 4 | Issue Fixes | Code Peer Review
Customer Interface Manager | MGMT | Customer Interface Manager - 6/7 | [6 empty] | G | 1 | Text Pages | 1 | 100 | 1 | 1 | 1 | 2010-06-14 | 21 | [5 empty] | 162.7188 | 100 | 0.61456 | 2011-05-23 | 2010-06-14 |  |  | 0 |  | 21 | 1 | 1
Generate Task List
Update Plan

## Schedule
TSP Schedule Planning Template - Form SCHEDULE
| Name | Team Member G
| Team | AIM |  |  |  |  | Total Task Plan Hours | 162.7188
| Date | 2026-07-29 |  |  |  |  | Total Schedule Plan Hours | 163
[7 empty] | Difference | -0.28117
Cycle
Date | Week | Plan Hours | Cumulative Plan Hours | Actual Hours | Cumulative Actual Hours | Planned Value | Cumulative PV | Earned Value | Cumulative EV | Predicted Hours | Cumulative Predicted Hours | Predicted Earned Value | Cumulative Predicted EV | Baseline Plan Hours | Baseline Cumulative Plan Hours | Baseline PV | Baseline Cumulative PV | Notes | Earned Value Trend
2010-01-25 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2010-02-01 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2010-02-08 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 16 | 16 | 5.8605 | 5.8605 | out all week due to unexpected family situation | 0
2010-02-15 | 4 | 16 | 16 | 3.7458 | 3.7458 | 7.8467 | 7.8467 | 6.706 | 6.706 |  |  | 6.706 | 6.706 | 16 | 32 | 2.9963 | 8.8568 |  | 0.14537
2010-02-22 | 5 | 16 | 32 | 5.6369 | 9.3828 | 10.8435 | 18.6902 | 4.6744 | 11.3804 |  |  | 4.6744 | 11.3804 | 16 | 48 | 10.0122 | 18.869 |  | 0.3911
2010-03-01 | 6 | 12 | 44 | 10.775 | 20.1578 | 7.7995 | 26.4897 | 7.3098 | 18.6902 |  |  | 7.3098 | 18.6902 | 12 | 60 | 2.8995 | 21.7685 |  | 0.29443
2010-03-08 | 7 | 9 | 53 | 4.8461 | 25.0039 | 5.3774 | 31.8671 | 4.828 | 23.5183 |  |  | 4.828 | 23.5183 | 16 | 76 | 10.0122 | 31.7807 | dr appt wed, reduce planned hours | 0.26199
2010-03-15 | 8 | 6 | 59 | 9.6731 | 34.6769 | 4.3142 | 36.1813 | 3.586 | 27.1043 |  |  | 3.586 | 27.1043 | 16 | 92 | 2.3485 | 34.1292 | took 2 days pto | 0.25088
2010-03-22 | 9 | 8 | 67 | 7.47 | 42.1469 | 0.22124 | 36.4026 | 21.2554 | 48.3596 |  |  | 21.2554 | 48.3596 | 16 | 108 | 10.0122 | 44.1414 | gone Friday for wife's surgery | -0.24725
2010-03-29 | 10 | 8 | 75 | 0 | 42.1469 | 0 | 36.4026 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 124 | 7.4925 | 51.6339 |  | -0.24725
2010-04-05 | 11 | 8 | 83 | 0 | 42.1469 | 14.4153 | 50.8179 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 140 | 5.5636 | 57.1975 |  | 0.048373
2010-04-12 | 12 | 8 | 91 | 0 | 42.1469 | 3.9304 | 54.7483 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 156 | 8.0582 | 65.2557 |  | 0.11669
2010-04-19 | 13 | 8 | 99 | 0 | 42.1469 | 5.8771 | 60.6254 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 172 | 6.6977 | 71.9534 |  | 0.20232
2010-04-26 | 14 | 8 | 107 | 0 | 42.1469 | 0.61456 | 61.2399 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 188 | 6.6977 | 78.6511 |  | 0.21033
2010-05-03 | 15 | 8 | 115 | 0 | 42.1469 | 0 | 61.2399 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 204 | 6.6977 | 85.3488 |  | 0.21033
2010-05-10 | 16 | 8 | 123 | 0 | 42.1469 | 12.8842 | 74.1242 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 220 | 6.6977 | 92.0465 |  | 0.34759
2010-05-17 | 17 | 8 | 131 | 0 | 42.1469 | 6.1332 | 80.2574 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 236 | 6.6977 | 98.7442 |  | 0.39744
2010-05-24 | 18 | 8 | 139 | 0 | 42.1469 | 3.5337 | 83.7911 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 252 | 1.2558 | 100 |  | 0.42285
2010-05-31 | 19 | 8 | 147 | 0 | 42.1469 | 5.7615 | 89.5525 | 0 | 48.3596 |  |  | 0 | 48.3596 | 16 | 268 |  |  |  | 0.45999
2010-06-07 | 20 | 8 | 155 | 0 | 42.1469 | 4.9165 | 94.469 | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | 0.48809
2010-06-14 | 21 | 8 | 163 | 0 | 42.1469 | 5.531 | 100 | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | 0.5164
2010-06-21 | 22 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-06-28 | 23 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-07-05 | 24 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-07-12 | 25 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-07-19 | 26 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-07-26 | 27 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-08-02 | 28 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-08-09 | 29 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-08-16 | 30 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-08-23 | 31 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-08-30 | 32 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-09-06 | 33 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-09-13 | 34 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 0 | 48.3596 | [5 empty] | -1
2010-09-20 | 35 |  |  | 0 | 42.1469 |  |  | 0 | 48.3596 |  |  | 1.4223 | 49.782 | [5 empty] | -1
2010-09-27 | 36 | [10 empty] | 1.4223 | 51.2043
2010-10-04 | 37 | [10 empty] | 1.4223 | 52.6267
2010-10-11 | 38 | [10 empty] | 1.4223 | 54.049
2010-10-18 | 39 | [10 empty] | 1.4223 | 55.4713
2010-10-25 | 40 | [10 empty] | 1.4223 | 56.8937
2010-11-01 | 41 | [10 empty] | 1.4223 | 58.316
2010-11-08 | 42 | [10 empty] | 1.4223 | 59.7384
2010-11-15 | 43 | [10 empty] | 1.4223 | 61.1607
2010-11-22 | 44 | [10 empty] | 1.4223 | 62.5831
2010-11-29 | 45 | [10 empty] | 1.4223 | 64.0054
2010-12-06 | 46 | [10 empty] | 1.4223 | 65.4277
2010-12-13 | 47 | [10 empty] | 1.4223 | 66.8501
2010-12-20 | 48 | [10 empty] | 1.4223 | 68.2724
2010-12-27 | 49 | [10 empty] | 1.4223 | 69.6948
2011-01-03 | 50 | [10 empty] | 1.4223 | 71.1171
2011-01-10 | 51 | [10 empty] | 1.4223 | 72.5395
2011-01-17 | 52 | [10 empty] | 1.4223 | 73.9618
2011-01-24 | 53 | [10 empty] | 1.4223 | 75.3841
2011-01-31 | 54 | [10 empty] | 1.4223 | 76.8065
2011-02-07 | 55 | [10 empty] | 1.4223 | 78.2288
2011-02-14 | 56 | [10 empty] | 1.4223 | 79.6512
2011-02-21 | 57 | [10 empty] | 1.4223 | 81.0735
2011-02-28 | 58 | [10 empty] | 1.4223 | 82.4958
2011-03-07 | 59 | [10 empty] | 1.4223 | 83.9182
2011-03-14 | 60 | [10 empty] | 1.4223 | 85.3405
2011-03-21 | 61 | [10 empty] | 1.4223 | 86.7629
2011-03-28 | 62 | [10 empty] | 1.4223 | 88.1852
2011-04-04 | 63 | [10 empty] | 1.4223 | 89.6076
2011-04-11 | 64 | [10 empty] | 1.4223 | 91.0299
2011-04-18 | 65 | [10 empty] | 1.4223 | 92.4522
2011-04-25 | 66 | [10 empty] | 1.4223 | 93.8746
2011-05-02 | 67 | [10 empty] | 1.4223 | 95.2969
2011-05-09 | 68 | [10 empty] | 1.4223 | 96.7193
2011-05-16 | 69 | [10 empty] | 1.4223 | 98.1416
2011-05-23 | 70 | [10 empty] | 1.4223 | 99.564
2011-05-30 | 71 | [10 empty] | 0.43605 | 100

## Risk (hidden)
Risk | Impact | Likelihood | Priority | Assigned | Date

## LOGT
TSP Time Recording Log - Form LOGT
Name | Team Member G |  |  | Date | 2026-07-29
Team | AIM
Cycle
|  |  |  | Hours Logged | 42.1469
Assembly | Phase | Task | Date | Start | Int. | Stop | Delta | Comments
Maint - LD - 952 | CODEINSP | Maint - LD - 952 CODEINSP | 2010-02-16 | 12:04 | 0 | 12:14 | 10.35
Maint - LD - 957 | CODEINSP | Maint - LD - 957 CODEINSP | 2010-02-16 | 12:48 | 0 | 13:01 | 12.9333
Maint - LD - 960 | CODEINSP | Maint - LD - 960 CODEINSP | 2010-02-16 | 13:02 | 0 | 13:08 | 6.1
Maint - LD - 884 | CODE | Maint - LD - 884 - Find and Fix | 2010-02-17 | 15:38 | 0 | 16:33 | 54.6333
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 | 13:58 | 0 | 14:21 | 23.3667
Add Checklist to all Review/Insp Phases | CODEINSP | Add Checklist to all Review/Insp Phases - Doc Inspection-NP | 2010-02-18 | 14:30 | 0 | 14:38 | 7.7167
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 | 15:02 | 0 | 15:13 | 11.05
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 | 15:20 | 0 | 15:24 | 4.9667
Update INS Form/Script | CODEINSP | Update INS Form/Script - Doc Inspection-NP | 2010-02-18 | 15:26 | 0 | 15:32 | 5.9667
Maint - LD - 884 | CODE | Maint - LD - 884 - Find and Fix | 2010-02-18 | 15:36 | 0 | 16:14 | 38.2
Maint - LD - 884 | CR | Maint - LD - 884 - Code Review | 2010-02-18 | 16:15 | 0 | 16:25 | 10.1667
Maint - LD - 884 | COMPILE | Maint - LD - 884 - Compile | 2010-02-18 | 16:27 | 0 | 16:31 | 4.3
Customer Interface Manager | MGMT | Customer Interface Manager - 2/15 | 2010-02-18 | 14:25 |  | 15:00 | 35
Maint - LD - 959 | CODEINSP | Maint - LD - 959 CODEINSP | 2010-02-23 | 11:40 | 0 | 12:35 | 55
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | 2010-02-23 | 12:45 | 0 | 13:05 | 20.15
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | 2010-02-23 | 15:55 |  | 16:20 | 24.2
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-24 | 7:30 | 0 | 8:12 | 42.6833
Define a Design Standard | CODEINSP | Define a Design Standard - Doc Inspection-NT | 2010-02-25 | 9:03 |  | 9:57 | 54
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | 2010-02-25 | 15:30 |  | 16:20 | 50
Customer Interface Manager | MGMT | Customer Interface Manager - 2/22 | 2010-02-26 | 7:50 |  | 8:30 | 40
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | 2010-02-26 | 16:05 | 0 | 16:57 | 52.1833
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | 2010-03-01 | 12:35 | 0 | 13:00 | 25.1667
Add PM to Dev Processes | CODEINSP | Add PM to Dev Processes - Doc Inspection-NP | 2010-03-01 | 14:33 |  | 14:38 | 5.05
Maint - LD - 884 | PM | Maint - LD - 884 - PM | 2010-03-01 | 14:41 |  | 14:48 | 7.05
Maint - LD - 885 | CODE | Maint - LD - 885 - Find and Fix | 2010-03-01 | 15:59 | 0 | 16:47 | 47.0833
Maint - LD - 885 | CR | Maint - LD - 885 - Code Review | 2010-03-02 | 7:55 | 0 | 8:04 | 9.0833
Maint - LD - 884 | COMPILE | Maint - LD - 884 - Compile | 2010-03-02 | 8:05 | 0 | 8:20 | 14.85
Maint - LD - 884 | CODEINSP | Maint - LD - 884 - Code Peer Review | 2010-03-02 | 9:12 | 22.8167 | 10:26 | 51.35
Maint - LD - 885 | UT | Maint - LD - 885 - Unit Test | 2010-03-02 | 10:59 | 149.75 | 14:08 | 39.6833
Customer Interface Manager | MGMT | Customer Interface Manager - 3/1 | 2010-03-03 | 8:15 | 0 | 8:53 | 37.4
Maint - LD - 885 | CODE | Maint - LD - 885 - Find and Fix | 2010-03-03 | 8:53 | 0 | 9:59 | 65.9667
Maint - LD - 885 | CR | Maint - LD - 885 - Code Review | 2010-03-03 | 10:19 | 308.9667 | 16:35 | 67.3667
Maint - LD - 885 | COMPILE | Maint - LD - 885 - Compile | 2010-03-03 | 16:40 |  | 16:45 | 4.15
Maint - LD - 885 | CODEINSP | Maint - LD - 885 - Code Peer Review | 2010-03-04 | 7:56 | 0 | 8:41 | 45.0167
Maint - LD - 885 | UT | Maint - LD - 885 - Unit Test | 2010-03-04 | 8:46 |  | 9:16 | 30.1167
Maint - LD - 885 | PM | Maint - LD - 885 - PM | 2010-03-04 | 9:19 |  | 9:27 | 8.0333
Maint - LD - 884 | UT | Maint - LD - 884 - Unit Test | 2010-03-03 | 16:45 |  | 17:05 | 19.2833
Create Peer Review Script | CODEINSP | Create Peer Review Script - Doc Inspection-NP | 2010-03-04 | 10:26 | 0 | 10:31 | 4.8
Add TCs to New Feature Process | CODEINSP | Add TCs to New Feature Process - Doc Inspection-NP | 2010-03-04 | 10:33 | 0 | 10:55 | 21.7
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-04 | 11:14 | 161.1833 | 15:33 | 97.15
Customer Interface Manager | MGMT | Customer Interface Manager - 3/1 | 2010-03-04 | 15:04 |  | 15:10 | 6.2
Cycle Postmortem | MGMT | Cycle Postmortem - Task | 2010-03-01 | 8:00 |  | 8:40 | 40
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-08 | 13:32 | 31.0167 | 14:15 | 11.6333
Maint - Doc - SRS INSP | MGMT | Maint - Doc - SRS INSP - Task | 2010-03-09 | 10:04 | 19.8 | 10:41 | 17.05
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-09 | 14:40 | 0 | 16:17 | 97.1667
Maint - LD - 953 | CODEINSP | Maint - LD - 953 - Code Peer Review | 2010-03-11 | 8:45 | 0 | 8:49 | 4.6167
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-11 | 13:20 | 45 | 16:16 | 130.3
Customer Interface Manager | MGMT | Customer Interface Manager - 3/8 | 2010-03-09 | 9:00 |  | 9:30 | 30
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | 2010-03-15 | 10:30 |  | 12:30 | 120
Maint - LD - 985 | CODE | Maint - LD - 985 - Find and Fix | 2010-03-15 | 13:30 |  | 13:54 | 23.3833
Maint - LD - 985 | CR | Maint - LD - 985 - Code Review | 2010-03-15 | 13:55 |  | 14:03 | 7.3833
Maint - LD - 985 | COMPILE | Maint - LD - 985 - Compile | 2010-03-15 | 14:05 |  | 14:11 | 5.35
Maint - LD - 985 | CODEINSP | Maint - LD - 985 - Code Peer Review | 2010-03-16 | 15:30 |  | 16:15 | 45
Customer Interface Manager | MGMT | Customer Interface Manager - 3/15 | 2010-03-16 | 10:12 |  | 10:19 | 7.15
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | 2010-03-16 | 10:22 | 10.4833 | 12:08 | 95.95
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-16 | 12:35 | 66.5167 | 16:32 | 170.2333
Maint - LD - 918 | CODE | Maint - LD - 918 - Find and Fix | 2010-03-17 | 8:30 | 439.2667 | 17:35 | 105.9333
Maint - LD - 967 | CODE | Maint - LD - 967 - Find and Fix | 2010-03-22 | 13:20 |  | 13:26 | 5.5
Maint - LD - 967 | CR | Maint - LD - 967 - Code Review | 2010-03-22 | 13:30 |  | 13:42 | 12.2667
Maint - LD - 967 | COMPILE | Maint - LD - 967 - Compile | 2010-03-22 | 13:45 |  | 13:50 | 5.1
Maint - LD - 967 | CODEINSP | Maint - LD - 967 - Code Peer Review | 2010-03-22 | 16:05 |  | 16:22 | 17
Maint - LD - 955 | CODEINSP | Maint - LD - 955 - Code Peer Review | 2010-03-22 | 16:25 |  | 16:34 | 8.9
Maint - LD - 985 | UT | Maint - LD - 985 - Unit Test | 2010-03-23 | 10:50 | 39.1 | 12:24 | 54.2333
Maint - LD - 985 | PM | Maint - LD - 985 - PM | 2010-03-23 | 12:25 | 0 | 12:46 | 21.2833
Maint - LD - 967 | UT | Maint - LD - 967 - Unit Test | 2010-03-23 | 12:34 | 70.3167 | 16:25 | 161.05
Maint - LD - 918 | CR | Maint - LD - 918 - Code Review | 2010-03-25 | 11:35 | 104.8 | 15:55 | 154.8667
Maint - LD - 967 | PM | Maint - LD - 967 - PM | 2010-03-23 | 16:30 |  | 16:38 | 8

## LOGD
TSP Defect Recording Log - Form LOGD
Name | Team Member G |  |  | Date | 2026-07-29
Team | AIM
Cycle
Date | Num | Type | Assembly | Injected | Removed | Fix Time | Fix Ref. | Description
2010-03-02 | 3 | 40 | Maint - LD - 885 | CODE | CR | 5 |  | okay comments
2010-03-03 | 4 | 60 | Maint - LD - 885 | CODE | CR | 66 |  | okay comments
2010-03-23 | 5 | 80 | Maint - LD - 967 | CODE | UT | 161.1 |  | okay comments

## Week
TSP Week Summary - Form WEEK
Name | Team Member G |  |  |  |  | Date | 2026-07-29
Team | AIM
Status for Week | 8 | Selected Assembly |  |  |  | Cycle
Week Date | 2010-03-15 | SYSTEM
Task Hours %Change |  | Weekly Data | Plan | Actual | Plan / Actual | Plan - Actual | Project End Dates
Baseline | 238.888 | Schedule hours for this week | 6 | 9.6731 | 0.62028 | -3.6731 | Baseline | 2010-05-24
Current | 162.7188 | Schedule hours this cycle to date | 59 | 34.6769 | 1.7014 | 24.3231 | Plan | 2010-06-14
%Change | -31.88% | Earned value for this week | 4.3142 | 3.586 | 1.2031 | 0.72819 | Predicted | 2011-05-23
|  | Earned value this cycle to date | 36.1813 | 27.1043 | 1.3349 | 9.0771
|  | To-date hours for tasks completed | 44.1037 | 23.1181 | 1.9078
|  | To-date average hours per week | 7.375 | 4.3346 | 1.7014
|  | EV per completed task hour to date | 0.61456 | 1.1724
|  | Consolidated Team Member Schedule Data |  | Plan Hours | Actual Hours | Plan Value | Earned Value
Team Leader
Customer Interface Manager
Design Manager
Implementation Manager
Planning Manager
|  | Totals |  | 0 | 0 | 0 | 0
Assembly | Phase | Task | Re-source | Plan Hrs. | Actual Hrs. | EV or PV | CPI | Baseline or Committed Date and Week |  | Plan Date and Week |  | Slip Date and Week |  | Predicted Date and Week |  | Actual Date and Week
TASKS COMPLETED IN WEEK 8
Demo - Docs - Req Doc | CODEINSP | Demo - Docs - Req Doc - Doc Inspection-NT | C, D, G | 4.375 | 2 | 2.6887 | 2.1875 | 2010-04-12 | 12 | 2010-03-01 | 6 |  |  | 2010-03-15 | 8 | 2010-03-15 | 8
Maint - LD - 954 | CODEINSP | Maint - LD - 954 - Code Peer Review | C, D, G | 0.4601 | 1.5992 | 0.28276 | 0.28772 | 2010-03-01 | 6 | 2010-03-01 | 6 |  |  | 2010-03-16 | 8 | 2010-03-16 | 8
Maint - LD - 955 | CODE | Maint - LD - 955 - Find and Fix | G | 0 |  | 0 |  | 2010-02-15 | 4 | 2010-03-01 | 6 |  |  | 2010-03-17 | 8 | 2010-03-17 | 8
Maint - LD - 955 | CR | Maint - LD - 955 - Code Review | G | 0 |  | 0 |  | 2010-02-15 | 4 | 2010-03-01 | 6 |  |  | 2010-03-17 | 8 | 2010-03-17 | 8
Maint - LD - 955 | COMPILE | Maint - LD - 955 - Compile | G | 0 |  | 0 |  | 2010-02-15 | 4 | 2010-03-01 | 6 |  |  | 2010-03-17 | 8 | 2010-03-17 | 8
Maint - LD - 955 | UT | Maint - LD - 955 - Unit Test | G | 0 |  | 0 |  | 2010-02-15 | 4 | 2010-03-01 | 6 |  |  | 2010-03-17 | 8 | 2010-03-17 | 8
Maint - LD - 955 | PM | Maint - LD - 955 - PM | G | 0 |  | 0 |  | 2010-02-15 | 4 | 2010-03-01 | 6 |  |  | 2010-03-17 | 8 | 2010-03-17 | 8
Customer Interface Manager | MGMT | Customer Interface Manager - 3/15 | G | 1 | 0.11917 | 0.61456 | 8.3916 | 2010-05-03 | 15 | 2010-03-08 | 7 |  |  | 2010-03-17 | 8 | 2010-03-17 | 8
TASKS DUE THROUGH WEEK 10
Maint - CM - Delivery Letters | MGMT | Maint - CM - Delivery Letters - Task | G | 4 |  | 2.4582 |  | 2010-02-08 | 3 | 2010-04-05 | 11 | 2010-04-05 | 11 | 2010-09-27 | 36
Maint - Doc - SVD | CODEINSP | Maint - Doc - SVD - Doc Inspection-M | F, G, C | 2.5568 |  | 1.5713 |  | 2010-02-15 | 4 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-04 | 37
Maint - LD - 918 | CR | Maint - LD - 918 - Code Review | G | 2.9528 | 2.5811 | 1.8147 | 1.144 | 2010-03-08 | 7 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-18 | 39
Maint - LD - 918 | COMPILE | Maint - LD - 918 - Compile | G | 0.88585 |  | 0.5444 |  | 2010-03-08 | 7 | 2010-04-12 | 12 | 2010-04-12 | 12 | 2010-10-18 | 39

## IRTL (hidden)
TSP Issue/Risk Tracking Log - Form IRTL
Name | Team Member G |  |  |  |  | Date | 2026-07-29
Team | AIM
Cycle
Issue or Risk Number | R=Risk I=Issue | Date Created | P=Personal T=Team | Likelihood (H,M,L) | Impact (H,M,L) | Owner | Follow-up Date | Description | Current Status | Date Status Changed

## IRWeek (hidden)
TSP Issue Risk Week Summary - Form IRWEEK
Name | Team Member G |  |  | Date | 2026-07-29
Team | AIM |  |  | Team
Week | 1 |  |  | Cycle
Issue/Risk Number | P=Personal T=Team | R=Risk I=Issue | Description |  | Status

## PIP (hidden)
TSP Process Improvement Proposal - Form PIP
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle
PIP Number | Date Created | P=Personal T=Team | Priority (H,M, L) | Owner | Problem Description | Improvement Suggestion | Process Elements Affected | How Closed? D=Deferred I=Implemented | Date Closed

## DefectTypes
Type | Description | Detailed Description
10 | Documentation
20 | Syntax
30 | Build, Package
40 | Assignment
50 | Interface
60 | Checking
70 | Data
80 | Function
90 | System
100 | Environment
200 | Doc Omission
210 | Doc Ambiguous Statement/Data
220 | Doc Duplicate Statement
230 | Doc Unclear Statement/Data
240 | Doc Incorrect Statement/Data
250 | Doc Grammer
260 | Doc Spelling
270 | Doc Format
280 | Doc Abbreviation
300 | Req Omission
310 | Req Ambiguous
320 | Req Duplicate
330 | Req Unclear
340 | Req Incorrect
350 | Req Inconsistent
360 | Req Extraneous Info
Restore Defect Type Defaults

## Phases (hidden)
Phase | Description | Task Generator S-System P-Part N-None | LOGT Track Time | LOGD Track Defects Injected | LOGD Track Defects Removed | PDF | DefDen | DefRatios | DevTimeRatio | RvwRate | PhaseYld | ProcYld | DI Rate | DR Rate
MGMT | Management and Miscellaneous | S | Y | N | N | N | N |  |  | N | N | N | N | N
STRAT | Launch and Strategy | S | Y | N | N | N | N |  |  | N | N | N | N | N
PLAN | Planning | S | Y | Y | Y | N | N |  |  | N | Y | Y | Y | Y
REQ | Requirements | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
STP | System Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
REQINSP | REQ Inspection | S | Y | Y | Y | N | Y |  | Requirements | Y | Y | N | Y | Y
HLD | High-Level Design | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
ITP | Integration Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
HLDINSP | HLD Inspection | S | Y | Y | Y | N | Y |  | High-Level Design | Y | Y | N | Y | Y
DLD | Detailed Design | P | Y | Y | Y | N | N |  | Code | N | Y | N | Y | Y
DLDR | DLD Review | P | Y | Y | Y | N | Y | Unit Test | Detailed Design | Y | Y | N | Y | Y
TD | Test Development | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
DLDINSP | DLD Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
CODE | Code | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
CR | Code Review | P | Y | Y | Y | N | Y | Compile | Code | Y | Y | N | Y | Y
COMPILE | Compile | P | Y | Y | Y | y | Y |  |  | N | Y | Y | Y | Y
CODEINSP | Code Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
UT | Unit Test | P | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
IT | Build and Integration Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
ST | System Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
DOC | Documentation | S | Y | N | N | N | N |  |  | N | N | N | N | N
PM | Postmortem | S | Y | N | N | N | N |  |  | N | N | N | N | N
AT | Acceptance Test | N | N | Y | Y | Y | Y |  |  | N | N | Y | N | N
PL | Product Life | N | N | Y | Y | Y | Y |  |  | N | N | N | N | N
Copyright 1998 James W. Over

## QProfParam (hidden)
Parameter | Value | Description
Design/Code Time | 100% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time
Restore Qprofile Parameter Defaults

## Custom Processes
TSP Custom Processes Form
Name | Team Member G
Team | AIM
Date | 2026-07-29
Cycle
Process | Phase | Default Task Name | Process Step Description | Map-to Phase | Time in Phase% | Defects Injected per Hour | Phase Yield | # of Resources
Team Software Process | PLAN | - Planning |  | PLAN | 2 | 0 | 0
Team Software Process | REQ | - Requirements |  | REQ | 2 | 0.25 | 0
Team Software Process | STP | - System Test Plan |  | STP | 2.5 | 0 | 0
Team Software Process | REQINSP | - REQ Inspection |  | REQINSP | 5 | 0 | 0.7
Team Software Process | HLD | - High-Level Design |  | HLD | 7 | 0.25 | 0
Team Software Process | ITP | - Integration Test Plan |  | ITP | 5 | 0 | 0
Team Software Process | HLDINSP | - HLD Inspection |  | HLDINSP | 3 | 0 | 0.7
Team Software Process | DLD | - Detailed Design |  | DLD | 11.5 | 0.75 | 0
Team Software Process | DLDR | - DLD Review |  | DLDR | 5 | 0 | 0.7
Team Software Process | TD | - Test Development |  | TD | 5 | 0 | 0
Team Software Process | DLDINSP | - DLD Inspection |  | DLDINSP | 10 | 0 | 0.7
Team Software Process | CODE | - Code |  | CODE | 15 | 2 | 0
Team Software Process | CR | - Code Review |  | CR | 5 | 0 | 0.7
Team Software Process | COMPILE | - Compile |  | COMPILE | 1 | 0.3 | 0.5
Team Software Process | CODEINSP | - Code Inspection |  | CODEINSP | 9 | 0 | 0.7
Team Software Process | UT | - Unit Test |  | UT | 3 | 0.067 | 0.9
Team Software Process | IT | - Build and Integration Test |  | IT | 3 | 0 | 0.8
Team Software Process | ST | - System Test |  | ST | 5 | 0 | 0.8
Team Software Process | PM | - Postmortem |  | PM | 1 |  | 0.65
Issue Fixes | Find and Fix | - Find and Fix |  | CODE | 58 | 0.038
Issue Fixes | Code Review | - Code Review |  | CR | 10 |  | 0.23077
Issue Fixes | Compile | - Compile |  | COMPILE | 3 |  | 0.3
Issue Fixes | Code Peer Review | - Code Peer Review |  | CODEINSP | 10 |  | 0.42857
Issue Fixes | Unit Test | - Unit Test |  | UT | 15 |  | 1
Issue Fixes | Postmortem | - PM |  | PM | 4
New Features | Detail Design | - Detailed Design |  | DLD | 25 | 1.12
New Features | UT Descriptions | - UT Description |  | TD | 5
New Features | Design Review | - Design Review |  | DLDR | 3 |  | 0.4375
New Features | Design Inspection | - Design Inspection |  | DLDINSP | 11 |  | 1
New Features | Code | - Code |  | CODE | 20 | 0.81
New Features | Code Review | - Code Review |  | CR | 3 |  | 0.375
New Features | Compile | - Compile |  | COMPILE | 1 |  | 0.4
New Features | Code Peer Review | - Code Peer Review |  | CODEINSP | 15 |  | 0.44444
New Features | Unit Test | - Unit Test |  | UT | 15 |  | 1
New Features | Postmortem | - PM |  | PM | 2
Test | Write Test Cases | - Write Test Cases |  | CODE | 50 | 0.64
Test | Review TC | - Review TC |  | CR | 10 |  | 0.76786
Test | Peer Review TC | - Peer Review TC |  | CODEINSP | 15 |  | 0.15385
Test | Validate TC and Test Software | - Validate TC and Test SW |  | ST | 17 |  | 1
Test | Analyze and Record Results | - Analyze and Record Results |  | PM | 8
New Prototype | Define Use Cases | - Define Use Cases |  | DLD | 30 | 1.12
New Prototype | Build Prototype | - Build Prototype |  | CODE | 40 | 0.81
New Prototype | Validate Prototype | - Validate Prototype |  | UT | 20 |  | 1
New Prototype | Demo Prototype | - Demo Prototype |  | PM | 10
DAR Prototype | Build Prototype | - Build Prototype |  | CODE | 55 | 0.81
DAR Prototype | Validate Prototype | - Validate Prototype |  | UT | 35 |  | 1
DAR Prototype | Demo Prototype | - Demo Prototype |  | PM | 10
DAR Process | DAR | - DAR |  | PLAN | 100
Document-Maintenance | Draft-M | - Draft-M |  | CODE | 65 | 0.4
Document-Maintenance | Doc Review-M | - Doc Review-M |  | CR | 15 |  | 0.32308
Document-Maintenance | Doc Inspection-M | - Doc Inspection-M |  | CODEINSP | 15 |  | 1
Document-Maintenance | Doc PM-M | - Doc PM-M |  | PM | 5
Document-New Process | Research-NP | - Research-NP |  | DLD | 20
Document-New Process | Draft-NP | - Draft-NP |  | CODE | 45 | 0.4
Document-New Process | Doc Review-NP | - Doc Review-NP |  | CR | 15 |  | 0.18605
Document-New Process | Doc Inspection-NP | - Doc Inspection-NP |  | CODEINSP | 15 |  | 1
Document-New Process | Doc PM-NP | - Doc PM-NP |  | PM | 5
Document-New Technical | Research-NT | - Research-NT |  | DLD | 35
Document-New Technical | Draft-NT | - Draft-NT |  | CODE | 30 | 1.2
Document-New Technical | Doc Review-NT | - Doc Review-NT |  | CR | 15 |  | 0.94118
Document-New Technical | Doc Inspection-NT | - Doc Inspection-NT |  | CODEINSP | 15 |  | 1
Document-New Technical | Doc PM-NT | - Doc PM-NT |  | PM | 5
Task | Task | - Task |  | MGMT | 100
Document-Test | Research-T | - Research-T |  | DLD | 35
Document-Test | Draft-T | - Draft-T |  | CODE | 30 | 0.4
Document-Test | Doc Review-T | - Doc Review-T |  | CR | 15 |  | 0.32
Document-Test | Doc Inspection-T | - Doc Inspection-T |  | CODEINSP | 15 |  | 0.32
Document-Test | Doc PM-T | - Doc PM-T |  | PM | 5 |  | 1

## PlanGuide
General | - If your team does not have historical data, use these guidelines as standard planning factors. - In all cases, use your judgement. If some guideline does not fit your case, use your best estimate instead.
TSP Plans | Overall plan - produced first by the total team and later adjusted to conform to the balanced plan. Bottom-up plan - produced by each engineer for the next phase Balanced plan - the next phase plan after load balancing
Requirements | - The Requirements process depends heavily on The nature of The project, so no General guidelines are given. - In General, expect that all input materials will have be to inspected and substantially reworked.
Requirements Inspections | - The QUAL guideline provides a General factor to use In determining The time needed for The Requirements inspection. - Again, If this number is unrealistic for your project and situation, use your best estimate.
High-Level Design | - The High-Level Design process is highly variable and The time depends principally on The size, complexity, and General nature of The system, so no General guideline is given. - Without prior data, most teams substantially underestimate The time High-Level Design will require.
Implementation Phase | Implementation covers detailed design through unit test. - Calculate total implementation time from LOC/hour rates. - New or large modifications: about 10 LOC per hour. - Small changes to large systems: about 5 LOC per hour. - Pick a number that seems appropriate for your project. - Maintenance fixes, use an average rate: 5 and 20 hours per fix, depending on complexity and degree of testing.
Implementation Allocation | In estimating the implementation phases, - Make an overall estimate based on LOC/hour rates. - Then use these percentages to Calculate The phase times.
Detailed design - 22.1%
Detailed design review - 11.1%
Detailed design inspection - 8.8%
Coding - 20.0%
Code review - 10.0%
Compiling - 3.4%
Code inspection - 8.8%
Unit test - 15.8%
Integration and System Test | For these phases, estimate the defect-free test time and add 5 hours per defect in integration and 10 hours in system test

## QualGuide
Measure | Goal | Comments
Percent Defect Free (PDF)
Compile | > 10%
Unit Test | > 50%
Integration Test | > 70%
System Test | > 90%
Defects/KLOC:
Total defects injected | 75 - 150 | If not PSP trained, use 100 to 200.
Compile | < 10 | All defects
Unit Test | < 5 | All major defects (in source LOC)
Integration Test | < 0.5 | All major defects (in source LOC)
System Test | < 0.2 | All major defects (in source LOC)
Defect Ratios
Detailed design review defects /unit test defects | > 2.0 | All major defects (in source LOC)
Code review defects/compile defects | > 2.0 | All major defects (in source LOC)
Development Time Ratios
Requirements inspection/requirements time | > 0.25 | Elicitation in requirements time
High-level design inspection/high-level design time | > 0.5 | Design work only, not studies
Detailed design/coding time | > 1.00
Detailed design review/detailed design time | > 0.5
Code review/code time | > 0.5
Review and Inspection Rates
Requirements pages/hour | < 2 | Single-spaced text pages
High-level design pages/hour | < 5 | Formatted design logic
Detailed design text lines/hour | < 100 | Pseudocode ~ equal to 3 LOC
Code LOC/hour | < 200 | Logical LOC
Defect Injection and Removal Rates
Requirements defects injected/hour | 0.25 | Only major defects
Requirements inspection defects removed/hour | 0.5 | Only major defects
High-level design defects injected/hour | 0.25 | Only major defects
High-level design inspection defects removed/hour | 0.5 | Only major defects
Detailed design defects injected/hour | 0.75 | Only design defects
Detailed design review defects removed/hour | 1.5 | Only design defects
Detailed design inspection defects removed/hour | 0.5 | Only design defects
Code defects injected/hour | 2 | All defects
Code review defects removed/hour | 4 | All defects in source LOC
Compile defects injected/hour | 0.3 | Any defects
Code inspection defects removed/hour | 1 | All defects in source LOC
Unit test defects injected/hour | 0.067 | Any defects
Phase Yields
Team requirements inspections | ~ 70% | Not counting editorial comments
Design reviews and inspections | ~ 70% | Using state analysis, trace tables
Code reviews and inspections | ~ 70% | Using personal checklists
Compiling | ~ 50% | 90+ % of syntax defects
Unit test - at 5 or less defects/KLOC | ~ 90% | For high defects/KLOC - 50-75%
Integration and system test - at < 1.0 defects/KLOC | ~ 80% | For high defects/KLOC - 30-65%
Acceptance test - at < 1.0 defects/KLOC | ~ 65% | For high defects/KLOC - 30%
Before compile | >75% | Assuming sound design methods
Before unit test | > 85% | Assuming logic checks in reviews
Before integration test | > 97.5% | For small products, 1 defect max.
Before system test | > 99% | For small products, 1 defect max.