Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Answers for
Schedule Management Exercise

TSP Executive Strategy Seminar

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Answers to Questions

Schedule

- How would you measure the rate at which the team has been working so far?

|  | In earned value per week |
| --- | --- |

- What is that rate?

|  | The team has been earning value at 2.42 per week. This is the 31.5 earned to date divided by |
| --- | --- |
|  | 13 weeks. |

- If the team continued working at that rate, when would it finish and how far ahead or behind schedule would it be?

|  | At the present rate, a total of 28.3 weeks of work remain. This is the (100-31.5) EV to go divided |
| --- | --- |
|  | by the current rate of 2.42, or 68.5/2.42 = 28.3 weeks to go. Since it should finish in 36-13 =23 |
|  | weeks, the team is now projected to finish 5.3 weeks behind schedule. |

- What would be the schedule impact of adding one PSP-trained developer to the team?

|  | Adding 1 developer to the current 5 would increase the EV rate by 20% to 2.904. At this rate, the |
| --- | --- |
|  | team would finish in 68.5/2.904 = 23.6 weeks, or slightly behind of the 23 week schedule. |

- What would be the schedule impact of the team putting in 5 more task hours per week?

|  | Adding 5 task hours per week to the current 75 would increase the team’s working rate by 6.67% |
| --- | --- |
|  | and increase the EV to 2.581 per week. The team would then finish in 68.5/2.581 = 26.5 weeks. |

Other Questions

- How accurate is the team's plan?

Compare the actual hours for completed work with the planned hours.

Planned hours for completed tasks = 952.1

Actual hours for completed tasks = 939.2

Over (+) and under (-) estimate in percent

= 100 x (Planned hours for completed tasks / Actual hours for completed tasks) - 100

= 100 x (952.1 / 939.2) - 100 =  + 1.37 %

- What would it cost (or save) the organization to accelerate the project schedule by increasing task hours or adding a developer?

Since increasing weekly task hours reduces the weeks of work for the same developers to complete the job, it would reduce project costs.

Adding a developer would not add to the project costs since the task hours would be unchanged.  However, the job would be done in less calendar time.

- What management actions would likely increase (or decrease) the team's weekly task hours?

Weekly task hours can only be increased by the developers themselves.  Management can help by providing assistance when the developers request it.  Edicts to increase weekly task hours generally do more harm than good.  Actions that typically help to increase weekly task hours are the following.

|  |  minimizing and shortening meetings involving the developers |
| --- | --- |
|  |  reducing interruptions |
|  |  providing clerical and other office support |
|  |  providing computing facilities support |
|  |  providing a contiguous team working space |
|  |  providing a quiet team working environment |
|  |  providing the team with process, configuration management, and quality assurance support |
|  |  providing TSP coaching support |

- What might cause the weeks-to-go estimates to be in error?

The weeks-to-go estimates depend on the EV the team earns per task hour and on the number of task hours the team works per week.  Changes in either of these would make the estimates invalid.  Examples of such changes are requirements additions, changes in estimate accuracy, or changes in the time the developers can work on the job.