Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Schedule Management Exercise

TSP Executive Strategy Seminar

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

TSP Executive Strategy Seminar

Schedule Management Exercise

Overview

| #### Exercise #### Overview | This exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | Background Information | 2 |
|  | Questions | 3 |
|  | Example WEEK form | 4 |

| #### Exercise Objectives | In this exercise, participants use earned value and TSP data to - precisely determine project status - assess the accuracy of the team's estimates - estimate likely project completion dates - determine the impact of adding developers to a team - understand the most effective ways to increase development task hours |
| --- | --- |

| #### Exercise Instructions | Read the background information below. Form into groups of two to four to answer the attached questions. After you have finished, there will be a group discussion. |
| --- | --- |

| #### Background Information | By using TSP project data and plans, managers can precisely determine schedule status. They can also understand why a project is ahead of or behind schedule, when the project will likely be completed, and the actions required to accelerate the work. This exercise uses data from Lisa's team to assess schedule status, estimate the likely completion date, and identify the actions required to meet the planned completion date. Lisa leads a team of five developers that has completed 13 weeks of the planned 36-week IOMGR project. Use the data on the team's weekly status to determine the answers to the following questions. These data are shown on the WEEK form on page 4. |
| --- | --- |

Questions

Schedule

- How would you measure the rate at which the team has been working so far?

- What is that rate?

- If the team continued working at that rate, when would it finish and how far ahead or behind schedule would it be?

- What would be the schedule impact of adding one PSP-trained developer to the team?

- What would be the schedule impact of the team putting in 5 more task hours per week?

Other Questions

- How accurate is the team's plan?

- What would it cost (or save) the organization to accelerate the project schedule by increasing task hours or adding a developer?

- What management actions would likely increase (or decrease) the team's weekly task hours?

- What might cause the earned-value schedule estimates to be in error?